## Competitor Queues
[6 empty] | Cycle Details | [12 empty] | Project Details | [26 empty] | Development
Changes from last Queue Pull | Competitor vs. NEER | Links | Notes | DPP Study Cycle | DPP Study Group | Request Status | Post GIA Status | Project # | Project Name Source | Project Name | Developer Source | Developer | PPA/BOT | E/N | E/N at study | ERIS MW | NRIS MW | Tech | County | State | Tier | Orig Prob | Dev Prob | Made it to Phase 2 | DP2 continue | M2 | M3 | Security-At-Risk | Current Phase Payment | TOIF | AFS | ERIS ($ MM) | NRIS ($ MM) | ERIS ($/kW) | SPP AFS ERIS | SPP AFS NRIS | OTH AFS | MISO ERIS | MISO NRIS | NEW ERIS ($ MM) | NEW NRIS ($ MM) | NEW ERIS ($/kW) | NEW NRIS ($/kW) | Total Network Upgrades | NCF | Permitting | NORADs/MTR | Request Status | Queue Date | Withdrawn Date | Done Date | Appl In Service Date | Transmission Owner | County | State | Study Cycle | Study Group | Study Phase | Service Type | POI Name | Summer MW | Winter MW | Fuel | Generating Facility | Post GIA Status | Negotiated In Service Date | Decision Point 1 ERIS MW | Decision Point 1 NRIS MW | Decision Point 2 ERIS MW | Decision Point 2 NRIS MW
|  |  |  | 0 | 0 | Done | In Service | E002 | [5 empty] | ERIS |  | 15 |  | Gas | Pointe Coupee | LA | [27 empty] | Done | 2013-09-13 |  | 2003-12-13 |  | Entergy | Pointe Coupee | LA |  |  |  | ERIS | 500 kV switchyard at Big Cajon II | 15 | 15 | Gas |  | In Service |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Under Construction | E291 | [5 empty] | ERIS |  | 27 |  | Hydro | 0 | TX | [27 empty] | Done | 2012-05-15 |  | 2013-10-22 | 2016-01-01 | Entergy |  | TX |  |  |  | ERIS | Rich 138 kV substation | 27 | 27 | Hydro | HY Hydraulic Turbine (including turnbines associated with delivery of water by pipeline) | Under Construction | 2016-01-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G063 | [5 empty] | ERIS |  | 90 |  | 0 | Manitowoc County | WI | [27 empty] | Withdrawn | 2000-10-26 | 2002-03-20 | 2002-03-20 |  | American Transmission Co. LLC | Manitowoc County | WI |  |  | Network Upgrade | ERIS | Unknown | 90 | 90 |  |  | Withdrawn | 2005-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Not Started | G002 | [5 empty] | ERIS |  | 174 |  | Coal | Trimble County | KY | [27 empty] | Done | 1998-12-01 |  |  |  | LG&E and KU Services Company as agent for Louisville Gas and Electric Company and Kentucky Utilities Company | Trimble County | KY |  |  |  | ERIS | Unknown | 174 | 174 | Coal |  | Not Started | 2016-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Not Started | G003 | [5 empty] | ERIS |  | 174 |  | Coal | Trimble County | KY | [27 empty] | Done | 1998-12-01 |  |  |  | LG&E and KU Services Company as agent for Louisville Gas and Electric Company and Kentucky Utilities Company | Trimble County | KY |  |  |  | ERIS | Unknown | 174 | 174 | Coal |  | Not Started | 2004-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G178 | [5 empty] | ERIS |  | 600 |  | 0 | Clinton County | IA | [27 empty] | Withdrawn | 2002-03-08 | 2002-05-24 | 2002-05-24 |  | ITC Midwest | Clinton County | IA |  |  |  | ERIS | Unknown | 600 | 600 |  |  | Not Started | 2003-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Not Started | G005 | [5 empty] | ERIS |  | 29 |  | Combined Cycle | Lincoln County | MN | [27 empty] | Done | 1999-02-15 |  |  |  | Northern States Power (Xcel Energy) | Lincoln County | MN |  |  |  | ERIS | Unknown | 29 | 29 | Combined Cycle |  | Not Started | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Not Started | G006 | [5 empty] | ERIS |  | 2 |  | Wind | Clay County | MN | [27 empty] | Done | 1999-02-15 |  |  |  | Northern States Power (Xcel Energy) | Clay County | MN |  |  |  | ERIS | Unknown | 2 | 2 | Wind | WT Wind Turbine | Not Started | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G179 | [5 empty] | ERIS |  | 600 |  | Combined Cycle | Clinton County | IA | [27 empty] | Withdrawn | 2002-03-08 | 2002-05-24 | 2002-05-24 |  | ITC Midwest | Clinton County | IA |  |  |  | ERIS | Unknown | 600 | 600 | Combined Cycle |  | Not Started | 2002-06-01 | 0 | 0 | 0 | 0
|  |  |  | G010 | G010 | Done | In Service | G010 | [5 empty] | ERIS |  | 500 |  | Gas | Vigo County | IN | [27 empty] | Done | 1999-08-13 |  |  |  | Duke Energy Corporation | Vigo County | IN | G010 | G010 | Network Upgrade | ERIS | Dresser - Cayuga CT 345kV | 500 | 500 | Gas | ST, CT | In Service | 2007-08-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G180 | [5 empty] | ERIS |  | 600 |  | Combined Cycle | Marshall County | IA | [27 empty] | Withdrawn | 2002-03-08 | 2002-05-24 | 2002-05-24 |  | ITC Midwest | Marshall County | IA |  |  |  | ERIS | Unknown | 600 | 600 | Combined Cycle |  | Not Started | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G182 | [5 empty] | ERIS |  | 600 |  | Combined Cycle | Buchanan County | IA | [27 empty] | Withdrawn | 2002-03-08 | 2002-05-24 | 2002-05-24 |  | ITC Midwest | Buchanan County | IA |  |  |  | ERIS | Unknown | 600 | 600 | Combined Cycle |  | Not Started | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G174 | [5 empty] | ERIS |  | 550 |  | Combined Cycle | Cerro Gordo County | IA | [27 empty] | Withdrawn | 2002-02-19 | 2002-06-11 | 2002-06-11 |  | ITC Midwest | Cerro Gordo County | IA |  |  |  | ERIS | Unknown | 550 | 550 | Combined Cycle |  | Not Started | 2003-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G004 | [5 empty] | ERIS |  | 174 |  | 0 | Mercer County | KY | [27 empty] | Withdrawn | 1998-12-01 | 2002-06-21 | 2002-06-21 |  | LG&E and KU Services Company as agent for Louisville Gas and Electric Company and Kentucky Utilities Company | Mercer County | KY |  |  |  | ERIS | Unknown | 174 | 174 |  |  | Withdrawn | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Not Started | G016 | [5 empty] | ERIS |  | 174 |  | Gas | Trimble County | KY | [27 empty] | Done | 1999-12-01 |  |  |  | LG&E and KU Services Company as agent for Louisville Gas and Electric Company and Kentucky Utilities Company | Trimble County | KY |  |  |  | ERIS | Unknown | 174 | 174 | Gas |  | Not Started | 2005-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Not Started | G017 | [5 empty] | ERIS |  | 174 |  | Gas | Trimble County | KY | [27 empty] | Done | 1999-12-01 |  |  |  | LG&E and KU Services Company as agent for Louisville Gas and Electric Company and Kentucky Utilities Company | Trimble County | KY |  |  |  | ERIS | Unknown | 174 | 174 | Gas |  | Not Started | 2004-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Not Started | G018 | [5 empty] | ERIS |  | 174 |  | Gas | Trimble County | KY | [27 empty] | Done | 1999-12-01 |  |  |  | LG&E and KU Services Company as agent for Louisville Gas and Electric Company and Kentucky Utilities Company | Trimble County | KY |  |  |  | ERIS | Unknown | 174 | 174 | Gas |  | Not Started | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G019 | [5 empty] | ERIS |  | 750 |  | Gas | Oldham County | KY | [27 empty] | Done | 1999-12-07 |  |  |  | LG&E and KU Services Company as agent for Louisville Gas and Electric Company and Kentucky Utilities Company | Oldham County | KY |  |  |  | ERIS | Unknown | 750 | 750 | Gas |  | In Service | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G020 | [5 empty] | ERIS |  | 147 |  | Coal | Dakota County | MN | [27 empty] | Done | 1999-12-13 |  |  |  | Northern States Power (Xcel Energy) | Dakota County | MN |  |  |  | ERIS | Unknown | 147 | 147 | Coal |  | In Service | 2005-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G021 | [5 empty] | ERIS |  | 142 |  | Gas | Williamson County | IL | [27 empty] | Done | 1999-12-14 |  | 2003-01-01 |  | Ameren Illinois | Williamson County | IL |  |  |  | ERIS | Unknown | 142 | 142 | Gas |  | In Service | 2002-04-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G022 | [5 empty] | NRIS |  | 71 |  | Gas | Williamson County | IL | [27 empty] | Done | 1999-12-14 |  | 2013-01-01 |  | Ameren Illinois | Williamson County | IL |  |  |  | NRIS | Unknown | 71 | 71 | Gas |  | In Service | 2002-04-02 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G023 | [5 empty] | ERIS |  | 710 |  | Gas | Wayne County | MI | [27 empty] | Done | 1999-12-16 |  |  |  | ITC Transmission | Wayne County | MI |  |  |  | ERIS | Unknown | 710 | 710 | Gas |  | In Service | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | G025 | G025 | Done | In Service | G025 | [5 empty] | ERIS |  | 189 |  | Gas | Marion County | IN | [27 empty] | Done | 2000-01-05 |  |  |  | Indianapolis Power & Light Company | Marion County | IN | G025 | G025 | DPP - SIS | ERIS | Unknown | 189 | 189 | Gas |  | In Service | 2007-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G026 | [5 empty] | ERIS |  | 240 |  | Combined Cycle | Wayne County | MI | [27 empty] | Done | 2000-01-20 |  |  |  | ITC Transmission | Wayne County | MI |  |  |  | ERIS | Unknown | 240 | 240 | Combined Cycle |  | In Service | 2001-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G231 | [5 empty] | ERIS |  | 60 |  | Gas | Outagamie County | WI | [27 empty] | Withdrawn | 2002-05-20 | 2002-07-02 | 2002-07-02 |  | American Transmission Co. LLC | Outagamie County | WI |  |  |  | ERIS | Unknown | 60 | 60 | Gas |  | Not Started | 2003-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G228 | [5 empty] | ERIS |  | 30 |  | Wind | Oceana County | MI | [27 empty] | Withdrawn | 2002-04-24 | 2002-07-05 | 2002-07-05 |  | Michigan Electric Transmission Company, LLC | Oceana County | MI |  |  |  | ERIS | Unknown | 30 | 30 | Wind | WT Wind Turbine | Not Started | 2004-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G135 | [5 empty] | ERIS |  | 660 |  | 0 | Chisago County | MN | [27 empty] | Withdrawn | 2001-09-19 | 2002-08-02 | 2002-08-02 |  | Northern States Power (Xcel Energy) | Chisago County | MN |  |  | SPA - SIS | ERIS | Unknown | 660 | 660 |  |  | Not Started | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G222 | [5 empty] | ERIS |  | 100 |  | Gas | Burnett County | WI | [27 empty] | Withdrawn | 2002-04-26 | 2002-08-08 | 2002-08-08 |  | NWEC | Burnett County | WI |  |  |  | ERIS | Unknown | 100 | 100 | Gas |  | Not Started | 2005-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G032 | [5 empty] | ERIS |  | 95 |  | Hydro | Hancock County | KY | [27 empty] | Done | 2000-03-01 |  | 2003-11-14 | 2008-06-01 | LG&E and KU Services Company as agent for Louisville Gas and Electric Company and Kentucky Utilities Company | Hancock County | KY |  |  |  | ERIS | Cloverport 138 kV Substation | 95 | 95 | Hydro | OT Other | In Service | 2001-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G220 | [5 empty] | ERIS |  | 650 |  | 0 | Buchanan County | IA | [27 empty] | Withdrawn | 2002-04-15 | 2002-08-09 | 2002-08-09 |  | ITC Midwest | Buchanan County | IA |  |  |  | ERIS | Unknown | 650 | 650 |  |  | Not Started | 2004-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G034 | [5 empty] | ERIS |  | 55 |  | Biomass | Swift County | MN | [27 empty] | Done | 2000-04-16 |  | 2005-02-07 |  | Great River Energy | Swift County | MN |  |  | SPA - SIS | ERIS | Benson 115 kV Substation S046 | 55 | 55 | Biomass | Combined Cycle | In Service | 2008-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G035 | [5 empty] | ERIS |  | 505 |  | Gas | Rock County | WI | [27 empty] | Done | 2000-04-25 |  |  |  | American Transmission Co. LLC | Rock County | WI |  |  | Network Upgrade | ERIS | Rock River 138kV Substation | 505 | 505 | Gas |  | In Service | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G236 | [5 empty] | ERIS |  | 650 |  | 0 | Chisago County | MN | [27 empty] | Withdrawn | 2002-06-24 | 2002-08-12 | 2002-08-12 |  | Northern States Power (Xcel Energy) | Chisago County | MN |  |  |  | ERIS | Unknown | 650 | 650 |  |  | Not Started | 2002-06-03 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G037 | [5 empty] | ERIS |  | 36 |  | Wind | Murray County | MN | [27 empty] | Done | 2000-05-12 |  | 2003-12-02 | 2010-07-30 | Northern States Power (Xcel Energy) | Murray County | MN |  |  | Network Upgrade | ERIS | Chanarambie Substation | 36 | 36 | Wind | WT Wind Turbine | In Service | 2002-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G038 | [5 empty] | ERIS |  | 360 |  | Gas | Wayne County | MI | [27 empty] | Done | 2000-05-19 |  |  |  | ITC Transmission | Wayne County | MI |  |  |  | ERIS | Unknown | 360 | 360 | Gas |  | In Service |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G163 | [5 empty] | ERIS |  | 200 |  | Wind | Murray County | MN | [27 empty] | Withdrawn | 2001-12-03 | 2002-08-21 | 2002-08-21 |  | Northern States Power (Xcel Energy) | Murray County | MN |  |  |  | ERIS | Unknown | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G175 | [5 empty] | ERIS |  | 49 |  | Gas | Ramsey County | MN | [27 empty] | Withdrawn | 2002-03-01 | 2002-08-21 | 2002-08-21 |  | Northern States Power (Xcel Energy) | Ramsey County | MN |  |  |  | ERIS | Unknown | 49 | 49 | Gas |  | Not Started | 2002-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G041 | [5 empty] | ERIS |  | 2 |  | Wind | Pipestone County | MN | [27 empty] | Done | 2000-05-31 |  |  |  | Northern States Power (Xcel Energy) | Pipestone County | MN |  |  |  | ERIS | Unknown | 2 | 2 | Wind | WT Wind Turbine | In Service | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G042 | [5 empty] | ERIS |  | 332 |  | Gas | St. Clair County | MI | [27 empty] | Done | 2000-06-21 |  |  |  | ITC Transmission | St. Clair County | MI |  |  |  | ERIS | Unknown | 332 | 332 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | G043 | G043 | Done | In Service | G043 | [5 empty] | ERIS |  | 37 |  | Biomass | Ramsey County | MN | [27 empty] | Done | 2000-06-21 |  |  |  | Northern States Power (Xcel Energy) | Ramsey County | MN | G043 | G043 | Network Upgrade | ERIS | High Bridge Substation | 37 | 37 | Biomass |  | In Service | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G044 | [5 empty] | ERIS |  | 600 |  | Gas | Outagamie County | WI | [27 empty] | Done | 2000-06-28 |  |  |  | Wisconsin Electric Power Company | Outagamie County | WI |  |  | Network Upgrade | ERIS | Point Beach - North Appleton 345kV | 600 | 600 | Gas | Combined Cycle | In Service |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G246 | [5 empty] | ERIS |  | 100 |  | 0 | Mower County | MN | [27 empty] | Withdrawn | 2002-08-19 | 2002-09-05 | 2002-09-05 |  | Northern States Power (Xcel Energy) | Mower County | MN |  |  |  | ERIS | Unknown | 100 | 100 |  |  | Not Started | 2003-10-01 | 0 | 0 | 0 | 0
|  |  |  | G046 | G046 | Done | In Service | G046 | [5 empty] | ERIS |  | 200 |  | Wind | Worth County | IA | [27 empty] | Done | 2000-07-23 |  | 2003-11-24 |  | ITC Midwest | Worth County | IA | G046 | G046 | Network Upgrade | ERIS | Worth County switching station | 200 | 200 | Wind | WT Wind Turbine | In Service | 2002-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G217 CONS 111 | [5 empty] | ERIS |  | 630 |  | Combined Cycle | Kent County | MI | [27 empty] | Withdrawn | 2001-12-04 | 2002-10-15 | 2002-10-15 |  | Michigan Electric Transmission Company, LLC | Kent County | MI |  |  |  | ERIS | Unknown | 630 | 630 | Combined Cycle |  | Not Started | 2007-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G223 | [5 empty] | ERIS |  | 750 |  | Combined Cycle | Dakota County | MN | [27 empty] | Withdrawn | 2002-04-29 | 2002-10-28 | 2002-10-28 |  | Northern States Power (Xcel Energy) | Dakota County | MN |  |  |  | ERIS | Unknown | 750 | 750 | Combined Cycle |  | Not Started | 2006-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G137 | [5 empty] | ERIS |  | 560 |  | Gas | St. Clair County | MI | [27 empty] | Withdrawn | 2001-10-04 | 2002-11-04 | 2002-11-04 |  | ITC Transmission | St. Clair County | MI |  |  |  | ERIS | Unknown | 560 | 560 | Gas |  | Not Started | 1905-06-26 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G051 | [5 empty] | ERIS |  | 1300 |  | Coal | Milwaukee County | WI | [27 empty] | Done | 2000-08-22 |  |  |  | Wisconsin Electric Power Company | Milwaukee County | WI |  |  | Network Upgrade | ERIS | Oak Creek Substation | 1300 | 1300 | Coal | Combined Cycle | In Service | 2003-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G183 | [5 empty] | ERIS |  | 200 |  | Wind | Murray County | MN | [27 empty] | Withdrawn | 2002-03-14 | 2002-11-06 | 2002-11-06 |  | ITC Midwest | Murray County | MN |  |  |  | ERIS | Unknown | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G221 | [5 empty] | ERIS |  | 180 |  | Wind | Dickey County | ND | [27 empty] | Withdrawn | 2002-04-16 | 2002-11-13 | 2002-11-13 |  | Montana-Dakota Utilities Company | Dickey County | ND |  |  |  | ERIS | Unknown | 180 | 180 | Wind | WT Wind Turbine | Not Started | 2005-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G229 | [5 empty] | ERIS |  | 30 |  | Wind | Oceana County | MI | [27 empty] | Withdrawn | 2002-04-24 | 2002-11-13 | 2002-11-13 |  | Michigan Electric Transmission Company, LLC | Oceana County | MI |  |  |  | ERIS | Unknown | 30 | 30 | Wind | WT Wind Turbine | Not Started | 2005-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G257 | [5 empty] | ERIS |  | 83 |  | 0 | Gibson County | IN | [27 empty] | Withdrawn | 2002-09-23 | 2002-12-04 | 2002-12-04 |  | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Gibson County | IN |  |  |  | ERIS | Unknown | 83 | 83 |  |  | Not Started | 2005-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G056 | [5 empty] | ERIS |  | 80 |  | Wind | Hancock County | IA | [27 empty] | Done | 2000-09-01 |  |  |  | ITC Midwest | Hancock County | IA |  |  |  | ERIS | Sioux Avenue Substation | 80 | 80 | Wind | WT Wind Turbine | In Service | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G057 | [5 empty] | ERIS |  | 80 |  | Wind | Murray County | MN | [27 empty] | Done | 2000-09-08 |  | 2003-11-14 |  | Northern States Power (Xcel Energy) | Murray County | MN |  |  |  | ERIS | Unknown | 80 | 80 | Wind | WT Wind Turbine | In Service | 1905-06-22 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G058 | [5 empty] | ERIS |  | 3 |  | Diesel | Grant County | SD | [27 empty] | Done | 2000-09-08 |  |  |  | Otter Tail Power Company | Grant County | SD |  |  |  | ERIS | Valley Queen 12.5kV | 3 | 3 | Diesel | IC Internal Combustion (diesel, piston) Engine | In Service | 2001-04-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G059 | [5 empty] | ERIS |  | 50 |  | Gas | Beltrami County | MN | [27 empty] | Done | 2000-09-08 |  | 2003-03-28 | 2003-04-01 | Otter Tail Power Company | Beltrami County | MN |  |  | SPA - SIS | ERIS | Solway CT substation | 50 | 50 | Gas | CT Combustion Turbine (Simple Cycle) | In Service |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G060 | [5 empty] | ERIS |  | 100 |  | Wind | Murray County | MN | [27 empty] | Done | 2000-09-18 |  | 2007-07-30 |  | Northern States Power (Xcel Energy) | Murray County | MN |  |  | SPA - SIS | ERIS | Chanarambie Substation | 100 | 100 | Wind | WT Wind Turbine | In Service | 2001-02-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G045 | [5 empty] | ERIS |  | 330 |  | 0 | Rock County | WI | [27 empty] | Withdrawn | 2000-07-07 | 2002-12-17 | 2002-12-17 |  | American Transmission Co. LLC | Rock County | WI |  |  | Network Upgrade | ERIS | Unknown | 330 | 330 |  |  | Withdrawn |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G029 | [5 empty] | ERIS |  | 500 |  | 0 | Lawrence County | IN | [27 empty] | Withdrawn | 2000-01-31 | 2002-12-30 | 2002-12-30 |  | Duke Energy Corporation | Lawrence County | IN |  |  |  | ERIS | Unknown | 500 | 500 |  |  | Not Started | 2002-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G030 | [5 empty] | ERIS |  | 500 |  | 0 | Switzerland County | IN | [27 empty] | Withdrawn | 2000-01-31 | 2002-12-30 | 2002-12-30 |  | Duke Energy Corporation | Switzerland County | IN |  |  |  | ERIS | Unknown | 500 | 500 |  |  | Not Started | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G064 | [5 empty] | ERIS |  | 210 |  | Gas | Hamilton County | IN | [27 empty] | Done | 2000-10-27 |  |  |  | Duke Energy Corporation | Hamilton County | IN |  |  | Network Upgrade | ERIS | Noblesville | 210 | 210 | Gas | Combined Cycle | In Service | 2005-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G260 | [5 empty] | ERIS |  | 1061 |  | Combined Cycle | Goodhue County | MN | [27 empty] | Withdrawn | 2002-10-11 | 2003-02-18 | 2003-02-18 |  | Northern States Power (Xcel Energy) | Goodhue County | MN |  |  |  | ERIS | Unknown | 1061 | 1061 | Combined Cycle |  | Not Started | 2004-04-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G075 | [5 empty] | ERIS |  | 500 |  | 0 | Putnam County | IN | [27 empty] | Withdrawn | 2001-01-31 | 2003-02-28 | 2003-02-28 |  | Duke Energy Corporation | Putnam County | IN |  |  | SPA - SIS | ERIS | Unknown | 500 | 500 |  |  | Withdrawn | 2003-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G067 | [5 empty] | ERIS |  | 2 |  | Diesel | Cass County | ND | [27 empty] | Done | 2000-11-09 |  |  |  | Otter Tail Power Company | Cass County | ND |  |  |  | ERIS | Unknown | 2 | 2 | Diesel |  | In Service | 2004-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G249 | [5 empty] | ERIS |  | 110 |  | Gas | Shawano County | WI | [27 empty] | Withdrawn | 2002-08-27 | 2003-03-04 | 2003-03-04 |  | American Transmission Co. LLC | Shawano County | WI |  |  |  | ERIS | Unknown | 110 | 110 | Gas |  | Not Started | 2003-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Not Started | G069 | [5 empty] | ERIS |  | 174 |  | Gas | Trimble County | KY | [27 empty] | Done | 2000-12-21 |  |  |  | LG&E and KU Services Company as agent for Louisville Gas and Electric Company and Kentucky Utilities Company | Trimble County | KY |  |  |  | ERIS | Unknown | 174 | 174 | Gas |  | Not Started | 2001-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G123 | [5 empty] | ERIS |  | 2 |  | 0 | Murray County | MN | [27 empty] | Withdrawn | 2001-09-04 | 2003-03-07 | 2003-03-07 |  | Northern States Power (Xcel Energy) | Murray County | MN |  |  |  | ERIS | Unknown | 2 | 2 |  |  | Not Started | 2003-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G124 | [5 empty] | ERIS |  | 1 |  | 0 | Murray County | MN | [27 empty] | Withdrawn | 2001-09-04 | 2003-03-07 | 2003-03-07 |  | Northern States Power (Xcel Energy) | Murray County | MN |  |  |  | ERIS | Unknown | 1 | 1 |  |  | Not Started | 2005-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G072 | [5 empty] | ERIS |  | 150 |  | Combined Cycle | Rock County | WI | [27 empty] | Done | 2001-01-17 |  | 2002-08-02 |  | American Transmission Co. LLC | Rock County | WI |  |  | Network Upgrade | ERIS | Rock River Substation | 150 | 150 | Combined Cycle | Combined Cycle | In Service | 2009-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G073 | [5 empty] | ERIS |  | 1 |  | Wind | Lincoln County | MN | [27 empty] | Done | 2001-01-26 |  | 2001-01-01 |  | Otter Tail Power Company | Lincoln County | MN |  |  |  | ERIS | Unknown | 1 | 1 | Wind | WT Wind Turbine | In Service | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G074 | [5 empty] | ERIS |  | 50 |  | Combined Cycle | Outagamie County | WI | [27 empty] | Done | 2001-01-31 |  |  |  | -- No Company -- | Outagamie County | WI |  |  | Network Upgrade | ERIS | Unknown | 50 | 50 | Combined Cycle |  | In Service | 2005-03-07 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G181 | [5 empty] | ERIS |  | 600 |  | Gas | Buchanan County | IA | [27 empty] | Withdrawn | 2002-03-08 | 2003-03-13 | 2003-03-13 |  | ITC Midwest | Buchanan County | IA |  |  |  | ERIS | Unknown | 600 | 600 | Gas |  | Not Started | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G224 | [5 empty] | ERIS |  | 60 |  | Gas | Outagamie County | WI | [27 empty] | Withdrawn | 2002-05-06 | 2003-03-15 | 2003-03-15 |  | American Transmission Co. LLC | Outagamie County | WI |  |  | SPA - SIS | ERIS | Unknown | 60 | 60 | Gas |  | Not Started | 2002-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G071 | [5 empty] | ERIS |  | 41 |  | 0 | Greene County | OH | [27 empty] | Withdrawn | 2001-01-09 | 2003-03-17 | 2003-03-17 |  | DEO&K | Greene County | OH |  |  |  | ERIS | Unknown | 41 | 41 |  |  | Not Started | 2006-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G169 | [5 empty] | ERIS |  | 120 |  | Coal | Sherburne County | MN | [27 empty] | Withdrawn | 2002-01-15 | 2003-03-25 | 2003-03-25 |  | Northern States Power (Xcel Energy) | Sherburne County | MN |  |  |  | ERIS | Unknown | 120 | 120 | Coal |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G296 | [5 empty] | ERIS |  | 25 |  | Wind | McPherson County | SD | [27 empty] | Withdrawn | 2003-02-10 | 2003-04-01 | 2003-04-01 |  | Montana-Dakota Utilities Company | McPherson County | SD |  |  |  | ERIS | Unknown | 25 | 25 | Wind | WT Wind Turbine | Not Started | 2009-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G011 | [5 empty] | ERIS |  | 900 |  | Gas | Pike County | IN | [27 empty] | Withdrawn | 1999-10-08 | 2003-04-02 | 2003-04-02 |  | Duke Energy Corporation | Pike County | IN |  |  | SPA - SIS | ERIS | Unknown | 900 | 900 | Gas |  | Withdrawn | 2002-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Not Started | G081 | [5 empty] | ERIS |  | 1 |  | Wind | Pipestone County | MN | [27 empty] | Done | 2001-02-22 |  | 2004-02-10 |  | Northern States Power (Xcel Energy) | Pipestone County | MN |  |  |  | ERIS | Unknown | 1 | 1 | Wind | WT Wind Turbine | Not Started | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G315 | [5 empty] | ERIS |  | 80 |  | Wind | Pocahontas County | IA | [27 empty] | Withdrawn | 2003-03-27 | 2003-04-02 | 2003-04-02 |  | MidAmerican Energy Company | Pocahontas County | IA |  |  |  | ERIS | Unknown | 80 | 80 | Wind | WT Wind Turbine | Not Started | 2004-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G316 | [5 empty] | ERIS |  | 80 |  | 0 | O'Brien County | IA | [27 empty] | Withdrawn | 2003-03-27 | 2003-04-02 | 2003-04-02 |  | ITC Midwest | O'Brien County | IA |  |  |  | ERIS | Unknown | 80 | 80 |  |  | Not Started | 2004-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G084 | [5 empty] | ERIS |  | 320 |  | Gas | Lawrence County | IN | [27 empty] | Done | 2001-03-05 |  | 2004-02-10 |  | Hoosier Energy REC, Inc. | Lawrence County | IN |  |  | SPA - SIS | ERIS | Napoleon - Taswell 161kV | 320 | 320 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2005-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Not Started | G085 | [5 empty] | ERIS |  | 7 |  | 0 | Jackson County | WI | [27 empty] | Done | 2001-03-05 |  |  |  | Northern States Power (Xcel Energy) | Jackson County | WI |  |  |  | ERIS | Unknown | 7 | 7 |  |  | Not Started | 2005-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G318 | [5 empty] | ERIS |  | 125 |  | 0 | Sioux County | IA | [27 empty] | Withdrawn | 2003-03-27 | 2003-04-02 | 2003-04-02 |  | ITC Midwest | Sioux County | IA |  |  |  | ERIS | Unknown | 125 | 125 |  |  | Not Started | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G154 | [5 empty] | ERIS |  | 150 |  | Wind | Deuel County | SD | [27 empty] | Withdrawn | 2001-11-16 | 2003-04-03 | 2003-04-03 |  | Otter Tail Power Company | Deuel County | SD |  |  |  | ERIS | Unknown | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2003-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G266 | [5 empty] | ERIS |  | 1005 |  | Combined Cycle | Scott County | MN | [27 empty] | Withdrawn | 2002-11-18 | 2003-04-03 | 2003-04-03 |  | Northern States Power (Xcel Energy) | Scott County | MN |  |  |  | ERIS | Unknown | 1005 | 1005 | Combined Cycle |  | Not Started | 2005-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G277 | [5 empty] | ERIS |  | 19 |  | 0 | Dickey County | ND | [27 empty] | Withdrawn | 2002-12-16 | 2003-04-03 | 2003-04-03 |  | Montana-Dakota Utilities Company | Dickey County | ND |  |  |  | ERIS | Unknown | 19 | 19 |  |  | Not Started | 2003-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G093 | [5 empty] | ERIS |  | 200 |  | Combined Cycle | Ozaukee County | WI | [27 empty] | Done | 2001-04-23 |  | 2001-12-14 |  | Wisconsin Electric Power Company | Ozaukee County | WI |  |  | SPA - SIS | ERIS | Port Washington Substation | 200 | 200 | Combined Cycle | Combined Cycle | In Service | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G134 | [5 empty] | ERIS |  | 840 |  | 0 | Washtenaw County | MI | [27 empty] | Withdrawn | 2001-09-18 | 2003-04-07 | 2003-04-07 |  | ITC Transmission | Washtenaw County | MI |  |  |  | ERIS | Unknown | 840 | 840 |  |  | Not Started | 2007-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G226.1 | [5 empty] | ERIS |  | 60 |  | 0 | Ingham County | MI | [27 empty] | Withdrawn | 2002-04-10 | 2003-04-09 | 2003-04-09 |  | Michigan Electric Transmission Company, LLC | Ingham County | MI |  |  |  | ERIS | Unknown | 60 | 60 |  |  | Not Started | 2004-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G096 | [5 empty] | ERIS |  | 105 |  | Combined Cycle | Dane County | WI | [27 empty] | Done | 2001-06-13 |  | 2002-11-01 | 2005-03-07 | Madison Gas and Electric Company | Dane County | WI |  |  | Network Upgrade | ERIS | Walnut 69 kV substation | 105 | 105 | Combined Cycle | Combined Cycle | In Service | 2002-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G227 | [5 empty] | ERIS |  | 24 |  | 0 | Ingham County | MI | [27 empty] | Withdrawn | 2002-04-10 | 2003-04-09 | 2003-04-09 |  | Michigan Electric Transmission Company, LLC | Ingham County | MI |  |  |  | ERIS | Unknown | 24 | 24 |  |  | Not Started | 2002-08-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G082 | [5 empty] | ERIS |  | 600 |  | 0 | Hamilton County | OH | [27 empty] | Withdrawn | 2001-03-05 | 2003-04-11 | 2003-04-11 |  | DEO&K | Hamilton County | OH |  |  |  | ERIS | Unknown | 600 | 600 |  |  | Not Started | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G087 | [5 empty] | ERIS |  | 200 |  | 0 | Grant County | WI | [27 empty] | Withdrawn | 2001-03-22 | 2003-04-14 | 2003-04-14 |  | American Transmission Co. LLC | Grant County | WI |  |  | SPA - SIS | ERIS | Unknown | 200 | 200 |  |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G094 | [5 empty] | ERIS |  | 30 |  | 0 | Butler County | OH | [27 empty] | Withdrawn | 2001-05-18 | 2003-04-17 | 2003-04-17 |  | DEO&K | Butler County | OH |  |  |  | ERIS | Unknown | 30 | 30 |  |  | Not Started | 2002-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G275 | [5 empty] | ERIS |  | 19 |  | Wind | McPherson County | SD | [27 empty] | Withdrawn | 2002-12-12 | 2003-04-17 | 2003-04-17 |  | Montana-Dakota Utilities Company | McPherson County | SD |  |  |  | ERIS | Unknown | 19 | 19 | Wind | WT Wind Turbine | Not Started | 2004-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G283 | [5 empty] | ERIS |  | 19 |  | Wind | McIntosh County | ND | [27 empty] | Withdrawn | 2003-01-09 | 2003-04-17 | 2003-04-17 |  | Montana-Dakota Utilities Company | McIntosh County | ND |  |  |  | ERIS | Unknown | 19 | 19 | Wind | WT Wind Turbine | Not Started | 2003-12-01 | 0 | 0 | 0 | 0
|  |  |  | G103 | G103 | Done | In Service | G103 | [5 empty] | ERIS |  | 370 |  | Wind | Sheboygan County | WI | [27 empty] | Done | 2001-06-20 |  | 2004-01-06 |  | American Transmission Co. LLC | Sheboygan County | WI | G103 | G103 | Network Upgrade | ERIS | Point Beach - Sheboygan Switching Station | 370 | 370 | Wind | WT Wind Turbine | In Service | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G284 | [5 empty] | ERIS |  | 19 |  | Wind | Dickey County | ND | [27 empty] | Withdrawn | 2003-01-09 | 2003-04-17 | 2003-04-17 |  | Montana-Dakota Utilities Company | Dickey County | ND |  |  |  | ERIS | Unknown | 19 | 19 | Wind | WT Wind Turbine | Not Started | 2003-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G276 | [5 empty] | ERIS |  | 300 |  | 0 | Stutsman County | ND | [27 empty] | Withdrawn | 2002-12-12 | 2003-04-28 | 2003-04-28 |  | Otter Tail Power Company | Stutsman County | ND |  |  |  | ERIS | Unknown | 300 | 300 |  |  | Not Started | 2005-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G302 | [5 empty] | ERIS |  | 160 |  | 0 | Green Lake County | WI | [27 empty] | Withdrawn | 2003-02-24 | 2003-04-28 | 2003-04-28 |  | American Transmission Co. LLC | Green Lake County | WI |  |  |  | ERIS | Unknown | 160 | 160 |  |  | Not Started | 2003-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G303 | [5 empty] | ERIS |  | 100 |  | 0 | Columbia County | WI | [27 empty] | Withdrawn | 2003-02-24 | 2003-04-28 | 2003-04-28 |  | American Transmission Co. LLC | Columbia County | WI |  |  |  | ERIS | Unknown | 100 | 100 |  |  | Not Started | 2003-04-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G306 | [5 empty] | ERIS |  | 200 |  | 0 | Dodge County | WI | [27 empty] | Withdrawn | 2003-03-03 | 2003-05-01 | 2003-05-01 |  | American Transmission Co. LLC | Dodge County | WI |  |  |  | ERIS | Unknown | 200 | 200 |  |  | Not Started | 2004-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G320 | [5 empty] | ERIS |  | 8 |  | Diesel | Marinette County | WI | [27 empty] | Withdrawn | 2003-03-31 | 2003-05-01 | 2003-05-01 |  | American Transmission Co. LLC | Marinette County | WI |  |  |  | ERIS | Unknown | 8 | 8 | Diesel |  | Not Started | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G111 | [5 empty] | ERIS |  | 85 |  | Coal | Brown County | WI | [27 empty] | Done | 2001-08-03 |  |  |  | Wisconsin Public Service Corporation | Brown County | WI |  |  | Network Upgrade | ERIS | Unknown | 85 | 85 | Coal |  | In Service | 2011-03-11 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G321 | [5 empty] | ERIS |  | 7 |  | 0 | Marathon County | WI | [27 empty] | Withdrawn | 2003-03-31 | 2003-05-01 | 2003-05-01 |  | American Transmission Co. LLC | Marathon County | WI |  |  |  | ERIS | Unknown | 7 | 7 |  |  | Not Started | 2003-10-01 | 0 | 0 | 0 | 0
|  |  |  | G113 | G113 | Done | In Service | G113 | [5 empty] | ERIS |  | 200 |  | Wind | Mower County | MN | [27 empty] | Done | 2001-08-08 |  | 2005-04-27 | 2006-12-31 | ITC Midwest | Mower County | MN | G113 | G113 | Network Upgrade | ERIS | Adams Substation | 200 | 200 | Wind | WT Wind Turbine | In Service | 2005-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G053 | [5 empty] | ERIS |  | 260 |  | Gas | Posey County | IN | [27 empty] | Withdrawn | 2000-03-20 | 2003-05-21 | 2003-05-21 |  | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Posey County | IN |  |  |  | ERIS | Unknown | 260 | 260 | Gas |  | Withdrawn | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G033 | [5 empty] | ERIS |  | 230 |  | Steam | Monroe County | IA | [27 empty] | Withdrawn | 2000-03-24 | 2003-05-22 | 2003-05-22 |  | ITC Midwest | Monroe County | IA |  |  | SPA - SIS | ERIS | Unknown | 230 | 230 | Steam |  | Not Started | 2001-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G108 | [5 empty] | ERIS |  | 1000 |  | 0 | Henderson County | KY | [27 empty] | Withdrawn | 2001-07-06 | 2003-05-27 | 2003-05-27 |  | LG&E and KU Services Company as agent for Louisville Gas and Electric Company and Kentucky Utilities Company | Henderson County | KY |  |  |  | ERIS | Unknown | 1000 | 1000 |  |  | Not Started | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | G117 | G117 | Done | Withdrawn | G117 | [5 empty] | ERIS |  | 324 |  | Combined Cycle | Douglas County | WI | [27 empty] | Done | 2001-08-09 |  | 2008-12-19 | 2014-05-01 | Minnesota Power (Allete, Inc.) | Douglas County | WI | G117 | G117 | Network Upgrade | ERIS | Stinson 115 kV Substation | 324 | 324 | Combined Cycle | Combined Cycle | Withdrawn | 2003-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G307 | [5 empty] | ERIS |  | 19 |  | Wind | McIntosh County | ND | [27 empty] | Withdrawn | 2003-03-12 | 2003-06-03 | 2003-06-03 |  | Montana-Dakota Utilities Company | McIntosh County | ND |  |  |  | ERIS | Unknown | 19 | 19 | Wind | WT Wind Turbine | Not Started | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G308 | [5 empty] | ERIS |  | 19 |  | Wind | McIntosh County | ND | [27 empty] | Withdrawn | 2003-03-12 | 2003-06-03 | 2003-06-03 |  | Montana-Dakota Utilities Company | McIntosh County | ND |  |  |  | ERIS | Unknown | 19 | 19 | Wind | WT Wind Turbine | Not Started | 2004-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G312 | [5 empty] | ERIS |  | 19 |  | Wind | Dickey County | ND | [27 empty] | Withdrawn | 2003-03-20 | 2003-06-03 | 2003-06-03 |  | Montana-Dakota Utilities Company | Dickey County | ND |  |  |  | ERIS | Unknown | 19 | 19 | Wind | WT Wind Turbine | Not Started | 2003-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G313 | [5 empty] | ERIS |  | 19 |  | Wind | Dickey County | ND | [27 empty] | Withdrawn | 2003-03-20 | 2003-06-03 | 2003-06-03 |  | Montana-Dakota Utilities Company | Dickey County | ND |  |  |  | ERIS | Unknown | 19 | 19 | Wind | WT Wind Turbine | Not Started | 2008-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G269 | [5 empty] | ERIS |  | 100 |  | Wind | Mower County | MN | [27 empty] | Withdrawn | 2002-11-19 | 2003-06-16 | 2003-06-16 |  | Northern States Power (Xcel Energy) | Mower County | MN |  |  |  | ERIS | Unknown | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2005-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G219 | [5 empty] | ERIS |  | 650 |  | Combined Cycle | Johnson County | IA | [27 empty] | Withdrawn | 2002-04-15 | 2003-06-23 | 2003-06-23 |  | MidAmerican Energy Company | Johnson County | IA |  |  |  | ERIS | Unknown | 650 | 650 | Combined Cycle |  | Not Started | 2006-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G268 | [5 empty] | ERIS |  | 189 |  | Gas | Wood County | WI | [27 empty] | Withdrawn | 2002-11-18 | 2003-06-24 | 2003-06-24 |  | American Transmission Co. LLC | Wood County | WI |  |  |  | ERIS | Unknown | 189 | 189 | Gas |  | Withdrawn | 2005-03-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G264 | [5 empty] | ERIS |  | 905 |  | Gas | Chisago County | MN | [27 empty] | Withdrawn | 2002-11-12 | 2003-06-25 | 2003-06-25 |  | Northern States Power (Xcel Energy) | Chisago County | MN |  |  |  | ERIS | Unknown | 905 | 905 | Gas |  | Not Started | 2007-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G254 | [5 empty] | ERIS |  | 590 |  | Gas | Portage County | WI | [27 empty] | Withdrawn | 2002-12-16 | 2003-06-30 | 2003-06-30 |  | American Transmission Co. LLC | Portage County | WI |  |  |  | ERIS | Unknown | 590 | 590 | Gas |  | Withdrawn | 2003-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G288 | [5 empty] | ERIS |  | 100 |  | Wind | Walworth County | WI | [27 empty] | Withdrawn | 2003-01-03 | 2003-06-30 | 2003-06-30 |  | American Transmission Co. LLC | Walworth County | WI |  |  |  | ERIS | Unknown | 100 | 100 | Wind | WT Wind Turbine | Withdrawn |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G289 | [5 empty] | ERIS |  | 100 |  | Wind | Rock County | WI | [27 empty] | Withdrawn | 2003-01-03 | 2003-06-30 | 2003-06-30 |  | American Transmission Co. LLC | Rock County | WI |  |  |  | ERIS | Unknown | 100 | 100 | Wind | WT Wind Turbine | Withdrawn | 2003-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G233 | [5 empty] | ERIS |  | 10 |  | Wind | Murray County | MN | [27 empty] | Withdrawn | 2002-06-03 | 2003-07-07 | 2003-07-07 |  | Northern States Power (Xcel Energy) | Murray County | MN |  |  |  | ERIS | Unknown | 10 | 10 | Wind | WT Wind Turbine | Not Started | 2003-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G015 | [5 empty] | ERIS |  | 800 |  | Combined Cycle | Lawrence County | IN | [27 empty] | Withdrawn | 1999-11-22 | 2003-07-09 | 2003-07-09 |  | Duke Energy Corporation | Lawrence County | IN |  |  | SPA - SIS | ERIS | Unknown | 800 | 800 | Combined Cycle |  | Withdrawn | 2003-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G304 | [5 empty] | ERIS |  | 250 |  | Gas | Putnam County | IN | [27 empty] | Withdrawn | 2003-02-28 | 2003-07-09 | 2003-07-09 |  | Duke Energy Corporation | Putnam County | IN |  |  |  | ERIS | Unknown | 250 | 250 | Gas |  | Not Started | 2004-11-01 | 0 | 0 | 0 | 0
|  |  |  | G132 | G132 | Done | In Service | G132 | [5 empty] | NRIS |  | 180 |  | Wind | Dickey County | ND | [27 empty] | Done | 2001-09-17 |  | 2005-10-24 |  | Montana-Dakota Utilities Company | Dickey County | ND | G132 | G132 | Network Upgrade | NRIS | Ellendale Sub 230 kV | 180 | 180 | Wind | WT Wind Turbine | In Service | 2003-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G118 | [5 empty] | ERIS |  | 650 |  | 0 | Grant County | SD | [27 empty] | Withdrawn | 2001-08-14 | 2003-07-10 | 2003-07-10 |  | Otter Tail Power Company | Grant County | SD |  |  | SPA - SIS | ERIS | Unknown | 650 | 650 |  |  | Not Started | 2005-06-24 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G244 | [5 empty] | ERIS |  | 100 |  | 0 | Mower County | MN | [27 empty] | Withdrawn | 2002-08-02 | 2003-07-10 | 2003-07-10 |  | Great River Energy | Mower County | MN |  |  |  | ERIS | Unknown | 100 | 100 |  |  | Not Started | 2005-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G245 | [5 empty] | ERIS |  | 100 |  | 0 | Mower County | MN | [27 empty] | Withdrawn | 2002-08-02 | 2003-07-10 | 2003-07-10 |  | Great River Energy | Mower County | MN |  |  |  | ERIS | Unknown | 100 | 100 |  |  | Not Started | 2002-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G106 | [5 empty] | ERIS |  | 520 |  | Combined Cycle | Wayne County | MI | [27 empty] | Withdrawn | 2001-07-01 | 2003-07-14 | 2003-07-14 |  | ITC Transmission | Wayne County | MI |  |  |  | ERIS | Unknown | 520 | 520 | Combined Cycle |  | Not Started | 2005-06-25 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G332 | [5 empty] | ERIS |  | 80 |  | Wind | Shawano County | WI | [27 empty] | Withdrawn | 2003-04-17 | 2003-07-14 | 2003-07-14 |  | American Transmission Co. LLC | Shawano County | WI |  |  |  | ERIS | Unknown | 80 | 80 | Wind | WT Wind Turbine | Not Started | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G333 | [5 empty] | ERIS |  | 80 |  | Wind | Shawano County | WI | [27 empty] | Withdrawn | 2003-04-17 | 2003-07-14 | 2003-07-14 |  | American Transmission Co. LLC | Shawano County | WI |  |  |  | ERIS | Unknown | 80 | 80 | Wind | WT Wind Turbine | Withdrawn | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | G009.NU2 | G009.NU2 | Withdrawn | Withdrawn | G009 | [5 empty] | ERIS |  | 640 |  | 0 | Vigo County | IN | [27 empty] | Withdrawn | 1999-07-30 | 2003-07-16 | 2003-07-16 |  | Duke Energy Corporation | Vigo County | IN | G009.NU2 | G009.NU2 | Network Upgrade | ERIS | Unknown | 640 | 640 |  |  | Withdrawn |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G140 | [5 empty] | ERIS |  | 2 |  | 0 | Nobles County | MN | [27 empty] | Done | 2001-10-15 |  |  |  | ITC Midwest | Nobles County | MN |  |  |  | ERIS | Unknown | 2 | 2 |  |  | In Service |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Withdrawn | G141 | [5 empty] | ERIS |  | 46 |  | Gas | Le Sueur County | MN | [27 empty] | Done | 2001-10-16 |  | 2004-02-20 |  | Northern States Power (Xcel Energy) | Le Sueur County | MN |  |  | SPA - SIS | ERIS | Loon Lake - Loon Tap 115kV | 46 | 46 | Gas | CT Combustion Turbine (Simple Cycle) | Withdrawn | 2007-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G142 | [5 empty] | ERIS |  | 2 |  | 0 | Nobles County | MN | [27 empty] | Done | 2001-10-19 |  |  |  | ITC Midwest | Nobles County | MN |  |  |  | ERIS | Unknown | 2 | 2 |  |  | In Service | 2001-12-20 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G279 | [5 empty] | ERIS |  | 4 |  | 0 | Lincoln County | MN | [27 empty] | Withdrawn | 2002-12-23 | 2003-08-08 | 2003-08-08 |  | Northern States Power (Xcel Energy) | Lincoln County | MN |  |  |  | ERIS | Unknown | 4 | 4 |  |  | Not Started | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G144 | [5 empty] | ERIS |  | 550 |  | Coal | Marathon County | WI | [27 empty] | Done | 2001-10-23 |  | 2004-01-08 |  | Wisconsin Public Service Corporation | Marathon County | WI |  |  | SPA - SIS | ERIS | WPS Weston 345 kV Substation | 550 | 550 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | In Service | 2004-03-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G280 | [5 empty] | ERIS |  | 4 |  | 0 | Lincoln County | MN | [27 empty] | Withdrawn | 2002-12-23 | 2003-08-08 | 2003-08-08 |  | Northern States Power (Xcel Energy) | Lincoln County | MN |  |  |  | ERIS | Unknown | 4 | 4 |  |  | Not Started | 2003-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G146 | [5 empty] | ERIS |  | 4 |  | Biomass | Otter Tail County | MN | [27 empty] | Done | 2001-10-30 |  |  |  | Otter Tail Power Company | Otter Tail County | MN |  |  |  | ERIS | PRRF Substation | 4 | 4 | Biomass | OT Other | In Service | 2006-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G336 | [5 empty] | ERIS |  | 55 |  | Gas | Rice County | MN | [27 empty] | Withdrawn | 2003-04-17 | 2003-09-12 | 2003-09-12 |  | Northern States Power (Xcel Energy) | Rice County | MN |  |  |  | ERIS | Unknown | 55 | 55 | Gas |  | Not Started | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G148 | [5 empty] | ERIS |  | 20 |  | Gas | Juneau County | WI | [27 empty] | Done | 2001-11-09 |  | 2002-12-11 |  | American Transmission Co. LLC | Juneau County | WI |  |  | Network Upgrade | ERIS | Unknown | 20 | 20 | Gas |  | In Service | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | Not Started | G150 | [5 empty] | ERIS |  | 12 |  | 0 | McIntosh County | ND | [28 empty] | 2001-11-13 |  |  |  | Montana-Dakota Utilities Company | McIntosh County | ND |  |  |  | ERIS | Unknown | 12 | 12 |  |  | Not Started | 2002-02-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G105 | [5 empty] | ERIS |  | 40 |  | Coal | Wayne County | MI | [27 empty] | Withdrawn | 2001-06-29 | 2003-09-16 | 2003-09-16 |  | ITC Transmission | Wayne County | MI |  |  | Network Upgrade | ERIS | Unknown | 40 | 40 | Coal |  | Withdrawn | 2003-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G168 | [5 empty] | ERIS |  | 700 |  | Combined Cycle | Dakota County | MN | [27 empty] | Withdrawn | 2002-01-14 | 2003-09-17 | 2003-09-17 |  | Northern States Power (Xcel Energy) | Dakota County | MN |  |  | Network Upgrade | ERIS | Unknown | 700 | 700 | Combined Cycle |  | Not Started | 2005-03-07 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G250 | [5 empty] | ERIS |  | 4 |  | Biomass | Shiawassee County | MI | [27 empty] | Withdrawn | 2002-08-26 | 2003-09-17 | 2003-09-17 |  | Michigan Electric Transmission Company, LLC | Shiawassee County | MI |  |  | SPA - SIS | ERIS | Unknown | 4 | 4 | Biomass |  | Withdrawn | 2003-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G271 | [5 empty] | ERIS |  | 670 |  | Combined Cycle | Dakota County | MN | [27 empty] | Withdrawn | 2002-12-01 | 2003-09-17 | 2003-09-17 |  | Northern States Power (Xcel Energy) | Dakota County | MN |  |  |  | ERIS | Unknown | 670 | 670 | Combined Cycle |  | Not Started | 2004-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G328 | [5 empty] | ERIS |  | 12 |  | Wind | McHenry County | ND | [27 empty] | Withdrawn | 2003-04-01 | 2003-09-30 | 2003-09-30 |  | Northern States Power (Xcel Energy) | McHenry County | ND |  |  |  | ERIS | Unknown | 12 | 12 | Wind | WT Wind Turbine | Not Started | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G339 | [5 empty] | ERIS |  | 150 |  | Wind | Dickey County | ND | [27 empty] | Withdrawn | 2003-05-02 | 2003-10-07 | 2003-10-07 |  | Montana-Dakota Utilities Company | Dickey County | ND |  |  |  | ERIS | Unknown | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2003-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G062 | [5 empty] | ERIS |  | 755 |  | 0 | Wood County | WI | [27 empty] | Withdrawn | 2000-10-12 | 2003-10-08 | 2003-10-08 |  | American Transmission Co. LLC | Wood County | WI |  |  | Network Upgrade | ERIS | Unknown | 755 | 755 |  |  | Withdrawn | 2001-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G160 | [5 empty] | ERIS |  | 45 |  | Gas | Dane County | WI | [27 empty] | Done | 2001-11-30 |  | 2003-05-23 |  | Madison Gas and Electric Company | Dane County | WI |  |  | Network Upgrade | ERIS | Walnut 69 kV substation | 45 | 45 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2003-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G314 | [5 empty] | ERIS |  | 50 |  | Wind | Cavalier County | ND | [27 empty] | Withdrawn | 2003-03-26 | 2003-11-11 | 2003-11-11 |  | Montana-Dakota Utilities Company | Cavalier County | ND |  |  |  | ERIS | Unknown | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2004-12-01 | 0 | 0 | 0 | 0
|  |  |  | G162 | G162 | Done | In Service | G162 | [5 empty] | NRIS |  | 200 |  | Wind | Nobles County | MN | [27 empty] | Done | 2001-12-03 |  | 2005-05-26 | 2007-05-25 | Northern States Power (Xcel Energy) | Nobles County | MN | G162 | G162 | Network Upgrade | NRIS | Fenton Substation | 200 | 200 | Wind | WT Wind Turbine | In Service | 2003-06-04 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G309 | [5 empty] | ERIS |  | 580 |  | Combined Cycle | Windsor | 0 | [27 empty] | Withdrawn | 2003-03-17 | 2003-11-20 | 2003-11-20 |  | ITC Transmission | Windsor |  |  |  |  | ERIS | Unknown | 580 | 580 | Combined Cycle |  | Not Started | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | G164 | G164 | Done | In Service | G164 | [5 empty] | ERIS |  | 200 |  | Wind | Martin County | MN | [27 empty] | Done | 2003-02-18 |  | 2005-10-01 | 2010-09-15 | ITC Midwest | Martin County | MN | G164 | G164 | Network Upgrade | ERIS | Lakefield Junction 345 kV substation | 200 | 200 | Wind | WT Wind Turbine | In Service | 2006-12-01 | 0 | 0 | 0 | 0
|  |  |  | G165 | G165 | Done | In Service | G165 | [5 empty] | ERIS |  | 38 |  | Nuclear | Kewaunee County | WI | [27 empty] | Done | 2001-12-14 |  | 2004-03-19 |  | Wisconsin Public Service Corporation | Kewaunee County | WI | G165 | G165 | Network Upgrade | ERIS | Kewaunee Substation | 38 | 38 | Nuclear | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | In Service | 2007-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G012 | [5 empty] | ERIS |  | 930 |  | 0 | St. Clair County | MI | [27 empty] | Withdrawn | 1999-10-14 | 2003-12-03 | 2003-12-03 |  | ITC Transmission | St. Clair County | MI |  |  |  | ERIS | Unknown | 930 | 930 |  |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G334 | [5 empty] | ERIS |  | 80 |  | Wind | Calumet County | WI | [27 empty] | Withdrawn | 2003-04-17 | 2003-12-05 | 2003-12-05 |  | American Transmission Co. LLC | Calumet County | WI |  |  |  | ERIS | Unknown | 80 | 80 | Wind | WT Wind Turbine | Not Started | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G040 | [5 empty] | ERIS |  | 202 |  | Wind | Nobles County | MN | [27 empty] | Withdrawn | 2000-05-30 | 2003-12-17 | 2003-12-17 |  | ITC Midwest | Nobles County | MN |  |  |  | ERIS | Unknown | 202 | 202 | Wind | WT Wind Turbine | Withdrawn | 2002-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G167 | [5 empty] | ERIS |  | 1200 |  | 0 | Kenosha County | WI | [27 empty] | Withdrawn | 2000-08-22 | 2004-01-06 | 2004-01-06 |  | American Transmission Co. LLC | Kenosha County | WI |  |  |  | ERIS | Unknown | 1200 | 1200 |  |  | Withdrawn | 2008-05-01 | 0 | 0 | 0 | 0
|  |  |  | G170 | G170 | Done | In Service | G170 | [5 empty] | ERIS |  | 20 |  | Coal | Washington County | MN | [27 empty] | Done | 2002-01-16 |  | 2005-07-20 | 2006-06-01 | Northern States Power (Xcel Energy) | Washington County | MN | G170 | G170 | Network Upgrade | ERIS | King Substation | 20 | 20 | Coal | OT Other | In Service | 2006-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G171 | [5 empty] | ERIS |  | 14 |  | Wind | Dodge County | MN | [27 empty] | Done | 2002-01-16 |  | 2003-03-06 |  | Northern States Power (Xcel Energy) | Dodge County | MN |  |  | SPA - SIS | ERIS | Dodge Center Substation | 14 | 14 | Wind | WT Wind Turbine | In Service |  | 0 | 0 | 0 | 0
|  |  |  | G172 | G172 | Done | In Service | G172 | [5 empty] | ERIS |  | 300 |  | Wind | Mower County | MN | [27 empty] | Done | 2003-12-23 |  | 2007-12-27 | 2008-10-01 | ITC Midwest | Mower County | MN | G172 | G172 | Network Upgrade | ERIS | Adams Substation | 300 | 300 | Wind | WT Wind Turbine | In Service | 2008-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G173 | [5 empty] | ERIS |  | 300 |  | Gas | Rice County | MN | [27 empty] | Done | 2002-02-18 |  | 2004-06-02 |  | Northern States Power (Xcel Energy) | Rice County | MN |  |  | SPA - SIS | ERIS | Lake Marion - West Faribault 115kV | 300 | 300 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2007-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G048 | [5 empty] | ERIS |  | 725 |  | 0 | Fond du Lac County | WI | [27 empty] | Withdrawn | 2000-08-11 | 2004-01-13 | 2004-01-13 |  | American Transmission Co. LLC | Fond du Lac County | WI |  |  | Network Upgrade | ERIS | Unknown | 725 | 725 |  |  | Withdrawn | 2006-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G357 | [5 empty] | ERIS |  | 20 |  | Wind | Sibley County | MN | [27 empty] | Withdrawn | 2003-08-04 | 2004-02-10 | 2004-02-10 |  | Northern States Power (Xcel Energy) | Sibley County | MN |  |  |  | ERIS | Unknown | 20 | 20 | Wind | WT Wind Turbine | Not Started | 2007-09-30 | 0 | 0 | 0 | 0
|  |  |  | G176 | G176 | Done | In Service | G176 | [5 empty] | NRIS |  | 100 |  | Wind | Lincoln County | MN | [27 empty] | Done | 2002-03-04 |  | 2006-02-02 | 2007-10-01 | Northern States Power (Xcel Energy) | Lincoln County | MN | G176 | G176 | Network Upgrade | NRIS | Yankee Substation | 100 | 100 | Wind | WT Wind Turbine | In Service | 2005-11-18 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Not Started | G177 | [5 empty] | ERIS |  | 5 |  | 0 | Lyon County | MN | [27 empty] | Done | 2002-03-04 |  | 2002-06-10 |  | Northern States Power (Xcel Energy) | Lyon County | MN |  |  |  | ERIS | Unknown | 5 | 5 |  |  | Not Started | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G378 | [5 empty] | ERIS |  | 100 |  | Wind | Rock County | WI | [27 empty] | Withdrawn | 2003-11-20 | 2004-02-17 | 2004-02-17 |  | American Transmission Co. LLC | Rock County | WI |  |  |  | ERIS | Unknown | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2004-04-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G379 | [5 empty] | ERIS |  | 100 |  | Wind | Walworth County | WI | [27 empty] | Withdrawn | 2003-11-20 | 2004-02-17 | 2004-02-17 |  | American Transmission Co. LLC | Walworth County | WI |  |  |  | ERIS | Unknown | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2005-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G317 | [5 empty] | ERIS |  | 80 |  | 0 | Palo Alto County | IA | [27 empty] | Withdrawn | 2003-03-27 | 2004-03-05 | 2004-03-05 |  | CBPC | Palo Alto County | IA |  |  |  | ERIS | Unknown | 80 | 80 |  |  | Not Started | 2004-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G377 | [5 empty] | ERIS |  | 200 |  | Wind | St. Louis County | MN | [27 empty] | Withdrawn | 2003-11-18 | 2004-03-05 | 2004-03-05 |  | Minnesota Power (Allete, Inc.) | St. Louis County | MN |  |  |  | ERIS | Unknown | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2004-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G331 | [5 empty] | ERIS |  | 200 |  | Wind | Worth County | IA | [27 empty] | Withdrawn | 2003-04-11 | 2004-03-17 | 2004-03-17 |  | ITC Midwest | Worth County | IA |  |  | SPA - SIS | ERIS | Adams - Lime Creek 161kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2006-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G404 | [5 empty] | ERIS |  | 80 |  | 0 | Deuel County | SD | [27 empty] | Withdrawn | 2004-02-11 | 2004-03-17 | 2004-03-17 |  | Otter Tail Power Company | Deuel County | SD |  |  |  | ERIS | Unknown | 80 | 80 |  |  | Not Started | 2005-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G337 | [5 empty] | ERIS |  | 55 |  | Gas | Waseca County | MN | [27 empty] | Withdrawn | 2003-04-17 | 2004-03-26 | 2004-03-26 |  | Northern States Power (Xcel Energy) | Waseca County | MN |  |  |  | ERIS | Unknown | 55 | 55 | Gas |  | Not Started | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | G185 | G185 | Done | In Service | G185 | [5 empty] | NRIS |  | 4 |  | Wind | Pipestone County | MN | [27 empty] | Done | 2002-03-21 |  | 2005-02-07 | 2009-06-30 | Northern States Power (Xcel Energy) | Pipestone County | MN | G185 | G185 | Network Upgrade | NRIS | Pipestone - Dell Rapids 69 kV | 4 | 4 | Wind | WT Wind Turbine | In Service | 2004-04-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G186 | [5 empty] | ERIS |  | 600 |  | Combined Cycle | Cerro Gordo County | IA | [27 empty] | Done | 2002-03-16 |  | 2003-05-23 |  | ITC Midwest | Cerro Gordo County | IA |  |  | SPA - SIS | ERIS | Emery Substation | 600 | 600 | Combined Cycle | Combined Cycle | In Service | 2007-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G335 | [5 empty] | ERIS |  | 160 |  | Wind | Fond du Lac County | WI | [27 empty] | Withdrawn | 2003-04-17 | 2004-04-08 | 2004-04-08 |  | American Transmission Co. LLC | Fond du Lac County | WI |  |  | SPA - SIS | ERIS | Forest Junction - Arcadian 345kV | 160 | 160 | Wind | WT Wind Turbine | Withdrawn | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G188 | [5 empty] | ERIS |  | 2 |  | Diesel | Henry County | IA | [27 empty] | Done | 2002-04-03 |  | 2003-02-21 |  | ITC Midwest | Henry County | IA |  |  | SPA - SIS | ERIS | New London Substation | 2 | 2 | Diesel | IC Internal Combustion (diesel, piston) Engine | In Service | 2002-03-06 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G373 | [5 empty] | ERIS |  | 9.89 |  | 0 | Murray County | MN | [27 empty] | Withdrawn | 2003-10-23 | 2004-04-16 | 2004-04-16 |  | Great River Energy | Murray County | MN |  |  |  | ERIS | Unknown | 9.89 | 9.89 |  |  | Not Started | 2004-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G415 | [5 empty] | ERIS |  | 25 |  | Diesel | Waupaca County | WI | [27 empty] | Withdrawn | 2004-03-10 | 2004-04-26 | 2004-04-26 |  | American Transmission Co. LLC | Waupaca County | WI |  |  |  | ERIS | Unknown | 25 | 25 | Diesel |  | Not Started | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G372 | [5 empty] | ERIS |  | 1.65 |  | Wind | Pope County | MN | [27 empty] | Withdrawn | 2003-11-10 | 2004-04-30 | 2004-04-30 |  | Northern States Power (Xcel Energy) | Pope County | MN |  |  |  | ERIS | Unknown | 1.65 | 1.65 | Wind | WT Wind Turbine | Not Started | 2009-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G425 | [5 empty] | ERIS |  | 200 |  | Wind | Jackson County | MN | [27 empty] | Withdrawn | 2004-04-23 | 2004-05-06 | 2004-05-06 |  | Great River Energy | Jackson County | MN |  |  |  | ERIS | Unknown | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2006-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G419 | [5 empty] | ERIS |  | 1.5 |  | Wind | Lyon County | IA | [27 empty] | Withdrawn | 2004-03-22 | 2004-05-10 | 2004-05-10 |  | Northern States Power (Xcel Energy) | Lyon County | IA |  |  |  | ERIS | Unknown | 1.5 | 1.5 | Wind | WT Wind Turbine | Not Started | 2005-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G095 | [5 empty] | ERIS |  | 644 |  | Gas | Wayne County | MI | [27 empty] | Withdrawn | 2001-06-10 | 2004-05-19 | 2004-05-19 |  | ITC Transmission | Wayne County | MI |  |  | Network Upgrade | ERIS | Unknown | 644 | 644 | Gas |  | Withdrawn | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G400 | [5 empty] | ERIS |  | 5 |  | 0 | McLeod County | MN | [27 empty] | Withdrawn | 2004-01-26 | 2004-06-02 | 2004-06-02 |  | Great River Energy | McLeod County | MN |  |  |  | ERIS | Unknown | 5 | 5 |  |  | Not Started | 2004-03-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G402 | [5 empty] | ERIS |  | 3.3 |  | Wind | Lincoln County | MN | [27 empty] | Withdrawn | 2004-02-09 | 2004-07-12 | 2004-07-12 |  | Northern States Power (Xcel Energy) | Lincoln County | MN |  |  |  | ERIS | Unknown | 3.3 | 3.3 | Wind | WT Wind Turbine | Not Started | 2005-06-01 | 0 | 0 | 0 | 0
|  |  |  | G218 | G218 | Done | In Service | G218 | [5 empty] | ERIS |  | 750 |  | Coal | Trimble County | KY | [27 empty] | Done | 2002-04-10 |  | 2004-04-12 | 2007-01-01 | LG&E and KU Services Company as agent for Louisville Gas and Electric Company and Kentucky Utilities Company | Trimble County | KY | G218 | G218 | Network Upgrade | ERIS | Trimble Substation | 750 | 750 | Coal | OT Other | In Service | 2006-06-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G429 | [5 empty] | ERIS |  | 200 |  | Wind | Jackson County | MN | [27 empty] | Withdrawn | 2004-05-28 | 2004-07-13 | 2004-07-13 |  | Northern States Power (Xcel Energy) | Jackson County | MN |  |  |  | ERIS | Lakefield Gen Station 345kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2006-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G104 | [5 empty] | ERIS |  | 118 |  | 0 | Winnebago County | IA | [27 empty] | Withdrawn | 2001-06-22 | 2004-07-21 | 2004-07-21 |  | Dairyland Power Cooperative | Winnebago County | IA |  |  |  | ERIS | Unknown | 118 | 118 |  |  | Not Started | 2005-06-25 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G121 | [5 empty] | ERIS |  | 6 |  | 0 | Winnebago County | IA | [27 empty] | Withdrawn | 2001-08-22 | 2004-07-21 | 2004-07-21 |  | Dairyland Power Cooperative | Winnebago County | IA |  |  |  | ERIS | Unknown | 6 | 6 |  |  | Not Started | 2008-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G387 | [5 empty] | ERIS |  | 19.79 |  | Wind | Nobles County | MN | [27 empty] | Withdrawn | 2003-12-30 | 2004-07-22 | 2004-07-22 |  | ITC Midwest | Nobles County | MN |  |  |  | ERIS | Unknown | 19.79 | 19.79 | Wind | WT Wind Turbine | Not Started | 2004-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G411 | [5 empty] | ERIS |  | 19.79 |  | Wind | Watonwan County | MN | [27 empty] | Withdrawn | 2004-02-25 | 2004-07-22 | 2004-07-22 |  | Northern States Power (Xcel Energy) | Watonwan County | MN |  |  |  | ERIS | Unknown | 19.79 | 19.79 | Wind | WT Wind Turbine | Not Started | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G097 | [5 empty] | ERIS |  | 2 |  | Wind | Murray County | MN | [27 empty] | Withdrawn | 2001-06-16 | 2004-07-26 | 2004-07-26 |  | Northern States Power (Xcel Energy) | Murray County | MN |  |  |  | ERIS | Unknown | 2 | 2 | Wind | WT Wind Turbine | Withdrawn |  | 0 | 0 | 0 | 0
|  |  |  | G225 | G225 | Done | In Service | G225 | [5 empty] | ERIS |  | 60 |  | Gas | Outagamie County | WI | [27 empty] | Done | 2002-05-06 |  | 2003-12-23 |  | Wisconsin Electric Power Company | Outagamie County | WI | G225 | G225 | Network Upgrade | ERIS | Kaukauna Central Substation | 60 | 60 | Gas |  | In Service | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Withdrawn | G226 | [5 empty] | ERIS |  | 9 |  | Wind | Pipestone County | MN | [27 empty] | Done | 2001-07-30 |  | 2003-12-02 |  | Northern States Power (Xcel Energy) | Pipestone County | MN |  |  |  | ERIS | Unknown | 9 | 9 | Wind | WT Wind Turbine | Withdrawn | 2007-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G414 | [5 empty] | ERIS |  | 10 |  | Wind | Clay County | MN | [27 empty] | Withdrawn | 2004-03-10 | 2004-08-02 | 2004-08-02 |  | Northern States Power (Xcel Energy) | Clay County | MN |  |  |  | ERIS | Unknown | 10 | 10 | Wind | WT Wind Turbine | Not Started | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G394 | [5 empty] | ERIS |  | 6.6 |  | Wind | Lincoln County | MN | [27 empty] | Withdrawn | 2004-01-21 | 2004-08-23 | 2004-08-23 |  | Northern States Power (Xcel Energy) | Lincoln County | MN |  |  |  | ERIS | Unknown | 6.6 | 6.6 | Wind | WT Wind Turbine | Not Started | 2005-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G395 | [5 empty] | ERIS |  | 4.94 |  | Wind | Lincoln County | MN | [27 empty] | Withdrawn | 2004-01-21 | 2004-08-23 | 2004-08-23 |  | Northern States Power (Xcel Energy) | Lincoln County | MN |  |  |  | ERIS | Unknown | 4.94 | 4.94 | Wind | WT Wind Turbine | Not Started | 2004-03-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G364 | [5 empty] | ERIS |  | 425 |  | Coal | Manistee County | MI | [27 empty] | Withdrawn | 2003-10-10 | 2004-08-25 | 2004-08-25 |  | Michigan Electric Transmission Company, LLC | Manistee County | MI |  |  | Network Upgrade | ERIS | Unknown | 425 | 425 | Coal |  | Withdrawn | 2007-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G230 | [5 empty] | ERIS |  | 2 |  | Diesel | Linn County | IA | [27 empty] | Done | 2002-05-20 |  | 2003-09-10 |  | ITC Midwest | Linn County | IA |  |  | SPA - SIS | ERIS | Coggon Municipal Substations | 2 | 2 | Diesel | IC Internal Combustion (diesel, piston) Engine | In Service | 2002-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G262 | [5 empty] | ERIS |  | 200 |  | Wind | Jackson County | MN | [27 empty] | Withdrawn | 2002-10-22 | 2004-09-09 | 2004-09-09 |  | ITC Midwest | Jackson County | MN |  |  | SPA - SIS | ERIS | Unknown | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2007-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G232 | [5 empty] | ERIS |  | 44 |  | Wind | Dickinson County | IA | [27 empty] | Done | 2002-05-29 |  | 2003-03-31 |  | ITC Midwest | Dickinson County | IA |  |  | SPA - SIS | ERIS | Unknown | 44 | 44 | Wind | WT Wind Turbine | In Service | 2007-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G423 | [5 empty] | ERIS |  | 19 |  | Wind | Columbia County | WI | [27 empty] | Withdrawn | 2004-04-07 | 2004-09-09 | 2004-09-09 |  | American Transmission Co. LLC | Columbia County | WI |  |  |  | ERIS | Unknown | 19 | 19 | Wind | WT Wind Turbine | Not Started | 2006-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G234 | [5 empty] | ERIS |  | 22 |  | Combined Cycle | Jackson County | MI | [27 empty] | Done | 2002-06-03 |  | 2002-10-08 |  | Michigan Electric Transmission Company, LLC | Jackson County | MI |  |  | SPA - SIS | ERIS | Unknown | 22 | 22 | Combined Cycle | Combined Cycle | In Service | 2005-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G450 | [5 empty] | ERIS |  | 1 |  | Wind | Rolette County | ND | [27 empty] | Withdrawn | 2004-08-13 | 2004-09-27 | 2004-09-27 |  | Otter Tail Power Company | Rolette County | ND |  |  |  | ERIS | Unknown | 1 | 1 | Wind | WT Wind Turbine | Not Started | 2006-11-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G371 | [5 empty] | ERIS |  | 100 |  | Wind | Columbia County | WI | [27 empty] | Withdrawn | 2003-10-27 | 2004-09-29 | 2004-09-29 |  | American Transmission Co. LLC | Columbia County | WI |  |  | SPA - SIS | ERIS | Friesland 138kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2004-03-01 | 0 | 0 | 0 | 0
|  |  |  | G237 | G237 | Done | In Service | G237 | [5 empty] | ERIS |  | 575 |  | Combined Cycle | Ramsey County | MN | [27 empty] | Done | 2003-01-21 |  | 2005-05-13 |  | Northern States Power (Xcel Energy) | Ramsey County | MN | G237 | G237 | Network Upgrade | ERIS | Highbridge Substation | 575 | 575 | Combined Cycle | Combined Cycle | In Service | 2004-05-01 | 0 | 0 | 0 | 0
|  |  |  | G238 | G238 | Done | In Service | G238 | [5 empty] | ERIS |  | 510 |  | Combined Cycle | Hennepin County | MN | [27 empty] | Done | 2003-01-21 |  | 2006-01-11 | 2009-05-01 | Northern States Power (Xcel Energy) | Hennepin County | MN | G238 | G238 | Network Upgrade | ERIS | Unknown | 510 | 510 | Combined Cycle | Combined Cycle | In Service | 2003-12-15 | 0 | 0 | 0 | 0
|  |  |  | G239 | G239 | Done | Withdrawn | G239 | [5 empty] | ERIS |  | 63 |  | Wind | Dodge County | MN | [27 empty] | Done | 2002-06-25 |  | 2004-11-10 |  | Northern States Power (Xcel Energy) | Dodge County | MN | G239 | G239 | Network Upgrade | ERIS | Kasson - Dodge Center 69 kV | 63 | 63 | Wind | WT Wind Turbine | Withdrawn | 2008-05-01 | 0 | 0 | 0 | 0
|  |  |  | G240 | G240 | Done | In Service | G240 | [5 empty] | ERIS |  | 55 |  | Gas | Manitowoc County | WI | [27 empty] | Done | 2002-07-29 |  | 2003-12-23 |  | Wisconsin Public Service Corporation | Manitowoc County | WI | G240 | G240 | Network Upgrade | ERIS | Lakefront Substation | 55 | 55 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2009-05-01 | 0 | 0 | 0 | 0
|  |  |  | G241 | G241 | Done | In Service | G241 | [5 empty] | NRIS |  | 2 |  | Wind | Lincoln County | MN | [27 empty] | Done | 2002-07-30 |  | 2004-11-10 |  | Northern States Power (Xcel Energy) | Lincoln County | MN | G241 | G241 | Network Upgrade | NRIS | Buffalo Ridge - Bravo 34.5kV | 2 | 2 | Wind | WT Wind Turbine | In Service | 2002-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G242 | [5 empty] | ERIS |  | 19 |  | Wind | Dodge County | MN | [27 empty] | Done | 2002-08-03 |  | 2003-03-06 |  | Northern States Power (Xcel Energy) | Dodge County | MN |  |  | SPA - SIS | ERIS | Dodge Center Substation | 19 | 19 | Wind | WT Wind Turbine | In Service | 2008-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G449 | [5 empty] | ERIS |  | 100 |  | Wind | Nodaway County | MO | [27 empty] | Withdrawn | 2004-09-03 | 2004-09-29 | 2004-09-29 |  | Ameren Missouri | Nodaway County | MO |  |  |  | ERIS | Maryville - Creston 161kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2006-11-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G435 | [5 empty] | ERIS |  | 494 |  | Combined Cycle | Williamson County | IL | [27 empty] | Withdrawn | 2004-07-06 | 2004-10-13 | 2004-10-13 |  | Ameren Illinois | Williamson County | IL |  |  |  | ERIS | Ameren E. West Frankfort | 545 | 494 | Combined Cycle |  | Not Started | 2010-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | IP05 | [5 empty] | ERIS |  | 1500 |  | 0 | Randolph County | IL | [27 empty] | Withdrawn | 2001-12-12 | 2004-10-21 | 2004-10-21 |  | Ameren Illinois | Randolph County | IL |  |  |  | ERIS | Unknown | 1500 | 1500 |  |  | Not Started | 2010-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | IP11 | [5 empty] | ERIS |  | 500 |  | 0 | Washington County | IL | [27 empty] | Withdrawn | 2000-07-20 | 2004-10-21 | 2004-10-21 |  | Ameren Illinois | Washington County | IL |  |  |  | ERIS | Unknown | 500 | 500 |  |  | Not Started | 2006-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Withdrawn | G248 | [5 empty] | ERIS |  | 19 |  | Wind | Dickey County | ND | [27 empty] | Done | 2002-08-20 |  | 2003-05-23 |  | Montana-Dakota Utilities Company | Dickey County | ND |  |  | SPA - SIS | ERIS | Wishek - Ashley - Ellendale 41.6 kV | 19 | 19 | Wind | WT Wind Turbine | Withdrawn | 2003-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | IP12 | [5 empty] | ERIS |  | 500 |  | 0 | Piatt County | IL | [27 empty] | Withdrawn | 2000-07-20 | 2004-10-21 | 2004-10-21 |  | Ameren Illinois | Piatt County | IL |  |  |  | ERIS | Unknown | 500 | 500 |  |  | Not Started | 2005-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G420 | [5 empty] | NRIS |  | 99 |  | Wind | Marathon County | WI | [27 empty] | Withdrawn | 2004-03-22 | 2004-11-08 | 2004-11-08 |  | American Transmission Co. LLC | Marathon County | WI |  |  | SPA - SIS | NRIS | Wien 115kV | 99 | 99 | Wind | WT Wind Turbine | Not Started | 2008-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G251 | [5 empty] | ERIS |  | 6 |  | Wind | Jackson County | MN | [27 empty] | Done | 2002-07-25 |  | 2005-03-14 |  | Great River Energy | Jackson County | MN |  |  | SPA - SIS | ERIS | Heron Lake - Fox Lake 69kV | 6 | 6 | Wind | WT Wind Turbine | In Service | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | G252 | G252 | Done | In Service | G252 | [5 empty] | NRIS |  | 10 |  | Wind | Murray County | MN | [27 empty] | Done | 2002-05-14 |  | 2005-11-10 | 2010-11-30 | Great River Energy | Murray County | MN | G252 | G252 | Network Upgrade | NRIS | GRE Rock River - Chandler Tap 69 kV | 10 | 10 | Wind | WT Wind Turbine | In Service | 2005-09-01 | 0 | 0 | 0 | 0
|  |  |  | G253 | G253 | Done | In Service | G253 | [5 empty] | NRIS |  | 12 |  | Wind | Rock County | MN | [27 empty] | Done | 2002-09-09 |  | 2004-10-26 |  | Northern States Power (Xcel Energy) | Rock County | MN | G253 | G253 | Network Upgrade | NRIS | Split Rock - Magnolia 161kV | 12 | 12 | Wind | WT Wind Turbine | In Service | 2002-11-01 | 0 | 0 | 0 | 0
|  |  |  | G281 | G281 | Withdrawn | Withdrawn | G281 | [5 empty] | ERIS |  | 130 |  | Wind | Green County | WI | [27 empty] | Withdrawn | 2003-11-21 | 2004-11-22 | 2004-11-22 |  | American Transmission Co. LLC | Green County | WI | G281 | G281 | Network Upgrade | ERIS | Unknown | 130 | 130 | Wind | WT Wind Turbine | Withdrawn | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | G255 | G255 | Done | In Service | G255 | [5 empty] | NRIS |  | 100 |  | Wind | Brookings County | SD | [27 empty] | Done | 2002-09-18 |  | 2006-02-21 |  | Northern States Power (Xcel Energy) | Brookings County | SD | G255 | G255 | Network Upgrade | NRIS | Yankee Substation | 100 | 100 | Wind | WT Wind Turbine | In Service | 2006-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G256 | [5 empty] | ERIS |  | 45 |  | Gas | Dawson County | MT | [27 empty] | Done | 2002-09-20 |  | 2003-06-18 |  | Montana-Dakota Utilities Company | Dawson County | MT |  |  | SPA - SIS | ERIS | Glendive Turbine Jct Substation | 45 | 45 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2003-02-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G421 | [5 empty] | NRIS |  | 50 |  | Wind | Brown County | WI | [27 empty] | Withdrawn | 2004-03-22 | 2004-12-02 | 2004-12-02 |  | American Transmission Co. LLC | Brown County | WI |  |  | SPA - SIS | NRIS | Wesmark - Finger Road 69kV | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2005-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G258 | [5 empty] | ERIS |  | 50 |  | Combined Cycle | Lee County | IA | [27 empty] | Done | 2002-10-04 |  | 2004-02-10 |  | ITC Midwest | Lee County | IA |  |  | SPA - SIS | ERIS | Roquette Substation | 50 | 50 | Combined Cycle | Combined Cycle | In Service | 2003-05-01 | 0 | 0 | 0 | 0
|  |  |  | G267 | G267 | Withdrawn | Not Started | G267 | [5 empty] | ERIS |  | 190 |  | Gas | McLeod County | MN | [27 empty] | Withdrawn | 2002-11-18 | 2004-12-21 | 2004-12-21 |  | Northern States Power (Xcel Energy) | McLeod County | MN | G267 | G267 | Network Upgrade | ERIS | Unknown | 190 | 190 | Gas |  | Not Started | 2007-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G293 | [5 empty] | ERIS |  | 400 |  | Coal | Buffalo County | WI | [27 empty] | Withdrawn | 2002-12-18 | 2004-12-28 | 2004-12-28 |  | Dairyland Power Cooperative | Buffalo County | WI |  |  |  | ERIS | Unknown | 400 | 400 | Coal |  | Not Started | 2004-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G261 | [5 empty] | NRIS |  | 667 |  | Combined Cycle | Blue Earth County | MN | [27 empty] | Done | 2002-10-11 |  | 2005-02-04 | 2018-06-01 | Northern States Power (Xcel Energy) | Blue Earth County | MN |  |  | Network Upgrade | NRIS | Mankato Substation | 667 | 667 | Combined Cycle | Combined Cycle | In Service | 2003-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G485 | [5 empty] | NRIS |  | 60 |  | Wind | Dodge County | WI | [27 empty] | Withdrawn | 2004-11-24 | 2005-01-04 | 2005-01-04 |  | American Transmission Co. LLC | Dodge County | WI |  |  |  | NRIS | S. Fond du Lac - Butternut | 60 | 60 | Wind | WT Wind Turbine | Not Started | 2009-01-01 | 0 | 0 | 0 | 0
|  |  |  | G263 | G263 | Done | In Service | G263 | [5 empty] | NRIS |  | 105 |  | Wind | Martin County | MN | [27 empty] | Done | 2002-10-22 |  | 2005-05-24 |  | Northern States Power (Xcel Energy) | Martin County | MN | G263 | G263 | Network Upgrade | NRIS | Lakefield Generating Substation | 105 | 105 | Wind | WT Wind Turbine | In Service | 2007-11-01 | 0 | 0 | 0 | 0
|  |  |  | G410 | G410 | Withdrawn | Not Started | G410 | [5 empty] | NRIS |  | 99 |  | Wind | Kewaunee County | WI | [27 empty] | Withdrawn | 2004-02-23 | 2005-03-07 | 2005-03-07 |  | American Transmission Co. LLC | Kewaunee County | WI | G410 | G410 | Network Upgrade | NRIS | Kewaunee - East Krok 138kV | 99 | 99 | Wind | WT Wind Turbine | Not Started | 2005-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G367 | [5 empty] | ERIS |  | 800 |  | Coal | Fulton County | IL | [27 empty] | Withdrawn | 2003-10-16 | 2005-03-25 | 2005-03-25 |  | Ameren Illinois | Fulton County | IL |  |  | SPA - SIS | ERIS | AEGR Duck Creek Gen Plant | 800 | 800 | Coal |  | Withdrawn | 2007-10-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G416 | [5 empty] | NRIS |  | 300 |  | Combined Cycle | Washington County | MN | [27 empty] | Withdrawn | 2004-03-17 | 2005-04-04 | 2005-04-04 |  | Northern States Power (Xcel Energy) | Washington County | MN |  |  | Feasibility | NRIS | Unknown | 300 | 300 | Combined Cycle |  | Not Started | 2004-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G445 | [5 empty] | NRIS |  | 200 |  | Wind | Howard County | IA | [27 empty] | Withdrawn | 2004-08-25 | 2005-04-12 | 2005-04-12 |  | ITC Midwest | Howard County | IA |  |  | Feasibility | NRIS | Unknown | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G501 | [5 empty] | 0 |  | 79.19 |  | Wind | McLean County | IL | [27 empty] | Withdrawn | 2005-03-11 | 2005-04-29 | 2005-04-29 |  | -- No Company -- | McLean County | IL |  |  |  |  | Unknown | 79.19 | 79.19 | Wind | WT Wind Turbine | Not Started | 2006-05-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | IP02 | [5 empty] | NRIS |  | 79.19 |  | Wind | McLean County | IL | [27 empty] | Withdrawn | 2004-01-14 | 2005-05-01 | 2005-05-01 |  | Ameren Illinois | McLean County | IL |  |  | Network Upgrade | NRIS | McLean County #7 Line 1582 | 79.19 | 79.19 | Wind | WT Wind Turbine | Not Started | 2011-03-31 | 0 | 0 | 0 | 0
|  |  |  | G270 | G270 | Done | In Service | G270 | [5 empty] | ERIS |  | 2 |  | Diesel | Nobles County | MN | [27 empty] | Done | 2002-12-09 |  | 2004-03-19 |  | ITC Midwest | Nobles County | MN | G270 | G270 | Network Upgrade | ERIS | Adrian Municipal Utilities Station | 2 | 2 | Diesel | IC Internal Combustion (diesel, piston) Engine | In Service | 2005-03-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G511 | [5 empty] | NRIS |  | 100 |  | Wind | Huron County | MI | [27 empty] | Withdrawn | 2005-03-21 | 2005-05-12 | 2005-05-12 |  | ITC Transmission | Huron County | MI |  |  |  | NRIS | Unknown | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2006-08-01 | 0 | 0 | 0 | 0
|  |  |  | G272 | G272 | Done | In Service | G272 | [5 empty] | NRIS |  | 10 |  | Wind | Murray County | MN | [27 empty] | Done | 2002-12-05 |  | 2005-05-27 | 2005-12-01 | Great River Energy | Murray County | MN | G272 | G272 | Network Upgrade | NRIS | Chandler Switching Station - Chandler Tap 69kV | 10 | 10 | Wind | WT Wind Turbine | In Service | 2004-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G499 | [5 empty] | NRIS |  | 109.5 |  | Wind | Story County | IA | [27 empty] | Withdrawn | 2005-02-22 | 2005-06-21 | 2005-06-21 |  | ITC Midwest | Story County | IA |  |  |  | NRIS | Fernald - Marshalltown 115kV | 109.5 | 109.5 | Wind | WT Wind Turbine | Not Started | 2006-08-01 | 0 | 0 | 0 | 0
|  |  |  | G441 | G441 | Withdrawn | Not Started | G441 | [5 empty] | ERIS |  | 439 |  | Gas | Sarnia | 0 | [27 empty] | Withdrawn | 2004-08-12 | 2005-06-24 | 2005-06-24 |  | ITC Transmission | Sarnia |  | G441 | G441 | SPA - SIS | ERIS | Bunce Creek Substation | 439 | 439 | Gas | CT Combined-Cycle Combustion ? Turbine Part | Not Started | 2006-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G516 | [5 empty] | ERIS |  | 6 |  | Wind | Nobles County | MN | [27 empty] | Withdrawn | 2005-04-29 | 2005-06-27 | 2005-06-27 |  | Northern States Power (Xcel Energy) | Nobles County | MN |  |  |  | ERIS | Unknown | 6 | 6 | Wind | WT Wind Turbine | Not Started | 2006-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G494 | [5 empty] | ERIS |  | 20 |  | Wind | Martin County | MN | [27 empty] | Withdrawn | 2005-02-09 | 2005-07-01 | 2005-07-01 |  | -- No Company -- | Martin County | MN |  |  |  | ERIS | Unknown | 20 | 20 | Wind | WT Wind Turbine | Not Started | 2005-10-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G446 | [5 empty] | ERIS |  | 19.5 |  | Wind | LaMoure County | ND | [27 empty] | Withdrawn | 2004-09-02 | 2005-07-13 | 2005-07-13 |  | Montana-Dakota Utilities Company | LaMoure County | ND |  |  |  | ERIS | Unknown | 19.5 | 19.5 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | G278 | G278 | Done | In Service | G278 | [5 empty] | NRIS |  | 8 |  | Wind | Pipestone County | MN | [27 empty] | Done | 2002-12-19 |  | 2005-02-07 | 2004-12-15 | Northern States Power (Xcel Energy) | Pipestone County | MN | G278 | G278 | Network Upgrade | NRIS | Pipestone - Dell Rapids 69kV | 8 | 8 | Wind | WT Wind Turbine | In Service | 2007-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G413 | [5 empty] | ERIS |  | 150 |  | Wind | McLean County | IL | [27 empty] | Withdrawn | 2004-03-08 | 2005-07-15 | 2005-07-15 |  | Ameren Illinois | McLean County | IL |  |  |  | ERIS | Unknown | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2006-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G476 | [5 empty] | NRIS |  | 494 |  | Coal | Williamson County | IL | [27 empty] | Withdrawn | 2004-10-13 | 2005-08-01 | 2005-08-01 |  | Ameren Illinois | Williamson County | IL |  |  |  | NRIS | East/West Frankfort 345 kV Substation | 545 | 494 | Coal |  | Not Started | 2004-10-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G500 | [5 empty] | NRIS |  | 710 |  | Combined Cycle | Shelby County | IL | [27 empty] | Withdrawn | 2005-02-18 | 2005-08-01 | 2005-08-01 |  | Ameren Illinois | Shelby County | IL |  |  |  | NRIS | Holland Plant | 710 | 710 | Combined Cycle |  | Not Started | 2005-02-12 | 0 | 0 | 0 | 0
|  |  |  | G282 | G282 | Done | Withdrawn | G282 | [5 empty] | ERIS |  | 99 |  | Wind | Lafayette County | WI | [27 empty] | Done | 2003-01-07 |  | 2005-04-22 | 2006-12-31 | American Transmission Co. LLC | Lafayette County | WI | G282 | G282 | Network Upgrade | ERIS | Hillman 138 kV | 99 | 99 | Wind | WT Wind Turbine | Withdrawn | 2004-05-05 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G505 | [5 empty] | NRIS |  | 150 |  | Coal | Williamson County | IL | [27 empty] | Withdrawn | 2005-03-16 | 2005-08-01 | 2005-08-01 |  | Ameren Illinois | Williamson County | IL |  |  |  | NRIS | East/West Frankfort Substation | 150 | 150 | Coal |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | G329 | G329 | Withdrawn | Not Started | G329 | [5 empty] | NRIS |  | 50 |  | Wind | St. Louis County | MN | [27 empty] | Withdrawn | 2003-04-03 | 2005-08-11 | 2005-08-11 |  | Minnesota Power (Allete, Inc.) | St. Louis County | MN | G329 | G329 | DPP - SIS | NRIS | LTV Steel Hoyt Lakes 138 kV | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G285 | [5 empty] | ERIS |  | 9 |  | Wind | Pipestone County | MN | [27 empty] | Done | 2001-07-30 |  | 2003-12-02 |  | Northern States Power (Xcel Energy) | Pipestone County | MN |  |  | SPA - SIS | ERIS | Pipestone - Lake Wilson 69kV | 9 | 9 | Wind | WT Wind Turbine | In Service | 2004-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G286 | [5 empty] | ERIS |  | 4 |  | Diesel | Tama County | IA | [27 empty] | Done | 2003-01-17 |  | 2003-08-13 |  | ITC Midwest | Tama County | IA |  |  | SPA - SIS | ERIS | Traer - Dysart 34.5kV | 4 | 4 | Diesel | IC Internal Combustion (diesel, piston) Engine | In Service | 2003-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G287 | [5 empty] | NRIS |  | 200 |  | Wind | Nobles County | MN | [27 empty] | Done | 2003-01-21 |  | 2006-04-24 |  | Northern States Power (Xcel Energy) | Nobles County | MN |  |  | SPA - SIS | NRIS | Nobles County Substation | 200 | 200 | Wind | WT Wind Turbine | In Service | 2004-06-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G365 | [5 empty] | ERIS |  | 11 |  | Wind | Pope County | MN | [27 empty] | Withdrawn | 2003-10-15 | 2005-08-19 | 2005-08-19 |  | Great River Energy | Pope County | MN |  |  | SPA - SIS | ERIS | Williams Substation | 11 | 11 | Wind | WT Wind Turbine | Not Started | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G430 | [5 empty] | ERIS |  | 8.25 |  | Wind | Pope County | MN | [27 empty] | Withdrawn | 2004-05-08 | 2005-08-19 | 2005-08-19 |  | Great River Energy | Pope County | MN |  |  |  | ERIS | Unknown | 8.25 | 8.25 | Wind | WT Wind Turbine | Not Started | 2005-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G493 | [5 empty] | NRIS |  | 1221 |  | 0 | Van Buren County | MI | [27 empty] | Withdrawn | 2005-02-07 | 2005-08-24 | 2005-08-24 |  | Michigan Electric Transmission Company, LLC | Van Buren County | MI |  |  |  | NRIS | Unknown | 1221 | 1221 |  |  | Not Started | 2006-10-01 | 0 | 0 | 0 | 0
|  |  |  | G291 | G291 | Done | In Service | G291 | [5 empty] | ERIS |  | 19 |  | Wind | LaMoure County | ND | [27 empty] | Done | 2003-02-05 |  | 2004-03-23 |  | Otter Tail Power Company | LaMoure County | ND | G291 | G291 | Network Upgrade | ERIS | Jamestown - Oakes 41.6kV | 19 | 19 | Wind | WT Wind Turbine | In Service | 2006-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G496 | [5 empty] | NRIS |  | 11.55 |  | Wind | Goodhue County | MN | [27 empty] | Withdrawn | 2005-02-11 | 2005-08-24 | 2005-08-24 |  | Northern States Power (Xcel Energy) | Goodhue County | MN |  |  |  | NRIS | Unknown | 11.55 | 11.55 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G447 | [5 empty] | ERIS |  | 150 |  | Wind | Clinton County | IN | [27 empty] | Withdrawn | 2004-09-02 | 2005-08-29 | 2005-08-29 |  | Duke Energy Corporation | Clinton County | IN |  |  |  | ERIS | Kokomo - Thorntown 230kV | 150 | 150 | Wind | WT Wind Turbine | Withdrawn | 2006-09-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G448 | [5 empty] | ERIS |  | 100 |  | Wind | Schuyler County | MO | [27 empty] | Withdrawn | 2004-09-03 | 2005-08-29 | 2005-08-29 |  | Ameren Missouri | Schuyler County | MO |  |  | Feasibility | ERIS | Adair - Appanoose 161 kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2005-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Withdrawn | G297 | [5 empty] | ERIS |  | 39 |  | Wind | Edmunds County | SD | [27 empty] | Done | 2003-02-12 |  | 2004-10-11 | 2007-05-31 | Montana-Dakota Utilities Company | Edmunds County | SD |  |  | SPA - SIS | ERIS | Glenham Jct substation | 39 | 39 | Wind | WT Wind Turbine | Withdrawn | 2008-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G298 | [5 empty] | ERIS |  | 100 |  | Wind | Dickinson County | IA | [27 empty] | Done | 2003-02-11 |  | 2005-04-29 | 2006-12-31 | ITC Midwest | Dickinson County | IA |  |  | Optional | ERIS | Wisdom - Triboji 161 kV | 100 | 100 | Wind | WT Wind Turbine | In Service | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G299 | [5 empty] | ERIS |  | 4 |  | Gas | Cass County | IN | [27 empty] | Done | 2003-02-19 |  | 2003-11-14 |  | Duke Energy Corporation | Cass County | IN |  |  | SPA - SIS | ERIS | Cinergy Walton Substation | 4 | 4 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2003-12-31 | 0 | 0 | 0 | 0
|  |  |  | G300 | G300 | Done | In Service | G300 | [5 empty] | ERIS |  | 6 |  | Diesel | Jackson County | IA | [27 empty] | Done | 2003-02-21 |  | 2003-08-14 |  | ITC Midwest | Jackson County | IA | G300 | G300 | Network Upgrade | ERIS | Maquoketa Municipal 34.5kV | 6 | 6 | Diesel | IC Internal Combustion (diesel, piston) Engine | In Service | 2007-05-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G301 | [5 empty] | ERIS |  | 4 |  | Wind | Osceola County | IA | [27 empty] | Done | 2003-02-24 |  | 2003-11-14 |  | ITC Midwest | Osceola County | IA |  |  | SPA - SIS | ERIS | Sibley - Triboji 69kV | 4 | 4 | Wind | WT Wind Turbine | In Service | 2003-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G529 | [5 empty] | NRIS |  | 650 |  | Coal | Williamson County | IL | [27 empty] | Withdrawn | 2005-06-17 | 2005-08-29 | 2005-08-29 |  | Ameren Illinois | Williamson County | IL |  |  |  | NRIS | East-West Frankfort Substation | 650 | 650 | Coal |  | Not Started | 2011-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G534 | [5 empty] | NRIS |  | 4.94 |  | Wind | Hancock County | IA | [27 empty] | Withdrawn | 2005-07-08 | 2005-08-30 | 2005-08-30 |  | ITC Midwest | Hancock County | IA |  |  |  | NRIS | Unknown | 4.94 | 4.94 | Wind | WT Wind Turbine | Not Started | 2011-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G508 | [5 empty] | ERIS |  | 15 |  | Biomass | Ballard County | KY | [27 empty] | Withdrawn | 2005-03-16 | 2005-10-13 | 2005-10-13 |  | -- No Company -- | Ballard County | KY |  |  |  | ERIS | Unknown | 15 | 15 | Biomass |  | Not Started | 2006-11-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G539 | [5 empty] | NRIS |  | 80 |  | Hydro | Bracken County | KY | [27 empty] | Withdrawn | 2005-08-15 | 2005-10-13 | 2005-10-13 |  | -- No Company -- | Bracken County | KY |  |  |  | NRIS | 2 miles south of Meldahl Dam at existing 138 kV KU line. | 80 | 80 | Hydro |  | Not Started | 2007-09-30 | 0 | 0 | 0 | 0
|  |  |  | G399 | G399 | Withdrawn | Not Started | G399 | [5 empty] | ERIS |  | 300 |  | Combined Cycle | Vigo County | IN | [27 empty] | Withdrawn | 2004-07-02 | 2005-10-27 | 2005-10-27 |  | Duke Energy Corporation | Vigo County | IN | G399 | G399 | SPA - SIS | ERIS | Wabash River | 300 | 300 | Combined Cycle |  | Not Started | 2004-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G480 | [5 empty] | NRIS |  | 80 |  | Wind | Madison County | OH | [27 empty] | Withdrawn | 2004-11-09 | 2005-11-01 | 2005-11-01 |  | FirstEnergy Solutions Corp. | Madison County | OH |  |  |  | NRIS | East Springfield - Tangy 138 kV | 80 | 80 | Wind | WT Wind Turbine | Not Started | 2005-08-08 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G506 | [5 empty] | NRIS |  | 100 |  | Wind | Monroe County | WI | [27 empty] | Withdrawn | 2005-03-11 | 2005-11-01 | 2005-11-01 |  | American Transmission Co. LLC | Monroe County | WI |  |  | Feasibility | NRIS | Sparta - Oakdale 138kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2007-10-30 | 0 | 0 | 0 | 0
|  |  |  | G310 | G310 | Done | In Service | G310 | [5 empty] | ERIS |  | 8 |  | Wind | Cerro Gordo County | IA | [27 empty] | Done | 2003-03-18 |  | 2004-08-26 |  | ITC Midwest | Cerro Gordo County | IA | G310 | G310 | Network Upgrade | ERIS | Cerro Gordo Substation | 8 | 8 | Wind | WT Wind Turbine | In Service | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | G311 | G311 | Done | Withdrawn | G311 | [5 empty] | ERIS |  | 19 |  | Wind | Bowman County | ND | [27 empty] | Done | 2003-03-19 |  | 2004-07-12 | 2009-08-10 | Montana-Dakota Utilities Company | Bowman County | ND | G311 | G311 | Network Upgrade | ERIS | Gascoyne Jct. 34.5 kV substation | 19 | 19 | Wind | WT Wind Turbine | Withdrawn | 2004-03-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G524 | [5 empty] | NRIS |  | 600 |  | Gas | Brown County | WI | [27 empty] | Withdrawn | 2005-06-02 | 2005-11-01 | 2005-11-01 |  | -- No Company -- | Brown County | WI |  |  |  | NRIS | Pulliam Generating Station | 600 | 600 | Gas |  | Not Started | 2008-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G488 | [5 empty] | NRIS |  | 20 |  | Wind | Cottonwood County | MN | [27 empty] | Withdrawn | 2004-12-29 | 2005-12-08 | 2005-12-08 |  | ITC Midwest | Cottonwood County | MN |  |  |  | NRIS | Unknown | 20 | 20 | Wind | WT Wind Turbine | Not Started | 2013-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G391 | [5 empty] | ERIS |  | 10 |  | Nuclear | Kewaunee County | WI | [27 empty] | Withdrawn | 2004-01-13 | 2006-01-03 | 2006-01-03 |  | American Transmission Co. LLC | Kewaunee County | WI |  |  |  | ERIS | Unknown | 10 | 10 | Nuclear |  | Not Started | 2004-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G554 | [5 empty] | NRIS |  | 100 |  | Wind | Palo Alto County | IA | [27 empty] | Withdrawn | 2005-10-24 | 2006-01-09 | 2006-01-09 |  | -- No Company -- | Palo Alto County | IA |  |  |  | NRIS | TBD (likely ALTW line) | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2007-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G582 | [5 empty] | ERIS |  | 0.52 |  | 0 | Eau Claire County | WI | [27 empty] | Withdrawn | 2005-12-29 | 2006-01-11 | 2006-01-11 |  | Northern States Power (Xcel Energy) | Eau Claire County | WI |  |  |  | ERIS | Unknown | 0.52 | 0.52 |  |  | Not Started | 2010-04-04 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G407 | [5 empty] | ERIS |  | 667 |  | Combined Cycle | Blue Earth County | MN | [27 empty] | Withdrawn | 2004-02-20 | 2006-02-02 | 2006-02-02 |  | Northern States Power (Xcel Energy) | Blue Earth County | MN |  |  |  | ERIS | Unknown | 667 | 667 | Combined Cycle |  | Not Started | 2004-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G570 | [5 empty] | NRIS |  | 125 |  | Wind | Kewaunee County | WI | [27 empty] | Withdrawn | 2005-11-17 | 2006-02-15 | 2006-02-15 |  | American Transmission Co. LLC | Kewaunee County | WI |  |  |  | NRIS | Unknown | 125 | 125 | Wind | WT Wind Turbine | Not Started | 2011-01-01 | 0 | 0 | 0 | 0
|  |  |  | G319 | G319 | Done | In Service | G319 | [5 empty] | ERIS |  | 2 |  | Diesel | Martin County | MN | [27 empty] | Done | 2003-03-28 | 2004-03-17 | 2004-07-26 |  | Northern States Power (Xcel Energy) | Martin County | MN | G319 | G319 | Network Upgrade | ERIS | Truman Muni 69kV Substation | 2 | 2 | Diesel |  | In Service | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G482 | [5 empty] | NRIS |  | 1200 |  | Coal | Ashtabula County | OH | [27 empty] | Withdrawn | 2004-11-19 | 2006-02-24 | 2006-02-24 |  | FirstEnergy Solutions Corp. | Ashtabula County | OH |  |  |  | NRIS | ATSI Perry - Ashtabula | 1200 | 1200 | Coal | CT Combined-Cycle Combustion ? Turbine Part | Not Started | 2006-11-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G561 | [5 empty] | NRIS |  | 210 |  | Wind | Bureau County | IL | [27 empty] | Withdrawn | 2005-10-31 | 2006-03-22 | 2006-03-22 |  | Ameren Illinois | Bureau County | IL |  |  |  | NRIS | Princeton 138 kV Substation | 210 | 210 | Wind | WT Wind Turbine | Not Started | 2007-04-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Retired | G322 | [5 empty] | ERIS |  | 10 |  | Diesel | Brown County | WI | [27 empty] | Done | 2003-03-31 |  | 2003-06-28 |  | Wisconsin Public Service Corporation | Brown County | WI |  |  | Network Upgrade | ERIS | James St. Substation | 10 | 10 | Diesel | IC Internal Combustion (diesel, piston) Engine | Retired | 2010-05-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Retired | G323 | [5 empty] | ERIS |  | 5 |  | Diesel | Oneida County | WI | [27 empty] | Done | 2003-03-31 |  | 2003-06-28 |  | Wisconsin Public Service Corporation | Oneida County | WI |  |  | SPA - SIS | ERIS | Piehl 115kV | 5 | 5 | Diesel | IC Internal Combustion (diesel, piston) Engine | Retired | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | G324 | G324 | Done | Retired | G324 | [5 empty] | ERIS |  | 19 |  | Diesel | Oneida County | WI | [27 empty] | Done | 2003-03-31 |  | 2003-06-28 |  | Wisconsin Public Service Corporation | Oneida County | WI | G324 | G324 | Network Upgrade | ERIS | Piehl 115kV | 19 | 19 | Diesel | IC Internal Combustion (diesel, piston) Engine | Retired | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | G325 | G325 | Done | Retired | G325 | [5 empty] | ERIS |  | 16 |  | Diesel | Oneida County | WI | [27 empty] | Done | 2003-03-31 |  | 2003-06-28 |  | Wisconsin Public Service Corporation | Oneida County | WI | G325 | G325 | Network Upgrade | ERIS | Venus 115kV | 16 | 16 | Diesel | IC Internal Combustion (diesel, piston) Engine | Retired | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Retired | G326 | [5 empty] | ERIS |  | 2 |  | Diesel | Marinette County | WI | [27 empty] | Done | 2003-03-31 |  | 2003-06-28 |  | Wisconsin Public Service Corporation | Marinette County | WI |  |  | Network Upgrade | ERIS | Crivitz 138kV | 2 | 2 | Diesel | IC Internal Combustion (diesel, piston) Engine | Retired | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Retired | G327 | [5 empty] | ERIS |  | 19 |  | Diesel | Marinette County | WI | [27 empty] | Done | 2003-03-31 |  | 2003-06-28 |  | Wisconsin Public Service Corporation | Marinette County | WI |  |  | Network Upgrade | ERIS | Crivitz 138kV | 19 | 19 | Diesel | IC Internal Combustion (diesel, piston) Engine | Retired | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G585 | [5 empty] | NRIS |  | 8 |  | Wind | Redwood County | MN | [27 empty] | Withdrawn | 2005-12-30 | 2006-03-24 | 2006-03-24 |  | ITC Midwest | Redwood County | MN |  |  |  | NRIS | Unknown | 8 | 8 | Wind | WT Wind Turbine | Not Started | 2008-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G596 | [5 empty] | ERIS |  | 1 |  | Wind | Morrison County | MN | [27 empty] | Withdrawn | 2006-02-14 | 2006-04-05 | 2006-04-05 |  | Northern States Power (Xcel Energy) | Morrison County | MN |  |  |  | ERIS | Unknown | 1 | 1 | Wind | WT Wind Turbine | Not Started | 2009-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G330 | [5 empty] | ERIS |  | 19 |  | Wind | Mower County | MN | [27 empty] | Done | 2003-04-11 |  | 2003-12-19 |  | ITC Midwest | Mower County | MN |  |  | SPA - SIS | ERIS | Adams - St. Angsgar 69kV | 19 | 19 | Wind | WT Wind Turbine | In Service | 2003-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G522 | [5 empty] | NRIS |  | 550 |  | Coal | Portage County | WI | [27 empty] | Withdrawn | 2005-05-31 | 2006-04-06 | 2006-04-06 |  | American Transmission Co. LLC | Portage County | WI |  |  |  | NRIS | Unknown | 550 | 550 | Coal |  | Not Started | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G523 | [5 empty] | NRIS |  | 550 |  | Coal | Marathon County | WI | [27 empty] | Withdrawn | 2005-05-31 | 2006-04-10 | 2006-04-10 |  | American Transmission Co. LLC | Marathon County | WI |  |  | SPA - SIS | NRIS | Weston Generating Station | 550 | 550 | Coal |  | Not Started | 2006-04-06 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G600 | [5 empty] | ERIS |  | 110 |  | Wind | Marshall County | MN | [27 empty] | Withdrawn | 2006-02-16 | 2006-04-28 | 2006-04-28 |  | Otter Tail Power Company | Marshall County | MN |  |  |  | ERIS | Viking Substation connecting to unnamed 115 kV OTP line | 110 | 110 | Wind | WT Wind Turbine | Not Started | 2010-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G627 | [5 empty] | NRIS |  | 0 |  | 0 | 0 | MI | [27 empty] | Withdrawn | 2006-04-28 | 2006-05-08 | 2006-05-08 |  | ITC Transmission |  | MI |  |  |  | NRIS | Unknown | 0 | 0 |  |  | Not Started | 2008-10-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G528 | [5 empty] | NRIS |  | 550 |  | Coal | Columbia County | WI | [27 empty] | Withdrawn | 2005-06-09 | 2006-05-19 | 2006-05-19 |  | American Transmission Co. LLC | Columbia County | WI |  |  | Feasibility | NRIS | Columbia Energy Center Substation | 550 | 550 | Coal |  | Not Started | 2011-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G509 | [5 empty] | NRIS |  | 75 |  | Wind | St. Louis County | MN | [27 empty] | Withdrawn | 2005-03-18 | 2006-06-22 | 2006-06-22 |  | Minnesota Power (Allete, Inc.) | St. Louis County | MN |  |  | SPA - SIS | NRIS | MP's #34 (115kV) line, approx 2-4 miles NW of Project Site | 75 | 75 | Wind | WT Wind Turbine | Not Started | 2006-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G498 | [5 empty] | ERIS |  | 1.1 |  | Gas | Richland County | OH | [27 empty] | Withdrawn | 2005-02-14 | 2006-07-19 | 2006-07-19 |  | -- No Company -- | Richland County | OH |  |  |  | ERIS | Unknown | 1.1 | 1.1 | Gas |  | Not Started | 2005-12-31 | 0 | 0 | 0 | 0
|  |  |  | G338 | G338 | Done | In Service | G338 | [5 empty] | ERIS |  | 54 |  | Wind | Dodge County | WI | [27 empty] | Done | 2003-04-23 |  | 2004-10-25 | 2008-08-15 | Wisconsin Electric Power Company | Dodge County | WI | G338 | G338 | Network Upgrade | ERIS | Rubicon - Hartford 138kV | 54 | 54 | Wind | WT Wind Turbine | In Service | 2003-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G504 | [5 empty] | NRIS |  | 158 |  | Wind | Sanilac County | MI | [27 empty] | Withdrawn | 2005-03-14 | 2006-08-07 | 2006-08-07 |  | ITC Transmission | Sanilac County | MI |  |  | SPA - SIS | NRIS | ITCT Sandusky - Lee 120kV | 158 | 158 | Wind | WT Wind Turbine | Not Started | 2005-09-09 | 0 | 0 | 0 | 0
|  |  |  | G340 | G340 | Done | In Service | G340 | [5 empty] | ERIS |  | 1 |  | Wind | Lincoln County | MN | [27 empty] | Done | 2003-05-01 |  | 2003-12-19 |  | Otter Tail Power Company | Lincoln County | MN | G340 | G340 | Network Upgrade | ERIS | Toronto 41.6kV | 1 | 1 | Wind | WT Wind Turbine | In Service | 2006-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G341 | [5 empty] | ERIS |  | 2 |  | Gas | Cottonwood County | MN | [27 empty] | Done | 2001-11-19 |  | 2003-08-21 |  | ITC Midwest | Cottonwood County | MN |  |  |  | ERIS | Unknown | 2 | 2 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | G342 | G342 | Done | Retired | G342 | [5 empty] | ERIS |  | 18 |  | Gas | Baraga County | MI | [27 empty] | Done | 2003-06-01 |  | 2003-06-30 |  | Upper Peninsula Power Company | Baraga County | MI | G342 | G342 | Network Upgrade | ERIS | Warden Gen Station | 18 | 18 | Gas | CT Combustion Turbine (Simple Cycle) | Retired | 2003-07-01 | 0 | 0 | 0 | 0
|  |  |  | G343 | G343 | Done | Retired | G343 | [5 empty] | ERIS |  | 20 |  | Diesel | Baraga County | MI | [27 empty] | Done | 2003-06-01 |  | 2003-06-30 |  | Upper Peninsula Power Company | Baraga County | MI | G343 | G343 | Network Upgrade | ERIS | Warden Gen Station | 20 | 20 | Diesel | IC Internal Combustion (diesel, piston) Engine | Retired | 2002-05-01 | 0 | 0 | 0 | 0
|  |  |  | G344 | G344 | Done | Retired | G344 | [5 empty] | ERIS |  | 15 |  | Diesel | Dickinson County | MI | [27 empty] | Done | 2003-06-01 |  | 2003-09-16 |  | Wisconsin Electric Power Company | Dickinson County | MI | G344 | G344 | Network Upgrade | ERIS | Plains Substation | 15 | 15 | Diesel | IC Internal Combustion (diesel, piston) Engine | Retired |  | 0 | 0 | 0 | 0
|  |  |  | G345 | G345 | Done | Retired | G345 | [5 empty] | ERIS |  | 5 |  | Diesel | Schoolcraft County | MI | [27 empty] | Done | 2003-06-01 |  | 2003-06-30 |  | Wisconsin Electric Power Company | Schoolcraft County | MI | G345 | G345 | Network Upgrade | ERIS | Manistique Substation | 5 | 5 | Diesel | IC Internal Combustion (diesel, piston) Engine | Retired |  | 0 | 0 | 0 | 0
|  |  |  | G346 | G346 | Done | Retired | G346 | [5 empty] | ERIS |  | 5 |  | Diesel | Schoolcraft County | MI | [27 empty] | Done | 2003-06-01 |  | 2003-09-16 |  | Wisconsin Electric Power Company | Schoolcraft County | MI | G346 | G346 | Network Upgrade | ERIS | Glen Jenks Substation | 5 | 5 | Diesel | IC Internal Combustion (diesel, piston) Engine | Retired |  | 0 | 0 | 0 | 0
|  |  |  | G347 | G347 | Done | Retired | G347 | [5 empty] | ERIS |  | 15 |  | Diesel | 0 | MI | [27 empty] | Done | 2003-06-01 |  | 2003-09-16 |  | Wisconsin Electric Power Company |  | MI | G347 | G347 | Network Upgrade | ERIS | Armory Substation | 15 | 15 | Diesel | IC Internal Combustion (diesel, piston) Engine | Retired |  | 0 | 0 | 0 | 0
|  |  |  | G348 | G348 | Done | In Service | G348 | [5 empty] | ERIS |  | 2 |  | Diesel | Cass County | IA | [27 empty] | Done | 2003-05-23 |  | 2003-09-12 |  | ITC Midwest | Cass County | IA | G348 | G348 | Network Upgrade | ERIS | ITC Midwest Anita 34.5 kV | 2 | 2 | Diesel | IC Internal Combustion (diesel, piston) Engine | In Service |  | 0 | 0 | 0 | 0
|  |  |  | G349 | G349 | Done | In Service | G349 | [5 empty] | ERIS |  | 200 |  | Wind | Lincoln County | MN | [27 empty] | Done | 2003-06-02 |  | 2006-05-26 | 2010-11-01 | Northern States Power (Xcel Energy) | Lincoln County | MN | G349 | G349 | Network Upgrade | ERIS | Brookings County Substation | 200 | 200 | Wind | WT Wind Turbine | In Service | 2006-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G350 | [5 empty] | ERIS |  | 159 |  | Nuclear | Monroe County | MI | [27 empty] | Done | 2003-06-18 |  | 2004-08-06 |  | ITC Transmission | Monroe County | MI |  |  | SPA - SIS | ERIS | Fermi 345 kV substation | 159 | 159 | Nuclear | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | In Service |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Withdrawn | G351 | [5 empty] | NRIS |  | 200 |  | Gas | Dakota County | MN | [27 empty] | Done | 2003-07-02 |  | 2006-07-05 |  | Northern States Power (Xcel Energy) | Dakota County | MN |  |  | Optional | NRIS | Dakota County 345 kV Substation | 200 | 200 | Gas | CT Combustion Turbine (Simple Cycle) | Withdrawn | 2005-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Withdrawn | G352 | [5 empty] | NRIS |  | 200 |  | Gas | Dakota County | MN | [27 empty] | Done | 2003-07-02 |  | 2006-07-05 |  | Northern States Power (Xcel Energy) | Dakota County | MN |  |  | Network Upgrade | NRIS | Dakota County 345 kV Substation | 200 | 200 | Gas | CT Combustion Turbine (Simple Cycle) | Withdrawn | 2011-11-30 | 0 | 0 | 0 | 0
|  |  |  | G353 | G353 | Done | In Service | G353 | [5 empty] | ERIS |  | 80 |  | Wind | Fond du Lac County | WI | [27 empty] | Done | 2003-07-23 |  | 2004-04-27 |  | Wisconsin Electric Power Company | Fond du Lac County | WI | G353 | G353 | Network Upgrade | ERIS | Acadian - Forest Junction 345kV | 80 | 80 | Wind | WT Wind Turbine | In Service | 2007-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G354 | [5 empty] | ERIS |  | 80 |  | Wind | Fond du Lac County | WI | [27 empty] | Done | 2003-07-23 |  | 2004-04-27 |  | Wisconsin Electric Power Company | Fond du Lac County | WI |  |  | Optional | ERIS | Acadian - Forest Junction 345kV | 80 | 80 | Wind | WT Wind Turbine | In Service | 2009-01-01 | 0 | 0 | 0 | 0
|  |  |  | G355 | G355 | Done | In Service | G355 | [5 empty] | ERIS |  | 6 |  | Diesel | Muscatine County | IA | [27 empty] | Done | 2003-06-27 |  | 2004-04-20 |  | ITC Midwest | Muscatine County | IA | G355 | G355 | Network Upgrade | ERIS | West Liberty Muni Sub 69kV | 6 | 6 | Diesel | IC Internal Combustion (diesel, piston) Engine | In Service | 2003-05-02 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G639 | [5 empty] | ERIS |  | 19.5 |  | Wind | Jackson County | MN | [27 empty] | Withdrawn | 2006-05-17 | 2006-08-10 | 2006-08-10 |  | Great River Energy | Jackson County | MN |  |  |  | ERIS | GRE Ferh Line 2miles south of G536 | 19.5 | 19.5 | Wind | WT Wind Turbine | Not Started | 2007-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G358 | [5 empty] | ERIS |  | 36 |  | Wind | Faribault County | MN | [27 empty] | Done | 2003-09-30 |  | 2007-01-24 | 2012-10-31 | ITC Midwest | Faribault County | MN |  |  | Network Upgrade | ERIS | Winco - Winnebago 161kV | 36 | 36 | Wind | WT Wind Turbine | In Service | 2003-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G647 | [5 empty] | NRIS |  | 102 |  | Wind | Allegan County | MI | [27 empty] | Withdrawn | 2006-06-20 | 2006-08-18 | 2006-08-18 |  | Michigan Electric Transmission Company, LLC | Allegan County | MI |  |  |  | NRIS | Argenta - Tallmadge 345 kV | 102 | 102 | Wind | WT Wind Turbine | Not Started | 2008-01-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-FEB | West | Done | In Service | G359R | [5 empty] | NRIS |  | 150 |  | Wind | Dickey County | ND | [27 empty] | Done | 2015-11-16 |  | 2019-03-20 | 2015-09-17 | Montana-Dakota Utilities Company | Dickey County | ND | DPP-2016-FEB | West | GIA | NRIS | Merricourt Substation | 150 | 150 | Wind | WT Wind Turbine | In Service | 2020-02-28 | 150 | 150 | 150 | 150
|  |  |  | G361 | G361 | Done | In Service | G361 | [5 empty] | ERIS |  | 210 |  | Gas | Isanti County | MN | [27 empty] | Done | 2002-07-10 |  | 2006-01-11 |  | Great River Energy | Isanti County | MN | G361 | G361 | Network Upgrade | ERIS | Cambridge 69kV | 210 | 210 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2006-05-01 | 0 | 0 | 0 | 0
|  |  |  | G362 | G362 | Done | In Service | G362 | [5 empty] | NRIS |  | 200 |  | Wind | Mower County | MN | [27 empty] | Done | 2003-09-30 |  | 2008-10-14 | 2011-10-01 | Great River Energy | Mower County | MN | G362 | G362 | Network Upgrade | NRIS | Pleasant Valley Substation | 200 | 200 | Wind | WT Wind Turbine | In Service | 2014-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G669 | [5 empty] | NRIS |  | 200 |  | Wind | Mower County | MN | [27 empty] | Withdrawn | 2006-08-10 | 2006-09-01 | 2006-09-01 |  | Northern States Power (Xcel Energy) | Mower County | MN |  |  |  | NRIS | Adams - Rochester 161 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2008-12-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G512 | [5 empty] | NRIS |  | 70 |  | Gas | Ford County | IL | [27 empty] | Withdrawn | 2005-04-15 | 2006-09-07 | 2006-09-07 |  | Ameren Illinois | Ford County | IL |  |  | SPA - SIS | NRIS | Gibson City South 138 kV Substation | 70 | 70 | Gas |  | Not Started | 2005-07-01 | 0 | 0 | 0 | 0
|  |  |  | G366 | G366 | Done | Withdrawn | G366 | [5 empty] | ERIS |  | 80 |  | Wind | Columbia County | WI | [27 empty] | Done | 2003-10-15 |  | 2005-02-23 |  | American Transmission Co. LLC | Columbia County | WI | G366 | G366 | Network Upgrade | ERIS | Friesland substation | 80 | 80 | Wind | WT Wind Turbine | Withdrawn | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G484 | [5 empty] | NRIS |  | 1290 |  | Coal | Switzerland County | IN | [27 empty] | Withdrawn | 2004-11-24 | 2006-09-20 | 2006-09-20 |  | Duke Energy Corporation | Switzerland County | IN |  |  | SPA - SIS | NRIS | Egypt Bottom 345 kV Substation | 1290 | 1290 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | Not Started | 2004-10-31 | 0 | 0 | 0 | 0
|  |  |  | G368 | G368 | Done | In Service | G368 | [5 empty] | NRIS |  | 200 |  | Wind | Dodge County | WI | [27 empty] | Done | 2003-10-15 |  | 2005-04-25 | 2007-12-31 | Wisconsin Electric Power Company | Dodge County | WI | G368 | G368 | Network Upgrade | NRIS | South Fond du Lac - Butternut 138kV | 200 | 200 | Wind | WT Wind Turbine | In Service | 2007-09-01 | 0 | 0 | 0 | 0
|  |  |  | G369 | G369 | Done | In Service | G369 | [5 empty] | ERIS |  | 385 |  | Gas | Scott County | MN | [27 empty] | Done | 2003-10-17 |  | 2004-10-28 |  | Northern States Power (Xcel Energy) | Scott County | MN | G369 | G369 | Network Upgrade | ERIS | Blue Lake 115 kV | 385 | 385 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2006-06-01 | 0 | 0 | 0 | 0
|  |  |  | G370 | G370 | Done | In Service | G370 | [5 empty] | ERIS |  | 205 |  | Gas | Minnehaha County | SD | [27 empty] | Done | 2003-10-17 |  | 2005-01-11 |  | Northern States Power (Xcel Energy) | Minnehaha County | SD | G370 | G370 | Network Upgrade | ERIS | Anson 4 | 205 | 205 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2007-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G565 | [5 empty] | ERIS |  | 60 |  | Wind | Huron County | MI | [27 empty] | Withdrawn | 2005-11-04 | 2006-09-27 | 2006-09-27 |  | Michigan Electric Transmission Company, LLC | Huron County | MI |  |  | Feasibility | ERIS | Existing 120 kV line near Rapson Rd and Minden Rd. | 60 | 60 | Wind | WT Wind Turbine | Not Started | 2007-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G679 | [5 empty] | ERIS |  | 9.89 |  | Wind | McLean County | IL | [27 empty] | Withdrawn | 2006-09-11 | 2006-09-28 | 2006-09-28 |  | Ameren Illinois | McLean County | IL |  |  |  | ERIS | Ameren 34.5 kV line near Lexington, IL | 9.89 | 9.89 | Wind | WT Wind Turbine | Not Started | 2012-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G537 | [5 empty] | NRIS |  | 100 |  | Wind | Iroquois County | IL | [27 empty] | Withdrawn | 2005-07-23 | 2006-09-29 | 2006-09-29 |  | Ameren Illinois | Iroquois County | IL |  |  | Feasibility | NRIS | Watseka - Goodland 138 kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2006-10-01 | 0 | 0 | 0 | 0
|  |  |  | G374 | G374 | Done | In Service | G374 | [5 empty] | NRIS |  | 6 |  | Wind | Nobles County | MN | [27 empty] | Done | 2003-11-13 |  | 2005-05-27 | 2006-04-07 | Great River Energy | Nobles County | MN | G374 | G374 | Network Upgrade | NRIS | Rushmore 69kV Substation | 6 | 6 | Wind | WT Wind Turbine | In Service | 2005-05-01 | 0 | 0 | 0 | 0
|  |  |  | G375 | G375 | Done | In Service | G375 | [5 empty] | NRIS |  | 20 |  | Wind | Cottonwood County | MN | [27 empty] | Done | 2003-11-10 |  | 2005-08-05 |  | ITC Midwest | Cottonwood County | MN | G375 | G375 | Network Upgrade | NRIS | Bat Lake - Mt. Lake 69kV | 20 | 20 | Wind | WT Wind Turbine | In Service | 2005-05-01 | 0 | 0 | 0 | 0
|  |  |  | G376 | G376 | Done | Withdrawn | G376 | [5 empty] | ERIS |  | 160 |  | Wind | Green Lake County | WI | [27 empty] | Done | 2003-11-10 |  | 2006-03-17 |  | American Transmission Co. LLC | Green Lake County | WI | G376 | G376 | Network Upgrade | ERIS | Green Lake - North Fond du Lac 138 kV | 160 | 160 | Wind | WT Wind Turbine | Withdrawn | 2006-04-07 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G605 | [5 empty] | NRIS |  | 200 |  | Wind | Montgomery County | IN | [27 empty] | Withdrawn | 2006-02-28 | 2006-09-29 | 2006-09-29 |  | Duke Energy Corporation | Montgomery County | IN |  |  | Feasibility | NRIS | Crawfordsville - Lafayette SE Switching Station 138 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2008-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G603 | [5 empty] | ERIS |  | 6.3 |  | Wind | Lincoln County | MN | [27 empty] | Withdrawn | 2006-02-18 | 2006-10-31 | 2006-10-31 |  | Northern States Power (Xcel Energy) | Lincoln County | MN |  |  |  | ERIS | #321 Xcel 34.5 kV line, 12-15 miles from Buffalo Ridge Sub | 6.3 | 6.3 | Wind | WT Wind Turbine | Not Started | 2009-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G678 | [5 empty] | NRIS |  | 99 |  | Wind | Dane County | WI | [27 empty] | Withdrawn | 2006-09-08 | 2006-11-17 | 2006-11-17 |  | American Transmission Co. LLC | Dane County | WI |  |  | Feasibility | NRIS | North Madison Substation 138 kV | 99 | 99 | Wind | WT Wind Turbine | Not Started | 2010-05-01 | 0 | 0 | 0 | 0
|  |  |  | G380 | G380 | Done | In Service | G380 | [5 empty] | ERIS |  | 150 |  | Wind | Pierce County | ND | [27 empty] | Done | 2003-11-21 |  | 2006-04-11 |  | Otter Tail Power Company | Pierce County | ND | G380 | G380 | Network Upgrade | ERIS | Rugby 115kV Substation | 150 | 150 | Wind | WT Wind Turbine | In Service | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | G382 | G382 | Done | In Service | G382 | [5 empty] | NRIS |  | 8 |  | Wind | Pipestone County | MN | [27 empty] | Done | 2003-11-26 |  | 2005-03-25 |  | Northern States Power (Xcel Energy) | Pipestone County | MN | G382 | G382 | Network Upgrade | NRIS | Chanarambie 115kV | 8 | 8 | Wind | WT Wind Turbine | In Service | 2007-11-30 | 0 | 0 | 0 | 0
|  |  |  | G383 | G383 | Done | In Service | G383 | [5 empty] | ERIS |  | 5 |  | Nuclear | Kewaunee County | WI | [27 empty] | Done | 2003-12-01 |  | 2004-03-19 |  | Wisconsin Public Service Corporation | Kewaunee County | WI | G383 | G383 | Network Upgrade | ERIS | Kewaunee Substation | 5 | 5 | Nuclear | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | In Service | 2002-11-01 | 0 | 0 | 0 | 0
|  |  |  | G384 | G384 | Done | Withdrawn | G384 | [5 empty] | ERIS |  | 99 |  | Wind | Manitowoc County | WI | [27 empty] | Done | 2003-12-08 |  | 2006-01-11 |  | Wisconsin Public Service Corporation | Manitowoc County | WI | G384 | G384 | Network Upgrade | ERIS | Mishicot 138 kV substation | 99 | 99 | Wind | WT Wind Turbine | Withdrawn | 2007-07-31 | 0 | 0 | 0 | 0
|  |  |  | G385 | G385 | Done | In Service | G385 | [5 empty] | NRIS |  | 2 |  | Wind | Nobles County | MN | [27 empty] | Done | 2003-11-07 |  | 2005-08-29 |  | ITC Midwest | Nobles County | MN | G385 | G385 | Network Upgrade | NRIS | Larkin 24kV | 2 | 2 | Wind | WT Wind Turbine | In Service | 2004-07-01 | 0 | 0 | 0 | 0
|  |  |  | G386 | G386 | Done | In Service | G386 | [5 empty] | NRIS |  | 100 |  | Wind | Martin County | MN | [27 empty] | Done | 2003-12-12 |  | 2007-03-21 |  | Northern States Power (Xcel Energy) | Martin County | MN | G386 | G386 | Network Upgrade | NRIS | Lakefield Substation 345kV | 100 | 100 | Wind | WT Wind Turbine | In Service | 2007-10-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G684 | [5 empty] | ERIS |  | 20 |  | Wind | Cottonwood County | MN | [27 empty] | Withdrawn | 2006-10-03 | 2007-01-08 | 2007-01-08 |  | ITC Midwest | Cottonwood County | MN |  |  |  | ERIS | Mt. Lake - Bat Lake 69 kV | 20 | 20 | Wind | WT Wind Turbine | Not Started | 2004-06-04 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G389 | [5 empty] | NRIS |  | 200 |  | Gas | Sherburne County | MN | [27 empty] | Done | 2003-11-03 |  | 2007-10-25 |  | Great River Energy | Sherburne County | MN |  |  | Network Upgrade | NRIS | Elk River 230 kV substation | 200 | 200 | Gas | CT Combined-Cycle Combustion ? Turbine Part | In Service | 2004-08-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G688 | [5 empty] | NRIS |  | 24 |  | Wind | Murray County | MN | [27 empty] | Withdrawn | 2006-10-12 | 2007-01-08 | 2007-01-08 |  | Northern States Power (Xcel Energy) | Murray County | MN |  |  | Feasibility | NRIS | Chanarambie Substation | 24 | 24 | Wind | WT Wind Turbine | Not Started | 2008-04-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G702 | [5 empty] | ERIS |  | 110 |  | Wind | Worth County | IA | [27 empty] | Withdrawn | 2006-11-09 | 2007-01-19 | 2007-01-19 |  | -- No Company -- | Worth County | IA |  |  |  | ERIS | 161 kV NIW Substation | 110 | 110 | Wind | WT Wind Turbine | Not Started | 2007-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G718 | [5 empty] | NRIS |  | 900 |  | Coal | Wapello County | IA | [27 empty] | Withdrawn | 2006-12-13 | 2007-01-23 | 2007-01-23 |  | ITC Midwest | Wapello County | IA |  |  |  | NRIS | Ottumwa Generating Station | 900 | 900 | Coal |  | Not Started | 2009-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G719 | [5 empty] | NRIS |  | 600 |  | Coal | Wapello County | IA | [27 empty] | Withdrawn | 2006-12-13 | 2007-01-23 | 2007-01-23 |  | ITC Midwest | Wapello County | IA |  |  |  | NRIS | Ottumwa Generating Station | 600 | 600 | Coal |  | Not Started | 2010-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G623 | [5 empty] | NRIS |  | 60 |  | Wind | Shelby County | IL | [27 empty] | Withdrawn | 2006-04-20 | 2007-02-15 | 2007-02-15 |  | Ameren Illinois | Shelby County | IL |  |  |  | NRIS | Mattoon West - Shelbyville | 60 | 60 | Wind | WT Wind Turbine | Not Started | 2007-10-01 | 0 | 0 | 0 | 0
|  |  |  | G396 | G396 | Done | In Service | G396 | [5 empty] | ERIS |  | 2 |  | Diesel | Grant County | SD | [27 empty] | Done | 2004-01-13 |  | 2004-06-03 |  | Otter Tail Power Company | Grant County | SD | G396 | G396 | Network Upgrade | ERIS | Milbank 41.6kV | 2 | 2 | Diesel | IC Internal Combustion (diesel, piston) Engine | In Service | 2004-07-01 | 0 | 0 | 0 | 0
|  |  |  | G397 | G397 | Done | In Service | G397 | [5 empty] | NRIS |  | 5 |  | Wind | Pipestone County | MN | [27 empty] | Done | 2004-01-22 |  | 2005-03-25 | 2005-08-15 | Northern States Power (Xcel Energy) | Pipestone County | MN | G397 | G397 | Network Upgrade | NRIS | Chanarambie 115kV | 5 | 5 | Wind | WT Wind Turbine | In Service | 2009-01-01 | 0 | 0 | 0 | 0
|  |  |  | G398 | G398 | Done | In Service | G398 | [5 empty] | NRIS |  | 2 |  | Wind | Pipestone County | MN | [27 empty] | Done | 2004-01-22 |  | 2005-05-27 | 2005-11-01 | Northern States Power (Xcel Energy) | Pipestone County | MN | G398 | G398 | Network Upgrade | NRIS | Chanarambie 115kV | 2 | 2 | Wind | WT Wind Turbine | In Service | 2010-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G732 | [5 empty] | ERIS |  | 34 |  | Coal | Lee County | IA | [27 empty] | Withdrawn | 2007-01-31 | 2007-02-22 | 2007-02-22 |  | ITC Midwest | Lee County | IA |  |  |  | ERIS | 13.2 kV feeding into existing Roquette America electrical infrastructure | 34 | 34 | Coal |  | Not Started | 2010-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G728 | [5 empty] | NRIS |  | 300 |  | Wind | Steele County | MN | [27 empty] | Withdrawn | 2007-01-24 | 2007-02-28 | 2007-02-28 |  | Northern States Power (Xcel Energy) | Steele County | MN |  |  |  | NRIS | Byron - W. Owatonna 161 kV | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2008-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G739 | [5 empty] | NRIS |  | 450 |  | Wind | White County | IN | [27 empty] | Withdrawn | 2007-02-12 | 2007-03-02 | 2007-03-02 |  | Northern Indiana Public Service Company | White County | IN |  |  |  | NRIS | Olive - Dequine 345 kV | 450 | 450 | Wind | WT Wind Turbine | Withdrawn | 2010-01-01 | 0 | 0 | 0 | 0
|  |  |  | G567 | G567 | Withdrawn | Not Started | G567 | [5 empty] | NRIS |  | 165 |  | Coal | Delta County | MI | [27 empty] | Withdrawn | 2005-11-14 | 2007-03-05 | 2007-03-05 |  | American Transmission Co. LLC | Delta County | MI | G567 | G567 | SPA - SIS | NRIS | Escanaba Generating 138 kV substation | 165 | 165 | Coal |  | Not Started | 2007-08-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G405 | [5 empty] | NRIS |  | 350 |  | Gas | Goodhue County | MN | [27 empty] | Done | 2004-02-17 |  | 2006-05-23 |  | Northern States Power (Xcel Energy) | Goodhue County | MN |  |  | Network Upgrade | NRIS | Cannon Falls Sub | 350 | 350 | Gas | Combined Cycle | In Service | 2004-07-01 | 0 | 0 | 0 | 0
|  |  |  | G568 | G568 | Withdrawn | Not Started | G568 | [5 empty] | NRIS |  | 135 |  | Coal | Delta County | MI | [27 empty] | Withdrawn | 2005-11-14 | 2007-03-05 | 2007-03-05 |  | American Transmission Co. LLC | Delta County | MI | G568 | G568 | SPA - SIS | NRIS | Escanaba Generating Station Sub | 135 | 135 | Coal |  | Not Started | 2009-12-31 | 0 | 0 | 0 | 0
|  |  |  | G408 | G408 | Done | In Service | G408 | [5 empty] | ERIS |  | 12 |  | Wind | McHenry County | ND | [27 empty] | Done | 2004-03-02 |  | 2005-11-22 |  | Great River Energy | McHenry County | ND | G408 | G408 | Network Upgrade | ERIS | McHenry - Souris 115kV | 12 | 12 | Wind | WT Wind Turbine | In Service | 2005-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G409 | [5 empty] | ERIS |  | 2 |  | Diesel | Dawson County | MT | [27 empty] | Done | 2004-02-23 |  | 2004-07-13 |  | Montana-Dakota Utilities Company | Dawson County | MT |  |  | Network Upgrade | ERIS | Glendive | 2 | 2 | Diesel | IC Internal Combustion (diesel, piston) Engine | In Service | 2007-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G729 | [5 empty] | ERIS |  | 2.5 |  | Wind | Otter Tail County | MN | [27 empty] | Withdrawn | 2007-01-25 | 2007-03-19 | 2007-03-19 |  | Otter Tail Power Company | Otter Tail County | MN |  |  |  | ERIS | Pelican Rapids NW Jct 41.6 kV Substation | 2.5 | 2.5 | Wind | WT Wind Turbine | Not Started | 2009-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G642 | [5 empty] | ERIS |  | 14 |  | Nuclear | Ottawa County | OH | [27 empty] | Withdrawn | 2006-05-24 | 2007-03-22 | 2007-03-22 |  | FirstEnergy Solutions Corp. | Ottawa County | OH |  |  | SPA - SIS | ERIS | FE Davis Besse 345 Substation | 14 | 14 | Nuclear |  | Not Started | 2007-12-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G412 | [5 empty] | NRIS |  | 200 |  | Coal | Sangamon County | IL | [27 empty] | Done | 2004-03-03 |  | 2007-02-16 |  | City of Springfield, IL - CWLP | Sangamon County | IL |  |  | SPA - SIS | NRIS | Dallman Substation (138 kV) | 200 | 200 | Coal | OT Other | In Service | 2004-03-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G760 | [5 empty] | NRIS |  | 135 |  | Wind | Hamilton County | KS | [27 empty] | Withdrawn | 2007-01-08 | 2007-03-22 | 2007-03-22 |  | -- No Company -- | Hamilton County | KS |  |  |  | NRIS | Unknown | 135 | 135 | Wind | WT Wind Turbine | Not Started | 2015-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G671 | [5 empty] | NRIS |  | 200 |  | Wind | Freeborn County | MN | [27 empty] | Withdrawn | 2006-08-10 | 2007-03-26 | 2007-03-26 |  | Northern States Power (Xcel Energy) | Freeborn County | MN |  |  | Feasibility | NRIS | Winnebago - Hayward 161 kV | 200 | 200 | Wind | WT Wind Turbine | Withdrawn | 2008-04-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G715 | [5 empty] | NRIS |  | 76 |  | Wind | Howard County | IA | [27 empty] | Withdrawn | 2006-12-12 | 2007-03-26 | 2007-03-26 |  | ITC Midwest | Howard County | IA |  |  |  | NRIS | Rice - Beaver Creek 115 kV | 76 | 76 | Wind | WT Wind Turbine | Not Started | 2010-02-13 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G653d | [5 empty] | NRIS |  | 23.25 |  | Diesel | Buchanan County | IA | [27 empty] | Withdrawn | 2006-07-03 | 2007-03-29 | 2007-03-29 |  | ITC Midwest | Buchanan County | IA |  |  | Feasibility | NRIS | Central Indy Substation (ALTW.INDY) Deliverability | 23.25 | 23.25 | Diesel |  | Not Started | 2008-04-01 | 0 | 0 | 0 | 0
|  |  |  | G417 | G417 | Done | In Service | G417 | [5 empty] | NRIS |  | 15 |  | Biomass | Scott County | MN | [27 empty] | Done | 2004-03-22 |  | 2007-09-28 |  | Northern States Power (Xcel Energy) | Scott County | MN | G417 | G417 | Network Upgrade | NRIS | Shakopee - Scott 69 kV | 15 | 15 | Biomass | OT - co-gen | In Service | 2006-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G756 | [5 empty] | NRIS |  | 100.8 |  | Wind | Logan County | OH | [27 empty] | Withdrawn | 2007-02-28 | 2007-04-05 | 2007-04-05 |  | FirstEnergy Solutions Corp. | Logan County | OH |  |  |  | NRIS | Blue Jacket - East Liberty Coop 138 kV | 100.8 | 100.8 | Wind | WT Wind Turbine | Not Started | 2009-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G629 | [5 empty] | NRIS |  | 201 |  | Wind | Henry County | IL | [27 empty] | Withdrawn | 2006-05-04 | 2007-04-17 | 2007-04-17 |  | MidAmerican Energy Company | Henry County | IL |  |  |  | NRIS | 69 kV line at Geneseo Sub | 201 | 201 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G730 | [5 empty] | NRIS |  | 73.5 |  | Wind | Emmet County | IA | [27 empty] | Withdrawn | 2007-01-29 | 2007-04-23 | 2007-04-23 |  | ITC Midwest | Emmet County | IA |  |  |  | NRIS | Maple Swtich Station | 73.5 | 73.5 | Wind | WT Wind Turbine | Not Started | 2008-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G795 | [5 empty] | NRIS |  | 0 |  | Coal | Jasper County | IL | [27 empty] | Withdrawn | 2007-04-30 | 2007-04-30 | 2007-04-30 |  | Ameren Illinois | Jasper County | IL |  |  |  | NRIS | AEG Newton Plant | 0 | 0 | Coal |  | Not Started | 2011-07-01 | 0 | 0 | 0 | 0
|  |  |  | G583 | G583 | Withdrawn | Not Started | G583 | [5 empty] | NRIS |  | 16 |  | Biomass | Ontonagon County | MI | [27 empty] | Withdrawn | 2005-12-29 | 2007-05-03 | 2007-05-03 |  | American Transmission Co. LLC | Ontonagon County | MI | G583 | G583 | SPA - SIS | NRIS | White Pine 69 kV Substation | 16 | 16 | Biomass |  | Not Started | 2015-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G424 | [5 empty] | ERIS |  | 100 |  | Wind | St. Louis County | MN | [27 empty] | Done | 2004-04-19 |  | 2006-08-04 |  | Minnesota Power (Allete, Inc.) | St. Louis County | MN |  |  | Network Upgrade | ERIS | Minntac Substation | 100 | 100 | Wind | WT Wind Turbine | In Service | 2005-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G716 | [5 empty] | NRIS |  | 150 |  | Wind | Howard County | IA | [27 empty] | Withdrawn | 2006-12-12 | 2007-05-04 | 2007-05-04 |  | ITC Midwest | Howard County | IA |  |  |  | NRIS | ITC Midwest Adams - Top Deck Holstein 345kV | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2008-12-01 | 0 | 0 | 0 | 0
|  |  |  | G426 | G426 | Done | In Service | G426 | [5 empty] | ERIS |  | 101 |  | Wind | Jackson County | MN | [27 empty] | Done | 2004-05-04 |  | 2005-10-13 |  | ITC Midwest | Jackson County | MN | G426 | G426 | Network Upgrade | ERIS | Lakefield Junction - Triboji 161kV | 101 | 101 | Wind | WT Wind Turbine | In Service | 2007-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Withdrawn | G427 | [5 empty] | NRIS |  | 98 |  | Wind | Fond du Lac County | WI | [27 empty] | Done | 2004-05-14 |  | 2005-11-10 |  | Wisconsin Electric Power Company | Fond du Lac County | WI |  |  | Optional | NRIS | Acadian - Forest Junction 345kV | 98 | 98 | Wind | WT Wind Turbine | Withdrawn | 2004-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G428 | [5 empty] | ERIS |  | 10 |  | Nuclear | Wright County | MN | [27 empty] | Done | 2004-05-24 |  | 2006-06-19 |  | Northern States Power (Xcel Energy) | Wright County | MN |  |  | SPA - SIS | ERIS | Monticello Nuclear Generating Station | 10 | 10 | Nuclear | Nuclear | In Service | 2005-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G659 | [5 empty] | NRIS |  | 50 |  | Wind | Oliver County | ND | [27 empty] | Withdrawn | 2006-07-17 | 2007-05-24 | 2007-05-24 |  | Minnesota Power (Allete, Inc.) | Oliver County | ND |  |  | Feasibility | NRIS | Center 230 kV Substation | 50 | 50 | Wind | WT Wind Turbine | Withdrawn | 2008-01-01 | 0 | 0 | 0 | 0
|  |  |  | G571 | G571 | Withdrawn | Withdrawn | G571 | [5 empty] | NRIS |  | 100 |  | Wind | Clinton County | IN | [27 empty] | Withdrawn | 2005-11-29 | 2007-06-04 | 2007-06-04 |  | Duke Energy Corporation | Clinton County | IN | G571 | G571 | SPA - SIS | NRIS | Kokomo - Thorntown 230 kV | 100 | 100 | Wind | WT Wind Turbine | Withdrawn | 2011-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G431 | [5 empty] | NRIS |  | 420 |  | Gas | Knox County | IN | [27 empty] | Done | 2004-06-14 |  | 2007-07-09 |  | Duke Energy Corporation | Knox County | IN |  |  | SPA - SIS | NRIS | Edwardsport Gen Station | 420 | 420 | Gas | Combined Cycle | In Service | 2007-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G616 | [5 empty] | NRIS |  | 120 |  | Wind | Benton County | IN | [27 empty] | Withdrawn | 2006-04-04 | 2007-07-06 | 2007-07-06 |  | Northern Indiana Public Service Company | Benton County | IN |  |  | SPA - SIS | NRIS | Goodland - Watseka 138 kV | 120 | 120 | Wind | WT Wind Turbine | Withdrawn | 2007-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G433 | [5 empty] | NRIS |  | 19 |  | Nuclear | Goodhue County | MN | [27 empty] | Done | 2004-06-25 |  | 2006-06-19 |  | Northern States Power (Xcel Energy) | Goodhue County | MN |  |  | SPA - SIS | NRIS | Prairie Island Nuclear Generating Plant Unit #1 | 19 | 19 | Nuclear | Nuclear | In Service | 2005-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G434 | [5 empty] | NRIS |  | 19 |  | Nuclear | Goodhue County | MN | [27 empty] | Done | 2004-06-25 |  | 2006-06-19 |  | Northern States Power (Xcel Energy) | Goodhue County | MN |  |  | SPA - SIS | NRIS | Prairie Island Nuclear Generating Plant Unit #2 | 19 | 19 | Nuclear | Nuclear | In Service | 2006-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | GS6 | Withdrawn | Not Started | G700 | [5 empty] | NRIS |  | 18.9 |  | Wind | Goodhue County | MN | [27 empty] | Withdrawn | 2006-11-07 | 2007-11-27 | 2007-11-27 |  | Northern States Power (Xcel Energy) | Goodhue County | MN |  | GS6 | SPA - SIS | NRIS | Kenyon - Dodge Center 69 kV | 18.9 | 18.9 | Wind | WT Wind Turbine | Not Started | 2007-12-01 | 0 | 0 | 0 | 0
|  |  |  | G436 | G436 | Done | In Service | G436 | [5 empty] | NRIS |  | 50 |  | Coal | Jasper County | IL | [27 empty] | Done | 2004-07-21 |  | 2006-02-22 |  | Ameren Illinois | Jasper County | IL | G436 | G436 | Network Upgrade | NRIS | Newton 345kV | 50 | 50 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | In Service | 2010-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G701 | [5 empty] | NRIS |  | 105 |  | Wind | Henry County | IL | [27 empty] | Withdrawn | 2006-11-09 | 2007-12-26 | 2007-12-26 |  | Ameren Illinois | Henry County | IL |  |  | Feasibility | NRIS | East Kewanee | 105 | 105 | Wind | WT Wind Turbine | Not Started | 2008-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G439 | [5 empty] | NRIS |  | 100 |  | Wind | Benton County | IN | [27 empty] | Done | 2004-07-29 |  | 2007-04-05 |  | Northern Indiana Public Service Company | Benton County | IN |  |  | Network Upgrade | NRIS | Morrison Ditch 138 kV | 100 | 100 | Wind | WT Wind Turbine | In Service | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | CS5 | Withdrawn | Not Started | G613 | [5 empty] | NRIS |  | 17 |  | Wind | Redwood County | MN | [27 empty] | Withdrawn | 2006-03-24 | 2008-03-24 | 2008-03-24 |  | Great River Energy | Redwood County | MN |  | CS5 | SPA - SIS | NRIS | Redwood Electric Substation 6 69 kV | 17 | 17 | Wind | WT Wind Turbine | Not Started | 2008-08-01 | 0 | 0 | 0 | 0
|  |  |  | G442 | G442 | Done | In Service | G442 | [5 empty] | ERIS |  | 50 |  | Wind | Cottonwood County | MN | [27 empty] | Done | 2004-08-18 |  | 2005-11-08 | 2006-05-15 | ITC Midwest | Cottonwood County | MN | G442 | G442 | Network Upgrade | ERIS | Storden 69 KV | 50 | 50 | Wind | WT Wind Turbine | In Service | 2010-06-01 | 0 | 0 | 0 | 0
|  |  |  | G443 | G443 | Done | In Service | G443 | [5 empty] | NRIS |  | 7 |  | Wind | Lincoln County | MN | [27 empty] | Done | 2004-08-23 |  | 2005-06-10 |  | Northern States Power (Xcel Energy) | Lincoln County | MN | G443 | G443 | Network Upgrade | NRIS | Buffalo Ridge 115kV | 7 | 7 | Wind | WT Wind Turbine | In Service | 2007-12-01 | 0 | 0 | 0 | 0
|  |  |  | G444 | G444 | Done | In Service | G444 | [5 empty] | NRIS |  | 5 |  | Wind | Lincoln County | MN | [27 empty] | Done | 2004-08-23 |  | 2005-06-10 |  | Northern States Power (Xcel Energy) | Lincoln County | MN | G444 | G444 | Network Upgrade | NRIS | Buffalo Ridge 115kV | 5 | 5 | Wind | WT Wind Turbine | In Service | 2005-09-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G651 | [5 empty] | NRIS |  | 115 |  | Wind | Cavalier County | ND | [27 empty] | Withdrawn | 2006-06-27 | 2008-03-25 | 2008-03-25 |  | Otter Tail Power Company | Cavalier County | ND |  |  | SPA - SIS | NRIS | OTP Hank's Corner - Walhalla 69 kV | 115 | 115 | Wind | WT Wind Turbine | Withdrawn | 2009-09-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G591 | [5 empty] | NRIS |  | 700 |  | Combined Cycle | St. Louis County | MN | [27 empty] | Withdrawn | 2006-01-25 | 2008-04-16 | 2008-04-16 |  | Minnesota Power (Allete, Inc.) | St. Louis County | MN |  |  | SPA - SIS | NRIS | Minntac 230 kV Substation | 700 | 700 | Combined Cycle |  | Not Started | 2007-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G969 | [5 empty] | ERIS |  | 18 |  | Wind | Benton County | IN | [27 empty] | Withdrawn | 2008-02-04 | 2008-05-14 | 2008-05-14 |  | Northern Indiana Public Service Company | Benton County | IN |  |  |  | ERIS | NIPSCO 69 kV transmission line, intersect 300N, 100W | 18 | 18 | Wind | WT Wind Turbine | Withdrawn | 2010-11-20 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G993 | [5 empty] | ERIS |  | 20 |  | Wind | Kidder County | ND | [27 empty] | Withdrawn | 2008-03-31 | 2008-05-15 | 2008-05-15 |  | Montana-Dakota Utilities Company | Kidder County | ND |  |  |  | ERIS | Proposed new sbstn or upgrded KEM 41.6 kV sbstn at N46 50 06/W104 14 22 | 20 | 20 | Wind | WT Wind Turbine | Withdrawn | 2016-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G799 | [5 empty] | NRIS |  | 120 |  | Wind | Houghton County | MI | [27 empty] | Withdrawn | 2007-05-14 | 2008-06-02 | 2008-06-02 |  | Upper Peninsula Power Company | Houghton County | MI |  |  | Feasibility | NRIS | Atlantic 69kV Substation | 120 | 120 | Wind | WT Wind Turbine | Not Started | 2009-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | H023 | [5 empty] | ERIS |  | 135 |  | Co-Gen | Lucas County | OH | [27 empty] | Withdrawn | 2008-05-14 | 2008-06-03 | 2008-06-03 |  | FirstEnergy Solutions Corp. | Lucas County | OH |  |  |  | ERIS | Ironville Substation | 135 | 135 | Co-Gen |  | Withdrawn | 2012-12-31 | 0 | 0 | 0 | 0
|  |  |  | G474 | G474 | Done | In Service | G474 | [5 empty] | ERIS |  | 20 |  | Wind | Grant County | MN | [27 empty] | Done | 2004-10-01 |  | 2007-05-25 |  | Otter Tail Power Company | Grant County | MN | G474 | G474 | Network Upgrade | ERIS | OTP Cyrus - Hoffman 41.6kV | 20 | 20 | Wind | WT Wind Turbine | In Service | 2005-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G475 | [5 empty] | NRIS |  | 56 |  | Nuclear | Callaway County | MO | [27 empty] | Done | 2004-10-07 |  | 2006-02-03 |  | Ameren Missouri | Callaway County | MO |  |  | Network Upgrade | NRIS | Callaway Nuclear Station | 56 | 56 | Nuclear | Nuclear | In Service | 2007-11-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H010 | [5 empty] | ERIS |  | 182 |  | Wind | Madison County | IA | [27 empty] | Withdrawn | 2008-04-22 | 2008-06-10 | 2008-06-10 |  | ITC Midwest | Madison County | IA |  |  |  | ERIS | Winterset Jct. - Creston 161 kV | 182 | 182 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Withdrawn | G477 | [5 empty] | NRIS |  | 552 |  | Coal | St. Louis County | MN | [27 empty] | Done | 2004-10-20 |  | 2007-07-09 |  | Minnesota Power (Allete, Inc.) | St. Louis County | MN |  |  | Network Upgrade | NRIS | Forbes Substation | 552 | 552 | Coal |  | Withdrawn | 2005-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G478 | [5 empty] | NRIS |  | 134 |  | Gas | Madison County | IL | [27 empty] | Done | 2004-10-15 |  | 2005-10-11 |  | Ameren Illinois | Madison County | IL |  |  | SPA - SIS | NRIS | Venice Switchyard at breaker position 32H | 134 | 134 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2005-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G479 | [5 empty] | NRIS |  | 29 |  | Coal | Ottawa County | MI | [27 empty] | Done | 2004-10-26 |  | 2006-08-29 |  | Michigan Electric Transmission Company, LLC | Ottawa County | MI |  |  | SPA - SIS | NRIS | Campbell 345kV Substation | 29 | 29 | Coal | OT Other | In Service | 2008-08-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G897 | [5 empty] | NRIS |  | 1500 |  | Wind | Benton County | MN | [27 empty] | Withdrawn | 2007-10-23 | 2008-06-11 | 2008-06-11 |  | Great River Energy | Benton County | MN |  |  |  | NRIS | Benton County 345 kV Substation | 1500 | 1500 | Wind | WT Wind Turbine | Not Started | 2010-12-01 | 0 | 0 | 0 | 0
|  |  |  | G481 | G481 | Done | In Service | G481 | [5 empty] | ERIS |  | 1 |  | Wind | Rolette County | ND | [27 empty] | Done | 2004-11-01 |  | 2005-05-11 | 2005-08-01 | Otter Tail Power Company | Rolette County | ND | G481 | G481 | Network Upgrade | ERIS | Belcourt 69kV Substation | 1 | 1 | Wind | WT Wind Turbine | In Service | 2007-03-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G898 | [5 empty] | NRIS |  | 1500 |  | Wind | Benton County | MN | [27 empty] | Withdrawn | 2007-10-23 | 2008-06-11 | 2008-06-11 |  | Great River Energy | Benton County | MN |  |  |  | NRIS | Benton County 345 kV substation | 1500 | 1500 | Wind | WT Wind Turbine | Not Started | 2010-12-01 | 0 | 0 | 0 | 0
|  |  |  | G483 | G483 | Done | Withdrawn | G483 | [5 empty] | NRIS |  | 50 |  | Wind | Green County | WI | [27 empty] | Done | 2004-11-23 |  | 2006-04-12 |  | American Transmission Co. LLC | Green County | WI | G483 | G483 | Network Upgrade | NRIS | 69kV line S.E. of Monroe | 50 | 50 | Wind | WT Wind Turbine | Withdrawn | 2005-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G899 | [5 empty] | NRIS |  | 1000 |  | Wind | Wright County | MN | [27 empty] | Withdrawn | 2007-10-23 | 2008-06-18 | 2008-06-18 |  | Northern States Power (Xcel Energy) | Wright County | MN |  |  |  | NRIS | Monticello 345 kV Substation | 1000 | 1000 | Wind | WT Wind Turbine | Not Started | 2011-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G900 | [5 empty] | NRIS |  | 1000 |  | Wind | Wright County | MN | [27 empty] | Withdrawn | 2007-10-23 | 2008-06-18 | 2008-06-18 |  | Northern States Power (Xcel Energy) | Wright County | MN |  |  |  | NRIS | Monticello 345 kV substation | 1000 | 1000 | Wind | WT Wind Turbine | Not Started | 2011-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | GS11 | Withdrawn | Not Started | G850 | [5 empty] | NRIS |  | 250 |  | Wind | Murray County | MN | [27 empty] | Withdrawn | 2007-08-24 | 2008-06-24 | 2008-06-24 |  | Great River Energy | Murray County | MN |  | GS11 | Feasibility | NRIS | Lake Sarah Tap Substation | 250 | 250 | Wind | WT Wind Turbine | Not Started | 2014-05-07 | 0 | 0 | 0 | 0
|  |  |  | 0 | GS11 | Withdrawn | Not Started | G851 | [5 empty] | NRIS |  | 250 |  | Wind | Murray County | MN | [27 empty] | Withdrawn | 2007-08-24 | 2008-06-24 | 2008-06-24 |  | Great River Energy | Murray County | MN |  | GS11 | Feasibility | NRIS | GRE Lake Sarah 115 kV Substation | 250 | 250 | Wind | WT Wind Turbine | Not Started | 2010-04-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G581 | [5 empty] | NRIS |  | 600 |  | Coal | Oliver County | ND | [27 empty] | Withdrawn | 2005-12-27 | 2008-07-01 | 2008-07-01 |  | Minnesota Power (Allete, Inc.) | Oliver County | ND |  |  | Network Upgrade | NRIS | Center 345 kV bus at the Milton R. Young Plant | 600 | 600 | Coal |  | Not Started | 2010-03-27 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G492 | [5 empty] | ERIS |  | 5 |  | Wind | Murray County | MN | [27 empty] | Done | 2005-02-04 |  | 2005-06-06 | 2005-10-31 | Northern States Power (Xcel Energy) | Murray County | MN |  |  |  | ERIS | Southridge Substation - SRD 211 | 5 | 5 | Wind | WT Wind Turbine | In Service | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | H035 | [5 empty] | NRIS |  | 15 |  | Biomass | Bowman County | ND | [27 empty] | Withdrawn | 2008-05-21 | 2008-07-17 | 2008-07-17 |  | Montana-Dakota Utilities Company | Bowman County | ND |  |  |  | NRIS | 41.6 k v line near Gascoyne Junct Sbstn, Section 34-131-99 | 15 | 15 | Biomass |  | Withdrawn | 2011-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H072 | [5 empty] | NRIS |  | 200 |  | Wind | McLeod County | MN | [27 empty] | Withdrawn | 2008-06-18 | 2008-07-30 | 2008-07-30 |  | -- No Company -- | McLeod County | MN |  |  |  | NRIS | Glencoe Municipal substation 115 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | G495 | Done | In Service | G495 | [5 empty] | NRIS |  | 150 |  | Coal | Washington County | IL | [27 empty] | Done | 2005-02-10 |  | 2007-11-13 | 2012-05-31 | Ameren Illinois | Washington County | IL |  | G495 | Optional | NRIS | Prairie State | 150 | 150 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | In Service | 2006-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | CS5 | Withdrawn | Withdrawn | G584 | [5 empty] | ERIS |  | 3 |  | Wind | Pipestone County | MN | [27 empty] | Withdrawn | 2005-12-29 | 2008-08-12 | 2008-08-12 |  | Great River Energy | Pipestone County | MN |  | CS5 | SPA - SIS | ERIS | Chanarambie - Buffalo Ridge 34.5 kV | 3 | 3 | Wind | WT Wind Turbine | Withdrawn | 2007-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H040 | [5 empty] | NRIS |  | 81 |  | Wind | O'Brien County | IA | [27 empty] | Withdrawn | 2008-06-09 | 2008-08-13 | 2008-08-13 |  | ITC Midwest | O'Brien County | IA |  |  |  | NRIS | Primghar Substation | 81 | 81 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G902 | [5 empty] | NRIS |  | 1500 |  | Wind | Winnebago County | IL | [27 empty] | Withdrawn | 2007-10-23 | 2008-08-19 | 2008-08-19 |  | American Transmission Co. LLC | Winnebago County | IL |  |  | Feasibility | NRIS | Paddtown 345 kV Substation | 1500 | 1500 | Wind | WT Wind Turbine | Not Started | 2012-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H032 | [5 empty] | NRIS |  | 180 |  | Wind | Polk County | MN | [27 empty] | Withdrawn | 2008-05-20 | 2008-09-15 | 2008-09-15 |  | Otter Tail Power Company | Polk County | MN |  |  | Feasibility | NRIS | Winger - Maple River 230 kV | 180 | 180 | Wind | WT Wind Turbine | Not Started | 2012-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G845 | [5 empty] | NRIS |  | 60 |  | Wind | Cavalier County | ND | [27 empty] | Withdrawn | 2007-08-28 | 2008-09-25 | 2008-09-25 |  | Otter Tail Power Company | Cavalier County | ND |  |  | Feasibility | NRIS | Langdon 115 kV Substation | 60 | 60 | Wind | WT Wind Turbine | Withdrawn | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | G502 | G502 | Done | In Service | G502 | [5 empty] | NRIS |  | 50 |  | Wind | Oliver County | ND | [27 empty] | Done | 2005-03-14 |  | 2006-04-20 |  | Minnesota Power (Allete, Inc.) | Oliver County | ND | G502 | G502 | Network Upgrade | NRIS | Milton S Young Station #2 Switchyard Center Bus Substation | 50 | 50 | Wind | WT Wind Turbine | In Service | 2007-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G503 | [5 empty] | NRIS |  | 158 |  | Wind | Huron County | MI | [27 empty] | Done | 2005-03-14 |  | 2008-01-08 |  | ITC Transmission | Huron County | MI |  |  | Network Upgrade | NRIS | Sanduskey - Wyatt 120 kV | 158 | 158 | Wind | WT Wind Turbine | In Service | 2008-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G578 | [5 empty] | NRIS |  | 300 |  | Wind | Adair County | MO | [27 empty] | Withdrawn | 2005-12-20 | 2008-09-30 | 2008-09-30 | 2010-12-31 | Ameren Missouri | Adair County | MO |  |  | Network Upgrade | NRIS | Adair 161kV Substation | 300 | 300 | Wind | WT Wind Turbine | Withdrawn | 2006-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H039 | [5 empty] | NRIS |  | 71 |  | Wind | Tama County | IA | [27 empty] | Withdrawn | 2008-06-06 | 2008-10-09 | 2008-10-09 |  | ITC Midwest | Tama County | IA |  |  | Feasibility | NRIS | Toledo - Marshalltown 115 kV | 71 | 71 | Wind | WT Wind Turbine | Not Started | 2011-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G832 | [5 empty] | ERIS |  | 20 |  | Biomass | Chippewa County | WI | [27 empty] | Withdrawn | 2007-08-02 | 2008-10-13 | 2008-10-13 |  | Northern States Power (Xcel Energy) | Chippewa County | WI |  |  | Feasibility | ERIS | Jim Falls - Holcombe 115 kV | 20 | 20 | Biomass |  | Not Started | 2010-11-01 | 0 | 0 | 0 | 0
|  |  |  | G507 | G507 | Done | In Service | G507 | [5 empty] | ERIS |  | 68 |  | Wind | Fond du Lac County | WI | [27 empty] | Done | 2005-03-11 |  | 2007-02-01 |  | Wisconsin Public Service Corporation | Fond du Lac County | WI | G507 | G507 | Network Upgrade | ERIS | Near intersection of 138kV line X-2 (OHM-MUR), 345kV line W-1 (SFL-EDG), and 345kV line 971L51 (FJT-ADN) | 68 | 68 | Wind | WT Wind Turbine | In Service | 2005-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G507b | [5 empty] | NRIS |  | 98 |  | Wind | Fond du Lac County | WI | [27 empty] | Done | 2006-03-16 |  | 2007-05-30 |  | Wisconsin Public Service Corporation | Fond du Lac County | WI |  |  | SPA - SIS | NRIS | Ohmstead - Kettle Moraine 138kV | 98 | 98 | Wind | WT Wind Turbine | In Service | 2008-08-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H080 | [5 empty] | NRIS |  | 200 |  | Wind | Carroll County | IL | [27 empty] | Withdrawn | 2008-06-24 | 2008-10-13 | 2008-10-13 |  | ITC Midwest | Carroll County | IL |  |  | Feasibility | NRIS | 161 kV line, approx 4 miles south of Savanna | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G995 | [5 empty] | NRIS |  | 99 |  | Wind | Lafayette County | WI | [27 empty] | Withdrawn | 2008-04-02 | 2008-10-22 | 2008-10-22 |  | American Transmission Co. LLC | Lafayette County | WI |  |  | Feasibility | NRIS | Hillman - Darlington 138 kV | 99 | 99 | Wind | WT Wind Turbine | Not Started | 2009-06-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G510 | [5 empty] | ERIS |  | 90 |  | Gas | Ozaukee County | WI | [27 empty] | Done | 2005-03-18 |  | 2006-08-31 |  | Wisconsin Electric Power Company | Ozaukee County | WI |  |  | SPA - SIS | ERIS | Port Washington, WI | 90 | 90 | Gas | Combined Cycle | In Service | 2005-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H063 | [5 empty] | NRIS |  | 40 |  | Wind | McLeod County | MN | [27 empty] | Withdrawn | 2008-06-16 | 2008-10-23 | 2008-10-23 |  | Great River Energy | McLeod County | MN |  |  | Feasibility | NRIS | GRE Glenco - Helen 69 kV | 40 | 40 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H064 | [5 empty] | NRIS |  | 39 |  | Wind | Sibley County | MN | [27 empty] | Withdrawn | 2008-06-16 | 2008-10-30 | 2008-10-30 |  | Northern States Power (Xcel Energy) | Sibley County | MN |  |  | Feasibility | NRIS | Crystal Foods Substation 69 kV | 39 | 39 | Wind | WT Wind Turbine | Not Started | 2011-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Withdrawn | G513 | [5 empty] | NRIS |  | 100 |  | Wind | Oceana County | MI | [27 empty] | Done | 2005-04-15 |  | 2009-12-28 | 2011-09-01 | Michigan Electric Transmission Company, LLC | Oceana County | MI |  |  | Feasibility | NRIS | METC White Lake 138kV Substation | 100 | 100 | Wind | WT Wind Turbine | Withdrawn | 2006-10-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G514 | [5 empty] | ERIS |  | 150 |  | Wind | Jackson County | MN | [27 empty] | Done | 2005-04-20 |  | 2009-05-20 | 2011-11-11 | Northern States Power (Xcel Energy) | Jackson County | MN |  |  | Network Upgrade | ERIS | Lakefield Station via Trimont G263 Interconnect | 150 | 150 | Wind | WT Wind Turbine | In Service | 2006-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G515 | [5 empty] | NRIS |  | 100 |  | Wind | Tazewell County | IL | [27 empty] | Done | 2005-04-21 |  | 2007-08-06 |  | Ameren Illinois | Tazewell County | IL |  |  | Network Upgrade | NRIS | Ameren Mason - Tazewell 138kV | 100 | 100 | Wind | WT Wind Turbine | In Service | 2007-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H066 | [5 empty] | NRIS |  | 70 |  | Wind | Rice County | MN | [27 empty] | Withdrawn | 2008-06-17 | 2008-10-30 | 2008-10-30 |  | ITC Midwest | Rice County | MN |  |  | Feasibility | NRIS | Montgomery - Waseca Junction 69 kV | 70 | 70 | Wind | WT Wind Turbine | Not Started | 2010-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G914 | [5 empty] | NRIS |  | 137 |  | Wind | Putnam County | IL | [27 empty] | Withdrawn | 2007-11-16 | 2008-10-31 | 2008-10-31 |  | Ameren Illinois | Putnam County | IL |  |  | Feasibility | NRIS | Hennepin Tap - Richland 138 kV | 137 | 137 | Wind | WT Wind Turbine | Not Started | 2012-11-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | GS4 | Done | In Service | G518 | [5 empty] | ERIS |  | 8 |  | Wind | Jackson County | MN | [27 empty] | Done | 2005-05-02 |  | 2006-09-27 |  | ITC Midwest | Jackson County | MN |  | GS4 | Network Upgrade | ERIS | Miloma - Round Lake 69 kV | 8 | 8 | Wind | WT Wind Turbine | In Service | 2007-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G915 | [5 empty] | NRIS |  | 150 |  | Wind | Montgomery County | IL | [27 empty] | Withdrawn | 2007-11-16 | 2008-10-31 | 2008-10-31 |  | Ameren Illinois | Montgomery County | IL |  |  | Feasibility | NRIS | North Pana - Coffeen 345kV | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2011-10-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | GS20 | Withdrawn | Not Started | G932 | [5 empty] | NRIS |  | 56 |  | Wind | Swift County | MN | [27 empty] | Withdrawn | 2007-12-11 | 2008-10-31 | 2008-10-31 |  | Great River Energy | Swift County | MN |  | GS20 | Feasibility | NRIS | GRE transmission line at the 69 kV rating | 56 | 56 | Wind | WT Wind Turbine | Not Started | 2012-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G521 | [5 empty] | NRIS |  | 30 |  | Nuclear | Ottawa County | OH | [27 empty] | Done | 2005-05-27 |  | 2006-03-10 |  | FirstEnergy Solutions Corp. | Ottawa County | OH |  |  | SPA - SIS | NRIS | FE Davis Besse 345 Substation | 30 | 30 | Nuclear | Nuclear | In Service | 2010-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G891 | [5 empty] | NRIS |  | 42 |  | Gas | Fallon County | MT | [27 empty] | Withdrawn | 2007-10-19 | 2008-11-03 | 2008-11-03 |  | Montana-Dakota Utilities Company | Fallon County | MT |  |  | Feasibility | NRIS | Baker Junction 115 KV Substation | 42 | 42 | Gas |  | Withdrawn | 2008-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H091 | [5 empty] | NRIS |  | 101 |  | Wind | Trumbull County | OH | [27 empty] | Withdrawn | 2008-07-24 | 2008-11-07 | 2008-11-07 |  | -- No Company -- | Trumbull County | OH |  |  | Feasibility | NRIS | Ohio Edison 138kV Cortland Substation | 101 | 101 | Wind | WT Wind Turbine | Not Started | 2011-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G745 | [5 empty] | NRIS |  | 130 |  | Wind | White County | IN | [27 empty] | Withdrawn | 2007-02-20 | 2008-11-12 | 2008-11-12 |  | Northern Indiana Public Service Company | White County | IN |  |  | Feasibility | NRIS | NIPSCO Westwood - S. Prairie 138kV | 130 | 130 | Wind | WT Wind Turbine | Withdrawn | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G526 | [5 empty] | NRIS |  | 52 |  | Wind | Huron County | MI | [27 empty] | Done | 2005-06-06 |  | 2007-07-03 |  | ITC Transmission | Huron County | MI |  |  | Network Upgrade | NRIS | Cosmo Tap - Bad Axe - Arrowhead 120kV | 52 | 52 | Wind | WT Wind Turbine | In Service | 2010-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Withdrawn | G527 | [5 empty] | NRIS |  | 280 |  | Coal | Grant County | WI | [27 empty] | Done | 2005-06-09 |  | 2009-03-02 |  | American Transmission Co. LLC | Grant County | WI |  |  | Network Upgrade | NRIS | Nelson-Dewey Generating Station Sub | 280 | 280 | Coal | Combined Cycle | Withdrawn | 2006-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G986 | [5 empty] | NRIS |  | 99 |  | Wind | Woodford County | IL | [27 empty] | Withdrawn | 2008-03-18 | 2008-11-12 | 2008-11-12 |  | Ameren Illinois | Woodford County | IL |  |  | Feasibility | NRIS | Minonk - El Paso Substations 138kV | 99 | 99 | Wind | WT Wind Turbine | Not Started | 2011-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G987 | [5 empty] | NRIS |  | 400 |  | Wind | Brown County | WI | [27 empty] | Withdrawn | 2008-03-18 | 2008-11-12 | 2008-11-12 |  | Wisconsin Public Service Corporation | Brown County | WI |  |  | Feasibility | NRIS | Kewaunee - North Appleton 345kV | 400 | 400 | Wind | WT Wind Turbine | Not Started | 2009-12-01 | 0 | 0 | 0 | 0
|  |  |  | G530 | G530 | Done | In Service | G530 | [5 empty] | NRIS |  | 14 |  | Wind | Greene County | IA | [27 empty] | Done | 2005-06-15 |  | 2006-11-14 |  | ITC Midwest | Greene County | IA | G530 | G530 | Network Upgrade | NRIS | Jefferson - Grand Junction 34.5 kV | 14 | 14 | Wind | WT Wind Turbine | In Service | 2006-10-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G738 | [5 empty] | ERIS |  | 300 |  | Wind | Lincoln County | MN | [27 empty] | Withdrawn | 2007-02-06 | 2008-11-14 | 2008-11-14 |  | Northern States Power (Xcel Energy) | Lincoln County | MN |  |  | SPA - SIS | ERIS | Xcel Zulu Substation | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2008-09-01 | 0 | 0 | 0 | 0
|  |  |  | G532 | G532 | Done | In Service | G532 | [5 empty] | ERIS |  | 20 |  | Wind | Cottonwood County | MN | [27 empty] | Done | 2005-07-06 |  | 2007-02-15 |  | ITC Midwest | Cottonwood County | MN | G532 | G532 | Network Upgrade | ERIS | Odin 69 kV | 20 | 20 | Wind | WT Wind Turbine | In Service | 2006-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G998 | [5 empty] | NRIS |  | 200 |  | Wind | Clinton County | IN | [27 empty] | Withdrawn | 2008-04-10 | 2008-11-18 | 2008-11-18 |  | Duke Energy Corporation | Clinton County | IN |  |  | Feasibility | NRIS | Lafayette-New London 230 kV | 200 | 200 | Wind | WT Wind Turbine | Withdrawn | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | G535 | G535 | Done | In Service | G535 | [5 empty] | NRIS |  | 16 |  | Coal | Fulton County | IL | [27 empty] | Done | 2005-07-15 |  | 2006-12-21 |  | Ameren Illinois | Fulton County | IL | G535 | G535 | SPA - SIS | NRIS | Duck Creek Power Station | 16 | 16 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | In Service | 2008-08-01 | 0 | 0 | 0 | 0
|  |  |  | G536 | G536 | Done | In Service | G536 | [5 empty] | ERIS |  | 20 |  | Wind | Jackson County | MN | [27 empty] | Done | 2005-07-20 |  | 2006-09-13 |  | ITC Midwest | Jackson County | MN | G536 | G536 | Network Upgrade | ERIS | W. Lakefield Tap 69 kV bus | 20 | 20 | Wind | WT Wind Turbine | In Service | 2009-04-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G999 | [5 empty] | NRIS |  | 200 |  | Wind | Clinton County | IN | [27 empty] | Withdrawn | 2008-04-10 | 2008-11-18 | 2008-11-18 |  | Duke Energy Corporation | Clinton County | IN |  |  | Feasibility | NRIS | Cayuga - New London 230 kV | 200 | 200 | Wind | WT Wind Turbine | Withdrawn | 2012-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | G538 | Done | In Service | G538 | [5 empty] | NRIS |  | 50 |  | Wind | Dickinson County | IA | [27 empty] | Done | 2005-08-08 |  | 2008-10-20 | 2008-09-30 | ITC Midwest | Dickinson County | IA |  | G538 | Network Upgrade | NRIS | Lakefield Junction - Triboji 161kV | 50 | 50 | Wind | WT Wind Turbine | In Service | 2007-04-25 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | H013 | [5 empty] | NRIS |  | 200 |  | Wind | Henry County | IN | [27 empty] | Withdrawn | 2008-04-30 | 2008-11-18 | 2008-11-18 |  | Duke Energy Corporation | Henry County | IN |  |  | Feasibility | NRIS | New Castle - Batesville 138 kV | 200 | 200 | Wind | WT Wind Turbine | Withdrawn | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | CS5 | Done | In Service | G540 | [5 empty] | NRIS |  | 80 |  | Wind | Worth County | IA | [27 empty] | Done | 2005-09-01 |  | 2008-12-15 |  | ITC Midwest | Worth County | IA |  | CS5 | DPP - SIS | NRIS | Adams - Lime Creek 161 kV | 80 | 80 | Wind | WT Wind Turbine | In Service | 2007-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G541 | [5 empty] | NRIS |  | 50 |  | Coal | Beaver County | PA | [27 empty] | Done | 2005-09-02 |  | 2006-01-13 |  | FirstEnergy Solutions Corp. | Beaver County | PA |  |  |  | NRIS | FE Mansfield Unit One | 50 | 50 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, | In Service | 2006-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Withdrawn | G542 | [5 empty] | NRIS |  | 50 |  | Coal | Beaver County | PA | [27 empty] | Done | 2005-09-02 |  | 2006-01-13 |  | FirstEnergy Solutions Corp. | Beaver County | PA |  |  |  | NRIS | FE Mansfield Two | 50 | 50 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, | Withdrawn | 2008-04-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G543 | [5 empty] | NRIS |  | 50 |  | Coal | Beaver County | PA | [27 empty] | Done | 2005-09-02 |  | 2006-01-13 |  | FirstEnergy Solutions Corp. | Beaver County | PA |  |  |  | NRIS | FE Mansfield Three | 50 | 50 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, | In Service | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | H014 | [5 empty] | NRIS |  | 300 |  | Wind | Rush County | IN | [27 empty] | Withdrawn | 2008-04-30 | 2008-11-18 | 2008-11-18 |  | Duke Energy Corporation | Rush County | IN |  |  | Feasibility | NRIS | Five Points - Batesville 138 kV | 300 | 300 | Wind | WT Wind Turbine | Withdrawn | 2011-07-01 | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | CIGS II | Done | In Service | G545 | [5 empty] | NRIS |  | 200 |  | Wind | Henry County | IL | [27 empty] | Done | 2005-09-07 |  | 2010-01-08 | 2012-12-31 | Ameren Illinois | Henry County | IL | Pre-Transition SIS | CIGS II | Network Upgrade | NRIS | East Kewanee 138 kV Substation | 200 | 200 | Wind | WT Wind Turbine | In Service | 2007-12-31 | 0 | 0 | 0 | 0
|  |  |  | G546 | G546 | Done | Withdrawn | G546 | [5 empty] | NRIS |  | 100 |  | Wind | Walworth County | WI | [27 empty] | Done | 2005-09-10 |  | 2007-07-09 |  | Wisconsin Electric Power Company | Walworth County | WI | G546 | G546 | Network Upgrade | NRIS | Sugar Creek 138 kV Substation | 100 | 100 | Wind | WT Wind Turbine | Withdrawn | 2006-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G547 | [5 empty] | NRIS |  | 15 |  | Hydro | Miller County | MO | [27 empty] | Done | 2005-09-17 |  | 2007-04-26 |  | Ameren Missouri | Miller County | MO |  |  | SPA - SIS | NRIS | Osage Switchyard | 15 | 15 | Hydro | HY Hydraulic Turbine (including turnbines associated with delive | In Service | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | CS5 | Done | In Service | G548 | [5 empty] | NRIS |  | 80 |  | Wind | Worth County | IA | [27 empty] | Done | 2005-09-17 |  | 2008-12-15 |  | ITC Midwest | Worth County | IA |  | CS5 | DPP - SIS | NRIS | Barton 161kV Substation | 80 | 80 | Wind | WT Wind Turbine | In Service | 2007-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | H015 | [5 empty] | NRIS |  | 200 |  | Wind | Boone County | IN | [27 empty] | Withdrawn | 2008-04-30 | 2008-11-18 | 2008-11-18 |  | Duke Energy Corporation | Boone County | IN |  |  | Feasibility | NRIS | Whitestown - Nucor 345 kV | 200 | 200 | Wind | WT Wind Turbine | Withdrawn | 2009-12-31 | 0 | 0 | 0 | 0
|  |  |  | G550 | G550 | Done | In Service | G550 | [5 empty] | NRIS |  | 24 |  | Gas | Jefferson County | WI | [27 empty] | Done | 2005-09-24 |  | 2006-10-25 |  | Wisconsin Electric Power Company | Jefferson County | WI | G550 | G550 | Network Upgrade | NRIS | Concord Generating Station | 24 | 24 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2006-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | CS5 | Done | In Service | G551 | [5 empty] | NRIS |  | 99 |  | Wind | Howard County | IA | [27 empty] | Done | 2005-09-27 |  | 2009-12-23 | 2009-12-01 | ITC Midwest | Howard County | IA |  | CS5 | DPP - SIS | NRIS | Rice 161 kV | 99 | 99 | Wind | WT Wind Turbine | In Service | 2006-12-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G712 | [5 empty] | NRIS |  | 513 |  | Coal | Bowman County | ND | [27 empty] | Withdrawn | 2006-12-11 | 2008-12-01 | 2008-12-01 |  | -- No Company -- | Bowman County | ND |  |  | SPA - SIS | NRIS | existing unnamed 230 kV transmission line 2 miles south of plant | 513 | 513 | Coal |  | Withdrawn | 2012-10-01 | 0 | 0 | 0 | 0
|  |  |  | G553 | G553 | Done | Withdrawn | G553 | [5 empty] | NRIS |  | 280 |  | Coal | Columbia County | WI | [27 empty] | Done | 2005-09-30 |  | 2009-03-02 |  | American Transmission Co. LLC | Columbia County | WI | G553 | G553 | Network Upgrade | NRIS | Columbia Energy Center sub | 280 | 280 | Coal | Combined Cycle | Withdrawn | 2007-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | GS16 | Withdrawn | Not Started | G895 | [5 empty] | NRIS |  | 1500 |  | Wind | Scott County | MN | [27 empty] | Withdrawn | 2007-10-23 | 2008-12-01 | 2008-12-01 |  | Northern States Power (Xcel Energy) | Scott County | MN |  | GS16 | Feasibility | NRIS | Scott Junction 345/115 kV substation | 1500 | 1500 | Wind | WT Wind Turbine | Not Started | 2010-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | GS16 | Withdrawn | Not Started | G896 | [5 empty] | NRIS |  | 1500 |  | Wind | Scott County | MN | [27 empty] | Withdrawn | 2007-10-23 | 2008-12-01 | 2008-12-01 |  | Northern States Power (Xcel Energy) | Scott County | MN |  | GS16 | Feasibility | NRIS | Scott Junction 345 kV Substation | 1500 | 1500 | Wind | WT Wind Turbine | Not Started | 2010-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H079 | [5 empty] | NRIS |  | 200 |  | Wind | Adams County | IL | [27 empty] | Withdrawn | 2008-06-23 | 2008-12-01 | 2008-12-01 |  | Ameren Illinois | Adams County | IL |  |  | Feasibility | NRIS | 138kV line approx. 4 miles sw of Liberty, IL | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2011-01-01 | 0 | 0 | 0 | 0
|  |  |  | G562 | G562 | Done | In Service | G562 | [5 empty] | ERIS |  | 1 |  | Hydro | Eau Claire County | WI | [27 empty] | Done | 2005-11-01 |  | 2006-09-29 |  | Northern States Power (Xcel Energy) | Eau Claire County | WI | G562 | G562 | SPA - SIS | ERIS | Dells Hydro Plant | 1 | 1 | Hydro | OT Other | In Service | 2007-10-01 | 0 | 0 | 0 | 0
|  |  |  | G563 | G563 | Done | In Service | G563 | [5 empty] | ERIS |  | 3 |  | Hydro | Eau Claire County | WI | [27 empty] | Done | 2005-11-01 |  | 2006-09-29 |  | Northern States Power (Xcel Energy) | Eau Claire County | WI | G563 | G563 | SPA - SIS | ERIS | Dells Hydro Plant | 3 | 3 | Hydro | OT Other | In Service | 2007-12-31 | 0 | 0 | 0 | 0
|  |  |  | G564 | G564 | Done | In Service | G564 | [5 empty] | ERIS |  | 3 |  | Hydro | Eau Claire County | WI | [27 empty] | Done | 2005-11-01 |  | 2006-09-29 |  | Northern States Power (Xcel Energy) | Eau Claire County | WI | G564 | G564 | SPA - SIS | ERIS | Dells Hydro Plant | 3 | 3 | Hydro | OT Other | In Service | 2007-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H089 | [5 empty] | NRIS |  | 200 |  | Wind | Carroll County | IL | [27 empty] | Withdrawn | 2008-07-15 | 2008-12-01 | 2008-12-01 |  | Ameren Illinois | Carroll County | IL |  |  | Feasibility | NRIS | 161 kVline approx. 9 miles south of Savanna | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | G566 | G566 | Done | In Service | G566 | [5 empty] | NRIS |  | 3 |  | Wind | Missaukee County | MI | [27 empty] | Done | 2005-11-07 |  | 2007-04-09 |  | Michigan Electric Transmission Company, LLC | Missaukee County | MI | G566 | G566 | Network Upgrade | NRIS | Cadillac - Leroy 69 kV | 3 | 3 | Wind | WT Wind Turbine | In Service | 2011-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G566d | [5 empty] | NRIS |  | 18 |  | Wind | Missaukee County | MI | [27 empty] | Done | 2006-10-19 |  | 2007-04-09 |  | Michigan Electric Transmission Company, LLC | Missaukee County | MI |  |  | SPA - SIS | NRIS | Cadillac - Leroy 69 kV | 18 | 18 | Wind | WT Wind Turbine | In Service | 2008-08-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G754 | [5 empty] | NRIS |  | 50 |  | Wind | Lucas County | OH | [27 empty] | Withdrawn | 2007-02-28 | 2008-12-08 | 2008-12-08 |  | FirstEnergy Solutions Corp. | Lucas County | OH |  |  | Network Upgrade | NRIS | 138 kV transmission line that serves City of Toledo pump station | 50 | 50 | Wind | WT Wind Turbine | Withdrawn | 2008-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G758 | [5 empty] | NRIS |  | 550 |  | Coal | Lake County | IN | [27 empty] | Withdrawn | 2007-03-07 | 2008-12-08 | 2008-12-08 |  | Northern Indiana Public Service Company | Lake County | IN |  |  | Feasibility | NRIS | #1-Marktown 138 kV Sub or #2-Sheffield 345 kV sub | 550 | 550 | Coal |  | Withdrawn | 2009-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Withdrawn | G569 | [5 empty] | NRIS |  | 200 |  | Wind | Mercer County | IL | [27 empty] | Done | 2005-11-11 |  | 2010-01-08 | 2010-12-31 | Ameren Illinois | Mercer County | IL |  |  | SPA - SIS | NRIS | Galesburg Substation (Knox County) | 200 | 200 | Wind | WT Wind Turbine | Withdrawn | 2007-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | CS5 | Withdrawn | Not Started | G630 | [5 empty] | NRIS |  | 21 |  | Wind | Big Stone County | MN | [27 empty] | Withdrawn | 2006-05-05 | 2008-12-09 | 2008-12-09 |  | Otter Tail Power Company | Big Stone County | MN |  | CS5 | SPA - SIS | NRIS | OTP Artichoke 41.6 kV Substation | 21 | 21 | Wind | WT Wind Turbine | Not Started | 2007-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G755 | [5 empty] | NRIS |  | 50 |  | Wind | Osceola County | MI | [27 empty] | Withdrawn | 2007-02-28 | 2008-12-10 | 2008-12-10 |  | Michigan Electric Transmission Company, LLC | Osceola County | MI |  |  | Feasibility | NRIS | WPSC LeRoy - Cadillac 69 kV | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2009-10-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | CS5 | Done | In Service | G573 | [5 empty] | NRIS |  | 80 |  | Wind | Franklin County | IA | [27 empty] | Done | 2005-12-09 |  | 2012-05-18 |  | ITC Midwest | Franklin County | IA |  | CS5 | DPP - SIS | NRIS | Franklin 161 kV Substation | 80 | 80 | Wind | WT Wind Turbine | In Service |  | 0 | 0 | 0 | 0
|  |  |  | 0 | CS5 | Done | In Service | G574 | [5 empty] | NRIS |  | 80 |  | Wind | Franklin County | IA | [27 empty] | Done | 2005-12-09 |  | 2012-05-18 |  | ITC Midwest | Franklin County | IA |  | CS5 | DPP - SIS | NRIS | Franklin 161 kV Substation | 80 | 80 | Wind | WT Wind Turbine | In Service | 2007-10-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | CS5 | Done | In Service | G575 | [5 empty] | NRIS |  | 40 |  | Wind | Franklin County | IA | [27 empty] | Done | 2005-12-09 |  | 2012-05-18 |  | ITC Midwest | Franklin County | IA |  | CS5 | DPP - SIS | NRIS | Franklin 161 kV Substation | 40 | 40 | Wind | WT Wind Turbine | In Service | 2006-10-01 | 0 | 0 | 0 | 0
|  |  |  | G901 | G901 | Withdrawn | Not Started | G901 | [5 empty] | NRIS |  | 600 |  | Wind | Winnebago County | IL | [27 empty] | Withdrawn | 2007-10-23 | 2008-12-23 | 2008-12-23 |  | American Transmission Co. LLC | Winnebago County | IL | G901 | G901 | SPA - SIS | NRIS | Paddtown 345 kV Substation | 600 | 600 | Wind | WT Wind Turbine | Not Started | 2010-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G577 | [5 empty] | NRIS |  | 50 |  | Coal | Clinton County | IA | [27 empty] | Done | 2005-12-19 |  | 2006-12-11 |  | ITC Midwest | Clinton County | IA |  |  | SPA - SIS | NRIS | ITC Midwest Liberty Avenue 69 kV Substation | 50 | 50 | Coal | Combined Cycle | In Service | 2007-09-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H036 | [5 empty] | NRIS |  | 30 |  | Wind | Columbia County | WI | [27 empty] | Withdrawn | 2008-05-27 | 2008-12-23 | 2008-12-23 |  | American Transmission Co. LLC | Columbia County | WI |  |  | Feasibility | NRIS | Friesland Substation 138kV bus | 30 | 30 | Wind | WT Wind Turbine | Not Started | 2011-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G579 | [5 empty] | NRIS |  | 50 |  | Coal | Jefferson County | OH | [27 empty] | Done | 2005-12-23 |  | 2007-06-21 | 2010-03-27 | FirstEnergy Solutions Corp. | Jefferson County | OH |  |  | Feasibility | NRIS | WH Sammis Unit 6 | 50 | 50 | Coal | Combined Cycle | In Service | 2006-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G580 | [5 empty] | NRIS |  | 50 |  | Coal | Jefferson County | OH | [27 empty] | Done | 2005-12-23 |  | 2007-06-21 | 2010-04-04 | FirstEnergy Solutions Corp. | Jefferson County | OH |  |  | Feasibility | NRIS | WH Sammis Plant Unit 7 | 20 | 50 | Coal | Combined Cycle | In Service | 2006-09-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G992 | [5 empty] | NRIS |  | 0 |  | Coal | Jasper County | IL | [27 empty] | Withdrawn | 2008-03-26 | 2008-12-31 | 2008-12-31 |  | Ameren Illinois | Jasper County | IL |  |  |  | NRIS | AEG Newton Plant 345kV | 0 | 0 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | Not Started | 2008-04-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | CS5 | Withdrawn | Not Started | G589 | [5 empty] | NRIS |  | 750 |  | Coal | Black Hawk County | IA | [27 empty] | Withdrawn | 2006-01-12 | 2009-01-05 | 2009-01-05 |  | ITC Midwest | Black Hawk County | IA |  | CS5 | SPA - SIS | NRIS | Hazelton 345 kV Substation | 750 | 750 | Coal |  | Not Started | 2006-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G710 | [5 empty] | ERIS |  | 10 |  | Waste Heat Recovery | McIntosh County | ND | [27 empty] | Withdrawn | 2006-12-08 | 2009-01-05 | 2009-01-05 |  | -- No Company -- | McIntosh County | ND |  |  | SPA - SIS | ERIS | Near Wishek Sub | 10 | 10 | Waste Heat Recovery |  | Withdrawn | 2010-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H060 | [5 empty] | NRIS |  | 270 |  | Wind | Jackson County | MN | [27 empty] | Withdrawn | 2008-06-16 | 2009-01-20 | 2009-01-20 |  | Missouri River Energy Services (MRES) | Jackson County | MN |  |  | SPA - SIS | NRIS | Jackson - Minowa 161 kV | 270 | 270 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G683 | [5 empty] | NRIS |  | 22 |  | Biomass | Hennepin County | MN | [27 empty] | Withdrawn | 2006-09-19 | 2009-02-06 | 2009-02-06 |  | Northern States Power (Xcel Energy) | Hennepin County | MN |  |  | Feasibility | NRIS | near Southtown Substation (13.8 kV) | 22 | 22 | Biomass |  | Not Started | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | CS5 | Done | In Service | G586 | [5 empty] | NRIS |  | 30 |  | Wind | Lincoln County | MN | [27 empty] | Done | 2005-12-30 |  | 2008-12-09 | 2009-12-31 | Northern States Power (Xcel Energy) | Lincoln County | MN |  | CS5 | DPP - SIS | NRIS | Xcel New Yankee Sub 34.5 kV | 30 | 30 | Wind | WT Wind Turbine | In Service | 2007-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | CS5 | Done | Withdrawn | G587 | [5 empty] | NRIS |  | 20 |  | Wind | Sibley County | MN | [27 empty] | Done | 2005-12-30 | 2017-03-13 | 2009-06-24 | 2014-06-01 | Northern States Power (Xcel Energy) | Sibley County | MN |  | CS5 | DPP - SIS | NRIS | 69 kV to Winthrop Sub | 20 | 20 | Wind | WT Wind Turbine | Withdrawn | 2010-01-01 | 0 | 0 | 0 | 0
|  |  |  | G588 | G588 | Done | In Service | G588 | [5 empty] | ERIS |  | 59.7 |  | Gas | Wood County | WI | [27 empty] | Done | 2006-01-06 |  | 2007-04-04 |  | American Transmission Co. LLC | Wood County | WI | G588 | G588 | Network Upgrade | ERIS | Hume - Arpin 115kV | 59.7 | 59.7 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2007-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G660 | [5 empty] | NRIS |  | 50 |  | Wind | St. Louis County | MN | [27 empty] | Withdrawn | 2006-07-17 | 2009-02-09 | 2009-02-09 |  | Minnesota Power (Allete, Inc.) | St. Louis County | MN |  |  | Feasibility | NRIS | Minntac 115 kV Substation | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2008-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Withdrawn | G590 | [5 empty] | NRIS |  | 98 |  | Wind | Calumet County | WI | [27 empty] | Done | 2006-01-23 |  | 2008-07-18 |  | Wisconsin Public Service Corporation | Calumet County | WI |  |  | Network Upgrade | NRIS | Tecumseh Road 138 kV Subsation | 98 | 98 | Wind | WT Wind Turbine | Withdrawn | 2007-08-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G950 | [5 empty] | NRIS |  | 25 |  | Biomass | St. Louis County | MN | [27 empty] | Withdrawn | 2008-01-16 | 2009-02-09 | 2009-02-09 |  | Minnesota Power (Allete, Inc.) | St. Louis County | MN |  |  | Feasibility | NRIS | Existing substation at the Laskin Site | 25 | 25 | Biomass |  | Not Started | 2009-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G953 | [5 empty] | NRIS |  | 50 |  | Wind | Grant County | WI | [27 empty] | Withdrawn | 2008-01-21 | 2009-02-12 | 2009-02-12 |  | American Transmission Co. LLC | Grant County | WI |  |  | SPA - SIS | NRIS | Platteville - Cuba City 69kV | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G954 | [5 empty] | NRIS |  | 50 |  | Wind | Grant County | WI | [27 empty] | Withdrawn | 2008-01-21 | 2009-02-12 | 2009-02-12 |  | American Transmission Co. LLC | Grant County | WI |  |  | SPA - SIS | NRIS | Platteville - Cuba City 69kV | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2010-10-01 | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | CS5 | Done | In Service | G595 | [5 empty] | ERIS |  | 150 |  | Wind | Hancock County | IA | [27 empty] | Done | 2006-02-13 |  | 2008-04-25 |  | ITC Midwest | Hancock County | IA | Pre-Transition SIS | CS5 | DPP - SIS | ERIS | Lime Creek 161 kV Substation | 150 | 150 | Wind | WT Wind Turbine | In Service | 2007-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G955 | [5 empty] | NRIS |  | 99 |  | Wind | Rock County | WI | [27 empty] | Withdrawn | 2008-01-21 | 2009-02-12 | 2009-02-12 |  | American Transmission Co. LLC | Rock County | WI |  |  | Feasibility | NRIS | Colley Rd - Brick Church 138kV | 99 | 99 | Wind | WT Wind Turbine | Not Started | 2009-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G956 | [5 empty] | NRIS |  | 50 |  | Wind | Walworth County | WI | [27 empty] | Withdrawn | 2008-01-21 | 2009-02-12 | 2009-02-12 |  | American Transmission Co. LLC | Walworth County | WI |  |  | Feasibility | NRIS | Scot Forge - Brick Church 69kV | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | Quincy Area | Done | Withdrawn | G598 | [5 empty] | NRIS |  | 144 |  | Wind | Adams County | IL | [27 empty] | Done | 2006-02-15 |  | 2011-04-01 | 2014-12-31 | Ameren Illinois | Adams County | IL |  | Quincy Area | Network Upgrade | NRIS | 120 kV sub at E. Quincy-Clayton-Meredosia 115-138 kV line | 144 | 144 | Wind | WT Wind Turbine | Withdrawn | 2006-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G766 | [5 empty] | NRIS |  | 300 |  | Wind | Hillsdale County | MI | [27 empty] | Withdrawn | 2007-03-19 | 2009-02-18 | 2009-02-18 |  | Michigan Electric Transmission Company, LLC | Hillsdale County | MI |  |  | Feasibility | NRIS | Moore - Dowling 138 kV | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2011-02-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G750 | [5 empty] | NRIS |  | 200 |  | Wind | Marquette County | MI | [27 empty] | Withdrawn | 2007-02-27 | 2009-03-02 | 2009-03-02 |  | Wisconsin Electric Power Company | Marquette County | MI |  |  | SPA - SIS | NRIS | Presque Isle - National 138 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2009-10-01 | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | CS5 | Done | In Service | G602 | [5 empty] | NRIS |  | 32 |  | Wind | Nobles County | MN | [27 empty] | Done | 2006-02-23 |  | 2012-05-08 | 2012-10-31 | Northern States Power (Xcel Energy) | Nobles County | MN | Pre-Transition SIS | CS5 | DPP - SIS | NRIS | Nobles County 115 kV Substation | 32 | 32 | Wind | WT Wind Turbine | In Service | 2007-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G720 | [5 empty] | NRIS |  | 600 |  | Coal | Marshall County | IA | [27 empty] | Withdrawn | 2006-12-13 | 2009-03-05 | 2009-03-05 |  | ITC Midwest | Marshall County | IA |  |  | SPA - SIS | NRIS | Sutherland Generating Station | 600 | 600 | Coal |  | Withdrawn | 2012-03-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | CS5 | Done | In Service | G604 | [5 empty] | NRIS |  | 44 |  | Wind | Steele County | MN | [27 empty] | Done | 2006-02-27 |  | 2009-06-18 | 2010-10-15 | ITC Midwest | Steele County | MN |  | CS5 | DPP - SIS | NRIS | Owatonna - County Line 69 kV | 44 | 44 | Wind | WT Wind Turbine | In Service | 2007-07-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G869 | [5 empty] | NRIS |  | 200 |  | Wind | Allamakee County | IA | [27 empty] | Withdrawn | 2007-10-01 | 2009-03-05 | 2009-03-05 |  | ITC Midwest | Allamakee County | IA |  |  | SPA - SIS | NRIS | ITC Midwest Decorah - Lansing 161 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2009-12-01 | 0 | 0 | 0 | 0
|  |  |  | G606 | G606 | Done | In Service | G606 | [5 empty] | NRIS |  | 30 |  | Wind | Benton County | IN | [27 empty] | Done | 2006-02-28 |  | 2007-11-01 |  | Northern Indiana Public Service Company | Benton County | IN | G606 | G606 | SPA - SIS | NRIS | Benton County Wind Farm POI | 30 | 30 | Wind | WT Wind Turbine | In Service | 2008-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G835 | [5 empty] | NRIS |  | 200 |  | Wind | Clinton County | IN | [27 empty] | Withdrawn | 2007-08-06 | 2009-03-06 | 2009-03-06 |  | Duke Energy Corporation | Clinton County | IN |  |  | SPA - SIS | NRIS | Wabash River - Kokomo 230 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2011-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G836 | [5 empty] | NRIS |  | 200 |  | Wind | Clinton County | IN | [27 empty] | Withdrawn | 2007-08-06 | 2009-03-06 | 2009-03-06 |  | Duke Energy Corporation | Clinton County | IN |  |  | SPA - SIS | NRIS | Wabash River - Kokomo 230 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2009-07-01 | 0 | 0 | 0 | 0
|  |  |  | G609 | G609 | Done | In Service | G609 | [5 empty] | ERIS |  | 6 |  | Hydro | Price County | WI | [27 empty] | Done | 2006-03-03 |  | 2007-01-25 |  | Northern States Power (Xcel Energy) | Price County | WI | G609 | G609 | Network Upgrade | ERIS | Flambolt Hydro Park Falls plant | 6 | 6 | Hydro | OT Other | In Service | 2008-10-25 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Withdrawn | G611 | [5 empty] | NRIS |  | 99 |  | Wind | Calumet County | WI | [27 empty] | Done | 2006-03-15 |  | 2008-09-11 | 2011-10-05 | Wisconsin Electric Power Company | Calumet County | WI |  |  | Network Upgrade | NRIS | Forest Junction - Elkhart Lake 138kV | 99 | 99 | Wind | WT Wind Turbine | Withdrawn | 2006-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | CS5 | Done | In Service | G612 | [5 empty] | ERIS |  | 150 |  | Wind | Story County | IA | [27 empty] | Done | 2006-03-20 |  | 2008-07-09 |  | ITC Midwest | Story County | IA |  | CS5 | DPP - SIS | ERIS | ITC Midwest Fernald 115 kV Substation | 150 | 150 | Wind | WT Wind Turbine | In Service | 2007-05-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G940 | [5 empty] | NRIS |  | 105 |  | Gas | Gibson County | IN | [27 empty] | Withdrawn | 2007-12-26 | 2009-03-06 | 2009-03-06 |  | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Gibson County | IN |  |  | Feasibility | NRIS | Near Intersection of County Roads 550E and 450N | 105 | 105 | Gas |  | Not Started | 2008-12-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G744 | [5 empty] | NRIS |  | 150 |  | Wind | Schuyler County | MO | [27 empty] | Withdrawn | 2007-02-20 | 2009-03-17 | 2009-03-17 |  | Ameren Missouri | Schuyler County | MO |  |  | SPA - SIS | NRIS | Adair - Appanoose 161kV | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2009-06-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G883 | [5 empty] | NRIS |  | 1500 |  | Wind | Olmsted County | MN | [27 empty] | Withdrawn | 2007-10-11 | 2009-03-31 | 2009-03-31 |  | Northern States Power (Xcel Energy) | Olmsted County | MN |  |  | SPA - SIS | NRIS | Hampton Corner 345 kV Substation | 1500 | 1500 | Wind | WT Wind Turbine | Not Started | 2011-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G724 | [5 empty] | NRIS |  | 99 |  | Wind | Dane County | WI | [27 empty] | Withdrawn | 2007-01-08 | 2009-04-08 | 2009-04-08 |  | Madison Gas and Electric Company | Dane County | WI |  |  | Network Upgrade | NRIS | North Madison - West Middleton 138 kV | 99 | 99 | Wind | WT Wind Turbine | Not Started | 2008-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G793 | [5 empty] | NRIS |  | 100 |  | Wind | Rock County | WI | [27 empty] | Withdrawn | 2007-04-30 | 2009-04-08 | 2009-04-08 |  | American Transmission Co. LLC | Rock County | WI |  |  | Network Upgrade | NRIS | Rock River - SW Delavan 138 kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2007-12-21 | 0 | 0 | 0 | 0
|  |  |  | 0 | CS5 | Done | In Service | G619 | [5 empty] | NRIS |  | 50 |  | Wind | Otter Tail County | MN | [27 empty] | Done | 2006-04-14 |  | 2009-07-08 | 2012-12-01 | Otter Tail Power Company | Otter Tail County | MN |  | CS5 | DPP - SIS | NRIS | GRE Tamarac 41 kV Substation | 50 | 50 | Wind | WT Wind Turbine | In Service | 2008-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J004 | [5 empty] | NRIS |  | 200 |  | Wind | Montgomery County | IN | [27 empty] | Withdrawn | 2008-10-22 | 2009-04-19 | 2009-04-19 |  | Duke Energy Corporation | Montgomery County | IN |  |  | Feasibility | NRIS | 230kV line, approx 3 miles south of Whitesville | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2011-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | CS5 | Done | Under Construction | G621 | [5 empty] | NRIS |  | 20 |  | Wind | Pipestone County | MN | [27 empty] | Done | 2006-04-18 |  | 2012-08-10 | 2018-12-01 | Northern States Power (Xcel Energy) | Pipestone County | MN |  | CS5 | DPP - SIS | NRIS | Golf - Wookstock 34.5 kV | 20 | 20 | Wind | WT Wind Turbine | Under Construction | 2009-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G747 | [5 empty] | NRIS |  | 100 |  | Wind | Rock County | WI | [27 empty] | Withdrawn | 2007-02-21 | 2009-04-27 | 2009-04-27 |  | American Transmission Co. LLC | Rock County | WI |  |  | Network Upgrade | NRIS | Town Line Rd - North Monroe 138kV | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | CIGS II | Withdrawn | Not Started | G544 | [5 empty] | NRIS |  | 200 |  | Wind | Henry County | IL | [27 empty] | Withdrawn | 2005-09-06 | 2009-05-04 | 2009-05-04 |  | Ameren Illinois | Henry County | IL |  | CIGS II | Network Upgrade | NRIS | East Kewanee 138 kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2006-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G687 | [5 empty] | NRIS |  | 750 |  | Coal | Midland County | MI | [27 empty] | Withdrawn | 2006-10-11 | 2009-05-04 | 2009-05-04 |  | Michigan Electric Transmission Company, LLC | Midland County | MI |  |  | Network Upgrade | NRIS | Tittabawassee 345 kV Substation | 750 | 750 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | Not Started | 2008-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | CS5 | Done | Withdrawn | G626 | [5 empty] | NRIS |  | 32 |  | Wind | Brown County | MN | [27 empty] | Done | 2006-04-25 | 2012-10-09 | 2008-10-03 | 2009-08-01 | Northern States Power (Xcel Energy) | Brown County | MN |  | CS5 | DPP - SIS | NRIS | Morgan - Sleepy Eye 69 kV | 32 | 32 | Wind | WT Wind Turbine | Withdrawn | 2007-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H004 | [5 empty] | NRIS |  | 860 |  | Gas | Eau Claire County | WI | [27 empty] | Withdrawn | 2008-04-14 | 2009-05-14 | 2009-05-14 |  | Northern States Power (Xcel Energy) | Eau Claire County | WI |  |  | SPA - SIS | NRIS | Eau Claire 345 kV Substation | 860 | 860 | Gas | CC(2), GT(1) | Not Started | 2009-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G854 | [5 empty] | NRIS |  | 150 |  | Wind | Mason County | MI | [27 empty] | Withdrawn | 2007-09-10 | 2009-05-19 | 2009-05-19 |  | Michigan Electric Transmission Company, LLC | Mason County | MI |  |  | Feasibility | NRIS | Pere Marquette - Stronach 138kV | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2010-08-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G923 | [5 empty] | NRIS |  | 200 |  | Wind | Tipton County | IN | [27 empty] | Withdrawn | 2007-12-03 | 2009-05-19 | 2009-05-19 |  | Duke Energy Corporation | Tipton County | IN |  |  | SPA - SIS | NRIS | Kokomo - Nobelsville 230 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2009-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G884 | [5 empty] | NRIS |  | 1500 |  | Wind | Roberts County | SD | [27 empty] | Withdrawn | 2007-10-11 | 2009-05-20 | 2009-05-20 |  | Northern States Power (Xcel Energy) | Roberts County | SD |  |  | SPA - SIS | NRIS | Monticello Substation | 1500 | 1500 | Wind | WT Wind Turbine | Not Started | 2011-04-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J010 | [5 empty] | NRIS |  | 23 |  | Coal | Oakland County | MI | [27 empty] | Withdrawn | 2009-01-05 | 2009-05-20 | 2009-05-20 |  | ITC Transmission | Oakland County | MI |  |  | Feasibility | NRIS | Montcalm Substation | 19 | 23 | Coal |  | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G656 | [5 empty] | NRIS |  | 500 |  | Wind | Benton County | IN | [27 empty] | Withdrawn | 2006-07-10 | 2009-05-26 | 2009-05-26 |  | Duke Energy Corporation | Benton County | IN |  |  | SPA - SIS | NRIS | DEM Dequine - Westwood 345 kV | 500 | 500 | Wind | WT Wind Turbine | Not Started | 2006-07-04 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G666 | [5 empty] | NRIS |  | 250 |  | Wind | Benton County | IN | [27 empty] | Withdrawn | 2006-08-09 | 2009-05-26 | 2009-05-26 |  | Duke Energy Corporation | Benton County | IN |  |  | SPA - SIS | NRIS | Dequine to Westwood 345 kV | 250 | 250 | Wind | WT Wind Turbine | Not Started | 2008-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H098 | [5 empty] | NRIS |  | 200 |  | Wind | Jackson County | IA | [27 empty] | Withdrawn | 2008-08-13 | 2009-06-03 | 2009-06-03 |  | ITC Midwest | Jackson County | IA |  |  | SPA - SIS | NRIS | ITC Midwest Dubuque - Quad Cities 345kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2012-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G648 | [5 empty] | NRIS |  | 101 |  | Wind | Edgar County | IL | [27 empty] | Withdrawn | 2006-06-12 | 2009-06-05 | 2009-06-05 |  | Ameren Illinois | Edgar County | IL |  |  | SPA - SIS | NRIS | Ameren Kansas Substation | 101 | 101 | Wind | WT Wind Turbine | Not Started | 2006-06-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G649 | [5 empty] | NRIS |  | 300 |  | Wind | Edgar County | IL | [27 empty] | Withdrawn | 2006-06-12 | 2009-06-05 | 2009-06-05 |  | Ameren Illinois | Edgar County | IL |  |  | SPA - SIS | NRIS | Ameren Kansas Substation | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2008-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J015 | [5 empty] | NRIS |  | 100 |  | Wind | Goodhue County | MN | [27 empty] | Withdrawn | 2009-01-06 | 2009-06-23 | 2009-06-23 |  | Northern States Power (Xcel Energy) | Goodhue County | MN |  |  | Feasibility | NRIS | Xcel Energy Zumbrota 69 kV substation | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2012-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J016 | [5 empty] | NRIS |  | 200 |  | Wind | Steele County | MN | [27 empty] | Withdrawn | 2009-01-06 | 2009-06-23 | 2009-06-23 |  | SMMPA | Steele County | MN |  |  | Feasibility | NRIS | SMMPA W. Faribault - Owatonna 115kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2012-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J017 | [5 empty] | NRIS |  | 200 |  | Wind | Stearns County | MN | [27 empty] | Withdrawn | 2009-01-06 | 2009-06-23 | 2009-06-23 |  | Northern States Power (Xcel Energy) | Stearns County | MN |  |  | Feasibility | NRIS | Xcel Wakefield 115 kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2012-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J018 | [5 empty] | NRIS |  | 100 |  | Wind | Bowman County | ND | [27 empty] | Withdrawn | 2009-01-06 | 2009-06-23 | 2009-06-23 |  | Montana-Dakota Utilities Company | Bowman County | ND |  |  | Feasibility | NRIS | MDU Rhame - Bowman 230 kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2012-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G641 | [5 empty] | ERIS |  | 18 |  | Diesel | Cook County | MN | [27 empty] | Done | 2006-05-24 |  | 2008-10-01 |  | Great River Energy | Cook County | MN |  |  | SPA - SIS | ERIS | Colville Sub | 18 | 18 | Diesel | IC Internal Combustion (diesel, piston) Engine | In Service | 2008-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J019 | [5 empty] | NRIS |  | 100 |  | Wind | Douglas County | MN | [27 empty] | Withdrawn | 2009-01-06 | 2009-06-23 | 2009-06-23 |  | Otter Tail Power Company | Douglas County | MN |  |  | Feasibility | NRIS | OTP 115 kV Douglas Co. substation | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2012-12-31 | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | CS5 | Withdrawn | Not Started | G438 | [5 empty] | NRIS |  | 20 |  | Wind | Marshall County | SD | [27 empty] | Withdrawn | 2004-07-26 | 2009-07-07 | 2009-07-07 |  | Otter Tail Power Company | Marshall County | SD | Pre-Transition SIS | CS5 | SPA - SIS | NRIS | 41.6 kV line served out of Browns Valley 230 kV source | 20 | 20 | Wind | WT Wind Turbine | Not Started | 2007-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G937 | [5 empty] | NRIS |  | 200 |  | Wind | Delta County | MI | [27 empty] | Withdrawn | 2007-12-20 | 2009-07-07 | 2009-07-07 |  | Wisconsin Electric Power Company | Delta County | MI |  |  | Feasibility | NRIS | Indian Lake - Perkins 138kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2010-10-01 | 0 | 0 | 0 | 0
|  |  |  | G645 | G645 | Done | In Service | G645 | [5 empty] | NRIS |  | 50 |  | Coal | Stutsman County | ND | [27 empty] | Done | 2006-05-26 |  | 2008-06-04 | 2010-01-01 | Otter Tail Power Company | Stutsman County | ND | G645 | G645 | Network Upgrade | NRIS | Ladish 115 kV Substation | 50 | 50 | Coal | IGCC | In Service | 2008-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G646 | [5 empty] | NRIS |  | 30 |  | Coal | Pike County | IN | [27 empty] | Done | 2006-05-31 |  | 2006-11-20 |  | Indianapolis Power & Light Company | Pike County | IN |  |  | Feasibility | NRIS | Petersburg Generation Plant | 30 | 30 | Coal | Combined Cycle | In Service | 2008-03-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G918 | [5 empty] | NRIS |  | 120 |  | Wind | Gratiot County | MI | [27 empty] | Withdrawn | 2009-05-15 | 2009-07-09 | 2009-07-09 |  | Michigan Electric Transmission Company, LLC | Gratiot County | MI |  |  | Feasibility | NRIS | Begole - Tittabawassee 138 kV | 120 | 120 | Wind | WT Wind Turbine | Not Started | 2010-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G694 | [5 empty] | NRIS |  | 62 |  | Wind | Knox County | IL | [27 empty] | Withdrawn | 2006-10-23 | 2009-07-16 | 2009-07-16 |  | Ameren Illinois | Knox County | IL |  |  | SPA - SIS | NRIS | Galesburg - Kewaunee 138 kV | 62 | 62 | Wind | WT Wind Turbine | Not Started | 2007-10-01 | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | 0 | Withdrawn | Not Started | G489 | [5 empty] | NRIS |  | 20 |  | Wind | Lyon County | MN | [27 empty] | Withdrawn | 2005-01-19 | 2009-08-04 | 2009-08-04 |  | Northern States Power (Xcel Energy) | Lyon County | MN | Pre-Transition SIS |  | Network Upgrade | NRIS | Lake Yankton - Lyon County 115kV | 20 | 20 | Wind | WT Wind Turbine | Not Started | 2005-09-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J047 | [5 empty] | NRIS |  | 32.5 |  | Wood | Perry County | MO | [27 empty] | Withdrawn | 2009-05-18 | 2009-08-04 | 2009-08-04 |  | Ameren Missouri | Perry County | MO |  |  |  | NRIS | Citizens Electric Coop 138 kV 1/2 mile east of Seminary Sub | 32 | 32.5 | Wood |  | Not Started | 2012-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G924 | [5 empty] | NRIS |  | 300 |  | Wind | Rice County | MN | [27 empty] | Withdrawn | 2007-12-03 | 2009-08-20 | 2009-08-20 |  | Northern States Power (Xcel Energy) | Rice County | MN |  |  | SPA - SIS | NRIS | Faribault Energy Park | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2009-11-01 | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | 0 | Done | Withdrawn | G652 | [5 empty] | NRIS |  | 48 |  | Wind | Erie County | OH | [27 empty] | Done | 2006-07-03 |  | 2010-06-15 | 2012-11-16 | FirstEnergy Solutions Corp. | Erie County | OH | Pre-Transition SIS |  | Network Upgrade | NRIS | Bellevue - Castalia 69 kV | 48 | 48 | Wind | WT Wind Turbine | Withdrawn | 2008-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H005 | [5 empty] | ERIS |  | 300 |  | Wind | Martin County | MN | [27 empty] | Withdrawn | 2008-04-15 | 2009-08-20 | 2009-08-20 |  | Northern States Power (Xcel Energy) | Martin County | MN |  |  | SPA - SIS | ERIS | Xel Lakefield Gen Substation | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2010-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G882 | [5 empty] | NRIS |  | 1500 |  | Wind | Dodge County | MN | [27 empty] | Withdrawn | 2007-10-11 | 2009-09-08 | 2009-09-08 |  | Northern States Power (Xcel Energy) | Dodge County | MN |  |  | SPA - SIS | NRIS | N. Rochester 345 kV Substation | 1500 | 1500 | Wind | WT Wind Turbine | Not Started | 2010-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J055 | [5 empty] | NRIS |  | 40 |  | Wind | Deuel County | SD | [27 empty] | Withdrawn | 2009-07-27 | 2009-10-01 | 2009-10-01 |  | Otter Tail Power Company | Deuel County | SD |  |  | Feasibility | NRIS | Brookings County Substation | 40 | 40 | Wind | WT Wind Turbine | Not Started | 2011-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J049 | [5 empty] | NRIS |  | 16 |  | Wind | Hancock County | IA | [27 empty] | Withdrawn | 2009-06-19 | 2009-10-28 | 2009-10-28 |  | ITC Midwest | Hancock County | IA |  |  | Feasibility | NRIS | Lime Creek Substation | 16 | 16 | Wind | WT Wind Turbine | Not Started | 2011-07-01 | 0 | 0 | 0 | 0
|  |  |  | G392 | G392 | Withdrawn | Not Started | G392 | [5 empty] | NRIS |  | 600 |  | Coal | Grant County | SD | [27 empty] | Withdrawn | 2004-02-03 | 2009-11-02 | 2009-11-02 |  | Otter Tail Power Company | Grant County | SD | G392 | G392 | Network Upgrade | NRIS | Bigstone 230kV Substation | 600 | 600 | Coal |  | Not Started | 2007-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H034 | [5 empty] | NRIS |  | 36 |  | Biomass | Kalkaska County | MI | [27 empty] | Withdrawn | 2009-07-09 | 2009-11-10 | 2009-11-10 |  | Michigan Electric Transmission Company, LLC | Kalkaska County | MI |  |  | Feasibility | NRIS | Clearwater 138 kV Substation | 36 | 36 | Biomass | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | Not Started | 2011-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | R47 | [5 empty] | 0 |  | 100 |  | Wind | Cherokee County | IA | [27 empty] | Withdrawn | 2008-01-15 | 2009-11-11 | 2009-11-11 |  | MidAmerican Energy Company | Cherokee County | IA |  |  | DPP - SIS |  | Lakefield - Raun 345 kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2009-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | R48 | [5 empty] | 0 |  | 100 |  | Wind | Cherokee County | IA | [27 empty] | Withdrawn | 2008-01-15 | 2009-11-11 | 2009-11-11 |  | MidAmerican Energy Company | Cherokee County | IA |  |  | DPP - SIS |  | Lakefield - Raun 345 kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2009-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J037 | [5 empty] | ERIS |  | 64.5 |  | Wind | Allegan County | MI | [27 empty] | Withdrawn | 2009-03-16 | 2009-11-13 | 2009-11-13 |  | Michigan Electric Transmission Company, LLC | Allegan County | MI |  |  | Feasibility | ERIS | Black River - Scott Lake 138 kV | 64.5 | 64.5 | Wind | WT Wind Turbine | Not Started | 2010-11-30 | 0 | 0 | 0 | 0
|  |  |  | G691 | G691 | Withdrawn | Not Started | G691 | [5 empty] | NRIS |  | 50 |  | Wind | Vernon County | WI | [27 empty] | Withdrawn | 2006-10-16 | 2009-11-17 | 2009-11-17 |  | Northern States Power (Xcel Energy) | Vernon County | WI | G691 | G691 | SPA - SIS | NRIS | Westby - Cashton Tap 69 kV | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2007-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G943 | [5 empty] | NRIS |  | 150 |  | Wind | Kent County | MI | [27 empty] | Withdrawn | 2007-12-26 | 2009-11-17 | 2009-11-17 |  | Michigan Electric Transmission Company, LLC | Kent County | MI |  |  | Feasibility | NRIS | Kenowa 345kV Substation | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2010-05-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | 0 | Done | In Service | G667 | [5 empty] | ERIS |  | 13 |  | Wind | Jackson County | MN | [27 empty] | Done | 2006-08-10 |  | 2011-02-11 | 2016-10-01 | Great River Energy | Jackson County | MN | DPP-2008-NOV |  | Network Upgrade | ERIS | Round Lake Tap 69 kV Substation | 13 | 13 | Wind | WT Wind Turbine | In Service | 2007-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G944 | [5 empty] | NRIS |  | 150 |  | Wind | Kent County | MI | [27 empty] | Withdrawn | 2007-12-26 | 2009-11-17 | 2009-11-17 |  | Michigan Electric Transmission Company, LLC | Kent County | MI |  |  | Feasibility | NRIS | Kenowa 345kV Substation | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2008-01-03 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G977 | [5 empty] | NRIS |  | 101 |  | Wind | Calumet County | WI | [27 empty] | Withdrawn | 2008-03-04 | 2009-11-17 | 2009-11-17 |  | Wisconsin Electric Power Company | Calumet County | WI |  |  | Feasibility | NRIS | Forest Junction 138kV Substation | 101 | 101 | Wind | WT Wind Turbine | Not Started | 2011-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H076 | [5 empty] | NRIS |  | 74 |  | Wind | Allegan County | MI | [27 empty] | Withdrawn | 2008-06-19 | 2009-11-17 | 2009-11-17 |  | ITC Transmission | Allegan County | MI |  |  | Feasibility | NRIS | near Consumers 138 kV sub 20 mi. west of Agrenta sub on 138 kV line | 74 | 74 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J063 | [5 empty] | NRIS |  | 200 |  | Wind | Clearwater County | MN | [27 empty] | Withdrawn | 2009-08-20 | 2009-11-25 | 2009-11-25 |  | Otter Tail Power Company | Clearwater County | MN |  |  | Feasibility | NRIS | Shevlin Jct. Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2013-12-31 | 0 | 0 | 0 | 0
|  |  |  | G674 | G674 | Done | In Service | G674 | [5 empty] | NRIS |  | 80 |  | Coal | Knox County | IN | [27 empty] | Done | 2006-08-31 |  | 2008-07-31 |  | Duke Energy Corporation | Knox County | IN | G674 | G674 | SPA - SIS | NRIS | Wheatland - AMO 345 kV | 80 | 80 | Coal | IGCC | In Service | 2008-04-01 | 0 | 0 | 0 | 0
|  |  |  | G675 | G675 | Done | In Service | G675 | [5 empty] | NRIS |  | 200 |  | Coal | Knox County | IN | [27 empty] | Done | 2006-08-31 |  | 2008-07-31 |  | Duke Energy Corporation | Knox County | IN | G675 | G675 | SPA - SIS | NRIS | Wheatland - AMO 345 kV | 200 | 200 | Coal | IGCC | In Service | 2008-04-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J064 | [5 empty] | NRIS |  | 100 |  | Wind | Beltrami County | MN | [27 empty] | Withdrawn | 2009-08-20 | 2009-11-25 | 2009-11-25 |  | Otter Tail Power Company | Beltrami County | MN |  |  | Feasibility | NRIS | Solway 115 kV Substation | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2011-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J050 | [5 empty] | NRIS |  | 250 |  | Wind | Stark County | ND | [27 empty] | Withdrawn | 2009-06-29 | 2010-01-13 | 2010-01-13 |  | Montana-Dakota Utilities Company | Stark County | ND |  |  | SPA - SIS | NRIS | MDU Dickinson - Beulah 115 kV | 250 | 250 | Wind | WT Wind Turbine | Not Started | 2012-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H087 | [5 empty] | NRIS |  | 300 |  | Wind | Porter County | IN | [27 empty] | Withdrawn | 2008-07-10 | 2010-01-14 | 2010-01-14 |  | Northern Indiana Public Service Company | Porter County | IN |  |  | Feasibility | NRIS | Schafer Gen - Tower Rd 345kV | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2012-12-01 | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | NORDAGS | Withdrawn | Not Started | G607 | [5 empty] | NRIS |  | 25 |  | Coal | Mercer County | ND | [27 empty] | Withdrawn | 2006-03-01 | 2010-01-15 | 2010-01-15 |  | Otter Tail Power Company | Mercer County | ND | Pre-Transition SIS | NORDAGS | Network Upgrade | NRIS | Coyote Station | 25 | 25 | Coal |  | Not Started | 2007-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G597 | [5 empty] | NRIS |  | 606 |  | Coal | Itasca County | MN | [27 empty] | Withdrawn | 2006-02-14 | 2010-01-20 | 2010-01-20 |  | Minnesota Power (Allete, Inc.) | Itasca County | MN |  |  | Optional | NRIS | MP Blackberry 230/115 kV Sub | 606 | 606 | Coal |  | Not Started | 2012-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J024 | [5 empty] | NRIS |  | 201 |  | Wind | Freeborn County | MN | [27 empty] | Withdrawn | 2009-02-05 | 2010-01-27 | 2010-01-27 |  | ITC Midwest | Freeborn County | MN |  |  | SPA - SIS | NRIS | ITC Midwest Hayward substation | 201 | 201 | Wind | WT Wind Turbine | Not Started | 2010-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H090 | [5 empty] | NRIS |  | 60 |  | Wind | Calumet County | WI | [27 empty] | Withdrawn | 2008-07-16 | 2010-01-28 | 2010-01-28 |  | Wisconsin Electric Power Company | Calumet County | WI |  |  | Feasibility | NRIS | Forest Junction - Tecumseh Rd 138 kV | 60 | 60 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | MN | Done | In Service | G685 | [5 empty] | ERIS |  | 20 |  | Wind | Meeker County | MN | [27 empty] | Done | 2006-10-03 |  | 2010-09-16 | 2010-12-31 | Northern States Power (Xcel Energy) | Meeker County | MN | DPP-2008-NOV | MN | Network Upgrade | ERIS | Lake Lillian - Atwater 69 kV | 20 | 20 | Wind | WT Wind Turbine | In Service | 2008-11-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-MAR | Individual | Withdrawn | Not Started | H024 | [5 empty] | NRIS |  | 48 |  | Wind | Columbia County | WI | [27 empty] | Withdrawn | 2008-05-14 | 2010-02-10 | 2010-02-10 |  | American Transmission Co. LLC | Columbia County | WI | DPP-2009-MAR | Individual | Network Upgrade | NRIS | Poynette - Deforest 69kV | 48 | 48 | Wind | WT Wind Turbine | Not Started | 2012-03-03 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H038 | [5 empty] | NRIS |  | 200 |  | Wind | Putnam County | MO | [27 empty] | Withdrawn | 2008-06-03 | 2010-02-19 | 2010-02-19 |  | Ameren Missouri | Putnam County | MO |  |  | Feasibility | NRIS | Approx. 20 miles N of Adair Sbstn on Ameren's 161 kV transm. System in Schuyler Cty, MO | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2010-08-01 | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | 0 | Done | In Service | G689 | [5 empty] | NRIS |  | 560 |  | Coal | Columbiana County | OH | [27 empty] | Done | 2006-10-12 |  | 2010-08-31 | 2013-12-30 | FirstEnergy Solutions Corp. | Columbiana County | OH | Pre-Transition SIS |  | Network Upgrade | NRIS | 345 kV line near Sammis Plant near Wellsville, OH | 560 | 560 | Coal | Combined Cycle | In Service | 2008-10-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J104 | [5 empty] | NRIS |  | 25.62 |  | Wood | Alger County | MI | [27 empty] | Withdrawn | 2009-12-21 | 2010-02-25 | 2010-02-25 |  | American Transmission Co. LLC | Alger County | MI |  |  | Feasibility | NRIS | ATC Munising 69kV Substation | 25.62 | 25.62 | Wood |  | Not Started | 2010-01-11 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G782 | [5 empty] | NRIS |  | 42 |  | Wind | Swift County | MN | [27 empty] | Withdrawn | 2007-04-16 | 2010-02-26 | 2010-02-26 |  | Great River Energy | Swift County | MN |  |  | SPA - SIS | NRIS | GRE Willmar 115 kV Substation | 42 | 42 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H068 | [5 empty] | NRIS |  | 40 |  | Wind | Rice County | MN | [27 empty] | Withdrawn | 2008-06-17 | 2010-03-01 | 2010-03-01 |  | Great River Energy | Rice County | MN |  |  | SPA - SIS | NRIS | French Lake substation Shieldsville Twp | 40 | 40 | Wind | WT Wind Turbine | Not Started | 2010-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J008 | [5 empty] | NRIS |  | 150 |  | Wind | Knox County | IL | [27 empty] | Withdrawn | 2008-10-31 | 2010-03-24 | 2010-03-24 |  | Ameren Illinois | Knox County | IL |  |  | Feasibility | NRIS | Ameren Galesburg Substation | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2010-06-01 | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | G698/G744 | Withdrawn | Not Started | G698 | [5 empty] | NRIS |  | 150 |  | Wind | Putnam County | MO | [27 empty] | Withdrawn | 2006-11-06 | 2010-03-26 | 2010-03-26 |  | Ameren Missouri | Putnam County | MO | Pre-Transition SIS | G698/G744 | Network Upgrade | NRIS | Adair - Appanoose 161kV | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2011-09-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G980 | [5 empty] | ERIS |  | 60 |  | Wind | Hettinger County | ND | [27 empty] | Withdrawn | 2008-03-10 | 2010-03-26 | 2010-03-26 |  | Montana-Dakota Utilities Company | Hettinger County | ND |  |  | SPA - SIS | ERIS | New substation tapped into MDU 115 kV line at N46 36 53/W102 46 12 | 60 | 60 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-JUL | Individual | Withdrawn | Not Started | J039 | [5 empty] | NRIS |  | 50 |  | Biomass | Delta County | MI | [27 empty] | Withdrawn | 2009-03-17 | 2010-03-26 | 2010-03-26 |  | American Transmission Co. LLC | Delta County | MI | DPP-2009-JUL | Individual | DPP - SIS | NRIS | Mead SS - 69kV | 50 | 50 | Biomass |  | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H043 | [5 empty] | NRIS |  | 50 |  | Wind | Martin County | MN | [27 empty] | Withdrawn | 2008-06-12 | 2010-03-29 | 2010-03-29 |  | ITC Midwest | Martin County | MN |  |  | SPA - SIS | NRIS | ITC Midwest Truman 69 kV Substation | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2012-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H053 | [5 empty] | NRIS |  | 50 |  | Wind | Waseca County | MN | [27 empty] | Withdrawn | 2008-06-12 | 2010-03-29 | 2010-03-29 |  | Northern States Power (Xcel Energy) | Waseca County | MN |  |  | SPA - SIS | NRIS | SMMPA 69kV Loon Lake Substation | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H054 | [5 empty] | NRIS |  | 40 |  | Wind | Redwood County | MN | [27 empty] | Withdrawn | 2008-06-12 | 2010-03-29 | 2010-03-29 |  | Northern States Power (Xcel Energy) | Redwood County | MN |  |  | SPA - SIS | NRIS | Xcel Morgan 69 kV Substation | 40 | 40 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J011 | [5 empty] | NRIS |  | 150 |  | Wind | LaPorte County | IN | [27 empty] | Withdrawn | 2009-01-05 | 2010-03-30 | 2010-03-30 |  | Northern Indiana Public Service Company | LaPorte County | IN |  |  | Feasibility | NRIS | NIPSCO Burr Oak - Schahfer 345 kV | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J012 | [5 empty] | NRIS |  | 27 |  | Wood | Crawford County | IN | [27 empty] | Withdrawn | 2009-01-06 | 2010-03-30 | 2010-03-30 |  | Duke Energy Corporation | Crawford County | IN |  |  | Feasibility | NRIS | Crawford Co, NW qtr of Sect 10, Tnsp 2 So, Rng 2 W | 28 | 27 | Wood |  | Not Started | 2007-08-09 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G847 | [5 empty] | NRIS |  | 62 |  | Gas | Audrain County | MO | [27 empty] | Withdrawn | 2007-08-27 | 2010-04-01 | 2010-04-01 |  | Ameren Missouri | Audrain County | MO |  |  | SPA - SIS | NRIS | Spencer Creek 345kV substation | 62 | 62 | Gas | CT Combined-Cycle Combustion ? Turbine Part | Not Started | 2009-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G860 | [5 empty] | NRIS |  | 900 |  | Wind | Burleigh County | ND | [27 empty] | Withdrawn | 2007-09-14 | 2010-04-01 | 2010-04-01 |  | Otter Tail Power Company | Burleigh County | ND |  |  | SPA - SIS | NRIS | Milton Young | 900 | 900 | Wind | WT Wind Turbine | Not Started | 2010-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G706 | [5 empty] | NRIS |  | 99 |  | Wind | Columbia County | WI | [27 empty] | Done | 2006-11-20 |  | 2008-09-18 | 2011-12-31 | American Transmission Co. LLC | Columbia County | WI |  |  | Network Upgrade | NRIS | Hamilton St. - N. Randolph 138 kV | 99 | 99 | Wind | WT Wind Turbine | In Service | 2008-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G552 | [5 empty] | NRIS |  | 50 |  | Wind | Emmet County | IA | [27 empty] | Withdrawn | 2005-09-28 | 2010-04-06 | 2010-04-06 |  | ITC Midwest | Emmet County | IA |  |  | SPA - SIS | NRIS | Maple Hill Substation 69 kV | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2006-06-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-MAR | MI | Withdrawn | Not Started | G774 | [5 empty] | NRIS |  | 70 |  | Wind | Mason County | MI | [27 empty] | Withdrawn | 2007-03-27 | 2010-04-09 | 2010-04-09 |  | Michigan Electric Transmission Company, LLC | Mason County | MI | DPP-2009-MAR | MI | Network Upgrade | NRIS | Pere Marquette - Stronach 138 kV | 70 | 70 | Wind | WT Wind Turbine | Not Started | 2010-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J031 | [5 empty] | NRIS |  | 250 |  | Wind | Stutsman County | ND | [27 empty] | Withdrawn | 2009-03-11 | 2010-04-09 | 2010-04-09 |  | Otter Tail Power Company | Stutsman County | ND |  |  | SPA - SIS | NRIS | OTP Jamestown 345 kV Substation | 250 | 250 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G800 | [5 empty] | NRIS |  | 250 |  | Gas | Itasca County | MN | [27 empty] | Withdrawn | 2007-05-24 | 2010-04-15 | 2010-04-15 |  | Minnesota Power (Allete, Inc.) | Itasca County | MN |  |  | Feasibility | NRIS | MN Steel 230 kV Substation | 250 | 250 | Gas |  | Not Started | 2008-12-31 | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | CS5 | Withdrawn | Not Started | G576 | [5 empty] | ERIS |  | 40 |  | Wind | Rock County | MN | [27 empty] | Withdrawn | 2005-12-12 | 2010-04-20 | 2010-04-20 |  | Great River Energy | Rock County | MN | Pre-Transition SIS | CS5 | Network Upgrade | ERIS | Split Rock - Magnolia 161 kV | 40 | 40 | Wind | WT Wind Turbine | Not Started | 2007-12-31 | 0 | 0 | 0 | 0
|  |  |  | G654 | G654 | Withdrawn | Not Started | G654 | [5 empty] | NRIS |  | 250 |  | Wind | Pike County | IL | [27 empty] | Withdrawn | 2006-07-05 | 2010-05-10 | 2010-05-10 |  | Ameren Illinois | Pike County | IL | G654 | G654 | DPP - SIS | NRIS | Hull 138 kV Substation | 250 | 250 | Wind | WT Wind Turbine | Not Started | 2007-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G727 | [5 empty] | NRIS |  | 100 |  | Wind | Turner County | SD | [27 empty] | Withdrawn | 2007-01-23 | 2010-05-12 | 2010-05-12 |  | Northern States Power (Xcel Energy) | Turner County | SD |  |  | SPA - SIS | NRIS | Grant Substation 115 kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2009-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G878 | [5 empty] | NRIS |  | 150 |  | Wind | Turner County | SD | [27 empty] | Withdrawn | 2007-10-09 | 2010-05-12 | 2010-05-12 |  | Northern States Power (Xcel Energy) | Turner County | SD |  |  | SPA - SIS | NRIS | Xcel Grant 115 kV substation | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2008-03-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-NOV | MI | Withdrawn | Not Started | G872 | [5 empty] | NRIS |  | 875 |  | Coal | Bay County | MI | [27 empty] | Withdrawn | 2007-10-02 | 2010-05-27 | 2010-05-27 |  | Michigan Electric Transmission Company, LLC | Bay County | MI | DPP-2009-NOV | MI | DPP - SIS | NRIS | Hampton 345 kV Substation | 863 | 875 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | Not Started | 2009-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-APR | 0 | Withdrawn | Not Started | J079 | [5 empty] | NRIS |  | 29 |  | Wind | Columbia County | WI | [27 empty] | Withdrawn | 2009-10-05 | 2010-05-27 | 2010-05-27 |  | American Transmission Co. LLC | Columbia County | WI | DPP-2010-APR |  | DPP - SIS | NRIS | substation 138 kV line adjacent to UWGP ethanol plant | 29 | 29 | Wind | WT Wind Turbine | Not Started | 2012-10-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G723 | [5 empty] | ERIS |  | 10 |  | Diesel | Morton County | ND | [27 empty] | Done | 2006-12-27 |  | 2009-05-04 | 2009-06-08 | Montana-Dakota Utilities Company | Morton County | ND |  |  | SPA - SIS | ERIS | Glen Ullin | 10 | 10 | Diesel | IC Internal Combustion (diesel, piston) Engine | In Service | 2008-08-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G661 | [5 empty] | NRIS |  | 726 |  | Coal | Coles County | IL | [27 empty] | Withdrawn | 2006-07-24 | 2010-06-18 | 2010-06-18 |  | Ameren Illinois | Coles County | IL |  |  | Feasibility | NRIS | NE Taylorville 138 kV Substation | 726 | 726 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | Not Started | 2007-11-07 | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | 0 | Done | In Service | G725 | [5 empty] | NRIS |  | 13 |  | Nuclear | Wright County | MN | [27 empty] | Done | 2007-01-17 |  | 2009-10-06 | 2013-12-01 | Northern States Power (Xcel Energy) | Wright County | MN | Pre-Transition SIS |  | SPA - SIS | NRIS | Monticello Nuclear Generating Station | 13 | 13 | Nuclear | ST Steam Turbine (including nuclear, geothermal and solar steam, | In Service | 2008-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G726 | [5 empty] | NRIS |  | 30 |  | Nuclear | Linn County | IA | [27 empty] | Done | 2007-01-19 |  | 2009-03-24 | 2009-03-25 | ITC Midwest | Linn County | IA |  |  | SPA - SIS | NRIS | Duane Arnold Energy Center | 30 | 30 | Nuclear | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | In Service | 2008-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G942 | [5 empty] | NRIS |  | 24 |  | Coal | Lorain County | OH | [27 empty] | Withdrawn | 2007-12-26 | 2010-06-18 | 2010-06-18 |  | FirstEnergy Solutions Corp. | Lorain County | OH |  |  | Feasibility | NRIS | Avon Lake 345 kV Substation | 24 | 24 | Coal |  | Not Started | 2011-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J148 | [5 empty] | ERIS |  | 4.94 |  | Wind | Olmsted County | MN | [27 empty] | Withdrawn | 2010-06-28 | 2010-07-13 | 2010-07-13 |  | -- No Company -- | Olmsted County | MN |  |  |  | ERIS | DPC 69kV line east side of NW Quarter of Sec. 3, Havehill Township | 4.94 | 4.94 | Wind | WT Wind Turbine | Not Started | 2011-08-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G973 | [5 empty] | NRIS |  | 501 |  | Wind | Washington County | IA | [27 empty] | Withdrawn | 2008-02-15 | 2010-07-29 | 2010-07-29 |  | MidAmerican Energy Company | Washington County | IA |  |  | SPA - SIS | NRIS | Hills - Sub T 345 kV | 501 | 501 | Wind | WT Wind Turbine | Not Started | 2011-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G770 | [5 empty] | NRIS |  | 100 |  | Wind | Martin County | MN | [27 empty] | Withdrawn | 2007-03-23 | 2010-08-02 | 2010-08-02 |  | Northern States Power (Xcel Energy) | Martin County | MN |  |  | SPA - SIS | NRIS | Lakefield Junction - Fox Lake 161 kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2008-11-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G958 | [5 empty] | NRIS |  | 120 |  | Wind | Kent County | MI | [27 empty] | Withdrawn | 2009-05-15 | 2010-08-04 | 2010-08-04 |  | Michigan Electric Transmission Company, LLC | Kent County | MI |  |  | Feasibility | NRIS | Kenowa 345kV Substation | 120 | 120 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G662 | [5 empty] | ERIS |  | 100 |  | Wind | Corson County | SD | [27 empty] | Withdrawn | 2006-07-26 | 2010-08-05 | 2010-08-05 |  | Montana-Dakota Utilities Company | Corson County | SD |  |  | SPA - SIS | ERIS | McLaughlin 115 kV Substation | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2007-11-07 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G796 | [5 empty] | NRIS |  | 300 |  | Wind | Dodge County | MN | [27 empty] | Withdrawn | 2007-05-02 | 2010-08-09 | 2010-08-09 |  | SMMPA | Dodge County | MN |  |  | SPA - SIS | NRIS | SMMPA Byron 345/161 kV Substation | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2007-05-27 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G841 | [5 empty] | NRIS |  | 250 |  | Wind | Lyon County | MN | [27 empty] | Withdrawn | 2007-08-17 | 2010-08-09 | 2010-08-09 |  | Northern States Power (Xcel Energy) | Lyon County | MN |  |  | SPA - SIS | NRIS | North Tracy Substation | 250 | 250 | Wind | WT Wind Turbine | Not Started | 2010-09-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | WEST | Done | In Service | G735 | [5 empty] | NRIS |  | 200 |  | Wind | Hancock County | IA | [27 empty] | Done | 2007-02-02 |  | 2015-03-23 | 2008-12-31 | ITC Midwest | Hancock County | IA | DPP-2012-AUG | WEST | Network Upgrade | NRIS | Lime Creek Substation | 200 | 200 | Wind | WT Wind Turbine | In Service | 2017-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | West | Done | In Service | G736 | [5 empty] | NRIS |  | 200 |  | Wind | Grant County | SD | [27 empty] | Done | 2007-02-02 |  | 2016-11-21 | 2017-09-30 | Otter Tail Power Company | Grant County | SD | DPP-2015-FEB | West | DPP - SIS | NRIS | Big Stone South 230kV Substation | 200 | 200 | Wind | WT Wind Turbine | In Service | 2019-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G842 | [5 empty] | NRIS |  | 250 |  | Wind | Lyon County | MN | [27 empty] | Withdrawn | 2007-08-17 | 2010-08-09 | 2010-08-09 |  | Northern States Power (Xcel Energy) | Lyon County | MN |  |  | SPA - SIS | NRIS | Lake Yankton - Ellsboro 115 kV | 250 | 250 | Wind | WT Wind Turbine | Not Started | 2008-01-06 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H088 | [5 empty] | NRIS |  | 150 |  | Wind | Sargent County | ND | [27 empty] | Withdrawn | 2008-07-15 | 2010-08-12 | 2010-08-12 |  | Otter Tail Power Company | Sargent County | ND |  |  | SPA - SIS | NRIS | OTP Forman 230kV Substation | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-NOV | IL | Withdrawn | Not Started | G677 | [5 empty] | NRIS |  | 275 |  | Coal | Moultrie County | IL | [27 empty] | Withdrawn | 2008-11-15 | 2010-08-25 | 2010-08-25 |  | Ameren Illinois | Moultrie County | IL | DPP-2009-NOV | IL | DPP - SIS | NRIS | Mattoon West 138 kV Substation | 275 | 275 | Coal | IGCC | Not Started | 2010-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G731 | [5 empty] | NRIS |  | 750 |  | Wind | Jerauld County | SD | [27 empty] | Withdrawn | 2007-01-29 | 2010-08-26 | 2010-08-26 |  | Northern States Power (Xcel Energy) | Jerauld County | SD |  |  | SPA - SIS | NRIS | Split Rock Substation | 750 | 750 | Wind | WT Wind Turbine | Not Started | 2007-05-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-MAR | MN | Done | In Service | G741 | [5 empty] | NRIS |  | 8 |  | Waste Heat Recovery | Martin County | MN | [27 empty] | Done | 2007-02-16 |  | 2010-03-08 | 2010-07-26 | ITC Midwest | Martin County | MN | DPP-2009-MAR | MN | DPP - SIS | NRIS | Near Alliant 69kV line | 8 | 8 | Waste Heat Recovery | BT Turbines Used in a Binary Cycle (such as used for geothermal | In Service | 2011-03-11 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J067 | [5 empty] | NRIS |  | 300 |  | Wind | Olmsted County | MN | [27 empty] | Withdrawn | 2009-09-02 | 2010-08-31 | 2010-08-31 |  | Great River Energy | Olmsted County | MN |  |  | SPA - SIS | NRIS | Byron Substation | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2011-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | MI | Done | In Service | G743 | [5 empty] | NRIS |  | 45 |  | Wind | Missaukee County | MI | [27 empty] | Done | 2007-02-16 |  | 2010-03-26 | 2010-12-06 | Wolverine Power Supply Cooperative, Inc. | Missaukee County | MI | DPP-2008-NOV | MI | Network Upgrade | NRIS | WPSC Cadillac - Leroy 69kV | 45 | 45 | Wind | WT Wind Turbine | In Service | 2009-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J135 | [5 empty] | 0 |  | 200 |  | Wind | Buffalo County | WI | [27 empty] | Withdrawn | 2008-02-20 | 2010-09-13 | 2010-09-13 |  | -- No Company -- | Buffalo County | WI |  |  | Feasibility |  | Alma - Tremval 161 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2011-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J136 | [5 empty] | 0 |  | 40 |  | Wind | Fillmore County | MN | [27 empty] | Withdrawn | 2009-02-05 | 2010-09-13 | 2010-09-13 |  | -- No Company -- | Fillmore County | MN |  |  | Feasibility |  | Harmony 69 kV line | 40 | 40 | Wind | WT Wind Turbine | Not Started | 2013-06-30 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | SE MN IA | Done | Withdrawn | G746 | [5 empty] | NRIS Only |  | 200 |  | Wind | Fillmore County | MN | [27 empty] | Done | 2007-02-21 |  | 2011-11-01 | 2012-12-01 | ITC Midwest | Fillmore County | MN | DPP-2008-NOV | SE MN IA | SPA - SIS | NRIS Only | ITC Midwest Lansing - Harmony 161 kV | 200 | 200 | Wind | WT Wind Turbine | Withdrawn | 2010-04-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J137 | [5 empty] | 0 |  | 100 |  | Wind | Mower County | MN | [27 empty] | Withdrawn | 2009-02-09 | 2010-09-13 | 2010-09-13 |  | -- No Company -- | Mower County | MN |  |  | Feasibility |  | East Austin Switching Station | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2009-12-31 | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | 0 | Done | Withdrawn | G749 | [5 empty] | NRIS |  | 50 |  | Wind | Lafayette County | WI | [27 empty] | Done | 2007-02-27 |  | 2010-03-23 | 2012-11-30 | American Transmission Co. LLC | Lafayette County | WI | Pre-Transition SIS |  | Network Upgrade | NRIS | Hillman - Eden 69kV | 50 | 50 | Wind | WT Wind Turbine | Withdrawn | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J140 | [5 empty] | 0 |  | 100 |  | Wind | Fillmore County | MN | [27 empty] | Withdrawn | 2009-11-23 | 2010-09-13 | 2010-09-13 |  | -- No Company -- | Fillmore County | MN |  |  | Feasibility |  | Adams - Harmony 161 kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J117 | [5 empty] | NRIS |  | 9.12 |  | Diesel | Brown County | MN | [27 empty] | Withdrawn | 2010-02-16 | 2010-09-20 | 2010-09-20 |  | ITC Midwest | Brown County | MN |  |  | Feasibility | NRIS | substation at 625 E Lincoln Street, Springfield, MN | 9.12 | 9.12 | Diesel |  | Not Started | 2016-06-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-APR | MT-ND | Done | In Service | G752 | [5 empty] | NRIS |  | 150 |  | Wind | Adams County | ND | [27 empty] | Done | 2007-02-27 |  | 2012-02-07 | 2015-07-31 | Montana-Dakota Utilities Company | Adams County | ND | DPP-2010-APR | MT-ND | Network Upgrade | NRIS | Bison - Hettinger 230 kV | 150 | 150 | Wind | WT Wind Turbine | In Service | 2009-09-30 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-NOV | MI | Withdrawn | Not Started | G814 | [5 empty] | NRIS |  | 36 |  | Biomass | Antrim County | MI | [27 empty] | Withdrawn | 2009-05-15 | 2010-10-12 | 2010-10-12 |  | Wolverine Power Supply Cooperative, Inc. | Antrim County | MI | DPP-2009-NOV | MI | DPP - SIS | NRIS | WPSC Westwood - Mancelona 69 kV | 36 | 36 | Biomass | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | Not Started | 2009-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J169 | [5 empty] | NRIS |  | 20 |  | Solar | Jersey County | IL | [27 empty] | Withdrawn | 2010-09-13 | 2010-10-18 | 2010-10-18 |  | Ameren Illinois | Jersey County | IL |  |  | Feasibility | NRIS | Ameren Jerseyville N.W. 138kV Substation | 20 | 20 | Solar | PV Photovoltaic | Not Started | 2015-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J160 | [5 empty] | NRIS |  | 101.2 |  | Wind | Macon County | IL | [27 empty] | Withdrawn | 2010-08-25 | 2010-10-19 | 2010-10-19 |  | Ameren Illinois | Macon County | IL |  |  | Feasibility | NRIS | Ameren Latham - Decatur North 138 kV | 101.2 | 101.2 | Wind | WT Wind Turbine | Not Started | 2012-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J059 | [5 empty] | ERIS |  | 99 |  | Wind | Allegan County | MI | [27 empty] | Withdrawn | 2009-07-27 | 2010-10-20 | 2010-10-20 | 2011-08-01 | Michigan Electric Transmission Company, LLC | Allegan County | MI |  |  | Feasibility | ERIS | ITC Beals Rd - Hazelwood 138kV | 99 | 99 | Wind | WT Wind Turbine | Not Started | 2012-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J159 | [5 empty] | NRIS |  | 101.2 |  | Wind | Macon County | IL | [27 empty] | Withdrawn | 2010-08-25 | 2010-11-03 | 2010-11-03 |  | Ameren Illinois | Macon County | IL |  |  | Feasibility | NRIS | Ameren Latham - Decatur North 138 kV | 101.2 | 101.2 | Wind | WT Wind Turbine | Not Started | 2012-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G907 | [5 empty] | ERIS |  | 450 |  | Wind | Mower County | MN | [27 empty] | Withdrawn | 2007-11-09 | 2010-11-08 | 2010-11-08 |  | Great River Energy | Mower County | MN |  |  | SPA - SIS | ERIS | Pleasant Valley peaking plant | 450 | 450 | Wind | WT Wind Turbine | Not Started | 2010-06-30 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | Individual | Withdrawn | Withdrawn | G922 | [5 empty] | NRIS |  | 120 |  | Biomass | Carroll County | IL | [27 empty] | Withdrawn | 2007-12-03 | 2010-11-15 | 2010-11-15 | 2014-01-01 | ITC Midwest | Carroll County | IL | DPP-2008-NOV | Individual | Network Upgrade | NRIS | Savana -York 161kV | 120 | 120 | Biomass | ST, CT | Withdrawn | 2017-03-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J029 | [5 empty] | NRIS |  | 102 |  | Wind | Howard County | IA | [27 empty] | Withdrawn | 2009-03-11 | 2010-11-29 | 2010-11-29 |  | ITC Midwest | Howard County | IA |  |  | Feasibility | NRIS | Adams Substation | 102 | 102 | Wind | WT Wind Turbine | Not Started | 2012-09-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-MAR | Individual | Done | In Service | G761 | [5 empty] | NRIS |  | 28 |  | Coal | Lee County | IA | [27 empty] | Done | 2007-03-09 |  | 2009-04-09 | 2009-06-04 | ITC Midwest | Lee County | IA | DPP-2009-MAR | Individual | DPP - SIS | NRIS | ITC Midwest Keokuk West - Keokuk Hydro 69kV | 28 | 28 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | In Service | 2014-12-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G643 | [5 empty] | NRIS |  | 20 |  | Wind | Mitchell County | IA | [27 empty] | Withdrawn | 2006-05-25 | 2010-11-30 | 2010-11-30 |  | ITC Midwest | Mitchell County | IA |  |  | SPA - SIS | NRIS | Osage Switch Station (69 kV) | 20 | 20 | Wind | WT Wind Turbine | Not Started | 2007-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H030 | [5 empty] | NRIS |  | 200 |  | Wind | Tuscola County | MI | [27 empty] | Withdrawn | 2009-09-21 | 2010-12-01 | 2010-12-01 |  | ITC Transmission | Tuscola County | MI |  |  | Feasibility | NRIS | Atlanta 120kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2014-10-01 | 0 | 0 | 0 | 0
|  |  |  | G418 | G418 | Withdrawn | Withdrawn | G418 | [5 empty] | NRIS |  | 140 |  | Wind | Oceana County | MI | [27 empty] | Withdrawn | 2004-03-22 | 2010-12-07 | 2010-12-07 | 2012-06-30 | Michigan Electric Transmission Company, LLC | Oceana County | MI | G418 | G418 | Network Upgrade | NRIS | Donaldson Creek 138 kV Substation | 140 | 140 | Wind | WT Wind Turbine | Withdrawn | 2009-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G797 | [5 empty] | ERIS |  | 30 |  | Wind | Martin County | MN | [27 empty] | Withdrawn | 2007-05-07 | 2010-12-16 | 2010-12-16 |  | Great River Energy | Martin County | MN |  |  | SPA - SIS | ERIS | N 43, 34.851'; W 094, 48.876' | 30 | 30 | Wind | WT Wind Turbine | Not Started | 2007-05-27 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H029 | [5 empty] | NRIS |  | 268 |  | Gas | Summit County | OH | [27 empty] | Withdrawn | 2009-10-01 | 2010-12-22 | 2010-12-22 |  | FirstEnergy Solutions Corp. | Summit County | OH |  |  | Feasibility | NRIS | Norton, OH in vicinity of FE Martin 69 kV substation | 268 | 268 | Gas |  | Not Started | 2013-12-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-MAR | 0 | Done | In Service | G767 | [5 empty] | NRIS |  | 30 |  | Wind | Fallon County | MT | [27 empty] | Done | 2007-03-20 |  | 2007-12-21 |  | Montana-Dakota Utilities Company | Fallon County | MT | DPP-2009-MAR |  | DPP - SIS | NRIS | existing 57 kV line | 30 | 30 | Wind | WT Wind Turbine | In Service | 2009-12-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | IL | Withdrawn | Not Started | J002 | [5 empty] | NRIS |  | 100 |  | Wind | Ford County | IL | [27 empty] | Withdrawn | 2008-10-22 | 2010-12-22 | 2010-12-22 |  | Ameren Illinois | Ford County | IL | DPP-2008-NOV | IL | Optional | NRIS | T23N R7E approximately two Miles EAST of the Gibson City South Substation on the Gibson City ?Paxton 138 kV line | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2006-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G753 | [5 empty] | NRIS |  | 300 |  | Wind | Fallon County | MT | [27 empty] | Withdrawn | 2007-02-27 | 2010-12-23 | 2010-12-23 |  | Montana-Dakota Utilities Company | Fallon County | MT |  |  | SPA - SIS | NRIS | Baker 230 kV Substation | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2010-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G733 | [5 empty] | NRIS |  | 1650 |  | Nuclear | Callaway County | MO | [27 empty] | Withdrawn | 2007-02-01 | 2010-12-28 | 2010-12-28 |  | Ameren Missouri | Callaway County | MO |  |  | SPA - SIS | NRIS | Callaway Plant Switchyard | 1650 | 1650 | Nuclear | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | Not Started | 2009-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G790 | [5 empty] | ERIS |  | 150 |  | Wind | Franklin County | IA | [27 empty] | Withdrawn | 2007-04-26 | 2010-12-28 | 2010-12-28 |  | ITC Midwest | Franklin County | IA |  |  | SPA - SIS | ERIS | ITC Midwest Franklin Substation | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2008-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G801 | [5 empty] | NRIS |  | 50 |  | Wind | Mower County | MN | [27 empty] | Withdrawn | 2007-05-24 | 2010-12-28 | 2010-12-28 |  | Great River Energy | Mower County | MN |  |  | SPA - SIS | NRIS | 161 kV GRE line in southwest 1/4 of section 26 Waltham Twp | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2009-11-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Withdrawn | G773 | [5 empty] | NRIS |  | 150 |  | Wind | Brown County | WI | [27 empty] | Done | 2007-03-27 |  | 2009-05-07 |  | Wisconsin Public Service Corporation | Brown County | WI |  |  | Network Upgrade | NRIS | Forest Junction - Lost Dauphin 138kV | 150 | 150 | Wind | WT Wind Turbine | Withdrawn | 2010-08-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G888 | [5 empty] | NRIS |  | 50 |  | Wind | Benton County | IN | [27 empty] | Withdrawn | 2007-10-16 | 2010-12-28 | 2010-12-28 |  | Northern Indiana Public Service Company | Benton County | IN |  |  | SPA - SIS | NRIS | Watseka - Goodland 138 kV | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2010-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G893 | [5 empty] | ERIS |  | 80 |  | Wind | Rock County | MN | [27 empty] | Withdrawn | 2007-10-18 | 2010-12-28 | 2010-12-28 |  | Northern States Power (Xcel Energy) | Rock County | MN |  |  | SPA - SIS | ERIS | Split Rock-Magnolia 161 kV | 80 | 80 | Wind | WT Wind Turbine | Not Started | 2010-06-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G952 | [5 empty] | NRIS |  | 100 |  | Wind | Tipton County | IN | [27 empty] | Withdrawn | 2008-01-15 | 2010-12-28 | 2010-12-28 |  | Duke Energy Corporation | Tipton County | IN |  |  | SPA - SIS | NRIS | Kokomo - Noblesville 230 kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2011-02-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G985 | [5 empty] | NRIS |  | 200 |  | Wind | Fayette County | IA | [27 empty] | Withdrawn | 2008-03-18 | 2010-12-28 | 2010-12-28 |  | ITC Midwest | Fayette County | IA |  |  | SPA - SIS | NRIS | Hazelton - Windsor 161 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2008-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J138 | [5 empty] | NRIS |  | 48 |  | Wind | Olmsted County | MN | [27 empty] | Withdrawn | 2009-09-22 | 2011-01-03 | 2011-01-03 |  | -- No Company -- | Olmsted County | MN |  |  | Feasibility | NRIS | Dairyland 69 kV line | 48 | 48 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G824 | [5 empty] | NRIS |  | 200 |  | Wind | Mower County | MN | [27 empty] | Withdrawn | 2007-07-16 | 2011-01-05 | 2011-01-05 |  | Northern States Power (Xcel Energy) | Mower County | MN |  |  | SPA - SIS | NRIS | T-103-N, R-16-W | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2010-06-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G780 | [5 empty] | NRIS |  | 578 |  | Gas | Vigo County | IN | [27 empty] | Done | 2007-04-09 |  | 2007-10-25 |  | Duke Energy Corporation | Vigo County | IN |  |  | SPA - SIS | NRIS | Sugar Creek Substation | 578 | 578 | Gas | Combined Cycle | In Service | 2009-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G828 | [5 empty] | NRIS |  | 76 |  | Wind | Blue Earth County | MN | [27 empty] | Withdrawn | 2007-07-16 | 2011-01-05 | 2011-01-05 |  | Northern States Power (Xcel Energy) | Blue Earth County | MN |  |  | SPA - SIS | NRIS | 345 kV line near Wilmarth substation | 76 | 76 | Wind | WT Wind Turbine | Not Started | 2010-08-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H019 | [5 empty] | NRIS |  | 150 |  | Wind | Watonwan County | MN | [27 empty] | Withdrawn | 2008-04-30 | 2011-01-05 | 2011-01-05 |  | Northern States Power (Xcel Energy) | Watonwan County | MN |  |  | SPA - SIS | NRIS | 1.5 miles north connected on the high side of the Watonwan Switching Station | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H044 | [5 empty] | NRIS |  | 75 |  | Wind | Watonwan County | MN | [27 empty] | Withdrawn | 2008-06-12 | 2011-01-05 | 2011-01-05 |  | ITC Midwest | Watonwan County | MN |  |  | SPA - SIS | NRIS | ITC Midwest Madelia 69 kV Subsation | 75 | 75 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H046 | [5 empty] | NRIS |  | 100 |  | Wind | Jackson County | MN | [27 empty] | Withdrawn | 2008-06-12 | 2011-01-05 | 2011-01-05 |  | ITC Midwest | Jackson County | MN |  |  | SPA - SIS | NRIS | Heron Lake, MN 161 kV substation | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-AUG | ND | Done | In Service | G788 | [5 empty] | NRIS |  | 49 |  | Coal | Stutsman County | ND | [27 empty] | Done | 2007-04-24 |  | 2012-06-15 | 2011-11-01 | Otter Tail Power Company | Stutsman County | ND | DPP-2010-AUG | ND | Optional | NRIS | Ladish 115 kV substation | 49 | 49 | Coal | Combined Cycle | In Service | 2011-08-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H051 | [5 empty] | NRIS |  | 40 |  | Wind | Redwood County | MN | [27 empty] | Withdrawn | 2008-06-12 | 2011-01-05 | 2011-01-05 |  | ITC Midwest | Redwood County | MN |  |  | SPA - SIS | NRIS | ITC Midwest Lamberton 69kV Substation | 40 | 40 | Wind | WT Wind Turbine | Not Started | 2011-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H056 | [5 empty] | NRIS |  | 40 |  | Wind | Rice County | MN | [27 empty] | Withdrawn | 2008-06-12 | 2011-01-05 | 2011-01-05 |  | Northern States Power (Xcel Energy) | Rice County | MN |  |  | SPA - SIS | NRIS | Walcott 69 kV Substation | 40 | 40 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H070 | [5 empty] | NRIS |  | 85 |  | Wind | Renville County | MN | [27 empty] | Withdrawn | 2008-06-17 | 2011-01-05 | 2011-01-05 |  | Northern States Power (Xcel Energy) | Renville County | MN |  |  | SPA - SIS | NRIS | Xcel Bird Island 69 kV Substation | 85 | 85 | Wind | WT Wind Turbine | Not Started | 2010-06-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J014 | [5 empty] | NRIS |  | 100 |  | Wind | Stearns County | MN | [27 empty] | Withdrawn | 2009-01-06 | 2011-01-05 | 2011-01-05 |  | Northern States Power (Xcel Energy) | Stearns County | MN |  |  | SPA - SIS | NRIS | Xcel Energy's Paynesville 115 kV substation | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2010-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Retired | G794 | [5 empty] | NRIS |  | 0 |  | Coal | Jasper County | IL | [27 empty] | Done | 2007-04-30 |  | 2007-05-25 | 2007-05-27 | Ameren Illinois | Jasper County | IL |  |  | SPA - SIS | NRIS | AEG Newton Plant 345kV | 0 | 0 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | Retired | 2009-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J144 | [5 empty] | NRIS |  | 25.62 |  | Biomass | Alger County | MI | [27 empty] | Withdrawn | 2010-06-25 | 2011-01-06 | 2011-01-06 |  | American Transmission Co. LLC | Alger County | MI |  |  | Feasibility | NRIS | ATC 69 kV Munising substation | 25.62 | 25.62 | Biomass |  | Not Started | 2010-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | R66 | [5 empty] | NRIS |  | 150 |  | Wind | Adams County | IA | [27 empty] | Withdrawn | 2009-04-30 | 2011-01-14 | 2011-01-14 |  | MidAmerican Energy Company | Adams County | IA |  |  | Feasibility | NRIS | Creston - Clarinda 161 kV | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-APR | G975 | Withdrawn | Not Started | G975 | [5 empty] | NRIS |  | 855 |  | Gas | Chisago County | MN | [27 empty] | Withdrawn | 2008-02-20 | 2011-01-18 | 2011-01-18 |  | Northern States Power (Xcel Energy) | Chisago County | MN | DPP-2010-APR | G975 | DPP - SIS | NRIS | Chisago Cty Sbstn 345 kV owned by NSP | 855 | 855 | Gas |  | Not Started | 2009-12-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | WEST | Done | In Service | G798 | [5 empty] | NRIS |  | 150 |  | Wind | Story County | IA | [27 empty] | Done | 2007-05-14 |  | 2015-03-23 | 2009-12-14 | ITC Midwest | Story County | IA | DPP-2012-AUG | WEST | Network Upgrade | NRIS | ITC Midwest Fernald 115kV Substation | 150 | 150 | Wind | WT Wind Turbine | In Service | 2008-12-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-AUG | 0 | Withdrawn | Not Started | J121 | [5 empty] | ERIS |  | 100 |  | Wind | Ford County | IL | [27 empty] | Withdrawn | 2010-04-05 | 2011-01-27 | 2011-01-27 |  | Ameren Illinois | Ford County | IL | DPP-2010-AUG |  | DPP - SIS | ERIS | Ameren Gibson City South Substation | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2012-07-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-NOV | Indiana | Withdrawn | Not Started | G887 | [5 empty] | NRIS |  | 20 |  | Wind | Benton County | IN | [27 empty] | Withdrawn | 2007-10-16 | 2011-02-07 | 2011-02-07 |  | Northern Indiana Public Service Company | Benton County | IN | DPP-2009-NOV | Indiana | DPP - SIS | NRIS | Watseka - Goodland 138 kV | 20 | 20 | Wind | WT Wind Turbine | Not Started | 2012-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-NOV | 0 | Withdrawn | Not Started | J083 | [5 empty] | NRIS |  | 200 |  | Wind | Warren County | IN | [27 empty] | Withdrawn | 2009-10-05 | 2011-02-07 | 2011-02-07 |  | Northern Indiana Public Service Company | Warren County | IN | DPP-2009-NOV |  | DPP - SIS | NRIS | South Prairie - Westwood 138kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2012-12-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-MAR | MN | Withdrawn | Not Started | G846 | [5 empty] | ERIS |  | 4 |  | Wind | Clay County | MN | [27 empty] | Withdrawn | 2007-08-28 | 2011-02-17 | 2011-02-17 |  | Otter Tail Power Company | Clay County | MN | DPP-2009-MAR | MN | Network Upgrade | ERIS | GRE Pelican Lake - Tansem 41.6 kV | 4 | 4 | Wind | WT Wind Turbine | Not Started | 2011-05-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-NOV | IN | Withdrawn | Not Started | J065 | [5 empty] | NRIS |  | 29 |  | Wood | Scott County | IN | [27 empty] | Withdrawn | 2009-08-21 | 2011-03-01 | 2011-03-01 |  | Duke Energy Corporation | Scott County | IN | DPP-2009-NOV | IN | Network Upgrade | NRIS | Duke Indiana's 69 kV between Scottsburg & Speed | 28 | 29 | Wood |  | Not Started | 2011-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-APR | Indiana | Withdrawn | Not Started | J076 | [5 empty] | NRIS |  | 151.2 |  | Wind | Howard County | IN | [27 empty] | Withdrawn | 2009-10-05 | 2011-03-03 | 2011-03-03 |  | Duke Energy Corporation | Howard County | IN | DPP-2010-APR | Indiana | DPP - SIS | NRIS | DEM Greentown - Mier 138 kV | 151.2 | 151.2 | Wind | WT Wind Turbine | Not Started | 2012-05-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J006 | [5 empty] | NRIS |  | 25 |  | Wind | Nicollet County | MN | [27 empty] | Withdrawn | 2008-10-29 | 2011-03-07 | 2011-03-07 |  | Northern States Power (Xcel Energy) | Nicollet County | MN |  |  | SPA - SIS | NRIS | Ft. Ridgely - Lafayette 69kV | 25 | 25 | Wind | WT Wind Turbine | Not Started | 2012-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G806 | [5 empty] | NRIS |  | 19 |  | Coal | Montgomery County | IL | [27 empty] | Done | 2007-06-06 |  | 2008-07-03 |  | Ameren Illinois | Montgomery County | IL |  |  | SPA - SIS | NRIS | Ameren Coffeen Unit #2 | 19 | 19 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | In Service | 2016-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Withdrawn | G807 | [5 empty] | NRIS |  | 20 |  | Coal | Franklin County | MO | [27 empty] | Done | 2007-06-06 |  | 2008-07-29 |  | Ameren Missouri | Franklin County | MO |  |  | SPA - SIS | NRIS | Ameren Labadie Plant | 20 | 20 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | Withdrawn | 2010-11-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | MI | Done | In Service | G809 | [5 empty] | NRIS |  | 193 |  | Gas | Midland County | MI | [27 empty] | Done | 2007-06-12 |  | 2010-07-08 | 2010-06-01 | Michigan Electric Transmission Company, LLC | Midland County | MI | DPP-2008-NOV | MI | Network Upgrade | NRIS | Tittabawassee 345kV Substation | 193 | 193 | Gas | CC (cogen) | In Service | 2009-12-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-APR | MT-ND | Withdrawn | Not Started | G885 | [5 empty] | NRIS |  | 199.5 |  | Wind | Barnes County | ND | [27 empty] | Withdrawn | 2007-10-16 | 2011-03-18 | 2011-03-18 |  | Otter Tail Power Company | Barnes County | ND | DPP-2010-APR | MT-ND | DPP - SIS | NRIS | Buffalo 345kV | 199.5 | 199.5 | Wind | WT Wind Turbine | Not Started | 2011-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J141 | [5 empty] | NRIS |  | 200 |  | Wind | Fillmore County | MN | [27 empty] | Withdrawn | 2009-11-23 | 2011-03-18 | 2011-03-18 |  | -- No Company -- | Fillmore County | MN |  |  | SPA - SIS | NRIS | Adams - Harmony 161 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2012-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J099 | [5 empty] | ERIS |  | 48.6 |  | Wind | Hillsdale County | MI | [27 empty] | Withdrawn | 2009-12-03 | 2011-04-06 | 2011-04-06 |  | Michigan Electric Transmission Company, LLC | Hillsdale County | MI |  |  | Feasibility | ERIS | METC Batavia - Beecher 138 kV | 48.6 | 48.6 | Wind | WT Wind Turbine | Not Started | 2012-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-NOV | 0 | Withdrawn | Not Started | J038 | [5 empty] | NRIS |  | 498 |  | Wind | Sangamon County | IL | [27 empty] | Withdrawn | 2009-03-16 | 2011-04-08 | 2011-04-08 |  | Ameren Illinois | Sangamon County | IL | DPP-2009-NOV |  | DPP - SIS | NRIS | N. Jacksonville - N. Auburn 138 kV | 498 | 498 | Wind | WT Wind Turbine | Not Started | 2010-11-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G805 | [5 empty] | NRIS |  | 300 |  | Wind | Stevens County | MN | [27 empty] | Withdrawn | 2007-06-05 | 2011-04-12 | 2011-04-12 |  | Otter Tail Power Company | Stevens County | MN |  |  | SPA - SIS | NRIS | Johnson Junction - Morris 115 kV | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2012-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J168 | [5 empty] | NRIS |  | 200 |  | Wind | DeKalb County | MO | [27 empty] | Withdrawn | 2010-09-13 | 2011-04-21 | 2011-04-21 |  | Ameren Missouri | DeKalb County | MO |  |  | Feasibility | NRIS | Ameren Excelsior Springs Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G827 | [5 empty] | NRIS |  | 100 |  | Wind | Minnehaha County | SD | [27 empty] | Withdrawn | 2007-07-16 | 2011-04-22 | 2011-04-22 |  | Northern States Power (Xcel Energy) | Minnehaha County | SD |  |  | SPA - SIS | NRIS | 115 kV line near Grant substation | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2010-08-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J129 | [5 empty] | NRIS |  | 300 |  | Gas | Polk County | WI | [27 empty] | Withdrawn | 2010-04-28 | 2011-04-22 | 2011-04-22 |  | -- No Company -- | Polk County | WI |  |  | Feasibility | NRIS | Apple River Stubstation | 300 | 300 | Gas |  | Not Started | 2011-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J130 | [5 empty] | NRIS |  | 300 |  | Gas | Hancock County | IA | [27 empty] | Withdrawn | 2010-04-26 | 2011-04-22 | 2011-04-22 |  | -- No Company -- | Hancock County | IA |  |  | Feasibility | NRIS | Hancock Substation | 300 | 300 | Gas |  | Not Started | 2011-08-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G965 | [5 empty] | NRIS |  | 300 |  | Wind | Mitchell County | IA | [27 empty] | Withdrawn | 2008-01-29 | 2011-04-27 | 2011-04-27 |  | ITC Midwest | Mitchell County | IA |  |  | SPA - SIS | NRIS | Mitchell County Substation | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G857 | [5 empty] | NRIS |  | 400 |  | Wind | Mower County | MN | [27 empty] | Withdrawn | 2007-09-11 | 2011-05-02 | 2011-05-02 |  | Northern States Power (Xcel Energy) | Mower County | MN |  |  | SPA - SIS | NRIS | Adams 345 kV Substation | 400 | 400 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | West | Done | In Service | G826 | [5 empty] | NRIS |  | 200 |  | Wind | Jackson County | MN | [27 empty] | Done | 2007-07-16 |  | 2014-12-17 | 2015-10-09 | Northern States Power (Xcel Energy) | Jackson County | MN | DPP-2012-AUG | West | DPP - SIS | NRIS | Xcel Lakefield Generation SW - Lakefield Junction 345kV | 200 | 200 | Wind | WT Wind Turbine | In Service | 2010-08-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-APR | UP Michigan | Withdrawn | Not Started | J078 | [5 empty] | NRIS |  | 26 |  | Biomass | Marquette County | MI | [27 empty] | Withdrawn | 2009-10-05 | 2011-05-03 | 2011-05-03 |  | Upper Peninsula Power Company | Marquette County | MI | DPP-2010-APR | UP Michigan | DPP - SIS | NRIS | ATC 69 kV Sawyer Line near UPPCO/Sawyer substation | 26 | 26 | Biomass |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G650 | [5 empty] | ERIS |  | 99 |  | Wind | Mountrail County | ND | [27 empty] | Withdrawn | 2006-06-22 | 2011-05-04 | 2011-05-04 |  | Montana-Dakota Utilities Company | Mountrail County | ND |  |  | SPA - SIS | ERIS | Tioga - Kenmyer 115 kV | 99 | 99 | Wind | WT Wind Turbine | Not Started | 2008-09-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G713 | [5 empty] | NRIS |  | 200 |  | Wind | Dickey County | ND | [27 empty] | Withdrawn | 2006-12-11 | 2011-05-04 | 2011-05-04 |  | Montana-Dakota Utilities Company | Dickey County | ND |  |  | SPA - SIS | NRIS | Wishek - Foreman 230 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2008-01-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | West | Done | In Service | G830 | [5 empty] | NRIS |  | 99 |  | Wind | McHenry County | ND | [27 empty] | Done | 2007-07-30 |  | 2012-09-20 | 2018-12-22 | Great River Energy | McHenry County | ND | DPP-2012-AUG | West | DPP - SIS | NRIS | GRE McHenry substation | 99 | 99 | Wind | WT Wind Turbine | In Service | 2010-08-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G734 | [5 empty] | NRIS |  | 101 |  | Wind | Brookings County | SD | [27 empty] | Withdrawn | 2007-02-02 | 2011-05-04 | 2011-05-04 |  | Northern States Power (Xcel Energy) | Brookings County | SD |  |  | SPA - SIS | NRIS | Xcel Brookings County 115kV Substation | 101 | 101 | Wind | WT Wind Turbine | Not Started | 2008-09-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G737 | [5 empty] | NRIS |  | 100 |  | Wind | Stevens County | MN | [27 empty] | Withdrawn | 2007-02-05 | 2011-05-04 | 2011-05-04 |  | Great River Energy | Stevens County | MN |  |  | SPA - SIS | NRIS | GRE Johnson Jnct - Morris 115 kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2008-09-01 | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | 0 | Done | In Service | G833 | [5 empty] | NRIS |  | 53 |  | Nuclear | Manitowoc County | WI | [27 empty] | Done | 2007-08-03 |  | 2010-07-12 | 2011-05-31 | Wisconsin Electric Power Company | Manitowoc County | WI | Pre-Transition SIS |  | Network Upgrade | NRIS | Point Beach Unit 2 | 53 | 53 | Nuclear | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | In Service | 2009-08-01 | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | 0 | Done | In Service | G834 | [5 empty] | NRIS |  | 53 |  | Nuclear | Manitowoc County | WI | [27 empty] | Done | 2007-08-03 |  | 2010-07-12 | 2011-11-30 | Wisconsin Electric Power Company | Manitowoc County | WI | Pre-Transition SIS |  | Network Upgrade | NRIS | Point Beach Unit 1 | 53 | 53 | Nuclear | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | In Service | 2008-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G751 | [5 empty] | NRIS |  | 200 |  | Wind | Adams County | ND | [27 empty] | Withdrawn | 2007-02-27 | 2011-05-04 | 2011-05-04 |  | Montana-Dakota Utilities Company | Adams County | ND |  |  | SPA - SIS | NRIS | Bison - Hettinger 230 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2009-06-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G772 | [5 empty] | NRIS |  | 200 |  | Wind | Nobles County | MN | [27 empty] | Withdrawn | 2007-03-23 | 2011-05-04 | 2011-05-04 |  | Northern States Power (Xcel Energy) | Nobles County | MN |  |  | SPA - SIS | NRIS | Xel Split Rock - Lakefield 345 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2010-01-01 | 0 | 0 | 0 | 0
|  |  |  | G837 | G837 | Done | In Service | G837 | [5 empty] | NRIS |  | 25 |  | Coal | Butler County | OH | [27 empty] | Done | 2007-08-10 |  | 2008-05-27 |  | DEO&K | Butler County | OH | G837 | G837 | Network Upgrade | NRIS | 601 N B Street existing co-generation systems | 25 | 25 | Coal | Combined Cycle | In Service | 2010-09-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G776 | [5 empty] | NRIS |  | 200 |  | Wind | Brookings County | SD | [27 empty] | Withdrawn | 2007-03-27 | 2011-05-04 | 2011-05-04 |  | Northern States Power (Xcel Energy) | Brookings County | SD |  |  | SPA - SIS | NRIS | Xcel Brookings County 115 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2010-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G777 | [5 empty] | ERIS |  | 20 |  | Wind | Stevens County | MN | [27 empty] | Withdrawn | 2007-03-29 | 2011-05-04 | 2011-05-04 |  | Great River Energy | Stevens County | MN |  |  | SPA - SIS | ERIS | Sec9-T123n-R43w | 20 | 20 | Wind | WT Wind Turbine | Not Started | 2009-08-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G781 | [5 empty] | ERIS |  | 150 |  | Wind | Adams County | ND | [27 empty] | Withdrawn | 2007-04-10 | 2011-05-04 | 2011-05-04 |  | Montana-Dakota Utilities Company | Adams County | ND |  |  | SPA - SIS | ERIS | Hettinger 115 kV Substation | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2008-11-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G783 | [5 empty] | NRIS |  | 122 |  | Wind | Ward County | ND | [27 empty] | Withdrawn | 2007-04-12 | 2011-05-04 | 2011-05-04 |  | Great River Energy | Ward County | ND |  |  | SPA - SIS | NRIS | Just north and west of the town of Ruso | 122 | 122 | Wind | WT Wind Turbine | Not Started | 2009-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G784 | [5 empty] | NRIS |  | 122 |  | Wind | Ward County | ND | [27 empty] | Withdrawn | 2007-04-12 | 2011-05-04 | 2011-05-04 |  | Great River Energy | Ward County | ND |  |  | SPA - SIS | NRIS | Just north and west of the town of Ruso | 122 | 122 | Wind | WT Wind Turbine | Not Started | 2008-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G802 | [5 empty] | NRIS |  | 125 |  | Wind | Grant County | SD | [27 empty] | Withdrawn | 2007-05-30 | 2011-05-04 | 2011-05-04 |  | Otter Tail Power Company | Grant County | SD |  |  | SPA - SIS | NRIS | Big Stone Bus | 125 | 125 | Wind | WT Wind Turbine | Not Started | 2010-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G803 | [5 empty] | NRIS |  | 150 |  | Wind | Deuel County | SD | [27 empty] | Withdrawn | 2007-05-30 | 2011-05-04 | 2011-05-04 |  | Otter Tail Power Company | Deuel County | SD |  |  | SPA - SIS | NRIS | Toronto 115 kV | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2009-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | Individual | Done | In Service | G848 | [5 empty] | NRIS |  | 80 |  | Hydro | Livingston County | KY | [27 empty] | Done | 2007-09-06 |  | 2012-07-06 | 2014-08-27 | Big Rivers Electric Corporation | Livingston County | KY | DPP-2008-NOV | Individual | DPP - SIS | NRIS | Renshaw - Livingston 161 kV | 80 | 80 | Hydro | HY Hydraulic Turbine (including turnbines associated with delivery of water by pipeline) | In Service | 2007-11-15 | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | 0 | Done | In Service | G849 | [5 empty] | NRIS |  | 84 |  | Hydro | Perry County | IN | [27 empty] | Done | 2007-09-06 |  | 2009-12-17 | 2014-01-15 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Perry County | IN | Pre-Transition SIS |  | DPP - SIS | NRIS | Cloverport 138 kV Substation | 84 | 84 | Hydro | OT Other | In Service |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G804 | [5 empty] | NRIS |  | 250 |  | Wind | Deuel County | SD | [27 empty] | Withdrawn | 2007-05-30 | 2011-05-04 | 2011-05-04 |  | Otter Tail Power Company | Deuel County | SD |  |  | SPA - SIS | NRIS | Blair - Big Stone 230 kV | 250 | 250 | Wind | WT Wind Turbine | Not Started | 2009-07-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G810 | [5 empty] | NRIS |  | 101 |  | Wind | Bowman County | ND | [27 empty] | Withdrawn | 2007-06-14 | 2011-05-04 | 2011-05-04 |  | Montana-Dakota Utilities Company | Bowman County | ND |  |  | SPA - SIS | NRIS | Hettinger 115 kV substation | 101 | 101 | Wind | WT Wind Turbine | Not Started | 2009-12-26 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G853 | [5 empty] | NRIS |  | 600 |  | Wind | Dickey County | ND | [27 empty] | Withdrawn | 2007-09-06 | 2011-05-04 | 2011-05-04 |  | Otter Tail Power Company | Dickey County | ND |  |  | SPA - SIS | NRIS | Oakes - Ellendale 230 kV | 600 | 600 | Wind | WT Wind Turbine | Not Started | 2013-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G861 | [5 empty] | NRIS |  | 960 |  | Wind | Burleigh County | ND | [27 empty] | Withdrawn | 2007-09-14 | 2011-05-04 | 2011-05-04 |  | Great River Energy | Burleigh County | ND |  |  | SPA - SIS | NRIS | near Bismarck ND | 960 | 960 | Wind | WT Wind Turbine | Not Started | 2014-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G890 | [5 empty] | NRIS |  | 200 |  | Wind | Fillmore County | MN | [27 empty] | Withdrawn | 2007-10-19 | 2011-05-04 | 2011-05-04 |  | ITC Midwest | Fillmore County | MN |  |  | SPA - SIS | NRIS | ITC Midwest Lansing - Harmony 161 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2008-05-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G910 | [5 empty] | NRIS |  | 99 |  | Wind | Mower County | MN | [27 empty] | Withdrawn | 2007-11-14 | 2011-05-04 | 2011-05-04 |  | Great River Energy | Mower County | MN |  |  | SPA - SIS | NRIS | Pleasant Valley 345 kV Substation | 99 | 99 | Wind | WT Wind Turbine | Not Started | 2010-10-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G911 | [5 empty] | NRIS |  | 99 |  | Wind | Mower County | MN | [27 empty] | Withdrawn | 2007-11-14 | 2011-05-04 | 2011-05-04 |  | Great River Energy | Mower County | MN |  |  | SPA - SIS | NRIS | Pleasant Valley 345 kV Substation | 99 | 99 | Wind | WT Wind Turbine | Not Started | 2010-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2013-FEB | West | Done | In Service | G858 | [5 empty] | NRIS |  | 38 |  | Wind | Stearns County | MN | [27 empty] | Done | 2013-01-07 |  | 2015-05-05 | 2016-03-01 | Northern States Power (Xcel Energy) | Stearns County | MN | DPP-2013-FEB | West | DPP - SIS | NRIS | XEL Black Oak 69 kV Substation | 38 | 38 | Wind | WT Wind Turbine | In Service | 2009-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G912 | [5 empty] | NRIS |  | 99 |  | Wind | Mower County | MN | [27 empty] | Withdrawn | 2007-11-14 | 2011-05-04 | 2011-05-04 |  | Great River Energy | Mower County | MN |  |  | SPA - SIS | NRIS | Pleasant Valley 345 kV Substation | 99 | 99 | Wind | WT Wind Turbine | Not Started | 2010-11-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G913 | [5 empty] | NRIS |  | 201 |  | Wind | Wilkin County | MN | [27 empty] | Withdrawn | 2007-11-14 | 2011-05-04 | 2011-05-04 |  | Otter Tail Power Company | Wilkin County | MN |  |  | SPA - SIS | NRIS | 230 kV OTP line | 201 | 201 | Wind | WT Wind Turbine | Not Started | 2011-11-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G970 | [5 empty] | NRIS |  | 100 |  | Wind | Howard County | IA | [27 empty] | Withdrawn | 2008-02-06 | 2011-05-04 | 2011-05-04 |  | ITC Midwest | Howard County | IA |  |  | SPA - SIS | NRIS | ITC Midwest Hazleton - Adams 345 kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H077 | [5 empty] | NRIS |  | 250 |  | Wind | Kossuth County | IA | [27 empty] | Withdrawn | 2008-06-20 | 2011-05-04 | 2011-05-04 |  | ITC Midwest | Kossuth County | IA |  |  | Optional | NRIS | Winnebago - Winco 161 kV | 250 | 250 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H082 | [5 empty] | NRIS |  | 500 |  | Wind | Oliver County | ND | [27 empty] | Withdrawn | 2008-06-30 | 2011-05-04 | 2011-05-04 |  | Otter Tail Power Company | Oliver County | ND |  |  | SPA - SIS | NRIS | OTP Center 345 kV Substation | 500 | 500 | Wind | WT Wind Turbine | Not Started | 2010-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H084 | [5 empty] | NRIS |  | 200 |  | Wind | McLean County | ND | [27 empty] | Withdrawn | 2008-07-03 | 2011-05-04 | 2011-05-04 |  | Great River Energy | McLean County | ND |  |  | SPA - SIS | NRIS | GRE McHenry - Stanton Line 230 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | IL | Done | In Service | G868 | [5 empty] | NRIS |  | 23 |  | Coal | Fulton County | IL | [27 empty] | Done | 2007-09-25 |  | 2010-01-14 | 2009-03-15 | Ameren Illinois | Fulton County | IL | DPP-2008-NOV | IL | Network Upgrade | NRIS | Ameren AERG Duck Creek Plant | 23 | 23 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | In Service | 2009-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H095 | [5 empty] | NRIS |  | 550 |  | Wind | Roberts County | SD | [27 empty] | Withdrawn | 2008-08-04 | 2011-05-04 | 2011-05-04 |  | Otter Tail Power Company | Roberts County | SD |  |  | SPA - SIS | NRIS | Invenergy's Hurricane Lake Wind Energy Center (MISO G699) proposed substation which will tap Big Stone-Hankinson 230kV | 550 | 550 | Wind | WT Wind Turbine | Not Started | 2010-06-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | WEST | Done | In Service | G870 | [5 empty] | NRIS |  | 201 |  | Wind | Freeborn County | MN | [27 empty] | Done | 2007-10-02 |  | 2015-05-11 | 2010-09-01 | ITC Midwest | Freeborn County | MN | DPP-2012-AUG | WEST | Network Upgrade | NRIS | Hayward - Winnebago 161 kV | 201 | 201 | Wind | WT Wind Turbine | In Service | 2009-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J051 | [5 empty] | NRIS |  | 200 |  | Wind | Jackson County | MN | [27 empty] | Withdrawn | 2009-06-30 | 2011-05-04 | 2011-05-04 |  | ITC Midwest | Jackson County | MN |  |  | Feasibility | NRIS | Lakefield 345 kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2009-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J146 | [5 empty] | NRIS |  | 99 |  | Wind | Fond du Lac County | WI | [27 empty] | Withdrawn | 2010-06-28 | 2011-05-13 | 2011-05-13 |  | American Transmission Co. LLC | Fond du Lac County | WI |  |  | SPA - SIS | NRIS | ATC Green Lake - N. Fond du Lac 138 kV | 99 | 99 | Wind | WT Wind Turbine | Not Started | 2012-03-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | R50 | [5 empty] | 0 |  | 501 |  | Wind | Washington County | IA | [27 empty] | Withdrawn | 2008-02-15 | 2011-05-18 | 2011-05-18 |  | MidAmerican Energy Company | Washington County | IA |  |  | DPP - SIS |  | MEC Sub T 345kV | 501 | 501 | Wind | WT Wind Turbine | Not Started | 2010-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | R51 | [5 empty] | 0 |  | 250.5 |  | Wind | Poweshiek County | IA | [27 empty] | Withdrawn | 2008-02-15 | 2011-05-18 | 2011-05-18 |  | MidAmerican Energy Company | Poweshiek County | IA |  |  | DPP - SIS |  | Montezuma 345kV | 250.5 | 250.5 | Wind | WT Wind Turbine | Not Started | 2009-08-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | ND | Done | In Service | G876 | [5 empty] | NRIS |  | 25 |  | Coal | McLean County | ND | [27 empty] | Done | 2007-10-09 |  | 2009-10-02 |  | Great River Energy | McLean County | ND | DPP-2008-NOV | ND | DPP - SIS | NRIS | GRE Coal Creek 230 kV Substation | 25 | 25 | Coal | Combined Cycle | In Service | 2009-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | ND | Done | In Service | G877 | [5 empty] | NRIS |  | 40 |  | Coal | McLean County | ND | [27 empty] | Done | 2007-10-09 |  | 2009-10-02 |  | Great River Energy | McLean County | ND | DPP-2008-NOV | ND | DPP - SIS | NRIS | GRE Coal Creek 230 kV Substation | 40 | 40 | Coal | Combined Cycle | In Service | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J166 | [5 empty] | NRIS |  | 99 |  | Wind | Fulton County | OH | [27 empty] | Withdrawn | 2010-09-10 | 2011-05-20 | 2011-05-20 |  | FirstEnergy Solutions Corp. | Fulton County | OH |  |  | Feasibility | NRIS | FE Allen Junction Substation 138kV | 99 | 99 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J111 | [5 empty] | NRIS |  | 150 |  | Wind | Mower County | MN | [27 empty] | Withdrawn | 2010-01-07 | 2011-05-24 | 2011-05-24 |  | Great River Energy | Mower County | MN |  |  | SPA - SIS | NRIS | Pleasant valley 345 kV Substation | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2012-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G871 | [5 empty] | ERIS |  | 201 |  | Wind | Freeborn County | MN | [27 empty] | Withdrawn | 2010-06-28 | 2011-05-27 | 2011-05-27 |  | ITC Midwest | Freeborn County | MN |  |  | SPA - SIS | ERIS | ITC Midwest Hayward Substation | 201 | 201 | Wind | WT Wind Turbine | Not Started | 2011-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-APR | 0 | Withdrawn | Not Started | J057 | [5 empty] | NRIS |  | 200 |  | Wind | Morrow County | OH | [27 empty] | Withdrawn | 2009-07-27 | 2011-06-01 | 2011-06-01 |  | FirstEnergy Solutions Corp. | Morrow County | OH | DPP-2010-APR |  | DPP - SIS | NRIS | Galion 138 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2012-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J124 | [5 empty] | NRIS |  | 50 |  | Wind | Ashtabula County | OH | [27 empty] | Withdrawn | 2010-04-20 | 2011-06-01 | 2011-06-01 |  | FirstEnergy Solutions Corp. | Ashtabula County | OH |  |  | Feasibility | NRIS | Ashtabula 138 kV Substation | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2011-09-30 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-AUG | 0 | Withdrawn | Not Started | J127 | [5 empty] | ERIS |  | 40 |  | Gas | Wood County | OH | [27 empty] | Withdrawn | 2010-04-26 | 2011-06-01 | 2011-06-01 |  | FirstEnergy Solutions Corp. | Wood County | OH | DPP-2010-AUG |  | DPP - SIS | ERIS | ATSI Lemoyne Substation | 40 | 40 | Gas |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J164 | [5 empty] | NRIS |  | 99 |  | Wind | Erie County | OH | [27 empty] | Withdrawn | 2010-09-10 | 2011-06-01 | 2011-06-01 |  | FirstEnergy Solutions Corp. | Erie County | OH |  |  | Feasibility | NRIS | FE Beaver - Greenfield 138kV | 99 | 99 | Wind | WT Wind Turbine | Not Started | 2014-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J165 | [5 empty] | NRIS |  | 97.6 |  | Wind | Fulton County | OH | [27 empty] | Withdrawn | 2010-09-10 | 2011-06-01 | 2011-06-01 |  | FirstEnergy Solutions Corp. | Fulton County | OH |  |  | Feasibility | NRIS | FE Allen Junction - Lyons 138kV | 97.6 | 97.6 | Wind | WT Wind Turbine | Not Started | 2012-01-06 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | MI | Done | In Service | G889 | [5 empty] | NRIS |  | 59.4 |  | Wind | Huron County | MI | [27 empty] | Done | 2007-10-18 |  | 2012-07-05 | 2012-09-17 | ITC Transmission | Huron County | MI | DPP-2008-NOV | MI | Network Upgrade | NRIS | ITC Cosmo Tap (Bad Axe - Arrowhead) 120 kV | 59.4 | 59.4 | Wind | WT Wind Turbine | In Service | 2008-02-28 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J172 | [5 empty] | NRIS |  | 3.2 |  | Landfill Gas | Mahoning County | OH | [27 empty] | Withdrawn | 2010-11-02 | 2011-06-01 | 2011-06-01 |  | FirstEnergy Solutions Corp. | Mahoning County | OH |  |  | Feasibility | NRIS | ATSI Loweville 69kV | 3.2 | 3.2 | Landfill Gas | CT Combustion Turbine (Simple Cycle) | Not Started | 2012-08-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J173 | [5 empty] | NRIS |  | 19.2 |  | Landfill Gas | Lorain County | OH | [27 empty] | Withdrawn | 2010-11-12 | 2011-06-01 | 2011-06-01 |  | FirstEnergy Solutions Corp. | Lorain County | OH |  |  | Feasibility | NRIS | Oberlin Road 69 kV | 19.2 | 19.2 | Landfill Gas | CT Combined-Cycle Combustion ? Turbine Part | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J181 | [5 empty] | ERIS |  | 29.8 |  | Nuclear | Lake County | OH | [27 empty] | Withdrawn | 2010-11-15 | 2011-06-01 | 2011-06-01 |  | FirstEnergy Solutions Corp. | Lake County | OH |  |  | Feasibility | ERIS | Perry 345kV Substation | 16 | 29.8 | Nuclear | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | FeS-2011-APR | 0 | Withdrawn | Not Started | J208 | [5 empty] | NRIS |  | 500 |  | Wind | Huron County | OH | [27 empty] | Withdrawn | 2011-03-03 | 2011-06-01 | 2011-06-01 |  | FirstEnergy Solutions Corp. | Huron County | OH | FeS-2011-APR |  | Feasibility | NRIS | FE Davis Besse - Beaver 345 kV | 500 | 500 | Wind | WT Wind Turbine | Not Started | 2014-12-31 | 0 | 0 | 0 | 0
|  |  |  | FeS-2011-APR | 0 | Withdrawn | Not Started | J211 | [5 empty] | ERIS |  | 268 |  | Gas | Summit County | OH | [27 empty] | Withdrawn | 2011-04-11 | 2011-06-01 | 2011-06-01 |  | FirstEnergy Solutions Corp. | Summit County | OH | FeS-2011-APR |  | Feasibility | ERIS | FE Martin 69 kV Substation | 268 | 268 | Gas | CT Combustion Turbine (Simple Cycle) | Not Started | 2013-06-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-NOV | 0 | Withdrawn | Not Started | G979 | [5 empty] | NRIS |  | 100 |  | Wind | Edgar County | IL | [27 empty] | Withdrawn | 2009-03-06 | 2011-06-07 | 2011-06-07 |  | Ameren Illinois | Edgar County | IL | DPP-2009-NOV |  | DPP - SIS | NRIS | Sydney - Kansas 345 kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2010-08-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-NOV | 0 | Withdrawn | Not Started | H006 | [5 empty] | NRIS |  | 100 |  | Wind | Douglas County | IL | [27 empty] | Withdrawn | 2008-04-16 | 2011-06-07 | 2011-06-07 |  | Ameren Illinois | Douglas County | IL | DPP-2009-NOV |  | DPP - SIS | NRIS | Sydney - Kansas 345 kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2012-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J162 | [5 empty] | NRIS |  | 270 |  | Gas | Dallas County | IA | [27 empty] | Withdrawn | 2010-09-02 | 2011-08-01 | 2011-08-01 |  | MidAmerican Energy Company | Dallas County | IA |  |  | SPA - SIS | NRIS | Grimes 161 kV substation | 270 | 270 | Gas | Compressed Air Energy Storage | Not Started | 2012-04-01 | 0 | 0 | 0 | 0
|  |  |  | FeS-2011-FEB | 0 | Withdrawn | Not Started | J194 | [5 empty] | NRIS |  | 300 |  | Wind | Manistee County | MI | [27 empty] | Withdrawn | 2011-02-04 | 2011-08-03 | 2011-08-03 |  | Michigan Electric Transmission Company, LLC | Manistee County | MI | FeS-2011-FEB |  | Feasibility | NRIS | Keystone - Ludington 345kV | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2012-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-NOV | 0 | Withdrawn | Not Started | J071 | [5 empty] | NRIS |  | 112 |  | Hydro | Bracken County | KY | [27 empty] | Withdrawn | 2009-09-30 | 2011-08-11 | 2011-08-11 |  | DEO&K | Bracken County | KY | DPP-2009-NOV |  | DPP - SIS | NRIS | DEM Zimmer - Silver Grove 345 kV | 112 | 112 | Hydro |  | Not Started | 2010-04-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J152 | [5 empty] | ERIS |  | 5.9 |  | Biomass | White County | IN | [27 empty] | Withdrawn | 2010-06-28 | 2011-08-15 | 2011-08-15 |  | Northern Indiana Public Service Company | White County | IN |  |  | Feasibility | ERIS | NIPSCO Monticello - Honey Creek 69kV | 5.9 | 5.9 | Biomass |  | Not Started | 2010-04-30 | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | CS5 | Withdrawn | Not Started | G608 | [5 empty] | ERIS |  | 6 |  | Wind | Pope County | MN | [27 empty] | Withdrawn | 2006-03-02 | 2011-08-18 | 2011-08-18 |  | Northern States Power (Xcel Energy) | Pope County | MN | Pre-Transition SIS | CS5 | DPP - SIS | ERIS | GRE Lake Johanna - Brooten 69 kV | 6 | 6 | Wind | WT Wind Turbine | Not Started | 2006-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J116 | [5 empty] | ERIS |  | 999 |  | Wind | Hancock County | IA | [27 empty] | Withdrawn | 2010-02-16 | 2011-08-18 | 2011-08-18 |  | Madison Gas and Electric Company | Hancock County | IA |  |  | SPA - SIS | ERIS | West Middleton 345 kV Substation | 999 | 999 | Wind | WT Wind Turbine | Not Started | 2013-08-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G903 | [5 empty] | ERIS |  | 2000 |  | Wind | Wright County | MN | [27 empty] | Withdrawn | 2007-10-31 | 2011-08-22 | 2011-08-22 |  | Northern States Power (Xcel Energy) | Wright County | MN |  |  | SPA - SIS | ERIS | Xel Crow River Substation | 2000 | 2000 | Wind | WT Wind Turbine | Not Started | 2010-12-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-JUL | MI | Done | In Service | G905 | [5 empty] | NRIS |  | 200 |  | Wind | Gratiot County | MI | [27 empty] | Done | 2009-02-23 |  | 2011-02-22 | 2012-04-27 | Michigan Electric Transmission Company, LLC | Gratiot County | MI | DPP-2009-JUL | MI | Network Upgrade | NRIS | Begole - Tittabawassee 138kV | 200 | 200 | Wind | WT Wind Turbine | In Service | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J179 | [5 empty] | NRIS |  | 47.5 |  | Wind | Goodhue County | MN | [27 empty] | Withdrawn | 2010-11-15 | 2011-08-30 | 2011-08-30 |  | Northern States Power (Xcel Energy) | Goodhue County | MN |  |  | SPA - SIS | NRIS | Xcel Goodhue 69kV Substation | 47.5 | 47.5 | Wind | WT Wind Turbine | Not Started | 2012-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J180 | [5 empty] | NRIS |  | 39 |  | Wind | Goodhue County | MN | [27 empty] | Withdrawn | 2010-11-15 | 2011-08-30 | 2011-08-30 |  | Northern States Power (Xcel Energy) | Goodhue County | MN |  |  | SPA - SIS | NRIS | Xcel Goodhue 69kV Substation | 39 | 39 | Wind | WT Wind Turbine | Not Started | 2012-11-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J204 | [5 empty] | NRIS |  | 200 |  | Wind | Calhoun County | MI | [27 empty] | Withdrawn | 2011-02-17 | 2011-08-30 | 2011-08-30 |  | Michigan Electric Transmission Company, LLC | Calhoun County | MI |  |  | SPA - SIS | NRIS | ITC Rice Creek - Denso 138 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2012-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J175 | [5 empty] | ERIS |  | 30 |  | Biomass | St. Louis County | MN | [27 empty] | Withdrawn | 2010-11-15 | 2011-09-09 | 2011-09-09 |  | Minnesota Power (Allete, Inc.) | St. Louis County | MN |  |  | SPA - SIS | ERIS | MP Virginia 115kV Substation | 30 | 30 | Biomass |  | Not Started | 2011-01-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G742 | [5 empty] | NRIS |  | 120 |  | Wind | Missaukee County | MI | [27 empty] | Withdrawn | 2010-06-17 | 2011-09-14 | 2011-09-14 |  | Michigan Electric Transmission Company, LLC | Missaukee County | MI |  |  | Feasibility | NRIS | METC Wexford - Keystone 138kV | 120 | 120 | Wind | WT Wind Turbine | Not Started | 2009-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H031 | [5 empty] | NRIS |  | 160 |  | Wind | Wilkin County | MN | [27 empty] | Withdrawn | 2008-05-20 | 2011-09-19 | 2011-09-19 |  | Otter Tail Power Company | Wilkin County | MN |  |  | SPA - SIS | NRIS | OTP Fergus Fall - Wahpeton 230 kV | 160 | 160 | Wind | WT Wind Turbine | Not Started | 2012-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J048 | [5 empty] | NRIS |  | 140 |  | Wind | Nelson County | ND | [27 empty] | Withdrawn | 2009-05-18 | 2011-09-19 | 2011-09-19 |  | Great River Energy | Nelson County | ND |  |  | SPA - SIS | NRIS | GRE Ramsey - Prairie 230 kV | 140 | 140 | Wind | WT Wind Turbine | Not Started | 2008-11-11 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J080 | [5 empty] | NRIS |  | 0 |  | Wind | Brookings County | SD | [27 empty] | Withdrawn | 2009-10-05 | 2011-09-19 | 2011-09-19 |  | Northern States Power (Xcel Energy) | Brookings County | SD |  |  | SPA - SIS | NRIS | Brookings County 345 kV substation | 200 | 0 | Wind | WT Wind Turbine | Not Started | 2011-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J081 | [5 empty] | NRIS |  | 200 |  | Wind | Mercer County | ND | [27 empty] | Withdrawn | 2009-10-05 | 2011-09-19 | 2011-09-19 |  | Montana-Dakota Utilities Company | Mercer County | ND |  |  | SPA - SIS | NRIS | Coyote - Green River 100-161 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2011-03-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J082 | [5 empty] | NRIS |  | 100 |  | Wind | Mercer County | ND | [27 empty] | Withdrawn | 2009-10-05 | 2011-09-19 | 2011-09-19 |  | Montana-Dakota Utilities Company | Mercer County | ND |  |  | SPA - SIS | NRIS | Coyote - Green River 100-161 kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2013-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G959 | [5 empty] | NRIS |  | 200 |  | Wind | Goodhue County | MN | [27 empty] | Withdrawn | 2011-04-12 | 2011-09-20 | 2011-09-20 |  | Northern States Power (Xcel Energy) | Goodhue County | MN |  |  | SPA - SIS | NRIS | Twin Cities - LaCrosse 345 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2010-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G960 | [5 empty] | NRIS |  | 200 |  | Wind | Goodhue County | MN | [27 empty] | Withdrawn | 2011-04-12 | 2011-09-20 | 2011-09-20 |  | Northern States Power (Xcel Energy) | Goodhue County | MN |  |  | SPA - SIS | NRIS | Twin Cities - LaCross 345kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G920 | [5 empty] | NRIS |  | -15 |  | Coal | Saint Charles County | MO | [27 empty] | Done | 2007-11-29 |  | 2008-05-30 |  | Ameren Missouri | Saint Charles County | MO |  |  |  | NRIS | Sioux - Maline 138kV | -15 | -15 | Coal | Combined Cycle | In Service | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G921 | [5 empty] | NRIS |  | 0 |  | Coal | Montgomery County | IL | [27 empty] | Done | 2007-11-29 |  | 2008-07-03 |  | Ameren Illinois | Montgomery County | IL |  |  |  | NRIS | Ameren Coffeen Plant 345 kV | 0 | 0 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | In Service | 2010-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G961 | [5 empty] | NRIS |  | 200 |  | Wind | Goodhue County | MN | [27 empty] | Withdrawn | 2011-04-12 | 2011-09-20 | 2011-09-20 |  | Northern States Power (Xcel Energy) | Goodhue County | MN |  |  | SPA - SIS | NRIS | Twin Cities - LaCrosse 345kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2012-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H025 | [5 empty] | NRIS |  | 200 |  | Wind | Minnehaha County | SD | [27 empty] | Withdrawn | 2011-04-28 | 2011-09-20 | 2011-09-20 |  | Northern States Power (Xcel Energy) | Minnehaha County | SD |  |  | SPA - SIS | NRIS | Anson Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G670 | [5 empty] | NRIS |  | 200 |  | Wind | Faribault County | MN | [27 empty] | Withdrawn | 2010-10-28 | 2011-10-04 | 2011-10-04 |  | ITC Midwest | Faribault County | MN |  |  | SPA - SIS | NRIS | Winnebago - Hayward 161 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2011-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-JUL | MN | Withdrawn | Not Started | G852 | [5 empty] | NRIS |  | 300 |  | Wind | Dodge County | MN | [27 empty] | Withdrawn | 2007-08-27 | 2011-10-10 | 2011-10-10 |  | Northern States Power (Xcel Energy) | Dodge County | MN | DPP-2009-JUL | MN | DPP - SIS | NRIS | Pleasant Valley - Byron 161 kV | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2012-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Withdrawn | G927 | [5 empty] | NRIS |  | 2 |  | Wind | Calumet County | WI | [27 empty] | Done | 2007-12-07 |  | 2008-09-11 |  | Wisconsin Electric Power Company | Calumet County | WI |  |  | SPA - SIS | NRIS | Forest Junction - Elkhart Lake 138kV | 2 | 2 | Wind | WT Wind Turbine | Withdrawn | 2014-10-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G929 | [5 empty] | NRIS |  | 60.8 |  | Nuclear | Wright County | MN | [27 empty] | Done | 2007-12-10 |  | 2009-10-06 | 2013-12-01 | Northern States Power (Xcel Energy) | Wright County | MN |  |  | Feasibility | NRIS | Monticello Substation | 60.8 | 60.8 | Nuclear | ST Steam Turbine (including nuclear, geothermal and solar steam, | In Service | 2010-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-MAR | MN | Done | In Service | G930 | [5 empty] | NRIS |  | 60 |  | Coal | Sherburne County | MN | [27 empty] | Done | 2007-12-10 |  | 2010-04-26 | 2013-04-01 | Northern States Power (Xcel Energy) | Sherburne County | MN | DPP-2009-MAR | MN | DPP - SIS | NRIS | Sherco Substation | 60 | 60 | Coal | Combined Cycle | In Service | 2009-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G931 | [5 empty] | NRIS |  | 150 |  | Wind | Iroquois County | IL | [27 empty] | Done | 2007-12-11 |  | 2010-02-08 | 2011-06-30 | Ameren Illinois | Iroquois County | IL |  |  | Optional | NRIS | Watseka - Goodland 138kV | 150 | 150 | Wind | WT Wind Turbine | In Service | 2009-03-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H042 | [5 empty] | NRIS |  | 50 |  | Wind | Waseca County | MN | [27 empty] | Withdrawn | 2008-06-12 | 2011-10-12 | 2011-10-12 |  | Great River Energy | Waseca County | MN |  |  | SPA - SIS | NRIS | St. Olaf Lake 69 kV 3 way junction | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2012-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-AUG | East (ITC) | Done | In Service | G934 | [5 empty] | NRIS |  | 150 |  | Wind | Gratiot County | MI | [27 empty] | Done | 2012-01-24 |  | 2017-07-24 | 2010-10-01 | Michigan Electric Transmission Company, LLC | Gratiot County | MI | DPP-2015-AUG | East (ITC) | DPP - SIS | NRIS | METC Nelson Road 345kV substation | 150 | 150 | Wind | WT Wind Turbine | In Service | 2020-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H045 | [5 empty] | NRIS |  | 50 |  | Wind | Cottonwood County | MN | [27 empty] | Withdrawn | 2008-06-12 | 2011-10-12 | 2011-10-12 |  | ITC Midwest | Cottonwood County | MN |  |  | SPA - SIS | NRIS | ITC Midwest Mountain Lake 69 kV Substation | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H052 | [5 empty] | NRIS |  | 50 |  | Wind | Brown County | MN | [27 empty] | Withdrawn | 2008-06-12 | 2011-10-12 | 2011-10-12 |  | Great River Energy | Brown County | MN |  |  | SPA - SIS | NRIS | Dotson, MN 69 kV substation | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G938 | [5 empty] | NRIS |  | 1 |  | Hydro | Newaygo County | MI | [27 empty] | Done | 2007-12-20 |  | 2008-07-24 |  | Michigan Electric Transmission Company, LLC | Newaygo County | MI |  |  |  | NRIS | Hardy - Croton 138kV | 1 | 1 | Hydro | HY Hydraulic Turbine (including turnbines associated with delivery of water by pipeline) | In Service | 2010-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H055 | [5 empty] | NRIS |  | 40 |  | Wind | Redwood County | MN | [27 empty] | Withdrawn | 2008-06-12 | 2011-10-12 | 2011-10-12 |  | Northern States Power (Xcel Energy) | Redwood County | MN |  |  | SPA - SIS | NRIS | Sheridan 69 kV Substation | 40 | 40 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J001 | [5 empty] | ERIS |  | 150 |  | Wind | Clay County | MN | [27 empty] | Withdrawn | 2008-10-17 | 2011-10-12 | 2011-10-12 |  | Otter Tail Power Company | Clay County | MN |  |  | SPA - SIS | ERIS | Sheyenne - Audubon 230 kV | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2002-06-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | Individual | Done | In Service | G941 | [5 empty] | NRIS |  | 67 |  | Waste Heat Recovery | Butler County | OH | [27 empty] | Done | 2007-12-26 |  | 2009-04-21 | 2011-03-01 | DEO&K | Butler County | OH | DPP-2008-NOV | Individual | Network Upgrade | NRIS | Todhunter 69 kV | 67 | 67 | Waste Heat Recovery | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | In Service | 2012-06-01 | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | CS5 | Withdrawn | Not Started | G618 | [5 empty] | NRIS |  | 138 |  | Wind | Yellow Medicine County | MN | [27 empty] | Withdrawn | 2006-04-11 | 2011-10-24 | 2011-10-24 |  | Otter Tail Power Company | Yellow Medicine County | MN | Pre-Transition SIS | CS5 | DPP - SIS | NRIS | Burr Jct - Toronto 115 kV | 138 | 138 | Wind | WT Wind Turbine | Not Started | 2008-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-APR | MT-ND | Withdrawn | Not Started | G690 | [5 empty] | NRIS |  | 200 |  | Wind | Dickey County | ND | [27 empty] | Withdrawn | 2006-10-16 | 2011-11-01 | 2011-11-01 |  | Montana-Dakota Utilities Company | Dickey County | ND | DPP-2010-APR | MT-ND | DPP - SIS | NRIS | Tatakana 230 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2010-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | R52 | [5 empty] | 0 |  | 500 |  | Wind | Adair County | IA | [27 empty] | Withdrawn | 2008-03-18 | 2011-11-01 | 2011-11-01 |  | MidAmerican Energy Company | Adair County | IA |  |  | DPP - SIS |  | MEC Council Bluffs - Madison 345 kV | 500 | 500 | Wind | WT Wind Turbine | Not Started | 2010-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | WEST | Done | In Service | G947 | [5 empty] | NRIS |  | 99 |  | Wind | Franklin County | IA | [27 empty] | Done | 2008-01-14 |  | 2015-04-01 | 2012-12-15 | ITC Midwest | Franklin County | IA | DPP-2012-AUG | WEST | Network Upgrade | NRIS | ITCM Whispering Wilows 161kV Substation | 99 | 99 | Wind | WT Wind Turbine | In Service | 2011-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | R53 | [5 empty] | 0 |  | 200 |  | Wind | Adair County | IA | [27 empty] | Withdrawn | 2008-03-18 | 2011-11-01 | 2011-11-01 |  | MidAmerican Energy Company | Adair County | IA |  |  | DPP - SIS |  | Atlantic - Earlham 161 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2010-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-APR | Indiana | Withdrawn | Not Started | H027 | [5 empty] | NRIS |  | 200 |  | Wind | Boone County | IN | [27 empty] | Withdrawn | 2008-05-14 | 2011-11-03 | 2011-11-03 |  | Duke Energy Corporation | Boone County | IN | DPP-2010-APR | Indiana | DPP - SIS | NRIS | Cayuga - Nucor 345 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2012-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G757 | [5 empty] | NRIS |  | 200 |  | Wind | Adams County | ND | [27 empty] | Withdrawn | 2011-05-03 | 2011-11-15 | 2011-11-15 |  | Montana-Dakota Utilities Company | Adams County | ND |  |  | SPA - SIS | NRIS | Gascoyne Generating Station Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2009-06-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-APR | MT-ND | Withdrawn | Not Started | G981 | [5 empty] | ERIS |  | 19.5 |  | Wind | Grant County | ND | [27 empty] | Withdrawn | 2008-03-10 | 2011-11-15 | 2011-11-15 |  | Montana-Dakota Utilities Company | Grant County | ND | DPP-2010-APR | MT-ND | DPP - SIS | ERIS | New IC owned sbstn tapping into a 69kV MDU line at N46? 19' 8" / W101? 54' 45" | 19.5 | 19.5 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-APR | MT-ND | Withdrawn | Not Started | G994 | [5 empty] | ERIS |  | 19.5 |  | Wind | Wibaux County | MT | [27 empty] | Withdrawn | 2008-03-31 | 2011-11-15 | 2011-11-15 |  | Montana-Dakota Utilities Company | Wibaux County | MT | DPP-2010-APR | MT-ND | DPP - SIS | ERIS | Proposed new 57kV wind farm substation at N47 0 05/W 104 14 22 | 19.5 | 19.5 | Wind | WT Wind Turbine | Not Started | 2008-04-13 | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | CIGS | Withdrawn | Not Started | G432 | [5 empty] | NRIS |  | 65 |  | Wind | Ford County | IL | [27 empty] | Withdrawn | 2004-06-17 | 2011-11-16 | 2011-11-16 |  | Ameren Illinois | Ford County | IL | Pre-Transition SIS | CIGS | SPA - SIS | NRIS | Gibson City | 65 | 65 | Wind | WT Wind Turbine | Not Started | 2005-12-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-Aug | ND | Withdrawn | Not Started | G624 | [5 empty] | NRIS |  | 150 |  | Wind | McIntosh County | ND | [27 empty] | Withdrawn | 2006-04-25 | 2011-11-21 | 2011-11-21 |  | Montana-Dakota Utilities Company | McIntosh County | ND | DPP-2010-Aug | ND | SPA - SIS | NRIS | Wishek Substation 115 kV | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2007-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J205 | [5 empty] | ERIS |  | 200 |  | Wind | Montgomery County | IL | [27 empty] | Withdrawn | 2011-02-17 | 2011-11-21 | 2011-11-21 |  | Ameren Illinois | Montgomery County | IL |  |  | Feasibility | ERIS | Pana - Midway 138kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2012-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J195 | [5 empty] | NRIS |  | 200 |  | Wind | Shiawassee County | MI | [27 empty] | Withdrawn | 2011-02-04 | 2011-11-28 | 2011-11-28 |  | Michigan Electric Transmission Company, LLC | Shiawassee County | MI |  |  | SPA - SIS | NRIS | Bell Road - North Corunna 138 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2012-08-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H097 | [5 empty] | NRIS |  | 120.6 |  | Wind | Boone County | IA | [27 empty] | Withdrawn | 2008-08-04 | 2011-12-01 | 2011-12-01 |  | ITC Midwest | Boone County | IA |  |  | Optional | NRIS | NE Ankeny - Perry 161kV | 120.6 | 120.6 | Wind | WT Wind Turbine | Not Started | 2011-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G908 | [5 empty] | NRIS |  | 150 |  | Wind | Morgan County | IL | [27 empty] | Withdrawn | 2009-03-23 | 2011-12-29 | 2011-12-29 |  | Ameren Illinois | Morgan County | IL |  |  | SPA - SIS | NRIS | Havana - E Springfield 138 kV | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2009-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G909 | [5 empty] | NRIS |  | 150 |  | Wind | Cass County | IL | [27 empty] | Withdrawn | 2009-03-23 | 2011-12-29 | 2011-12-29 |  | Ameren Illinois | Cass County | IL |  |  | SPA - SIS | NRIS | Jacksonville - Auburn 138kV | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2011-10-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | MN | Withdrawn | Not Started | G789 | [5 empty] | ERIS |  | 20 |  | Wind | Pope County | MN | [27 empty] | Withdrawn | 2007-04-25 | 2011-12-30 | 2011-12-30 |  | Northern States Power (Xcel Energy) | Pope County | MN | DPP-2008-NOV | MN | Network Upgrade | ERIS | T-126-N, R-36-W | 20 | 20 | Wind | WT Wind Turbine | Not Started | 2010-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-AUG | MI | Withdrawn | Not Started | J149 | [5 empty] | NRIS |  | 13.64 |  | Landfill Gas | Wayne County | MI | [27 empty] | Withdrawn | 2010-06-28 | 2011-12-30 | 2011-12-30 | 2012-06-30 | Michigan Electric Transmission Company, LLC | Wayne County | MI | DPP-2010-AUG | MI | Network Upgrade | NRIS | Visteon 120 kV | 13.64 | 13.64 | Landfill Gas |  | Not Started | 2013-09-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-AUG | 0 | Withdrawn | Not Started | J120 | [5 empty] | NRIS |  | 134.5 |  | Combined Cycle | Butler County | OH | [27 empty] | Withdrawn | 2010-03-23 | 2011-12-31 | 2011-12-31 |  | DEO&K | Butler County | OH | DPP-2010-AUG |  | Network Upgrade | NRIS | AK Steel Middletown - AK Steel 1C Substation 138kV | 128 | 134.5 | Combined Cycle |  | Not Started | 2010-07-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G599 | [5 empty] | NRIS |  | 144 |  | Wind | Adams County | IL | [27 empty] | Withdrawn | 2006-02-15 | 2012-01-04 | 2012-01-04 | 2013-12-31 | Ameren Illinois | Adams County | IL |  |  | Network Upgrade | NRIS | S. Quincy - Meredosia 120 kV | 144 | 144 | Wind | WT Wind Turbine | Not Started | 2014-01-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-APR | MT-ND | Withdrawn | Not Started | G622 | [5 empty] | ERIS |  | 148.8 |  | Wind | Dickey County | ND | [27 empty] | Withdrawn | 2006-04-20 | 2012-01-26 | 2012-01-26 |  | Montana-Dakota Utilities Company | Dickey County | ND | DPP-2010-APR | MT-ND | DPP - SIS | ERIS | MDU Ellendale - Wishek 230 kV | 148.8 | 148.8 | Wind | WT Wind Turbine | Not Started | 2007-04-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | MI | Withdrawn | Not Started | G820 | [5 empty] | NRIS |  | 600 |  | Coal | Presque Isle County | MI | [27 empty] | Withdrawn | 2007-07-16 | 2012-01-26 | 2012-01-26 |  | Michigan Electric Transmission Company, LLC | Presque Isle County | MI | DPP-2008-NOV | MI | Network Upgrade | NRIS | Port Calcite - Rockport 138kV | 600 | 600 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | Not Started | 2010-05-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-APR | MT-ND | Withdrawn | Not Started | G988 | [5 empty] | ERIS |  | 200 |  | Wind | McIntosh County | ND | [27 empty] | Withdrawn | 2008-03-18 | 2012-01-30 | 2012-01-30 |  | Montana-Dakota Utilities Company | McIntosh County | ND | DPP-2010-APR | MT-ND | Optional | ERIS | MDU Wishek - Tatakana 230 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2009-12-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-MAR | Individual | Done | Withdrawn | G967 | [5 empty] | NRIS |  | 101 |  | Wind | Newton County | IN | [27 empty] | Done | 2008-01-30 |  | 2010-11-22 | 2014-12-31 | Northern Indiana Public Service Company | Newton County | IN | DPP-2009-MAR | Individual | Network Upgrade | NRIS | Thayer - Schahfer 138 kV | 101 | 101 | Wind | WT Wind Turbine | Withdrawn | 2010-09-30 | 0 | 0 | 0 | 0
|  |  |  | DPP-2011-JUN | MI | Withdrawn | Not Started | J197 | [5 empty] | NRIS |  | 124.8 |  | Wind | Lenawee County | MI | [27 empty] | Withdrawn | 2011-02-07 | 2012-02-02 | 2012-02-02 |  | Michigan Electric Transmission Company, LLC | Lenawee County | MI | DPP-2011-JUN | MI | DPP - SIS | NRIS | METC Moore Rd - Beecher 138 kV | 124.8 | 124.8 | Wind | WT Wind Turbine | Not Started | 2013-12-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G763 | [5 empty] | ERIS |  | 50 |  | Wind | Minnehaha County | SD | [27 empty] | Withdrawn | 2007-03-15 | 2012-02-03 | 2012-02-03 |  | Northern States Power (Xcel Energy) | Minnehaha County | SD |  |  | SPA - SIS | ERIS | Anson 115 kV station | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2008-09-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J178 | [5 empty] | NRIS |  | 99.6 |  | Wind | Burleigh County | ND | [27 empty] | Withdrawn | 2010-11-15 | 2012-02-07 | 2012-02-07 |  | Montana-Dakota Utilities Company | Burleigh County | ND |  |  | SPA - SIS | NRIS | MDU Bismarck - Linton 115kV | 99.6 | 99.6 | Wind | WT Wind Turbine | Not Started | 2012-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-MAR | MN | Done | In Service | G971 | [5 empty] | ERIS |  | 20 |  | Wind | Meeker County | MN | [27 empty] | Done | 2008-02-13 |  | 2010-09-16 | 2010-12-31 | Northern States Power (Xcel Energy) | Meeker County | MN | DPP-2009-MAR | MN | Network Upgrade | ERIS | 69 kV line in SE 1/4 of Sec 17 in Cosmos Twp | 20 | 20 | Wind | WT Wind Turbine | In Service | 2009-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J223 | [5 empty] | ERIS |  | 30 |  | Wind | Mower County | MN | [27 empty] | Withdrawn | 2011-08-22 | 2012-02-07 | 2012-02-07 |  | SMMPA | Mower County | MN |  |  | Feasibility | ERIS | Austin Northeast Plant 69kV | 30 | 30 | Wind | WT Wind Turbine | Not Started | 2012-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J198 | [5 empty] | NRIS |  | 99 |  | Wind | Lyon County | MN | [27 empty] | Withdrawn | 2011-02-07 | 2012-02-08 | 2012-02-08 |  | Northern States Power (Xcel Energy) | Lyon County | MN |  |  | Feasibility | NRIS | Buffalo Ridge - Lake Yankton 115kV | 99 | 99 | Wind | WT Wind Turbine | Not Started | 2012-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J237 | [5 empty] | NRIS |  | 642 |  | Coal | Henderson County | KY | [27 empty] | Withdrawn | 2007-07-20 | 2012-02-13 | 2012-02-13 |  | Big Rivers Electric Corporation | Henderson County | KY |  |  | DPP - SIS | NRIS | Reid 345 kV Substation | 564 | 642 | Coal | CT Combined-Cycle Combustion ? Turbine Part | Not Started | 2013-06-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G963 | [5 empty] | NRIS |  | 200 |  | Wind | Mitchell County | IA | [27 empty] | Withdrawn | 2008-01-29 | 2012-02-15 | 2012-02-15 |  | ITC Midwest | Mitchell County | IA |  |  | SPA - SIS | NRIS | Mitchell County Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2012-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H028 | [5 empty] | NRIS |  | 299 |  | Wind | Olmsted County | MN | [27 empty] | Withdrawn | 2008-05-15 | 2012-02-15 | 2012-02-15 |  | Northern States Power (Xcel Energy) | Olmsted County | MN |  |  | SPA - SIS | NRIS | Eyota Twp, MN, Section 106, Range 12 | 299 | 299 | Wind | WT Wind Turbine | Not Started | 2013-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J009 | [5 empty] | NRIS |  | 250 |  | Wind | Clinton County | IA | [27 empty] | Withdrawn | 2008-12-18 | 2012-02-15 | 2012-02-15 |  | ITC Midwest | Clinton County | IA |  |  | SPA - SIS | NRIS | Rock Creek - Salem 345 kV | 250 | 250 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J072 | [5 empty] | NRIS |  | 200.1 |  | Wind | O'Brien County | IA | [27 empty] | Withdrawn | 2009-10-02 | 2012-02-15 | 2012-02-15 |  | ITC Midwest | O'Brien County | IA |  |  | SPA - SIS | NRIS | ITC Midwest Lakefield Junction - Raun 345 kV | 200.1 | 200.1 | Wind | WT Wind Turbine | Not Started | 2012-09-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J100 | [5 empty] | NRIS |  | 300 |  | Wind | Henry County | IL | [27 empty] | Withdrawn | 2009-12-04 | 2012-02-15 | 2012-02-15 |  | MidAmerican Energy Company | Henry County | IL |  |  | SPA - SIS | NRIS | MEC Barstow - Louisa 345 kV | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2012-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J101 | [5 empty] | NRIS |  | 300 |  | Wind | Henry County | IL | [27 empty] | Withdrawn | 2009-12-04 | 2012-02-15 | 2012-02-15 |  | MidAmerican Energy Company | Henry County | IL |  |  | SPA - SIS | NRIS | MEC Barstow - Louisa 345 kV | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2011-08-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J103 | [5 empty] | NRIS |  | 20 |  | Wind | Story County | IA | [27 empty] | Withdrawn | 2009-12-15 | 2012-02-15 | 2012-02-15 |  | ITC Midwest | Story County | IA |  |  | SPA - SIS | NRIS | ITC 161 kV Story County Energy Center | 20 | 20 | Wind | WT Wind Turbine | Not Started | 2014-09-30 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | IL | Done | In Service | G983 | [5 empty] | NRIS |  | 42 |  | Coal | Jasper County | IL | [27 empty] | Done | 2008-03-17 |  | 2009-12-22 | 2010-12-31 | Ameren Illinois | Jasper County | IL | DPP-2008-NOV | IL | Network Upgrade | NRIS | AEG Newton Unit 2 345kV | 42 | 42 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | In Service | 2010-07-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | IL | Done | Retired | G984 | [5 empty] | NRIS |  | 42 |  | Coal | Jasper County | IL | [27 empty] | Done | 2008-03-17 |  | 2009-12-22 | 2015-03-30 | Ameren Illinois | Jasper County | IL | DPP-2008-NOV | IL | Network Upgrade | NRIS | AEG Newton Unit 1 345kV | 42 | 42 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | Retired | 2011-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J108 | [5 empty] | NRIS |  | 165 |  | Wind | Ford County | IL | [27 empty] | Withdrawn | 2009-12-21 | 2012-02-15 | 2012-02-15 |  | Ameren Illinois | Ford County | IL |  |  | SPA - SIS | NRIS | Paxton East 138kV Substation | 165 | 165 | Wind | WT Wind Turbine | Not Started | 2010-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J113 | [5 empty] | ERIS |  | 100.5 |  | Wind | Atchison County | MO | [27 empty] | Withdrawn | 2010-02-11 | 2012-02-15 | 2012-02-15 |  | MidAmerican Energy Company | Atchison County | MO |  |  | SPA - SIS | ERIS | MEC Cooper - Atchison 345 kV | 100.5 | 100.5 | Wind | WT Wind Turbine | Not Started | 2012-06-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J114 | [5 empty] | NRIS |  | 150 |  | Wind | Tama County | IA | [27 empty] | Withdrawn | 2010-02-11 | 2012-02-15 | 2012-02-15 |  | ITC Midwest | Tama County | IA |  |  | SPA - SIS | NRIS | ITC Midwest Traer Substation | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2011-06-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | R61 | [5 empty] | NRIS |  | 200 |  | Wind | Greene County | IA | [27 empty] | Withdrawn | 2009-04-08 | 2012-02-15 | 2012-02-15 |  | MidAmerican Energy Company | Greene County | IA |  |  | SPA - SIS | NRIS | Carroll-Grand Junction 161 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2010-06-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G989 | [5 empty] | NRIS |  | 330 |  | Coal | Clermont County | OH | [27 empty] | Done | 2008-03-21 |  | 2008-06-02 |  | DEO&K | Clermont County | OH |  |  | SPA - SIS | NRIS | Zimmer 345 kV Station | 330 | 330 | Coal | Combined Cycle | In Service | 2010-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | G990 | [5 empty] | NRIS |  | 52 |  | Coal | Clermont County | OH | [27 empty] | Done | 2008-03-21 |  | 2008-06-02 |  | DEO&K | Clermont County | OH |  |  | SPA - SIS | NRIS | Pierce 345 kV Substation | 52 | 52 | Coal | Combined Cycle | In Service | 2011-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | R63 | [5 empty] | NRIS |  | 300 |  | Wind | Calhoun County | IA | [27 empty] | Withdrawn | 2009-04-08 | 2012-02-15 | 2012-02-15 |  | MidAmerican Energy Company | Calhoun County | IA |  |  | SPA - SIS | NRIS | Raun - Lehigh 345 kV | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H033 | [5 empty] | NRIS |  | 300 |  | Wind | Kandiyohi County | MN | [27 empty] | Withdrawn | 2008-05-21 | 2012-02-22 | 2012-02-22 |  | Northern States Power (Xcel Energy) | Kandiyohi County | MN |  |  | SPA - SIS | NRIS | Wilmar - Paynesville 230 kV | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2011-12-01 | 0 | 0 | 0 | 0
|  |  |  | FeS-2011-APR | 0 | Withdrawn | Not Started | J210 | [5 empty] | ERIS |  | 20 |  | Solar | Butler County | OH | [27 empty] | Withdrawn | 2011-04-05 | 2012-02-22 | 2012-02-22 |  | DEO&K | Butler County | OH | FeS-2011-APR |  | Feasibility | ERIS | Todd Hunter 69 kV Substation | 20 | 20 | Solar | PV Photovoltaic | Not Started | 2013-10-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J218 | [5 empty] | NRIS |  | 150 |  | Wind | Adams County | ND | [27 empty] | Withdrawn | 2011-06-27 | 2012-03-02 | 2012-03-02 |  | Montana-Dakota Utilities Company | Adams County | ND |  |  | SPA - SIS | NRIS | Hettinger 230kV | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2012-10-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-NOV | IN | Withdrawn | Not Started | G906 | [5 empty] | NRIS |  | 200 |  | Wind | Montgomery County | IN | [27 empty] | Withdrawn | 2007-11-06 | 2012-03-06 | 2012-03-06 | 2014-11-01 | Duke Energy Corporation | Montgomery County | IN | DPP-2009-NOV | IN | Network Upgrade | NRIS | Duke 230 kV line | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2009-01-07 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | IL | Done | In Service | G996 | [5 empty] | NRIS |  | 150 |  | Wind | Ford County | IL | [27 empty] | Done | 2008-04-04 |  | 2010-02-05 | 2012-02-01 | Ameren Illinois | Ford County | IL | DPP-2008-NOV | IL | Optional | NRIS | Paxton East 138kV Substation | 150 | 150 | Wind | WT Wind Turbine | In Service | 2010-12-05 | 0 | 0 | 0 | 0
|  |  |  | DPP-2013-AUG | MI | Done | In Service | G997 | [5 empty] | NRIS |  | 50 |  | Wind | Huron County | MI | [27 empty] | Done | 2010-12-07 |  | 2013-12-23 | 2014-10-31 | ITC Transmission | Huron County | MI | DPP-2013-AUG | MI | DPP - SIS | NRIS | ITCT Minden Substation | 50 | 50 | Wind | WT Wind Turbine | In Service | 2009-06-30 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-NOV | IN | Withdrawn | Not Started | G949 | [5 empty] | NRIS |  | 200 |  | Wind | Montgomery County | IN | [27 empty] | Withdrawn | 2008-01-16 | 2012-03-06 | 2012-03-06 | 2014-11-01 | Duke Energy Corporation | Montgomery County | IN | DPP-2009-NOV | IN | Network Upgrade | NRIS | DEM Tippicanoe Junction - Crawfordsville 138 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2011-09-01 | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | CS5 | Withdrawn | Not Started | G555 | [5 empty] | NRIS |  | 100 |  | Wind | Stevens County | MN | [27 empty] | Withdrawn | 2005-10-24 | 2012-03-08 | 2012-03-08 |  | Otter Tail Power Company | Stevens County | MN | Pre-Transition SIS | CS5 | DPP - SIS | NRIS | Morris - Grand County 115 kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2006-08-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J074 | [5 empty] | NRIS |  | 350 |  | Wind | Huron County | MI | [27 empty] | Withdrawn | 2009-10-05 | 2012-03-13 | 2012-03-13 |  | ITC Transmission | Huron County | MI |  |  | SPA - SIS | NRIS | Harbor Beach - Wyatt 120 kV | 350 | 350 | Wind | WT Wind Turbine | Not Started | 2012-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G779 | [5 empty] | NRIS |  | 259.9 |  | Wind | Dodge County | MN | [27 empty] | Withdrawn | 2007-04-02 | 2012-03-16 | 2012-03-16 |  | SMMPA | Dodge County | MN |  |  | SPA - SIS | NRIS | Byron - Alcorns 161kV | 259.9 | 259.9 | Wind | WT Wind Turbine | Not Started | 2009-01-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-APR | 0 | Withdrawn | Not Started | J044 | [5 empty] | NRIS |  | 99 |  | Wind | Edgar County | IL | [27 empty] | Withdrawn | 2009-05-15 | 2012-03-19 | 2012-03-19 |  | Ameren Illinois | Edgar County | IL | DPP-2010-APR |  | DPP - SIS | NRIS | Kansas substation 138 kV | 99 | 99 | Wind | WT Wind Turbine | Not Started | 2012-01-18 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J157 | [5 empty] | NRIS |  | 27 |  | Wind | Ramsey County | ND | [27 empty] | Withdrawn | 2010-06-28 | 2012-03-19 | 2012-03-19 |  | Great River Energy | Ramsey County | ND |  |  | Feasibility | NRIS | 230 kV line near Ramsey substation | 27 | 27 | Wind | WT Wind Turbine | Not Started | 2011-06-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-APR | IL | Withdrawn | Not Started | G978 | [5 empty] | NRIS |  | 100 |  | Wind | Douglas County | IL | [27 empty] | Withdrawn | 2009-03-06 | 2012-03-21 | 2012-03-21 |  | Ameren Illinois | Douglas County | IL | DPP-2010-APR | IL | DPP - SIS | NRIS | Sydney - Murdock 138 kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2010-08-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | IN | Withdrawn | Not Started | H001 | [5 empty] | NRIS |  | 200 |  | Wind | Clinton County | IN | [27 empty] | Withdrawn | 2008-04-10 | 2012-03-30 | 2012-03-30 | 2014-12-31 | Duke Energy Corporation | Clinton County | IN | DPP-2008-NOV | IN | Network Upgrade | NRIS | Wabash - Kokomo 230 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2009-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-MAR | IA | Done | In Service | H007 | [5 empty] | NRIS |  | 41 |  | Wind | Delaware County | IA | [27 empty] | Done | 2008-04-22 |  | 2010-04-30 | 2011-08-01 | ITC Midwest | Delaware County | IA | DPP-2009-MAR | IA | DPP - SIS | NRIS | Edgewood 69 kV Substation | 41 | 41 | Wind | WT Wind Turbine | In Service | 2015-10-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | West | Done | In Service | H008 | [5 empty] | NRIS |  | 36 |  | Wind | Fayette County | IA | [27 empty] | Done | 2008-04-22 |  | 2015-01-07 | 2012-11-01 | ITC Midwest | Fayette County | IA | DPP-2012-AUG | West | DPP - SIS | NRIS | ITC Midwest Richfield 69 kV Substation | 36 | 36 | Wind | WT Wind Turbine | In Service | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | WEST | Done | In Service | H009 | [5 empty] | ERIS |  | 150 |  | Wind | Tama County | IA | [27 empty] | Done | 2008-04-22 |  | 2015-04-01 | 2012-12-03 | ITC Midwest | Tama County | IA | DPP-2012-AUG | WEST | Network Upgrade | ERIS | ITC Midwest Traer - Marshalltown 161 kV | 150 | 150 | Wind | WT Wind Turbine | In Service | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-NOV | IN | Withdrawn | Not Started | H002 | [5 empty] | NRIS |  | 200 |  | Wind | Clinton County | IN | [27 empty] | Withdrawn | 2009-07-24 | 2012-04-18 | 2012-04-18 | 2014-12-31 | Duke Energy Corporation | Clinton County | IN | DPP-2009-NOV | IN | Network Upgrade | NRIS | Carmel - Kokomo 230 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2009-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J216 | [5 empty] | NRIS |  | 25 |  | Wind | Mower County | MN | [27 empty] | Withdrawn | 2011-06-24 | 2012-04-20 | 2012-04-20 |  | SMMPA | Mower County | MN |  |  | SPA - SIS | NRIS | Austin Northeast 69 kV Substation | 25 | 25 | Wind | WT Wind Turbine | Not Started | 2013-06-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | Individual | Done | In Service | H012 | [5 empty] | NRIS |  | 150 |  | Wind | Columbia County | WI | [27 empty] | Done | 2008-04-29 |  | 2010-04-14 | 2011-12-31 | American Transmission Co. LLC | Columbia County | WI | DPP-2008-NOV | Individual | Network Upgrade | NRIS | Hamilton St. - N. Randolph 138 kV | 150 | 150 | Wind | WT Wind Turbine | In Service | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G703 | [5 empty] | NRIS |  | 1500 |  | Wind | Hand County | SD | [27 empty] | Withdrawn | 2006-11-10 | 2012-04-23 | 2012-04-23 |  | Northern States Power (Xcel Energy) | Hand County | SD |  |  | SPA - SIS | NRIS | Sioux Falls or Brookings Substation | 1500 | 1500 | Wind | WT Wind Turbine | Not Started | 2007-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G704 | [5 empty] | NRIS |  | 1500 |  | Wind | Hand County | SD | [27 empty] | Withdrawn | 2006-11-10 | 2012-04-23 | 2012-04-23 |  | Northern States Power (Xcel Energy) | Hand County | SD |  |  | SPA - SIS | NRIS | Sioux Falls or Brookings Sub | 1500 | 1500 | Wind | WT Wind Turbine | Not Started | 2007-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G705 | [5 empty] | NRIS |  | 2000 |  | Wind | Hand County | SD | [27 empty] | Withdrawn | 2006-11-10 | 2012-04-23 | 2012-04-23 |  | Northern States Power (Xcel Energy) | Hand County | SD |  |  | SPA - SIS | NRIS | Sioux Falls or Brookings Sub | 2000 | 2000 | Wind | WT Wind Turbine | Not Started | 2009-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-AUG | MI | Withdrawn | Not Started | J088 | [5 empty] | NRIS |  | 81 |  | Wind | Lenawee County | MI | [27 empty] | Withdrawn | 2010-04-20 | 2012-05-01 | 2012-05-01 |  | ITC Transmission | Lenawee County | MI | DPP-2010-AUG | MI | Network Upgrade | NRIS | ITC Beach - Samaria - Whiting 138kV | 81 | 81 | Wind | WT Wind Turbine | Not Started | 2012-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G894 | [5 empty] | NRIS |  | 49.5 |  | Wind | Big Stone County | MN | [27 empty] | Withdrawn | 2007-10-24 | 2012-05-07 | 2012-05-07 |  | Otter Tail Power Company | Big Stone County | MN |  |  | SPA - SIS | NRIS | Ortonville and Johnson Junction 115kV | 49.5 | 49.5 | Wind | WT Wind Turbine | Not Started | 2010-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G982 | [5 empty] | NRIS |  | 300 |  | Wind | Roberts County | SD | [27 empty] | Withdrawn | 2008-03-14 | 2012-05-07 | 2012-05-07 |  | Montana-Dakota Utilities Company | Roberts County | SD |  |  | SPA - SIS | NRIS | Browns Valley - Big Stone 230 kV | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2009-06-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H065 | [5 empty] | NRIS |  | 40 |  | Wind | Renville County | MN | [27 empty] | Withdrawn | 2008-06-16 | 2012-05-10 | 2012-05-10 |  | Northern States Power (Xcel Energy) | Renville County | MN |  |  | SPA - SIS | NRIS | Xel Bird Island 69kV Substation | 40 | 40 | Wind | WT Wind Turbine | Not Started | 2010-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J125 | [5 empty] | NRIS |  | 151.2 |  | Wind | Macon County | IL | [27 empty] | Withdrawn | 2011-08-22 | 2012-05-11 | 2012-05-11 |  | Ameren Illinois | Macon County | IL |  |  | SPA - SIS | NRIS | Latham - Maroa West 345 kV | 151.2 | 151.2 | Wind | WT Wind Turbine | Not Started | 2014-05-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | WEST | Done | In Service | H021 | [5 empty] | NRIS |  | 138.6 |  | Wind | Grundy County | IA | [27 empty] | Done | 2008-05-01 |  | 2015-03-23 | 2014-06-09 | ITC Midwest | Grundy County | IA | DPP-2012-AUG | WEST | Network Upgrade | NRIS | Wellsburg 115kV Substation | 138.6 | 138.6 | Wind | WT Wind Turbine | In Service | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J134 | [5 empty] | ERIS |  | 150 |  | Wind | Dane County | WI | [27 empty] | Withdrawn | 2010-05-25 | 2012-05-14 | 2012-05-14 |  | American Transmission Co. LLC | Dane County | WI |  |  | SPA - SIS | ERIS | Cardinal - North Madison 138 kV | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2013-09-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J154 | [5 empty] | NRIS |  | 500 |  | Wind | Washington County | IA | [27 empty] | Withdrawn | 2010-06-28 | 2012-05-17 | 2012-05-17 |  | MidAmerican Energy Company | Washington County | IA |  |  | SPA - SIS | NRIS | Grimes 161 kV substation | 500 | 500 | Wind | WT Wind Turbine | Not Started | 2011-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J192 | [5 empty] | NRIS |  | 500 |  | Wind | Washington County | IA | [27 empty] | Withdrawn | 2011-01-31 | 2012-05-17 | 2012-05-17 | 2012-09-01 | Ameren Missouri | Washington County | IA |  |  | SPA - SIS | NRIS | Hills - Sub T 345 kV | 500 | 500 | Wind | WT Wind Turbine | Not Started | 2012-12-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G721 | [5 empty] | NRIS |  | 160 |  | Wind | Otter Tail County | MN | [27 empty] | Withdrawn | 2006-12-19 | 2012-05-22 | 2012-05-22 |  | Great River Energy | Otter Tail County | MN |  |  | SPA - SIS | NRIS | Bison - Alexandria S.S. 345kV | 160 | 160 | Wind | WT Wind Turbine | Not Started | 2012-03-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J070 | [5 empty] | NRIS |  | 49.2 |  | Wind | Clinton County | MI | [27 empty] | Withdrawn | 2011-04-11 | 2012-06-11 | 2012-06-11 |  | Michigan Electric Transmission Company, LLC | Clinton County | MI |  |  | Feasibility | NRIS | METC Bingham - David 138 kV | 49.2 | 49.2 | Wind | WT Wind Turbine | Not Started | 2009-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G823 | [5 empty] | NRIS |  | 300 |  | Wind | Yellow Medicine County | MN | [27 empty] | Withdrawn | 2007-07-24 | 2012-06-19 | 2012-06-19 |  | Otter Tail Power Company | Yellow Medicine County | MN |  |  | SPA - SIS | NRIS | Burr - Toronto 115 kV | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2009-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G765 | [5 empty] | NRIS |  | 240 |  | Gas | Brookings County | SD | [27 empty] | Withdrawn | 2011-02-01 | 2012-06-20 | 2012-06-20 |  | Northern States Power (Xcel Energy) | Brookings County | SD |  |  | Feasibility | NRIS | Brookings County 345 kV Substation | 240 | 240 | Gas |  | Not Started | 2010-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G844 | [5 empty] | NRIS |  | 60 |  | Combined Cycle | Brookings County | SD | [27 empty] | Withdrawn | 2011-02-01 | 2012-06-20 | 2012-06-20 |  | Northern States Power (Xcel Energy) | Brookings County | SD |  |  | Feasibility | NRIS | Brookings County 345 kV Substation | 60 | 60 | Combined Cycle |  | Not Started | 2011-11-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-JUL | MN | Withdrawn | Not Started | G768 | [5 empty] | ERIS |  | 50 |  | Wind | Watonwan County | MN | [27 empty] | Withdrawn | 2007-03-21 | 2012-06-26 | 2012-06-26 |  | Northern States Power (Xcel Energy) | Watonwan County | MN | DPP-2009-JUL | MN | DPP - SIS | ERIS | Watonwan 69 kV | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2009-06-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-JUL | MN | Withdrawn | Not Started | G769 | [5 empty] | ERIS |  | 50 |  | Wind | Cottonwood County | MN | [27 empty] | Withdrawn | 2007-03-21 | 2012-06-26 | 2012-06-26 |  | ITC Midwest | Cottonwood County | MN | DPP-2009-JUL | MN | DPP - SIS | ERIS | Storden - Heron Lake 161kV | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2010-08-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G825 | [5 empty] | NRIS |  | 100 |  | Wind | Brookings County | SD | [27 empty] | Withdrawn | 2007-07-16 | 2012-06-26 | 2012-06-26 |  | Otter Tail Power Company | Brookings County | SD |  |  | SPA - SIS | NRIS | Toronto - Bruce 115kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2013-10-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H017 | [5 empty] | NRIS |  | 100 |  | Wind | Cottonwood County | MN | [27 empty] | Withdrawn | 2008-04-30 | 2012-06-26 | 2012-06-26 |  | Northern States Power (Xcel Energy) | Cottonwood County | MN |  |  | SPA - SIS | NRIS | Lakefield Junction 345kV Substation | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2009-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H018 | [5 empty] | NRIS |  | 150 |  | Wind | Cottonwood County | MN | [27 empty] | Withdrawn | 2008-04-30 | 2012-06-26 | 2012-06-26 |  | Northern States Power (Xcel Energy) | Cottonwood County | MN |  |  | SPA - SIS | NRIS | Storden - Heron Lake 161kV | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H047 | [5 empty] | NRIS |  | 35 |  | Wind | Steele County | MN | [27 empty] | Withdrawn | 2008-06-12 | 2012-06-26 | 2012-06-26 |  | ITC Midwest | Steele County | MN |  |  | SPA - SIS | NRIS | ITC Midwest Medford Junction 69 kV Substation | 35 | 35 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | MN | Withdrawn | Not Started | H049 | [5 empty] | NRIS |  | 45 |  | Wind | Stearns County | MN | [27 empty] | Withdrawn | 2008-06-12 | 2012-06-26 | 2012-06-26 |  | Northern States Power (Xcel Energy) | Stearns County | MN | DPP-2008-NOV | MN | Network Upgrade | NRIS | GRE Albany 69 kV Substation | 45 | 45 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Not Started | H037 | [5 empty] | NRIS |  | 135 |  | Co-Gen | Lucas County | OH | [27 empty] | Done | 2008-05-29 |  | 2011-05-12 |  | FirstEnergy Solutions Corp. | Lucas County | OH |  |  | Feasibility | NRIS | Millard Road and Tiffin Drive, Ironville Substation | 135 | 135 | Co-Gen | OT - co-gen | Not Started | 2010-01-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-JUL | MN | Withdrawn | Not Started | H050 | [5 empty] | NRIS |  | 200 |  | Wind | Meeker County | MN | [27 empty] | Withdrawn | 2008-06-12 | 2012-06-26 | 2012-06-26 |  | Northern States Power (Xcel Energy) | Meeker County | MN | DPP-2009-JUL | MN | DPP - SIS | NRIS | GRE Big Swan 115 kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-JUL | MN | Withdrawn | Not Started | H057 | [5 empty] | NRIS |  | 40 |  | Wind | Jackson County | MN | [27 empty] | Withdrawn | 2008-06-12 | 2012-06-26 | 2012-06-26 |  | ITC Midwest | Jackson County | MN | DPP-2009-JUL | MN | DPP - SIS | NRIS | ITC Midwest Wilder Junction 69kV Substation | 40 | 40 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-JUL | MN | Withdrawn | Not Started | H059 | [5 empty] | NRIS |  | 40 |  | Wind | Nobles County | MN | [27 empty] | Withdrawn | 2008-06-12 | 2012-06-26 | 2012-06-26 |  | ITC Midwest | Nobles County | MN | DPP-2009-JUL | MN | DPP - SIS | NRIS | 69kV 3 way switch at the Worthington, 2.5 miles South of Elk substation | 40 | 40 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-JUL | MN | Withdrawn | Not Started | H069 | [5 empty] | NRIS |  | 55 |  | Wind | Waseca County | MN | [27 empty] | Withdrawn | 2008-06-17 | 2012-06-26 | 2012-06-26 |  | Northern States Power (Xcel Energy) | Waseca County | MN | DPP-2009-JUL | MN | DPP - SIS | NRIS | Waseca 69 kV sub | 55 | 55 | Wind | WT Wind Turbine | Not Started | 2010-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-JUL | MN | Withdrawn | Not Started | H073 | [5 empty] | NRIS |  | 100 |  | Wind | Douglas County | MN | [27 empty] | Withdrawn | 2008-06-18 | 2012-06-26 | 2012-06-26 |  | Otter Tail Power Company | Douglas County | MN | DPP-2009-JUL | MN | DPP - SIS | NRIS | Alexandria 115 kV Substation | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | MN | Withdrawn | Not Started | H074 | [5 empty] | NRIS |  | 47.5 |  | Wind | Goodhue County | MN | [27 empty] | Withdrawn | 2008-06-18 | 2012-06-26 | 2012-06-26 |  | Northern States Power (Xcel Energy) | Goodhue County | MN | DPP-2008-NOV | MN | Network Upgrade | NRIS | Goodhue 69kV Substation | 47.5 | 47.5 | Wind | WT Wind Turbine | Not Started | 2009-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J013 | [5 empty] | NRIS |  | 200 |  | Wind | Stutsman County | ND | [27 empty] | Withdrawn | 2009-01-06 | 2012-06-26 | 2012-06-26 |  | Otter Tail Power Company | Stutsman County | ND |  |  | SPA - SIS | NRIS | OTP Jamestown 115 kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2012-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J131 | [5 empty] | NRIS |  | 300 |  | Gas | Lyon County | MN | [27 empty] | Withdrawn | 2010-04-26 | 2012-06-26 | 2012-06-26 |  | Northern States Power (Xcel Energy) | Lyon County | MN |  |  | Feasibility | NRIS | Lake Yankton substation | 300 | 300 | Gas |  | Not Started | 2013-09-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J115 | [5 empty] | NRIS |  | 500 |  | Wind | Saint Francois County | MO | [27 empty] | Withdrawn | 2010-02-16 | 2012-06-27 | 2012-06-27 |  | Ameren Missouri | Saint Francois County | MO |  |  | SPA - SIS | NRIS | Palmyra Tap 345kV Substation | 500 | 500 | Wind | WT Wind Turbine | Not Started | 2012-10-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2011-JUN | MI | Withdrawn | Not Started | J206 | [5 empty] | ERIS |  | 25 |  | Solar | Wayne County | MI | [27 empty] | Withdrawn | 2011-02-25 | 2012-06-27 | 2012-06-27 |  | Michigan Electric Transmission Company, LLC | Wayne County | MI | DPP-2011-JUN | MI | DPP - SIS | ERIS | Dayton 120 kV Substation | 25 | 25 | Solar | PV Photovoltaic | Not Started | 2012-12-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J207 | [5 empty] | ERIS |  | 100 |  | Solar | Washtenaw County | MI | [27 empty] | Withdrawn | 2011-03-01 | 2012-06-27 | 2012-06-27 |  | Michigan Electric Transmission Company, LLC | Washtenaw County | MI |  |  | SPA - SIS | ERIS | Luzon - Kentucky 120 kV | 100 | 100 | Solar | PV Photovoltaic | Not Started | 2013-03-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J220 | [5 empty] | ERIS |  | 45 |  | Solar | Monroe County | MI | [27 empty] | Withdrawn | 2011-06-27 | 2012-06-27 | 2012-06-27 |  | Michigan Electric Transmission Company, LLC | Monroe County | MI |  |  | Feasibility | ERIS | Beecher - Whiting 138 kV | 45 | 45 | Solar | PV Photovoltaic | Not Started | 2014-12-31 | 0 | 0 | 0 | 0
|  |  |  | G813 | G813 | Withdrawn | Not Started | G813 | [5 empty] | NRIS |  | 100 |  | Wind | Boone County | IA | [27 empty] | Withdrawn | 2007-06-29 | 2012-07-02 | 2012-07-02 |  | ITC Midwest | Boone County | IA | G813 | G813 | SPA - SIS | NRIS | Dodge Twp., north central section of Boone Co., IA | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2009-09-30 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-APR | Missouri | Withdrawn | Not Started | H086 | [5 empty] | NRIS |  | 299.2 |  | Wind | Monroe County | MO | [27 empty] | Withdrawn | 2008-07-09 | 2012-07-02 | 2012-07-02 |  | Ameren Missouri | Monroe County | MO | DPP-2010-APR | Missouri | DPP - SIS | NRIS | 10 miles N of Spencer Creek sub | 299.2 | 299.2 | Wind | WT Wind Turbine | Not Started | 2012-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G764 | [5 empty] | ERIS |  | 241.5 |  | Wind | Minnehaha County | SD | [27 empty] | Withdrawn | 2007-03-15 | 2012-07-03 | 2012-07-03 |  | Northern States Power (Xcel Energy) | Minnehaha County | SD |  |  | SPA - SIS | ERIS | Anson 115 kV station | 241.5 | 241.5 | Wind | WT Wind Turbine | Not Started | 2013-12-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G976 | [5 empty] | ERIS |  | 18 |  | Wind | Johnson County | IA | [27 empty] | Withdrawn | 2010-06-16 | 2012-07-05 | 2012-07-05 |  | ITC Midwest | Johnson County | IA |  |  | SPA - SIS | ERIS | Tap on 34.5 kV line, approximately 2 miles north of Alliant sub (West Branch 115 kV), along Oasis Rd | 18 | 18 | Wind | WT Wind Turbine | Not Started | 2010-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J153 | [5 empty] | NRIS |  | 30 |  | Wind | Johnson County | IA | [27 empty] | Withdrawn | 2010-06-28 | 2012-07-05 | 2012-07-05 |  | ITC Midwest | Johnson County | IA |  |  | SPA - SIS | NRIS | Bertram - Hills 161kV | 30 | 30 | Wind | WT Wind Turbine | Not Started | 2012-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J213 | [5 empty] | NRIS |  | 200 |  | Wind | Sangamon County | IL | [27 empty] | Withdrawn | 2011-04-11 | 2012-07-06 | 2012-07-06 |  | Ameren Illinois | Sangamon County | IL |  |  | SPA - SIS | NRIS | N. Auburn 138kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2014-01-10 | 0 | 0 | 0 | 0
|  |  |  | FeS-2011-FEB | 0 | Withdrawn | Not Started | J188 | [5 empty] | NRIS |  | 99 |  | Wind | Lenawee County | MI | [27 empty] | Withdrawn | 2010-12-07 | 2012-07-10 | 2012-07-10 |  | Michigan Electric Transmission Company, LLC | Lenawee County | MI | FeS-2011-FEB |  | Feasibility | NRIS | Moore Rd - Beecher 138 kV line | 99 | 99 | Wind | WT Wind Turbine | Not Started | 2013-09-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H099 | [5 empty] | NRIS |  | 150 |  | Wind | Clay County | MN | [27 empty] | Withdrawn | 2008-08-14 | 2012-07-12 | 2012-07-12 |  | Otter Tail Power Company | Clay County | MN |  |  | SPA - SIS | NRIS | OTP Sheyenne - Audubon 230 kV | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2013-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J189 | [5 empty] | ERIS |  | 200 |  | Wind | Minnehaha County | SD | [27 empty] | Withdrawn | 2010-12-20 | 2012-07-12 | 2012-07-12 |  | Northern States Power (Xcel Energy) | Minnehaha County | SD |  |  | Feasibility | ERIS | Anson Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2012-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G699 | [5 empty] | NRIS |  | 250 |  | Wind | Roberts County | SD | [27 empty] | Withdrawn | 2006-11-07 | 2012-07-18 | 2012-07-18 |  | Otter Tail Power Company | Roberts County | SD |  |  | SPA - SIS | NRIS | Big Stone - Hankinson 230 kV | 250 | 250 | Wind | WT Wind Turbine | Not Started | 2008-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G855 | [5 empty] | NRIS |  | 200 |  | Wind | Freeborn County | MN | [27 empty] | Withdrawn | 2007-09-11 | 2012-07-18 | 2012-07-18 |  | ITC Midwest | Freeborn County | MN |  |  | SPA - SIS | NRIS | Hayward 161 kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2012-10-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | MN | Done | Withdrawn | H061 | [5 empty] | NRIS |  | 39 |  | Wind | Goodhue County | MN | [27 empty] | Done | 2008-06-16 |  | 2010-08-27 | 2012-12-01 | Great River Energy | Goodhue County | MN | DPP-2008-NOV | MN | Network Upgrade | NRIS | Vasa 69 kV substation | 39 | 39 | Wind | WT Wind Turbine | Withdrawn | 2010-12-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | MN | Done | Withdrawn | H062 | [5 empty] | NRIS |  | 39 |  | Wind | Goodhue County | MN | [27 empty] | Done | 2008-06-16 |  | 2010-09-01 | 2012-12-01 | Great River Energy | Goodhue County | MN | DPP-2008-NOV | MN | Network Upgrade | NRIS | Goodhue 69 kV Substation | 39 | 39 | Wind | WT Wind Turbine | Withdrawn | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G972 | [5 empty] | NRIS |  | 400 |  | Wind | Fayette County | IA | [27 empty] | Withdrawn | 2008-02-14 | 2012-07-18 | 2012-07-18 |  | ITC Midwest | Fayette County | IA |  |  | SPA - SIS | NRIS | Hazelton 345 kV Substation | 400 | 400 | Wind | WT Wind Turbine | Not Started | 2010-03-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J085 | [5 empty] | NRIS |  | 0 |  | Wind | Hillsdale County | MI | [27 empty] | Withdrawn | 2009-10-05 | 2012-07-18 | 2012-07-18 | 2015-12-31 | Michigan Electric Transmission Company, LLC | Hillsdale County | MI |  |  | Network Upgrade | NRIS | Moore Road - Dowling 138 kV substation | 150 | 0 | Wind | WT Wind Turbine | Not Started | 2012-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J170 | [5 empty] | NRIS |  | 200 |  | Wind | Tuscola County | MI | [27 empty] | Withdrawn | 2010-09-14 | 2012-07-18 | 2012-07-18 |  | Michigan Electric Transmission Company, LLC | Tuscola County | MI |  |  | DPP - SIS | NRIS | Karn - Manning 138kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2011-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | Buffalo Ridge | Withdrawn | Not Started | H083 | [5 empty] | NRIS |  | 200 |  | Wind | Lyon County | MN | [27 empty] | Withdrawn | 2008-06-30 | 2012-07-20 | 2012-07-20 |  | Northern States Power (Xcel Energy) | Lyon County | MN |  | Buffalo Ridge | SPA - SIS | NRIS | Lyon County 345kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2015-12-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | MN | Done | Withdrawn | H067 | [5 empty] | NRIS |  | 40 |  | Wind | Kandiyohi County | MN | [27 empty] | Done | 2008-06-17 |  | 2011-04-20 | 2013-12-31 | Northern States Power (Xcel Energy) | Kandiyohi County | MN | DPP-2008-NOV | MN | Network Upgrade | NRIS | GRE Atwater 69 kV Substation | 40 | 40 | Wind | WT Wind Turbine | Withdrawn | 2009-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J126 | [5 empty] | ERIS |  | 4.94 |  | Wind | Winona County | MN | [27 empty] | Withdrawn | 2010-04-23 | 2012-07-20 | 2012-07-20 |  | Dairyland Power Cooperative | Winona County | MN |  |  | Feasibility | ERIS | ITC Midwest Rushford - Wilson 69kV | 4.94 | 4.94 | Wind | WT Wind Turbine | Not Started | 2012-10-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G668 | [5 empty] | NRIS |  | 100 |  | Wind | Big Stone County | MN | [27 empty] | Withdrawn | 2006-08-10 | 2012-07-25 | 2012-07-25 |  | Great River Energy | Big Stone County | MN |  |  | SPA - SIS | NRIS | Graceville/Johnson facilities in Big Stone County, MN | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2009-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G792 | [5 empty] | NRIS |  | 50 |  | Wind | Big Stone County | MN | [27 empty] | Withdrawn | 2007-04-30 | 2012-07-25 | 2012-07-25 |  | Great River Energy | Big Stone County | MN |  |  | SPA - SIS | NRIS | Johnson Station facilities | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2009-06-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2013-FEB | West | Done | In Service | H071 | [5 empty] | NRIS |  | 40 |  | Wind | Stearns County | MN | [27 empty] | Done | 2013-01-07 |  | 2015-05-05 | 2016-03-01 | Northern States Power (Xcel Energy) | Stearns County | MN | DPP-2013-FEB | West | DPP - SIS | NRIS | Xcel Black Oak 69 kV Substation | 40 | 40 | Wind | WT Wind Turbine | In Service | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J007 | [5 empty] | NRIS |  | 250 |  | Wind | Osceola County | IA | [27 empty] | Withdrawn | 2008-10-31 | 2012-07-25 | 2012-07-25 |  | ITC Midwest | Osceola County | IA |  |  | SPA - SIS | NRIS | ITC Midwest Lakefield Junction - Raun 345 kV | 250 | 250 | Wind | WT Wind Turbine | Not Started | 2012-02-28 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J062 | [5 empty] | NRIS |  | 250 |  | Wind | Polk County | MN | [27 empty] | Withdrawn | 2009-08-20 | 2012-07-25 | 2012-07-25 |  | Otter Tail Power Company | Polk County | MN |  |  | SPA - SIS | NRIS | Winger Substation 115 kV facility | 250 | 250 | Wind | WT Wind Turbine | Not Started | 2009-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J133 | [5 empty] | NRIS |  | 200 |  | Wind | Codington County | SD | [27 empty] | Withdrawn | 2010-05-25 | 2012-07-25 | 2012-07-25 |  | Otter Tail Power Company | Codington County | SD |  |  | Feasibility | NRIS | Big Stone Substation 230 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2013-09-30 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | MN | Done | Withdrawn | H075 | [5 empty] | NRIS |  | 43.2 |  | Wind | Oceana County | MI | [27 empty] | Done | 2008-06-19 |  | 2010-10-04 | 2013-04-01 | Michigan Electric Transmission Company, LLC | Oceana County | MI | DPP-2008-NOV | MN | Network Upgrade | NRIS | METC Redwood Substation | 43.2 | 43.2 | Wind | WT Wind Turbine | Withdrawn | 2009-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | GS5 | Withdrawn | Not Started | G617 | [5 empty] | ERIS |  | 50 |  | Wind | Blue Earth County | MN | [27 empty] | Withdrawn | 2006-04-11 | 2012-07-26 | 2012-07-26 |  | Great River Energy | Blue Earth County | MN |  | GS5 | DPP - SIS | ERIS | GRE Amboy - Willow 69 kV | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2007-08-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G957 | [5 empty] | NRIS |  | 300 |  | Wind | Emmet County | IA | [27 empty] | Withdrawn | 2008-01-23 | 2012-07-26 | 2012-07-26 |  | ITC Midwest | Emmet County | IA |  |  | SPA - SIS | NRIS | Winnco Corner 161 Substation | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | IA | Done | In Service | H078 | [5 empty] | ERIS |  | 121 |  | Wind | Marshall County | IA | [27 empty] | Done | 2008-06-20 |  | 2010-07-15 | 2011-10-31 | ITC Midwest | Marshall County | IA | DPP-2008-NOV | IA | Network Upgrade | ERIS | new 161 kV substation near Laurel, IA approx b/t Marshalltown & Jasper | 121 | 121 | Wind | WT Wind Turbine | In Service | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G695 | [5 empty] | ERIS |  | 200 |  | Wind | Winnebago County | IA | [27 empty] | Withdrawn | 2006-10-24 | 2012-07-30 | 2012-07-30 |  | ITC Midwest | Winnebago County | IA |  |  | SPA - SIS | ERIS | Winco - Winnebago 161 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2008-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G722 | [5 empty] | NRIS |  | 250 |  | Wind | Grant County | SD | [27 empty] | Withdrawn | 2006-12-21 | 2012-07-30 | 2012-07-30 |  | Otter Tail Power Company | Grant County | SD |  |  | SPA - SIS | NRIS | Big Stone 230 kV Substation | 250 | 250 | Wind | WT Wind Turbine | Not Started | 2012-03-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | West | Done | In Service | H081 | [5 empty] | ERIS |  | 201 |  | Wind | Lyon County | MN | [27 empty] | Done | 2008-06-24 |  | 2014-12-05 | 2017-09-01 | Northern States Power (Xcel Energy) | Lyon County | MN | DPP-2012-AUG | West | Network Upgrade | ERIS | Brookings County - Lyon County 345kV | 201 | 201 | Wind | WT Wind Turbine | In Service | 2011-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H003 | [5 empty] | NRIS |  | 200 |  | Wind | McDonough County | IL | [27 empty] | Withdrawn | 2010-09-28 | 2012-08-03 | 2012-08-03 |  | Ameren Illinois | McDonough County | IL |  |  | SPA - SIS | NRIS | 138 kV line, 5 miles North of Macomb | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2009-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J222 | [5 empty] | NRIS |  | 200 |  | Wind | Gratiot County | MI | [27 empty] | Withdrawn | 2011-08-22 | 2012-08-13 | 2012-08-13 |  | Michigan Electric Transmission Company, LLC | Gratiot County | MI |  |  | Feasibility | NRIS | METC Nelson Road - Goss 345 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2014-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J139 | [5 empty] | NRIS |  | 200 |  | Wind | Grant County | WI | [27 empty] | Withdrawn | 2009-10-12 | 2012-08-20 | 2012-08-20 |  | -- No Company -- | Grant County | WI |  |  | SPA - SIS | NRIS | Gran Grea - Nelson Dewey 161 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J176 | [5 empty] | NRIS |  | 200 |  | Wind | Gratiot County | MI | [27 empty] | Withdrawn | 2010-11-15 | 2012-08-20 | 2012-08-20 |  | Michigan Electric Transmission Company, LLC | Gratiot County | MI |  |  | Network Upgrade | NRIS | METC Nelson - Goss 345kV | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J163 | [5 empty] | ERIS |  | 100 |  | Wind | Tippecanoe County | IN | [27 empty] | Withdrawn | 2010-09-10 | 2012-08-22 | 2012-08-22 |  | Duke Energy Corporation | Tippecanoe County | IN |  |  | Feasibility | ERIS | Klondike 138 kV Substation | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2014-04-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H020 | [5 empty] | NRIS |  | 200 |  | Wind | Webster County | IA | [27 empty] | Withdrawn | 2008-04-30 | 2012-08-23 | 2012-08-23 |  | ITC Midwest | Webster County | IA |  |  | SPA - SIS | NRIS | Boone Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H085 | [5 empty] | NRIS |  | 200 |  | Wind | Marshall County | IA | [27 empty] | Withdrawn | 2008-07-03 | 2012-08-23 | 2012-08-23 |  | ITC Midwest | Marshall County | IA |  |  | SPA - SIS | NRIS | ITC 161kV approx 8 miles south of Marshalltown Sub | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2013-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J005 | [5 empty] | NRIS |  | 17.5 |  | Wind | Todd County | MN | [27 empty] | Withdrawn | 2008-10-24 | 2012-08-23 | 2012-08-23 |  | Minnesota Power (Allete, Inc.) | Todd County | MN |  |  | Network Upgrade | NRIS | R34WT133N, Section 7, Bartlett Twp | 17.5 | 17.5 | Wind | WT Wind Turbine | Not Started | 2009-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J073 | [5 empty] | NRIS |  | 194 |  | Gas | Blue Earth County | MN | [27 empty] | Withdrawn | 2010-10-25 | 2012-08-23 | 2012-08-23 |  | Northern States Power (Xcel Energy) | Blue Earth County | MN |  |  | Feasibility | NRIS | Mankato Energy Center substation | 161.5 | 194 | Gas |  | Not Started | 2012-04-03 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J090 | [5 empty] | NRIS |  | 200 |  | Wind | Mercer County | ND | [27 empty] | Withdrawn | 2009-10-08 | 2012-08-23 | 2012-08-23 |  | Great River Energy | Mercer County | ND |  |  | SPA - SIS | NRIS | GRE Stanton 230 kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2012-08-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | MN | Done | In Service | H092 | [5 empty] | NRIS |  | 60 |  | Coal | Itasca County | MN | [27 empty] | Done | 2008-07-25 |  | 2010-09-01 | 2011-02-16 | Minnesota Power (Allete, Inc.) | Itasca County | MN | DPP-2008-NOV | MN | Network Upgrade | NRIS | MP Boswell Substation | 60 | 60 | Coal | Combined Cycle | In Service | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | Individual | Done | In Service | H093 | [5 empty] | ERIS |  | 5 |  | Landfill Gas | Mahoning County | OH | [27 empty] | Done | 2008-07-25 |  | 2010-12-02 | 2011-11-11 | FirstEnergy Solutions Corp. | Mahoning County | OH | DPP-2008-NOV | Individual | Network Upgrade | ERIS | Boardman - Columbia 69kV | 5 | 5 | Landfill Gas | IC Internal Combustion (diesel, piston) Engine | In Service | 2011-06-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-MAR | IL | Done | In Service | H094 | [5 empty] | NRIS |  | 99 |  | Wind | Vermilion County | IL | [27 empty] | Done | 2008-07-28 |  | 2011-01-04 | 2014-12-31 | Ameren Illinois | Vermilion County | IL | DPP-2009-MAR | IL | Network Upgrade | NRIS | 22 N Range: 12 West/1/50 miles west of Rossville, IL/138kV line | 99 | 99 | Wind | WT Wind Turbine | In Service | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J096 | [5 empty] | NRIS |  | 150 |  | Wind | Tama County | IA | [27 empty] | Withdrawn | 2009-11-02 | 2012-08-23 | 2012-08-23 |  | ITC Midwest | Tama County | IA |  |  | SPA - SIS | NRIS | Toledo 115kV substation | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2012-09-30 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | WEST | Done | In Service | H096 | [5 empty] | NRIS |  | 50 |  | Wind | Greene County | IA | [27 empty] | Done | 2009-03-13 |  | 2015-04-06 | 2012-10-15 | ITC Midwest | Greene County | IA | DPP-2012-AUG | WEST | Network Upgrade | NRIS | Grand Junction - Perry 161 kV | 50 | 50 | Wind | WT Wind Turbine | In Service | 2008-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G966 | [5 empty] | NRIS |  | 100 |  | Wind | Ford County | IL | [27 empty] | Withdrawn | 2009-02-20 | 2012-08-28 | 2012-08-28 |  | Ameren Illinois | Ford County | IL |  |  | SPA - SIS | NRIS | East Paxton 138kV substation | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J128 | [5 empty] | NRIS |  | 100 |  | Wind | Marshall County | IL | [27 empty] | Withdrawn | 2010-04-26 | 2012-08-28 | 2012-08-28 |  | Ameren Illinois | Marshall County | IL |  |  | Feasibility | NRIS | Oglesby - El Paso 138kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2011-06-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J187 | [5 empty] | NRIS |  | 198 |  | Wind | Shiawassee County | MI | [27 empty] | Withdrawn | 2010-12-07 | 2012-08-31 | 2012-08-31 |  | Michigan Electric Transmission Company, LLC | Shiawassee County | MI |  |  | Feasibility | NRIS | St. Johns - Cornell 138 kV | 198 | 198 | Wind | WT Wind Turbine | Not Started | 2013-09-30 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | IL | Done | In Service | H100 | [5 empty] | NRIS |  | 200 |  | Wind | Vermilion County | IL | [27 empty] | Done | 2008-08-19 |  | 2011-04-05 | 2012-12-31 | Ameren Illinois | Vermilion County | IL | DPP-2008-NOV | IL | Network Upgrade | NRIS | Vermillion 138kV substation | 200 | 200 | Wind | WT Wind Turbine | In Service | 2012-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G864 | [5 empty] | NRIS |  | 200 |  | Wind | White County | IN | [27 empty] | Withdrawn | 2007-09-18 | 2012-09-05 | 2012-09-05 |  | Northern Indiana Public Service Company | White County | IN |  |  | DPP - SIS | NRIS | Reynolds Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2013-10-01 | 0 | 0 | 0 | 0
|  |  |  | IP01 | IP01 | Done | Withdrawn | IP01 | [5 empty] | NRIS |  | 50 |  | Wind | McLean County | IL | [27 empty] | Done | 2004-01-14 | 2006-09-26 | 2006-09-26 |  | Ameren Illinois | McLean County | IL | IP01 | IP01 | SPA - SIS | NRIS | McLean County #6, 69 kV, Line 6612 | 50 | 50 | Wind | WT Wind Turbine | Withdrawn | 2012-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G865 | [5 empty] | NRIS |  | 201 |  | Wind | Benton County | IN | [27 empty] | Withdrawn | 2010-11-01 | 2012-09-05 | 2012-09-05 |  | Northern Indiana Public Service Company | Benton County | IN |  |  | Feasibility | NRIS | Goodland Sub | 201 | 201 | Wind | WT Wind Turbine | Not Started | 2012-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Withdrawn | IP03 | [5 empty] | NRIS |  | 79 |  | Wind | McLean County | IL | [27 empty] | Done | 2004-01-14 |  | 2007-08-06 |  | Ameren Illinois | McLean County | IL |  |  | Network Upgrade | NRIS | McLean County #8 Line 1376 | 79 | 79 | Wind | WT Wind Turbine | Withdrawn | 2010-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | IP04 | [5 empty] | NRIS |  | 150 |  | Wind | McLean County | IL | [27 empty] | Done | 2004-04-22 |  | 2007-08-28 |  | Ameren Illinois | McLean County | IL |  |  | Network Upgrade | NRIS | Mcean County #9 , 138 kV, Line 1382 | 150 | 150 | Wind | WT Wind Turbine | In Service | 2004-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G991 | [5 empty] | NRIS |  | 200 |  | Wind | Fillmore County | MN | [27 empty] | Withdrawn | 2011-04-28 | 2012-09-05 | 2012-09-05 |  | ITC Midwest | Fillmore County | MN |  |  | SPA - SIS | NRIS | Harmony - Lansing 161kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2008-04-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Withdrawn | IP08 | [5 empty] | NRIS |  | 80 |  | Wind | Woodford County | IL | [27 empty] | Done | 2003-10-22 |  | 2007-09-06 |  | Ameren Illinois | Woodford County | IL |  |  | Network Upgrade | NRIS | IP line 1382, 138 kV | 80 | 80 | Wind | WT Wind Turbine | Withdrawn | 2006-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H026 | [5 empty] | NRIS |  | 150 |  | Wind | Tippecanoe County | IN | [27 empty] | Withdrawn | 2008-05-14 | 2012-09-05 | 2012-09-05 |  | Duke Energy Corporation | Tippecanoe County | IN |  |  | DPP - SIS | NRIS | Cayuga - Frankfort 230kV | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2011-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J098 | [5 empty] | NRIS |  | 150 |  | Wind | Dickey County | ND | [27 empty] | Withdrawn | 2009-11-10 | 2012-09-05 | 2012-09-05 |  | Montana-Dakota Utilities Company | Dickey County | ND |  |  | SPA - SIS | NRIS | MDU Ellendale-Tatanka 230 kV | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2012-05-01 | 0 | 0 | 0 | 0
|  |  |  | IP14 | IP14 | Done | In Service | IP14 | [5 empty] | NRIS |  | 1500 |  | Coal | Washington County | IL | [27 empty] | Done | 2001-07-17 |  | 2004-10-06 | 2010-05-31 | Ameren Illinois | Washington County | IL | IP14 | IP14 | Network Upgrade | NRIS | Prairie State | 1500 | 1500 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | In Service | 2006-08-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Not Started | IP17 | [5 empty] | NRIS |  | 550 |  | Coal | Franklin County | IL | [27 empty] | Done | 2001-12-02 |  | 2004-10-06 |  | Ameren Illinois | Franklin County | IL |  |  |  | NRIS | Unknown | 550 | 550 | Coal |  | Not Started | 2002-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J119 | [5 empty] | NRIS |  | 61.2 |  | Wind | Chippewa County | MI | [27 empty] | Withdrawn | 2010-03-17 | 2012-09-13 | 2012-09-13 |  | American Transmission Co. LLC | Chippewa County | MI |  |  | DPP - SIS | NRIS | Pine River 69 kV Substation | 61.2 | 61.2 | Wind | WT Wind Turbine | Not Started | 2011-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G951 | [5 empty] | NRIS |  | 99 |  | Wind | Sheridan County | ND | [27 empty] | Withdrawn | 2011-04-28 | 2012-09-18 | 2012-09-18 |  | Otter Tail Power Company | Sheridan County | ND |  |  | SPA - SIS | NRIS | OTP Coal Creek - Harvey 230 kV | 99 | 99 | Wind | WT Wind Turbine | Not Started | 2010-10-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-MAR | Individual | Done | In Service | J003 | [5 empty] | NRIS |  | 20 |  | Wind | Bowman County | ND | [27 empty] | Done | 2008-10-22 |  | 2010-04-28 | 2010-05-01 | Montana-Dakota Utilities Company | Bowman County | ND | DPP-2009-MAR | Individual | DPP - SIS | NRIS | 132N, 105W, Section 23 NE 1/4 | 20 | 20 | Wind | WT Wind Turbine | In Service | 2005-04-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | GS5 | Withdrawn | Not Started | G593 | [5 empty] | NRIS |  | 100 |  | Wind | Jackson County | MN | [27 empty] | Withdrawn | 2006-02-07 | 2012-09-26 | 2012-09-26 |  | ITC Midwest | Jackson County | MN |  | GS5 | DPP - SIS | NRIS | Lakefield Junction - Triboji 161 kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2007-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J209 | [5 empty] | ERIS |  | 250 |  | Wind | McIntosh County | ND | [27 empty] | Withdrawn | 2011-03-28 | 2012-09-26 | 2012-09-26 |  | Montana-Dakota Utilities Company | McIntosh County | ND |  |  | SPA - SIS | ERIS | Wishek - Tatanka 230 kV | 250 | 250 | Wind | WT Wind Turbine | Not Started | 2014-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J243 | [5 empty] | NRIS |  | 75 |  | Wind | Jackson County | MN | [27 empty] | Withdrawn | 2012-05-21 | 2012-09-26 | 2012-09-26 |  | ITC Midwest | Jackson County | MN |  |  | Feasibility | NRIS | Lakefield - Triboji 161 kV | 75 | 75 | Wind | WT Wind Turbine | Not Started | 2015-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J234 | [5 empty] | ERIS |  | 35 |  | Wood | Midland County | MI | [27 empty] | Withdrawn | 2011-11-15 | 2012-09-27 | 2012-09-27 |  | Michigan Electric Transmission Company, LLC | Midland County | MI |  |  | Feasibility | ERIS | Tittabawassee Substation | 35 | 35 | Wood |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G935 | [5 empty] | NRIS |  | 201 |  | Wind | Clinton County | IN | [27 empty] | Withdrawn | 2010-06-28 | 2012-10-02 | 2012-10-02 |  | Duke Energy Corporation | Clinton County | IN |  |  | SPA - SIS | NRIS | DEM New London - Frankfort 230 kV | 201 | 201 | Wind | WT Wind Turbine | Not Started | 2010-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J105 | [5 empty] | NRIS |  | 80 |  | Wind | Ford County | IL | [27 empty] | Withdrawn | 2009-12-21 | 2012-10-07 | 2012-10-07 |  | Ameren Illinois | Ford County | IL |  |  | DPP - SIS | NRIS | East Paxton 138kV Substation | 80 | 80 | Wind | WT Wind Turbine | Not Started | 2011-08-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G925 | [5 empty] | NRIS |  | 300 |  | Wind | DeWitt County | IL | [27 empty] | Withdrawn | 2010-05-12 | 2012-10-08 | 2012-10-08 |  | Ameren Illinois | DeWitt County | IL |  |  | SPA - SIS | NRIS | Clinton - Brokaw 345kV | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2010-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G831 | [5 empty] | NRIS |  | 50 |  | Wind | Murray County | MN | [27 empty] | Withdrawn | 2007-07-30 | 2012-10-09 | 2012-10-09 |  | Northern States Power (Xcel Energy) | Murray County | MN |  |  | SPA - SIS | NRIS | Ellsboro - Lake Yankton 115 kV | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2010-08-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G879 | [5 empty] | NRIS |  | 150 |  | Wind | Murray County | MN | [27 empty] | Withdrawn | 2007-10-09 | 2012-10-09 | 2012-10-09 |  | Northern States Power (Xcel Energy) | Murray County | MN |  |  | SPA - SIS | NRIS | Lake Yankton - Ellsborough 115 kV | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2010-03-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H022 | [5 empty] | NRIS |  | 33 |  | Wind | Barnes County | ND | [27 empty] | Withdrawn | 2011-04-28 | 2012-11-02 | 2012-11-02 |  | Otter Tail Power Company | Barnes County | ND |  |  | SPA - SIS | NRIS | OTP Sanborn 41.6 kV Substation | 33 | 33 | Wind | WT Wind Turbine | Not Started | 2012-12-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | East (ATC) | Withdrawn | Withdrawn | J248 | [5 empty] | NRIS Only |  | 675 |  | Gas | Outagamie County | WI | [27 empty] | Withdrawn | 2012-06-27 | 2012-11-02 | 2012-11-02 |  | American Transmission Co. LLC | Outagamie County | WI | DPP-2012-AUG | East (ATC) | DPP - SIS | NRIS Only | Fox Plant 345kV Substation | 650 | 675 | Gas |  | Withdrawn | 2013-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | R56 | [5 empty] | NRIS |  | 150 |  | Wind | Audubon County | IA | [27 empty] | Withdrawn | 2009-01-06 | 2012-11-16 | 2012-11-16 |  | MidAmerican Energy Company | Audubon County | IA |  |  | SPA - SIS | NRIS | Council Bluffs - Grimes 345 kV | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2010-01-01 | 0 | 0 | 0 | 0
|  |  |  | G594 | G594 | Withdrawn | Not Started | G594 | [5 empty] | NRIS |  | 50 |  | Wind | Jackson County | MN | [27 empty] | Withdrawn | 2006-02-07 | 2012-11-28 | 2012-11-28 |  | ITC Transmission | Jackson County | MN | G594 | G594 | Network Upgrade | NRIS | Lakefield Junction - Triboji 161 kV | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2007-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J214 | [5 empty] | NRIS |  | 150 |  | Wind | Marshall County | IN | [27 empty] | Withdrawn | 2011-04-11 | 2012-12-05 | 2012-12-05 |  | Northern Indiana Public Service Company | Marshall County | IN |  |  | Feasibility | NRIS | Plmouth - Lessburg 138kV | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2014-01-01 | 0 | 0 | 0 | 0
|  |  |  | G634 | G634 | Withdrawn | Not Started | G634 | [5 empty] | ERIS |  | 96 |  | Wind | Brookings County | SD | [27 empty] | Withdrawn | 2006-04-27 | 2012-12-27 | 2012-12-27 |  | Northern States Power (Xcel Energy) | Brookings County | SD | G634 | G634 | Network Upgrade | ERIS | Brookings Substation 115 kV | 96 | 96 | Wind | WT Wind Turbine | Not Started | 2007-07-30 | 0 | 0 | 0 | 0
|  |  |  | G635 | G635 | Withdrawn | Not Started | G635 | [5 empty] | ERIS |  | 101 |  | Wind | Deuel County | SD | [27 empty] | Withdrawn | 2006-04-27 | 2012-12-27 | 2012-12-27 |  | Otter Tail Power Company | Deuel County | SD | G635 | G635 | Network Upgrade | ERIS | OTP Toronto Substation | 101 | 101 | Wind | WT Wind Turbine | Not Started | 2007-07-30 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-JUL | MN | Done | In Service | J020 | [5 empty] | NRIS |  | 24.35 |  | Diesel | Wright County | MN | [27 empty] | Done | 2009-01-05 |  | 2010-10-27 | 2010-06-01 | Northern States Power (Xcel Energy) | Wright County | MN | DPP-2009-JUL | MN | DPP - SIS | NRIS | SE corner of Hwy 12 & CR 17 E of Crow River | 24.35 | 24.35 | Diesel | IC Internal Combustion (diesel, piston) Engine | In Service | 2013-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-JUL | MN | Done | In Service | J021 | [5 empty] | NRIS |  | 41.15 |  | Diesel | McLeod County | MN | [27 empty] | Done | 2009-01-05 |  | 2010-04-29 |  | Northern States Power (Xcel Energy) | McLeod County | MN | DPP-2009-JUL | MN | DPP - SIS | NRIS | 305 11th St. E. & 1019 Armstrongs Ave. N. | 41.15 | 41.15 | Diesel | IC Internal Combustion (diesel, piston) Engine | In Service | 2013-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-JUL | 0 | Done | In Service | J022 | [5 empty] | NRIS |  | 6 |  | Nuclear | Manitowoc County | WI | [27 empty] | Done | 2009-01-16 |  | 2010-07-12 | 2011-05-31 | Wisconsin Electric Power Company | Manitowoc County | WI | DPP-2009-JUL |  | Network Upgrade | NRIS | Point Beach Nuclear Plant Unit 1 | 6 | 6 | Nuclear | ST Steam Turbine (including nuclear, geothermal and solar steam, | In Service | 2008-08-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-JUL | 0 | Done | In Service | J023 | [5 empty] | NRIS |  | 6 |  | Nuclear | Manitowoc County | WI | [27 empty] | Done | 2009-01-14 |  | 2010-07-12 | 2011-11-30 | Wisconsin Electric Power Company | Manitowoc County | WI | DPP-2009-JUL |  | Network Upgrade | NRIS | Point Beach Nuclear Plant Unit 2 | 6 | 6 | Nuclear | ST Steam Turbine (including nuclear, geothermal and solar steam, | In Service | 2007-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G964 | [5 empty] | NRIS |  | 300 |  | Wind | Mitchell County | IA | [27 empty] | Withdrawn | 2008-01-29 | 2012-12-27 | 2012-12-27 |  | ITC Midwest | Mitchell County | IA |  |  | SPA - SIS | NRIS | Mitchell County Substation | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | J025 | [5 empty] | ERIS |  | 12.8 |  | Landfill Gas | Macomb County | MI | [27 empty] | Done | 2009-02-27 |  | 2011-05-27 | 2011-10-14 | ITC Transmission | Macomb County | MI |  |  | Network Upgrade | ERIS | Jewell - Spokane - St. Claire 120 kV | 12.8 | 12.8 | Landfill Gas | IC Internal Combustion (diesel, piston) Engine | In Service | 2010-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H011 | [5 empty] | NRIS |  | 250 |  | Wind | Mower County | MN | [27 empty] | Withdrawn | 2008-04-23 | 2012-12-27 | 2012-12-27 |  | ITC Midwest | Mower County | MN |  |  | SPA - SIS | NRIS | Frankfort Corner 161kV Substation | 250 | 250 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J045 | [5 empty] | NRIS |  | 23.1 |  | Wind | Pipestone County | MN | [27 empty] | Withdrawn | 2009-05-18 | 2012-12-27 | 2012-12-27 |  | Northern States Power (Xcel Energy) | Pipestone County | MN |  |  | SPA - SIS | NRIS | RockRiver - South Ridge 69 kV | 23.1 | 23.1 | Wind | WT Wind Turbine | Not Started | 2010-06-30 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-JUL | Individual | Done | Withdrawn | J028 | [5 empty] | NRIS |  | 200 |  | Wind | Tippecanoe County | IN | [27 empty] | Done | 2009-03-09 |  | 2011-01-20 | 2015-12-31 | Duke Energy Corporation | Tippecanoe County | IN | DPP-2009-JUL | Individual | Network Upgrade | NRIS | Attica - Lafayette 230 kV | 200 | 200 | Wind | WT Wind Turbine | Withdrawn | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J095 | [5 empty] | NRIS |  | 300 |  | Wind | Cerro Gordo County | IA | [27 empty] | Withdrawn | 2009-10-30 | 2012-12-27 | 2012-12-27 |  | ITC Midwest | Cerro Gordo County | IA |  |  | SPA - SIS | NRIS | Hancock - Emery 161 kV | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2010-07-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Withdrawn | J030 | [5 empty] | NRIS |  | 198 |  | Wind | Howard County | IA | [27 empty] | Done | 2009-03-11 |  | 2011-01-12 | 2008-12-31 | ITC Midwest | Howard County | IA |  |  | Feasibility | NRIS | Adams Substation | 198 | 198 | Wind | WT Wind Turbine | Withdrawn | 2010-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J151 | [5 empty] | NRIS |  | 350 |  | Wind | Moody County | SD | [27 empty] | Withdrawn | 2010-06-28 | 2012-12-27 | 2012-12-27 |  | Northern States Power (Xcel Energy) | Moody County | SD |  |  | SPA - SIS | NRIS | Split Rock Substation | 350 | 350 | Wind | WT Wind Turbine | Not Started | 2011-05-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J219 | [5 empty] | ERIS |  | 46 |  | Gas | Washtenaw County | MI | [27 empty] | Withdrawn | 2011-06-27 | 2013-01-22 | 2013-01-22 |  | Michigan Electric Transmission Company, LLC | Washtenaw County | MI |  |  | Feasibility | ERIS | Dayton - Judd 120kV | 46 | 46 | Gas |  | Not Started | 2012-08-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-JUL | MN | Done | Withdrawn | J033 | [5 empty] | ERIS |  | 4.94 |  | Wind | Cottonwood County | MN | [27 empty] | Done | 2009-03-11 |  | 2011-02-08 | 2012-07-31 | ITC Midwest | Cottonwood County | MN | DPP-2009-JUL | MN | DPP - SIS | ERIS | 1 pole north of sub, Alliant 69 kV line | 4.94 | 4.94 | Wind | WT Wind Turbine | Withdrawn | 2010-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G778 | [5 empty] | ERIS |  | 5.9 |  | Wind | Grant County | MN | [27 empty] | Withdrawn | 2007-03-29 | 2013-01-24 | 2013-01-24 |  | Great River Energy | Grant County | MN |  |  | SPA - SIS | ERIS | OTP Nashua Tintah - Wendell 41.6kV | 5.9 | 5.9 | Wind | WT Wind Turbine | Not Started | 2009-01-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-JUL | MN | Done | Withdrawn | J035 | [5 empty] | ERIS |  | 4.94 |  | Wind | Wilkin County | MN | [27 empty] | Done | 2009-03-16 |  | 2010-12-28 | 2012-08-31 | Otter Tail Power Company | Wilkin County | MN | DPP-2009-JUL | MN | DPP - SIS | ERIS | OTP Wahpeton 41.6 kV | 4.94 | 4.94 | Wind | WT Wind Turbine | Withdrawn | 2010-11-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J086 | [5 empty] | NRIS |  | 100 |  | Wind | Kandiyohi County | MN | [27 empty] | Withdrawn | 2009-10-05 | 2013-01-24 | 2013-01-24 |  | Great River Energy | Kandiyohi County | MN |  |  | SPA - SIS | NRIS | Willmar - Kerkhoven 115 kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2012-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J087 | [5 empty] | NRIS |  | 30 |  | Wind | Kandiyohi County | MN | [27 empty] | Withdrawn | 2009-10-05 | 2013-01-24 | 2013-01-24 |  | Great River Energy | Kandiyohi County | MN |  |  | SPA - SIS | NRIS | Kandiyohi 69 kV substation | 30 | 30 | Wind | WT Wind Turbine | Not Started | 2012-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G859 | [5 empty] | NRIS |  | 600 |  | Wind | Clay County | MN | [27 empty] | Withdrawn | 2007-09-14 | 2013-01-30 | 2013-01-30 |  | Otter Tail Power Company | Clay County | MN |  |  | SPA - SIS | NRIS | Maple River 345 kV | 600 | 600 | Wind | WT Wind Turbine | Not Started | 2009-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J027 | [5 empty] | NRIS |  | 48.3 |  | Wind | Kandiyohi County | MN | [27 empty] | Withdrawn | 2009-03-04 | 2013-01-30 | 2013-01-30 |  | Great River Energy | Kandiyohi County | MN |  |  | SPA - SIS | NRIS | Willmar - Sunburg 69 kV | 48.3 | 48.3 | Wind | WT Wind Turbine | Not Started | 2010-02-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-JUL | Individual | Done | Withdrawn | J040 | [5 empty] | NRIS |  | 50 |  | Biomass | Marathon County | WI | [27 empty] | Done | 2009-03-17 |  | 2011-05-16 | 2013-09-01 | American Transmission Co. LLC | Marathon County | WI | DPP-2009-JUL | Individual | Network Upgrade | NRIS | 115 kV T-line west of I39, south of S Hwy 29 | 50 | 50 | Biomass | Combined Cycle | Withdrawn | 2010-08-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-AUG | West | Done | In Service | J041 | [5 empty] | NRIS |  | 90 |  | Wind | Grundy County | IA | [27 empty] | Done | 2009-04-16 |  |  | 2010-09-01 | ITC Midwest | Grundy County | IA | DPP-2015-AUG | West | DPP - SIS | NRIS | Wellsburg 161 kV Substation | 90 | 90 | Wind | WT Wind Turbine | In Service | 2019-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J042 | [5 empty] | NRIS |  | 199.8 |  | Wind | Morrison County | MN | [27 empty] | Withdrawn | 2009-05-12 | 2013-01-30 | 2013-01-30 |  | Great River Energy | Morrison County | MN |  |  | SPA - SIS | NRIS | GRE Benton - Brainerd 230kV | 199.8 | 199.8 | Wind | WT Wind Turbine | Not Started | 2013-03-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-JUL | MI | Done | In Service | J043 | [5 empty] | ERIS |  | 3.2 |  | Landfill Gas | Macomb County | MI | [27 empty] | Done | 2009-05-11 |  | 2010-08-24 | 2010-08-02 | ITC Transmission | Macomb County | MI | DPP-2009-JUL | MI | DPP - SIS | ERIS | Carbon Tap 120 kV - Connecting to ITC at Jewel, St. Clair & Spokane substations | 3.2 | 3.2 | Landfill Gas | IC Internal Combustion (diesel, piston) Engine | In Service | 2010-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | Big Stone Area | Withdrawn | Not Started | J077 | [5 empty] | NRIS |  | 50 |  | Wind | Polk County | MN | [27 empty] | Withdrawn | 2009-10-05 | 2013-01-30 | 2013-01-30 |  | Otter Tail Power Company | Polk County | MN |  | Big Stone Area | SPA - SIS | NRIS | OTP Winger 115kV Substation | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2014-05-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | MN | Withdrawn | Withdrawn | G875 | [5 empty] | NRIS |  | 80 |  | Wind | Kittson County | MN | [27 empty] | Withdrawn | 2007-10-09 | 2013-02-11 | 2011-03-25 | 2012-12-31 | Otter Tail Power Company | Kittson County | MN | DPP-2008-NOV | MN | Network Upgrade | NRIS | Donaldson - Warsaw 115 kV | 80 | 80 | Wind | WT Wind Turbine | Withdrawn | 2015-03-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-JUL | IL | Done | In Service | J046 | [5 empty] | NRIS |  | 31 |  | Coal | Fulton County | IL | [27 empty] | Done | 2009-05-18 |  | 2011-05-25 | 2010-06-07 | Ameren Illinois | Fulton County | IL | DPP-2009-JUL | IL | DPP - SIS | NRIS | AERG Duck Creek Plant | 31 | 31 | Coal | Combined Cycle | In Service | 2011-09-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J107 | [5 empty] | NRIS |  | 200 |  | Wind | Logan County | IL | [27 empty] | Withdrawn | 2012-01-30 | 2013-02-28 | 2013-02-28 |  | City of Springfield, IL - CWLP | Logan County | IL |  |  | Feasibility | NRIS | CWLP Interstate Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2011-08-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J123 | [5 empty] | ERIS |  | 200 |  | Nuclear | Goodhue County | MN | [27 empty] | Withdrawn | 2010-04-19 | 2013-03-14 | 2013-03-14 |  | Northern States Power (Xcel Energy) | Goodhue County | MN |  |  | Optional | ERIS | Prairie Island 345kV | 200 | 200 | Nuclear |  | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J147 | [5 empty] | NRIS |  | 60 |  | Wind | Chippewa County | MI | [27 empty] | Withdrawn | 2010-06-28 | 2013-03-18 | 2013-03-18 |  | American Transmission Co. LLC | Chippewa County | MI |  |  | DPP - SIS | NRIS | ATC 9-mile switching | 60 | 60 | Wind | WT Wind Turbine | Not Started | 2010-05-01 | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | CS5 | Withdrawn | Withdrawn | G614 | [5 empty] | NRIS |  | 200 |  | Wind | Emmet County | IA | [27 empty] | Withdrawn | 2006-03-24 | 2013-03-20 | 2012-07-03 | 2018-11-01 | Northern States Power (Xcel Energy) | Emmet County | IA | Pre-Transition SIS | CS5 | Optional | NRIS | Lakefield Junction - Fox Lake 161 kV | 200 | 200 | Wind | WT Wind Turbine | Withdrawn | 2009-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G640 | [5 empty] | NRIS |  | 30 |  | Wind | Todd County | MN | [27 empty] | Withdrawn | 2006-05-22 | 2013-04-03 | 2013-04-03 |  | Minnesota Power (Allete, Inc.) | Todd County | MN |  |  | Network Upgrade | NRIS | MP Long Prairie - Wing Rive 115kV | 30 | 30 | Wind | WT Wind Turbine | Not Started | 2007-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-NOV | MI | Done | In Service | J052 | [5 empty] | NRIS |  | 100 |  | Wind | Bay County | MI | [27 empty] | Done | 2009-07-10 |  | 2011-06-24 | 2012-12-01 | Michigan Electric Transmission Company, LLC | Bay County | MI | DPP-2009-NOV | MI | Network Upgrade | NRIS | Manning substation 138kV | 100 | 100 | Wind | WT Wind Turbine | In Service | 2011-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-NOV | 0 | Done | Withdrawn | J053 | [5 empty] | NRIS |  | 200 |  | Wind | Boone County | IN | [27 empty] | Done | 2009-07-24 |  | 2012-05-18 | 2014-12-31 | Duke Energy Corporation | Boone County | IN | DPP-2009-NOV |  | Network Upgrade | NRIS | 345kV/230kV near Whitestown Substation | 200 | 200 | Wind | WT Wind Turbine | Withdrawn | 2010-09-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J224 | [5 empty] | ERIS |  | 29.5 |  | Wood | Clay County | IN | [27 empty] | Withdrawn | 2011-08-22 | 2013-04-04 | 2013-04-04 |  | Hoosier Energy REC, Inc. | Clay County | IN |  |  | Feasibility | ERIS | Stauton - Keller 69kV | 29.5 | 29.5 | Wood |  | Not Started | 2014-06-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2008-NOV | MN | Withdrawn | Withdrawn | G873 | [5 empty] | NRIS |  | 20 |  | Wind | Kittson County | MN | [27 empty] | Withdrawn | 2007-10-09 | 2013-04-11 | 2011-03-25 | 2012-12-31 | Otter Tail Power Company | Kittson County | MN | DPP-2008-NOV | MN | Network Upgrade | NRIS | Kennedy - Donaldson 41.6 kV | 20 | 20 | Wind | WT Wind Turbine | Withdrawn | 2009-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J269 | [5 empty] | NRIS |  | 26 |  | Coal | Columbia County | WI | [27 empty] | Withdrawn | 2013-01-14 | 2013-04-15 | 2013-04-15 |  | -- No Company -- | Columbia County | WI |  |  | SPA - SIS | NRIS | ATC Columbia 345 kV Substation | 26 | 26 | Coal |  | Not Started | 2014-05-15 | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | CS5 | Withdrawn | Withdrawn | G631 | [5 empty] | ERIS |  | 19 |  | Wind | Nobles County | MN | [27 empty] | Withdrawn | 2006-05-08 | 2013-04-29 | 2012-07-06 | 2018-11-01 | ITC Midwest | Nobles County | MN | Pre-Transition SIS | CS5 | DPP - SIS | ERIS | Adrian - Adrian Tap 69 kV | 19 | 19 | Wind | WT Wind Turbine | Withdrawn | 2007-09-01 | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | CS5 | Withdrawn | Withdrawn | G632 | [5 empty] | ERIS |  | 19 |  | Wind | Nobles County | MN | [27 empty] | Withdrawn | 2006-05-08 | 2013-04-29 | 2012-07-06 | 2018-11-01 | ITC Midwest | Nobles County | MN | Pre-Transition SIS | CS5 | DPP - SIS | ERIS | Magnolia - Worthington 69 kV | 19 | 19 | Wind | WT Wind Turbine | Withdrawn | 2007-11-01 | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | CS5 | Withdrawn | Withdrawn | G633 | [5 empty] | ERIS |  | 19 |  | Wind | Nobles County | MN | [27 empty] | Withdrawn | 2006-05-08 | 2013-04-29 | 2012-07-06 | 2018-11-01 | ITC Midwest | Nobles County | MN | Pre-Transition SIS | CS5 | DPP - SIS | ERIS | ITC Midwest Elk - Magnolia 161 kV | 19 | 19 | Wind | WT Wind Turbine | Withdrawn | 2007-07-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-NOV | Individual | Done | In Service | J060 | [5 empty] | NRIS |  | 29 |  | Wind | Delta County | MI | [27 empty] | Done | 2009-07-27 |  | 2010-12-10 | 2012-03-30 | American Transmission Co. LLC | Delta County | MI | DPP-2009-NOV | Individual | Network Upgrade | NRIS | ATC line west of Indian lake | 29 | 29 | Wind | WT Wind Turbine | In Service | 2011-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G519 | [5 empty] | NRIS |  | 600 |  | Coal | Itasca County | MN | [27 empty] | Withdrawn | 2005-05-19 | 2013-05-07 | 2007-12-10 | 2012-07-31 | Minnesota Power (Allete, Inc.) | Itasca County | MN |  |  | Optional | NRIS | Blackberry 230/115kV Substation | 600 | 600 | Coal |  | Withdrawn | 2006-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J257 | [5 empty] | NRIS |  | 149.5 |  | Wind | Newton County | IN | [27 empty] | Withdrawn | 2012-10-29 | 2013-05-07 | 2013-05-07 |  | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Newton County | IN |  |  | Feasibility | NRIS | NIPSCO Thayer - Schafer 138kV line | 149.5 | 149.5 | Wind |  | Not Started | 2018-10-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-MAR | MN | Withdrawn | Withdrawn | G968 | [5 empty] | NRIS |  | 100 |  | Wind | Marshall County | MN | [27 empty] | Withdrawn | 2008-01-31 | 2013-05-13 | 2011-01-18 | 2012-11-20 | Otter Tail Power Company | Marshall County | MN | DPP-2009-MAR | MN | Network Upgrade | NRIS | Strandquist - Viking 115 kV | 100 | 100 | Wind | WT Wind Turbine | Withdrawn | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | MI | Withdrawn | Withdrawn | J185 | [5 empty] | NRIS |  | 100 |  | Wind | Huron County | MI | [27 empty] | Withdrawn | 2010-11-15 | 2013-05-29 | 2013-05-29 | 2015-05-31 | ITC Transmission | Huron County | MI | DPP-2012-AUG | MI | DPP - SIS | NRIS | Bauer - Rapson 345 kV | 100 | 100 | Wind | WT Wind Turbine | Withdrawn | 2011-09-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J094 | [5 empty] | NRIS |  | 200 |  | Wind | Manitowoc County | WI | [27 empty] | Withdrawn | 2011-11-14 | 2013-06-07 | 2013-06-07 |  | -- No Company -- | Manitowoc County | WI |  |  | Feasibility | NRIS | Kewaunee - Shoto 138 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2010-07-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-APR | UP Michigan | Done | Withdrawn | J066 | [5 empty] | NRIS |  | 60 |  | Wind | Chippewa County | MI | [27 empty] | Done | 2009-08-26 |  | 2012-02-01 | 2014-12-31 | American Transmission Co. LLC | Chippewa County | MI | DPP-2010-APR | UP Michigan | Network Upgrade | NRIS | Pine River 69kV Substation | 60 | 60 | Wind | WT Wind Turbine | Withdrawn | 2011-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G680 | [5 empty] | ERIS |  | 20 |  | Wind | Yellow Medicine County | MN | [27 empty] | Withdrawn | 2006-09-11 | 2013-06-10 | 2013-06-10 |  | Otter Tail Power Company | Yellow Medicine County | MN |  |  | SPA - SIS | ERIS | OTP Burr Jct - Toronto 115 kV | 20 | 20 | Wind | WT Wind Turbine | Not Started | 2008-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-APR | MI | Withdrawn | Withdrawn | J056 | [5 empty] | NRIS |  | 100.8 |  | Wind | Hillsdale County | MI | [27 empty] | Withdrawn | 2009-07-27 | 2013-06-14 | 2012-07-13 | 2015-10-15 | Michigan Electric Transmission Company, LLC | Hillsdale County | MI | DPP-2010-APR | MI | Network Upgrade | NRIS | Litchfield - Coldwater 138kV | 100.8 | 100.8 | Wind | WT Wind Turbine | Withdrawn | 2012-07-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-NOV | Indiana | Done | In Service | J069 | [5 empty] | NRIS |  | 3.9 |  | Hydro | Perry County | IN | [27 empty] | Done | 2009-09-28 |  | 2011-03-07 | 2010-04-15 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Perry County | IN | DPP-2009-NOV | Indiana | DPP - SIS | NRIS | Tell City - Cloverpoint 138 kV | 3.9 | 3.9 | Hydro | OT Other | In Service | 2011-09-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J212 | [5 empty] | ERIS |  | 600 |  | Wind | Ward County | ND | [27 empty] | Withdrawn | 2011-04-11 | 2013-06-21 | 2013-06-21 |  | Great River Energy | Ward County | ND |  |  | Optional | ERIS | GRE Coal Creek 230kV Substation | 600 | 600 | Wind | WT Wind Turbine | Not Started | 2012-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J244 | [5 empty] | NRIS |  | 726 |  | Gas | Christian County | IL | [27 empty] | Withdrawn | 2012-05-21 | 2013-06-24 | 2013-06-24 |  | Ameren Illinois | Christian County | IL |  |  | Feasibility | NRIS | AMIL Pawnee 345 kV Substation | 601 | 726 | Gas |  | Not Started | 2012-02-29 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | West | Withdrawn | Withdrawn | J182 | [5 empty] | ERIS |  | 150 |  | Wind | Dodge County | MN | [27 empty] | Withdrawn | 2010-11-15 | 2013-06-26 | 2013-06-26 |  | Great River Energy | Dodge County | MN | DPP-2012-AUG | West | DPP - SIS | ERIS | Pleasant Valley Substation | 150 | 150 | Wind | WT Wind Turbine | Withdrawn |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | West | Withdrawn | Withdrawn | G681 | [5 empty] | NRIS |  | 44 |  | Wind | Freeborn County | MN | [27 empty] | Withdrawn | 2006-09-18 | 2013-06-27 | 2013-06-27 |  | ITC Midwest | Freeborn County | MN | DPP-2012-AUG | West | DPP - SIS | NRIS | Walters - Albert Lea 69 kV | 44 | 44 | Wind | WT Wind Turbine | Withdrawn | 2007-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J225 | [5 empty] | NRIS |  | 100 |  | Wind | Eaton County | MI | [27 empty] | Withdrawn | 2011-09-19 | 2013-07-02 | 2013-07-02 |  | Michigan Electric Transmission Company, LLC | Eaton County | MI |  |  | Feasibility | NRIS | Charlotte - Delhi 115 kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2012-08-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | MI | Done | In Service | J075 | [5 empty] | NRIS |  | 150 |  | Wind | Huron County | MI | [27 empty] | Done | 2009-10-05 |  | 2013-05-31 | 2013-12-15 | ITC Transmission | Huron County | MI | DPP-2012-AUG | MI | Int FaS | NRIS | Bauer - Rapson 345 kV | 150 | 150 | Wind | WT Wind Turbine | In Service | 2015-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | R64 | [5 empty] | NRIS |  | 70 |  | Wind | Carroll County | IA | [27 empty] | Withdrawn | 2011-09-08 | 2013-07-02 | 2013-07-02 |  | MidAmerican Energy Company | Carroll County | IA |  |  | Feasibility | NRIS | Victory Substation | 70 | 70 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G962 | [5 empty] | NRIS |  | 100 |  | Wind | Mitchell County | IA | [27 empty] | Withdrawn | 2008-01-29 | 2013-07-30 | 2013-07-30 |  | ITC Midwest | Mitchell County | IA |  |  | SPA - SIS | NRIS | Mitchell County Substation | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2012-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J193 | [5 empty] | NRIS |  | 50 |  | Wind | Otter Tail County | MN | [27 empty] | Withdrawn | 2011-02-03 | 2013-08-01 | 2013-08-01 |  | Great River Energy | Otter Tail County | MN |  |  | SPA - SIS | NRIS | Tamarac 115 kV sub | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2011-08-09 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G904 | [5 empty] | NRIS |  | 150 |  | Wind | Rolette County | ND | [27 empty] | Withdrawn | 2007-11-02 | 2013-08-05 | 2013-08-05 | 2012-11-15 | Northern States Power (Xcel Energy) | Rolette County | ND |  |  | Network Upgrade | NRIS | Rugby - Glenboro 230kV | 150 | 150 | Wind | WT Wind Turbine | Withdrawn | 2010-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G771 | [5 empty] | NRIS |  | 200 |  | Wind | Howard County | IA | [27 empty] | Withdrawn | 2011-05-03 | 2013-08-07 | 2013-08-07 |  | ITC Midwest | Howard County | IA |  |  | SPA - SIS | NRIS | ITCM Adams - Hazleton 345 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2008-11-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H041 | [5 empty] | ERIS |  | 400 |  | Wind | Lincoln County | MN | [27 empty] | Withdrawn | 2010-09-27 | 2013-08-13 | 2013-08-13 |  | Northern States Power (Xcel Energy) | Lincoln County | MN |  |  | SPA - SIS | ERIS | Buffalo Ridge 115 kV Substation | 400 | 400 | Wind | WT Wind Turbine | Not Started | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G762 | [5 empty] | NRIS |  | 150.39 |  | Wind | Mower County | MN | [27 empty] | Withdrawn | 2007-03-14 | 2013-08-21 | 2013-08-21 |  | Great River Energy | Mower County | MN |  |  | SPA - SIS | NRIS | Pleasant Valley 345 kV Substation | 150.39 | 150.39 | Wind | WT Wind Turbine | Not Started | 2008-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G740 | [5 empty] | NRIS |  | 150 |  | Wind | Howard County | IA | [27 empty] | Withdrawn | 2007-02-13 | 2013-09-03 | 2013-09-03 |  | ITC Midwest | Howard County | IA |  |  | SPA - SIS | NRIS | Adams - Hazleton 345 kV | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2012-12-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-NOV | Individual | Done | Withdrawn | J084 | [5 empty] | NRIS |  | 50 |  | Wind | Grant County | WI | [27 empty] | Done | 2009-10-05 |  | 2011-09-08 | 2015-12-31 | American Transmission Co. LLC | Grant County | WI | DPP-2009-NOV | Individual | Network Upgrade | NRIS | Bloomington 69 kV Substation | 50 | 50 | Wind | WT Wind Turbine | Withdrawn | 2012-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J109 | [5 empty] | NRIS |  | 99 |  | Wind | Lafayette County | WI | [27 empty] | Withdrawn | 2011-04-26 | 2013-09-03 | 2013-09-03 |  | American Transmission Co. LLC | Lafayette County | WI |  |  | SPA - SIS | NRIS | ATC Darlington - Hillman 138 kV | 99 | 99 | Wind | WT Wind Turbine | Not Started | 2013-08-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J158 | [5 empty] | NRIS |  | 150 |  | Wind | Piatt County | IL | [27 empty] | Withdrawn | 2010-08-19 | 2013-09-09 | 2013-09-09 |  | Ameren Illinois | Piatt County | IL |  |  | SPA - SIS | NRIS | Ameren Brokaw - Champaign 138kV | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2012-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J177 | [5 empty] | ERIS |  | 97.5 |  | Wind | Saint Croix County | WI | [27 empty] | Withdrawn | 2010-11-15 | 2013-09-09 | 2013-09-09 |  | Northern States Power (Xcel Energy) | Saint Croix County | WI |  |  | SPA - SIS | ERIS | Pine Lake - Apple River 161kV | 97.5 | 97.5 | Wind | WT Wind Turbine | Not Started | 2015-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G663 | [5 empty] | ERIS |  | 20 |  | Wind | Lincoln County | MN | [27 empty] | Withdrawn | 2006-08-07 | 2013-10-09 | 2013-10-09 |  | Northern States Power (Xcel Energy) | Lincoln County | MN |  |  | SPA - SIS | ERIS | Yankee 34.5kV Substation | 20 | 20 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2009-NOV | 0 | Done | In Service | J089 | [5 empty] | NRIS |  | 447 |  | Coal | Warrick County | IN | [27 empty] | Done | 2009-10-05 |  | 2011-01-26 |  | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Warrick County | IN | DPP-2009-NOV |  | Network Upgrade | NRIS | Vectren Culley 138 kV substation | 447 | 447 | Coal | Combined Cycle | In Service | 2012-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G658 | [5 empty] | ERIS |  | 20 |  | Wind | Pope County | MN | [27 empty] | Withdrawn | 2006-07-14 | 2013-10-21 | 2013-10-21 |  | Northern States Power (Xcel Energy) | Pope County | MN |  |  | Network Upgrade | ERIS | Xel Westport 69 kV Substation | 20 | 20 | Wind | WT Wind Turbine | Not Started | 2008-08-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | WEST | Done | In Service | J091 | [5 empty] | NRIS |  | 66 |  | Wind | Hancock County | IA | [27 empty] | Done | 2009-10-15 |  | 2015-03-13 | 2009-12-11 | ITC Midwest | Hancock County | IA | DPP-2012-AUG | WEST | Network Upgrade | NRIS | ITCM Lime Creek 161 kV Substation | 66 | 66 | Wind | WT Wind Turbine | In Service | 2011-06-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G657 | [5 empty] | ERIS |  | 20 |  | Wind | Pope County | MN | [27 empty] | Withdrawn | 2006-07-14 | 2013-10-23 | 2013-10-23 |  | Northern States Power (Xcel Energy) | Pope County | MN |  |  | Network Upgrade | ERIS | Glenwood 69 kV sub | 20 | 20 | Wind | WT Wind Turbine | Not Started | 2007-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | Individual | Withdrawn | Not Started | J217 | [5 empty] | NRIS |  | 50 |  | Wind | Columbia County | WI | [27 empty] | Withdrawn | 2011-06-24 | 2013-11-04 | 2013-11-04 |  | American Transmission Co. LLC | Columbia County | WI |  | Individual | DPP - SIS | NRIS | North Randolph 69 kV Substation | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2014-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G638 | [5 empty] | ERIS |  | 20 |  | Wind | Stevens County | MN | [27 empty] | Withdrawn | 2006-05-17 | 2013-11-07 | 2013-11-07 |  | Otter Tail Power Company | Stevens County | MN |  |  | Network Upgrade | ERIS | OTP Graceville - Morris 41 kV | 20 | 20 | Wind | WT Wind Turbine | Not Started | 2007-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G843 | [5 empty] | NRIS |  | 100 |  | Wind | Otter Tail County | MN | [27 empty] | Withdrawn | 2007-08-24 | 2013-11-07 | 2013-11-07 |  | Otter Tail Power Company | Otter Tail County | MN |  |  | Network Upgrade | NRIS | GRE Elmo - Miltona 115kV | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2010-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H101 | [5 empty] | NRIS |  | 50 |  | Gas | Beltrami County | MN | [27 empty] | Withdrawn | 2008-08-25 | 2013-11-07 | 2013-11-07 |  | Otter Tail Power Company | Beltrami County | MN |  |  | Network Upgrade | NRIS | OTP Solway 115kV Substation | 50 | 50 | Gas |  | Not Started | 2011-08-01 | 0 | 0 | 0 | 0
|  |  |  | FES-2013-JUL | 0 | Withdrawn | Not Started | J287 | [5 empty] | ERIS |  | 56.7 |  | Wind | Nobles County | MN | [27 empty] | Withdrawn | 2013-06-24 | 2013-11-14 | 2013-11-14 |  | ITC Midwest | Nobles County | MN | FES-2013-JUL |  | Feasibility | ERIS | approx 12 east of ITC Midwest 161 kV Magnolia Substation | 56.7 | 56.7 | Wind |  | Not Started | 2015-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J167 | [5 empty] | NRIS |  | 500 |  | Gas | Dakota County | MN | [27 empty] | Withdrawn | 2010-09-10 | 2013-11-18 | 2013-11-18 |  | Northern States Power (Xcel Energy) | Dakota County | MN |  |  | SPA - SIS | NRIS | Black Dog 115kV | 500 | 500 | Gas | CT Combined-Cycle Combustion ? Turbine Part | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J240 | [5 empty] | NRIS |  | 720 |  | Gas | Vermillion County | IN | [27 empty] | Withdrawn | 2012-04-02 | 2013-11-18 | 2013-11-18 |  | Duke Energy Corporation | Vermillion County | IN |  |  | Feasibility | NRIS | DEM Clinton - Cayuga 230 kV | 720 | 720 | Gas |  | Not Started | 2016-04-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J311 | [5 empty] | NRIS |  | 201 |  | Wind | Nodaway County | MO | [27 empty] | Withdrawn | 2013-11-18 | 2013-11-22 | 2013-11-22 |  | -- No Company -- | Nodaway County | MO |  |  |  | NRIS | 161 kV Maryville-Creston | 201 | 201 | Wind |  | Not Started | 2016-11-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J542 | [5 empty] | NRIS |  | 1235 |  | Gas | Vigo County | IN | [27 empty] | Withdrawn | 2016-01-11 | 2017-07-21 |  | 2020-04-30 | Duke Energy Corporation | Vigo County | IN |  |  | SPA - SIS | NRIS | Unknown | 1120 | 1235 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | 0 | Withdrawn | Withdrawn | J215 | [5 empty] | NRIS |  | 670 |  | Gas | St. Joseph County | IN | [27 empty] | Withdrawn | 2011-06-23 | 2013-12-03 | 2013-12-03 |  | Northern Indiana Public Service Company | St. Joseph County | IN | DPP-2012-AUG |  | DPP - SIS | NRIS | Stillwell 345 kV | 670 | 670 | Gas |  | Withdrawn | 2014-08-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J543 | [5 empty] | ERIS |  | 19.5 |  | Wood | Houghton County | MI | [27 empty] | Withdrawn | 2016-01-11 | 2017-07-21 |  | 2018-03-01 | American Transmission Co. LLC | Houghton County | MI |  |  | Feasibility | ERIS | Unknown | 19 | 19.5 | Wood | OT - co-gen | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | G517 | [5 empty] | ERIS |  | 130 |  | Wind | Cottonwood County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-10-24 |  | 2021-04-15 | ITC Midwest | Cottonwood County | MN | DPP-2017-AUG | West | PHASE 3 | ERIS | Summit Switch Station - South Storden 69 kV line | 130 | 130 | Wind | WT Wind Turbine | Not Started | 2006-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G491 | [5 empty] | ERIS |  | 100 |  | Wind | Pipestone County | MN | [27 empty] | Withdrawn | 2004-12-29 | 2013-12-04 | 2007-08-28 | 2014-12-31 | Northern States Power (Xcel Energy) | Pipestone County | MN |  |  | Network Upgrade | ERIS | Chanarambie Substation | 100 | 100 | Wind | WT Wind Turbine | Withdrawn | 2010-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J247 | [5 empty] | NRIS |  | 150 |  | Wind | Sanilac County | MI | [27 empty] | Withdrawn | 2012-05-21 | 2013-12-12 | 2013-12-12 |  | Michigan Electric Transmission Company, LLC | Sanilac County | MI |  |  | Feasibility | NRIS | Sandusky 120 kV Substation | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2013-11-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | MI | Withdrawn | Withdrawn | J199 | [5 empty] | NRIS |  | 120 |  | Wind | Gratiot County | MI | [27 empty] | Withdrawn | 2011-02-08 | 2013-12-18 | 2013-12-18 |  | Michigan Electric Transmission Company, LLC | Gratiot County | MI | DPP-2012-AUG | MI | Int FaS | NRIS | Slate Substation via J132 Interconnection Facilities | 120 | 120 | Wind | WT Wind Turbine | Withdrawn | 2013-12-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ATC) | Active | Not Started | J1000 | [5 empty] | NRIS | N | 50 |  | Solar | Grant County | WI |  |  |  | 1 | 1 | 200000 | 0 | [9 empty] | 0 | 6441458 |  | 6441458 | 6441458 | 128.8292 | 128.8292 | 6441458 |  |  |  | Active | 2018-03-12 |  |  | 2021-10-01 | American Transmission Co. LLC | Grant County | WI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | Nelson Dewey - Lancaster 138kV Line | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 50 | 50 | 50 | 50
|  |  |  | 0 | 0 | Withdrawn | Not Started | R57 | [5 empty] | NRIS |  | 100 |  | Wind | Carroll County | IA | [27 empty] | Withdrawn | 2009-03-30 | 2014-01-06 | 2014-01-06 |  | MidAmerican Energy Company | Carroll County | IA |  |  | SPA - SIS | NRIS | Victory 161 kV Substation | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2010-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J245 | [5 empty] | NRIS |  | 100 |  | Wind | Tuscola County | MI | [27 empty] | Withdrawn | 2012-05-21 | 2014-01-09 | 2014-01-09 |  | Michigan Electric Transmission Company, LLC | Tuscola County | MI |  |  | Feasibility | NRIS | ITC Thumb Loop | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2018-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J221 | [5 empty] | ERIS |  | 5 |  | Wind | Saint Croix County | WI | [27 empty] | Withdrawn | 2011-08-22 | 2014-01-30 | 2014-01-30 |  | Northern States Power (Xcel Energy) | Saint Croix County | WI |  |  | SPA - SIS | ERIS | Pine Lake - Apple River 161 kV | 5 | 5 | Wind | WT Wind Turbine | Not Started | 2014-01-01 | 0 | 0 | 0 | 0
|  |  |  | FES-2013-DEC | 0 | Withdrawn | Not Started | J314 | [5 empty] | NRIS |  | 101 |  | Wind | Columbia County | WI | [27 empty] | Withdrawn | 2013-11-18 | 2014-02-25 | 2014-02-25 |  | -- No Company -- | Columbia County | WI | FES-2013-DEC |  | Feasibility | NRIS | Unknown | 101 | 101 | Wind |  | Not Started | 2017-09-01 | 0 | 0 | 0 | 0
|  |  |  | FES-20113-DEC | 0 | Withdrawn | Not Started | J315 | [5 empty] | NRIS |  | 101 |  | Wind | Rock County | WI | [27 empty] | Withdrawn | 2013-11-18 | 2014-02-25 | 2014-02-25 |  | -- No Company -- | Rock County | WI | FES-20113-DEC |  | Feasibility | NRIS | ATC 138 kV Sunrise-Lakehead Tap | 101 | 101 | Wind |  | Not Started | 2017-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | J186 | [5 empty] | NRIS |  | 100 |  | Wind | Huron County | MI | [27 empty] | Withdrawn | 2010-11-15 | 2014-03-12 | 2014-03-12 | 2015-12-15 | ITC Transmission | Huron County | MI |  |  | Optional | NRIS | Baker - Rapson 345kV Substation near Slate | 100 | 100 | Wind | WT Wind Turbine | Withdrawn | 2011-09-30 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | West | Withdrawn | Withdrawn | H048 | [5 empty] | NRIS |  | 50 |  | Wind | Stearns County | MN | [27 empty] | Withdrawn | 2008-06-12 | 2014-03-19 | 2013-03-19 | 2012-12-30 | Northern States Power (Xcel Energy) | Stearns County | MN | DPP-2012-AUG | West | DPP - SIS | NRIS | Xcel Paynesville 69 kV Substation | 50 | 50 | Wind | WT Wind Turbine | Withdrawn | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | West | Withdrawn | Withdrawn | H058 | [5 empty] | NRIS |  | 45 |  | Wind | Stearns County | MN | [27 empty] | Withdrawn | 2008-06-12 | 2014-03-19 | 2014-03-19 | 2012-12-30 | Northern States Power (Xcel Energy) | Stearns County | MN | DPP-2012-AUG | West | DPP - SIS | NRIS | Xcel Paynesville 69kV Substation | 45 | 45 | Wind | WT Wind Turbine | Withdrawn | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | FES-2012-SEP | 0 | Withdrawn | Not Started | J250 | [5 empty] | NRIS |  | 999 |  | Gas | Shelby County | IN | [27 empty] | Withdrawn | 2012-08-28 | 2014-04-08 | 2014-04-08 |  | Duke Energy Corporation | Shelby County | IN | FES-2012-SEP |  | Feasibility | NRIS | Prescott 345 kV Substation | 875 | 999 | Gas |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J155 | [5 empty] | ERIS |  | 4.94 |  | Wind | Lyon County | MN | [27 empty] | Withdrawn | 2010-06-28 | 2014-04-21 | 2014-04-21 |  | Northern States Power (Xcel Energy) | Lyon County | MN |  |  | SPA - SIS | ERIS | Xcel Milroy - Yellow Medicine 69kV | 4.94 | 4.94 | Wind | WT Wind Turbine | Not Started | 2012-11-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J036 | [5 empty] | ERIS |  | 4.94 |  | Wind | Jackson County | MN | [27 empty] | Withdrawn | 2009-03-16 | 2014-04-22 | 2014-04-22 |  | ITC Midwest | Jackson County | MN |  |  | SPA - SIS | ERIS | Windom - Heron Lake 69 kV | 4.94 | 4.94 | Wind | WT Wind Turbine | Not Started | 2010-08-01 | 0 | 0 | 0 | 0
|  |  |  | FES-2012-SEP | 0 | Withdrawn | Not Started | J254 | [5 empty] | ERIS |  | 200 |  | Wind | Lyon County | MN | [27 empty] | Withdrawn | 2012-09-10 | 2014-04-22 | 2014-04-22 |  | Northern States Power (Xcel Energy) | Lyon County | MN | FES-2012-SEP |  | Feasibility | ERIS | Brookings County - Lyon County 345 kV | 200 | 200 | Wind |  | Not Started | 2014-10-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J318 | [5 empty] | ERIS |  | 30 |  | Wind | Morgan County, Sangamon County | IL | [27 empty] | Withdrawn | 2013-12-18 | 2014-05-15 | 2014-05-15 |  | Prairie Power, Inc. | Morgan County, Sangamon County | IL |  |  |  | ERIS | SW corner of Berlin Tower Rd & Huff Road | 30 | 30 | Wind |  | Not Started | 2017-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-APR | MI | Done | In Service | J102 | [5 empty] | NRIS |  | 26 |  | Nuclear | Van Buren County | MI | [27 empty] | Done | 2009-12-14 |  | 2011-01-07 | 2010-10-31 | Michigan Electric Transmission Company, LLC | Van Buren County | MI | DPP-2010-APR | MI | DPP - SIS | NRIS | Palisades Nuclear Power Plant switchyard | 26 | 26 | Nuclear | ST Steam Turbine (including nuclear, geothermal and solar steam, | In Service | 2013-09-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G916 | [5 empty] | NRIS |  | 53 |  | Wind | Sheridan County | ND | [27 empty] | Withdrawn | 2011-04-28 | 2014-05-28 | 2014-05-28 |  | Otter Tail Power Company | Sheridan County | ND |  |  | SPA - SIS | NRIS | OTP Harvey 230kV Substation | 53 | 53 | Wind | WT Wind Turbine | Not Started | 2010-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J349 | [5 empty] | NRIS |  | 72 |  | Solar | Sherburne County | MN | [27 empty] | Withdrawn | 2014-05-19 | 2014-06-03 | 2014-06-03 |  | Xcel Energy | Sherburne County | MN |  |  |  | NRIS | SE Corner of 137th ST & 140th AV, Becker, MN | 100 | 72 | Solar |  | Not Started | 2016-05-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1001 | [5 empty] | NRIS | N | 40 |  | Solar | Lincoln County | MN |  |  |  | 1 | 0 | 160000 | 345292 | [7 empty] | 0 | 33148 | 0 | 8265000 | 0 | 8265000 | 8298148 | 206.625 | 207.4537 | 8298148 |  |  |  | Withdrawn | 2018-03-12 | 2021-03-09 |  | 2020-09-01 | Northern States Power (Xcel Energy) | Lincoln County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Buffalo Ridge 115kV Substation | 40 | 40 | Solar | PV Photovoltaic | Not Started |  | 40 | 40 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J054 | [5 empty] | NRIS |  | 197.8 |  | Wind | Tipton County | IN | [27 empty] | Withdrawn | 2013-01-07 | 2014-06-26 | 2014-06-26 | 2015-10-15 | Duke Energy Corporation | Tipton County | IN |  |  | Network Upgrade | NRIS | DEM Kokomo - Noblesville 230kV | 197.8 | 197.8 | Wind | WT Wind Turbine | Not Started | 2011-09-01 | 0 | 0 | 0 | 0
|  |  |  | FES-2013-JAN | 0 | Withdrawn | Not Started | J268 | [5 empty] | NRIS |  | 801 |  | Gas | Genesee County | MI | [27 empty] | Withdrawn | 2013-01-14 | 2014-07-02 | 2014-07-02 |  | Michigan Electric Transmission Company, LLC | Genesee County | MI | FES-2013-JAN |  | Feasibility | NRIS | Thelford 345kV Substation | 725 | 801 | Gas |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ATC) | Active | Not Started | J1002 | [5 empty] | NRIS | N | 99 |  | Solar | Waushara County | WI |  |  |  | 1 | 1 | 396000 | 0 | [9 empty] | 887272 | 2618981 | 0 | 2618981 | 3506253 | 26.4544 | 35.4167 | 3506253 |  |  |  | Active | 2018-03-12 |  |  | 2021-10-01 | American Transmission Co. LLC | Waushara County | WI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | Wautoma 138kV Switchyard | 99 | 99 | Solar | PV Photovoltaic | Not Started |  | 99 | 99 | 99 | 99
|  |  |  | DPP-2018-APR | East (ATC) | Active | Not Started | J1003 | [5 empty] | NRIS | N | 50 |  | Solar | Dodge County | WI |  |  |  | 1 | 1 | 200000 | 0 | [9 empty] | 410328 | 366697 | 2798507 | 366697 | 3575532 | 7.3339 | 71.5106 | 3575532 |  |  |  | Active | 2018-03-12 |  |  | 2021-10-01 | American Transmission Co. LLC | Dodge County | WI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | North Beaver Dam 69 kV Substation | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 50 | 50 | 50 | 50
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1004 | [5 empty] | NRIS |  | 800 |  | Wind | Mecosta County,Montcalm County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2018-11-01 |  | 2020-09-01 | Michigan Electric Transmission Company, LLC | Mecosta County,Montcalm County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Kenowa - Nelson Road 345kV Line Tap | 800 | 800 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1005 | [5 empty] | NRIS |  | 200 |  | Solar | Midland County,Saginaw County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-06-30 |  | 2021-09-01 | Michigan Electric Transmission Company, LLC | Midland County,Saginaw County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Murphy 345kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
|  |  |  | FES-2014-JUN | 0 | Withdrawn | Not Started | J355 | [5 empty] | NRIS |  | 810 |  | Gas | Adair County | IA | [27 empty] | Withdrawn | 2014-05-19 | 2014-07-07 | 2014-07-07 |  | MidAmerican Energy Company | Adair County | IA | FES-2014-JUN |  | Feasibility | NRIS | Cooper-Atchison Co-Booneville 345 kV crosses Pony Creek-Rolling Hills 345 kV | 660 | 810 | Gas |  | Not Started | 2017-08-01 | 0 | 0 | 0 | 0
|  |  |  | FES-2014-JUN | 0 | Withdrawn | Not Started | J357 | [5 empty] | NRIS |  | 135 |  | Coal | Woodbury County | IA | [27 empty] | Withdrawn | 2014-05-19 | 2014-07-07 | 2014-07-07 |  | MidAmerican Energy Company | Woodbury County | IA | FES-2014-JUN |  | Feasibility | NRIS | Neal North Plant | 135 | 135 | Coal |  | Not Started | 2018-01-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1006 | [5 empty] | NRIS |  | 100 |  | Solar | Brookings County | SD | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2020-09-01 | Northern States Power (Xcel Energy) | Brookings County | SD | DPP-2018-APR | West | PHASE 3 | NRIS | Brookings - Yankee 115kV Line Tap | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES_2014-JUN | 0 | Withdrawn | Not Started | J358 | [5 empty] | NRIS |  | 280 |  | Coal | Woodbury County | IA | [27 empty] | Withdrawn | 2014-05-19 | 2014-07-07 | 2014-07-07 |  | MidAmerican Energy Company | Woodbury County | IA | FES_2014-JUN |  | Feasibility | NRIS | Neal North Plant | 280 | 280 | Coal |  | Not Started | 2016-01-10 | 0 | 0 | 0 | 0
|  |  |  | FES-2014-JUN | 0 | Withdrawn | Not Started | J359 | [5 empty] | NRIS |  | 232 |  | Gas | Woodbury County | IA | [27 empty] | Withdrawn | 2014-05-19 | 2014-07-07 | 2014-07-07 |  | MidAmerican Energy Company | Woodbury County | IA | FES-2014-JUN |  | Feasibility | NRIS | Neal North Plant | 168 | 232 | Gas |  | Not Started | 2015-04-01 | 0 | 0 | 0 | 0
|  |  |  | FES-2014-JUN | 0 | Withdrawn | Not Started | J362 | [5 empty] | NRIS |  | 116 |  | Gas | Polk County | IA | [27 empty] | Withdrawn | 2014-05-19 | 2014-07-07 | 2014-07-07 |  | MidAmerican Energy Company | Polk County | IA | FES-2014-JUN |  | Feasibility | NRIS | DPS 161 kV bus | 84 | 116 | Gas |  | Not Started | 2016-01-10 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Done | Under Construction | J1007 | [5 empty] | NRIS |  | 200 |  | Solar | Crittenden County | AR | [21 empty] | 0 | 0 |  |  |  |  | Done | 2018-03-12 |  | 2020-08-12 | 2021-09-01 | Entergy Arkansas, LLC | Crittenden County | AR | DPP-2018-APR | South | GIA | NRIS | Marion - Marked Tree 161kV Line Tap | 200 | 200 | Solar | PV Photovoltaic | Under Construction | 2023-06-01 | 200 | 200 | 180 | 180
|  |  |  | FES-2014-JUN | 0 | Withdrawn | Not Started | J363 | [5 empty] | NRIS |  | 810 |  | Gas | Pottawattamie County | IA | [27 empty] | Withdrawn | 2014-05-19 | 2014-07-07 | 2014-07-07 |  | MidAmerican Energy Company | Pottawattamie County | IA | FES-2014-JUN |  | Feasibility | NRIS | CBPS-Fallow Ave 345 kV line near Pony Creek 345 kV station | 660 | 810 | Gas |  | Not Started | 2016-01-10 | 0 | 0 | 0 | 0
|  |  |  | FES-2014-JUN | 0 | Withdrawn | Not Started | J364 | [5 empty] | NRIS |  | 464 |  | Gas | Adair County | IA | [27 empty] | Withdrawn | 2014-05-19 | 2014-07-07 | 2014-07-07 |  | MidAmerican Energy Company | Adair County | IA | FES-2014-JUN |  | Feasibility | NRIS | Cooper-Atchison Co-Booneville 345 kV crosses CBPS Pony Creek-Rolling Hills-Madison Co 345 kV line | 336 | 464 | Gas |  | Not Started | 2016-01-10 | 0 | 0 | 0 | 0
|  |  |  | FES-2014-JUN | 0 | Withdrawn | Not Started | J365 | [5 empty] | NRIS |  | 464 |  | Gas | Pottawattamie County | IA | [27 empty] | Withdrawn | 2014-05-19 | 2014-07-07 | 2014-07-07 |  | MidAmerican Energy Company | Pottawattamie County | IA | FES-2014-JUN |  | Feasibility | NRIS | CBPS-Fallow Av 345 kV near Pony Creek 345 kV Switching Station | 336 | 464 | Gas |  | Not Started | 2018-01-01 | 0 | 0 | 0 | 0
|  |  |  | FES-2014-JUN | 0 | Withdrawn | Not Started | J366 | [5 empty] | NRIS |  | 232 |  | Gas | Pottawattamie County | IA | [27 empty] | Withdrawn | 2014-05-19 | 2014-07-07 | 2014-07-07 |  | MidAmerican Energy Company | Pottawattamie County | IA | FES-2014-JUN |  | Feasibility | NRIS | Overland Trail 161 kV bus | 168 | 232 | Gas |  | Not Started | 2016-01-10 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J259 | [5 empty] | NRIS |  | 1065 |  | Gas | Shelby County | IN | [27 empty] | Withdrawn | 2012-11-06 | 2014-07-08 | 2014-07-08 |  | Duke Energy Corporation | Shelby County | IN |  |  | Feasibility | NRIS | Gwynneville 345 kV Substation | 938 | 1065 | Gas |  | Not Started | 2015-04-10 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J266 | [5 empty] | NRIS |  | 200 |  | Wind | Roberts County | SD | [27 empty] | Withdrawn | 2012-11-19 | 2014-07-08 | 2014-07-08 |  | -- No Company -- | Roberts County | SD |  |  | Feasibility | NRIS | OTP Big Stone Substation 345 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2014-10-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1008 | [5 empty] | NRIS |  | 50 |  | Solar | Faribault County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2020-09-01 | ITC Midwest | Faribault County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Blue Earth IPL - Blue Earth 69kV Line Tap | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | West | Withdrawn | Withdrawn | J092 | [5 empty] | NRIS |  | 20 |  | Wind | Greene County | IA | [27 empty] | Withdrawn | 2009-10-28 | 2014-07-18 | 2014-07-18 |  | ITC Midwest | Greene County | IA | DPP-2012-AUG | West | DPP - SIS | NRIS | Scranton substation | 20 | 20 | Wind | WT Wind Turbine | Withdrawn | 2012-09-30 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ATC) | Withdrawn | Not Started | J1009 | [5 empty] | NRIS | N | 400 |  | Solar | Kenosha County,Racine County | WI |  |  |  | 1 | 0 | 1600000 | 0 | [9 empty] | 6050000 | 10951322 | 0 | 10951322 | 17001322 | 27.3783 | 42.5033 | 17001322 |  |  |  | Withdrawn | 2018-03-12 | 2020-05-19 |  | 2020-09-01 | American Transmission Co. LLC | Kenosha County,Racine County | WI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | Pleasant Prairie - Racine 345kV Line Tap | 400 | 400 | Solar | PV Photovoltaic | Not Started |  | 400 | 400 | 0 | 0
|  |  |  | DPP-2018-APR | East (ATC) | Withdrawn | Not Started | J1010 | [5 empty] | NRIS | N | 400 |  | Solar | Kenosha County,Racine County | WI |  |  |  | 1 | 0 | 1600000 | 0 | [9 empty] | 6520000 | 2753837 | 0 | 2753837 | 9273837 | 6.8846 | 23.1846 | 9273837 |  |  |  | Withdrawn | 2018-03-12 | 2020-05-19 |  | 2020-09-01 | American Transmission Co. LLC | Kenosha County,Racine County | WI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | Arcadian - Zion 345kV Line Tap | 400 | 400 | Solar | PV Photovoltaic | Not Started |  | 400 | 400 | 0 | 0
|  |  |  | DPP-2013-FEB | West | Withdrawn | Withdrawn | J118 | [5 empty] | NRIS |  | 50 |  | Wind | Greene County | IA | [27 empty] | Withdrawn | 2013-01-07 | 2014-07-18 | 2014-07-18 |  | MidAmerican Energy Company | Greene County | IA | DPP-2013-FEB | West | Network Upgrade | NRIS | MEC Drager - Grand Junction 161 kV | 50 | 50 | Wind | WT Wind Turbine | Withdrawn | 2013-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ATC) | Withdrawn | Not Started | J1011 | [5 empty] | NRIS | N | 400 |  | Solar | Kenosha County,Racine County | WI |  |  |  | 1 | 0 | 1600000 | 0 | [9 empty] | 25368000 | 2753837 | 0 | 2753837 | 28121837 | 6.8846 | 70.3046 | 28121837 |  |  |  | Withdrawn | 2018-03-12 | 2020-05-19 |  | 2022-09-01 | American Transmission Co. LLC | Kenosha County,Racine County | WI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | Arcadian - Zion 345kV Line Tap | 400 | 400 | Solar | PV Photovoltaic | Not Started |  | 400 | 400 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G644 | [5 empty] | ERIS |  | 20 |  | Wind | Stevens County | MN | [27 empty] | Withdrawn | 2006-05-26 | 2014-08-07 |  |  | Great River Energy | Stevens County | MN |  |  | SPA - SIS | ERIS | GRE Morris Tap - Walden 115 kV | 20 | 20 | Wind | WT Wind Turbine | Not Started | 2007-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J342 | [5 empty] | NRIS |  | 305 |  | Wind | Buchanan County | IA | [27 empty] | Withdrawn | 2014-05-19 | 2014-08-11 |  |  | ITC Midwest | Buchanan County | IA |  |  | Feasibility | NRIS | 345 kV substioin on Hazleton - Arnold line | 305 | 305 | Wind |  | Not Started | 2015-08-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J267 | [5 empty] | NRIS |  | 125 |  | Wind | Tuscola County | MI | [27 empty] | Withdrawn | 2013-01-14 | 2014-09-09 |  |  | ITC Transmission | Tuscola County | MI |  |  | Feasibility | NRIS | Karn - Garfield 138 kV line | 125 | 125 | Wind | WT Wind Turbine | Not Started | 2015-04-27 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J322 | [5 empty] | ERIS |  | 40 |  | Solar | Renville County | MN | [27 empty] | Withdrawn | 2014-01-13 | 2014-09-12 |  |  | Xcel Energy | Renville County | MN |  |  | Feasibility | ERIS | 69 kV bus at Sacred Heart substation | 40 | 40 | Solar |  | Not Started | 2014-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J345 | [5 empty] | ERIS |  | 40 |  | Solar | Waseca County | MN | [27 empty] | Withdrawn | 2014-05-19 | 2014-09-12 |  |  | Xcel Energy | Waseca County | MN |  |  | Feasibility | ERIS | 69 kV bus at Meriden Substation | 40 | 40 | Solar |  | Not Started | 2016-07-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J1012 | [5 empty] | NRIS | N | 100 |  | Solar | Scott County | IL |  |  |  | 0 | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-03-28 |  | 2021-09-01 | Prairie Power, Inc. | Scott County | IL | DPP-2018-APR | Central | PHASE 3 | NRIS | Jacksonville Ind. Park - Winchester 138kV Line Tap | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J367 | [5 empty] | NRIS |  | 39 |  | Solar | Goodhue County | MN | [27 empty] | Withdrawn | 2014-05-19 | 2014-09-12 |  |  | Xcel Energy | Goodhue County | MN |  |  | Feasibility | NRIS | 3 mi to 69 kV line ( XCEL switing and Vasa sub) | 39 | 39 | Solar |  | Not Started | 2016-01-10 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | R68 | [5 empty] | NRIS |  | 249.6 |  | Wind | Hancock County | IA | [27 empty] | Withdrawn | 2009-05-08 | 2014-09-12 |  |  | MidAmerican Energy Company | Hancock County | IA |  |  | SPA - SIS | NRIS | MEC Webster 345 kV Substation | 249.6 | 249.6 | Wind | WT Wind Turbine | Not Started | 2012-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G697 | [5 empty] | ERIS |  | 21 |  | Wind | Otter Tail County | MN | [27 empty] | Withdrawn | 2006-10-31 | 2014-09-18 |  |  | Great River Energy | Otter Tail County | MN |  |  | SPA - SIS | ERIS | OTP Pelican Rapid - Edge Tap 115 kV | 21 | 21 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | FES-2013-SEP | 0 | Withdrawn | Not Started | J294 | [5 empty] | NRIS |  | 588 |  | Gas | Brown County | WI | [27 empty] | Withdrawn | 2013-09-10 | 2014-09-25 |  |  | American Transmission Co. LLC | Brown County | WI | FES-2013-SEP |  | Feasibility | NRIS | Pulliam 138kV substation | 510 | 588 | Gas |  | Not Started | 2020-06-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1013 | [5 empty] | NRIS |  | 80 |  | Solar | Branch County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-12-02 |  | 2021-09-01 | Michigan Electric Transmission Company, LLC | Branch County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Batavia 138kV Substation | 80 | 80 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2014-AUG | 0 | Withdrawn | Not Started | J381 | [5 empty] | ERIS |  | 25 |  | Solar | DeSoto County | MS | [27 empty] | Withdrawn | 2014-07-14 | 2014-09-30 |  |  | Entergy | DeSoto County | MS | FES-2014-AUG |  | Feasibility | ERIS | Unknown | 25 | 25 | Solar |  | Not Started | 2016-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G948 | [5 empty] | NRIS |  | 249.6 |  | Wind | Clay County | IA | [27 empty] | Withdrawn | 2008-01-15 | 2014-10-15 |  |  | MidAmerican Energy Company | Clay County | IA |  |  | SPA - SIS | NRIS | Sheldon (Obrien County sub) 345kV | 249.6 | 249.6 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1014 | [5 empty] | NRIS |  | 80 |  | Solar | Jackson County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-12-02 |  | 2021-09-01 | Michigan Electric Transmission Company, LLC | Jackson County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Tompkins - Blackstone 138kV Line | 80 | 80 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | R67 | [5 empty] | NRIS |  | 148.8 |  | Wind | Clay County | IA | [27 empty] | Withdrawn | 2009-05-05 | 2014-10-15 |  |  | MidAmerican Energy Company | Clay County | IA |  |  | SPA - SIS | NRIS | Sheldon (Obrien county sub) 345 kV | 148.8 | 148.8 | Wind | WT Wind Turbine | Not Started | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-APR | J057/J106 | Done | In Service | J106 | [5 empty] | NRIS |  | 32 |  | Gas | Sandusky County | OH | [27 empty] | Done | 2009-12-21 |  | 2011-05-27 |  | FirstEnergy Solutions Corp. | Sandusky County | OH | DPP-2010-APR | J057/J106 | DPP - SIS | NRIS | Freemont 138kV Substation | 32 | 32 | Gas | ST, CT | In Service | 2011-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1015 | [5 empty] | NRIS |  | 80 |  | Solar | Otsego County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-03-27 |  | 2020-09-01 | Michigan Electric Transmission Company, LLC | Otsego County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Gaylord 138kV Substation | 80 | 80 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G829 | [5 empty] | NRIS |  | 100 |  | Wind | Minnehaha County | SD | [27 empty] | Withdrawn | 2007-07-16 | 2014-10-21 |  |  | Northern States Power (Xcel Energy) | Minnehaha County | SD |  |  | SPA - SIS | NRIS | Split Rock 115kV Substation | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | Material Modification | Done | In Service | J591 | [5 empty] | NRIS |  | 0 |  | Combined Cycle | Newton County | TX | [27 empty] | Done | 2016-05-02 |  | 2016-06-16 |  | Entergy | Newton County | TX |  | Material Modification | DPP - SIS | NRIS | Cotton Wood | 0 | 0 | Combined Cycle | Combined Cycle | In Service | 2017-09-15 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J560 | [5 empty] | NRIS |  | 835 |  | Combined Cycle | Douglas County | WI | [27 empty] | Withdrawn | 2016-05-04 | 2017-04-25 |  | 2022-01-01 | American Transmission Co. LLC | Douglas County | WI |  |  | Feasibility | NRIS | Unknown | 835 | 835 | Combined Cycle | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | H016 | [5 empty] | ERIS |  | 200 |  | Wind | Minnehaha County | SD | [27 empty] | Withdrawn | 2008-04-30 | 2014-10-21 |  |  | Northern States Power (Xcel Energy) | Minnehaha County | SD |  |  | SPA - SIS | ERIS | Split Rock 115kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J184 | [5 empty] | ERIS |  | 100 |  | Wind | Rock County | MN | [27 empty] | Withdrawn | 2010-11-15 | 2014-10-21 |  |  | Northern States Power (Xcel Energy) | Rock County | MN |  |  | SPA - SIS | ERIS | Split Rock Substation 115kV | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2014-MAR | 0 | Withdrawn | Not Started | J326 | [5 empty] | ERIS |  | 100 |  | Solar | Chisago County | MN | [27 empty] | Withdrawn | 2014-03-17 | 2014-10-21 |  | 2016-08-01 | Xcel Energy | Chisago County | MN | FES-2014-MAR |  | Feasibility | ERIS | Unknown | 100 | 100 | Solar |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J561 | [5 empty] | NRIS |  | 190 |  | Gas | Kalamazoo County | MI | [27 empty] | Withdrawn | 2016-05-04 | 2017-07-21 |  | 2018-08-01 | Consumers Energy Transmission Owner | Kalamazoo County | MI |  |  | Feasibility | NRIS | Unknown | 155 | 190 | Gas |  | Not Started | 2017-10-10 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G636 | [5 empty] | NRIS |  | 18.9 |  | Wind | Swift County | MN | [27 empty] | Withdrawn | 2006-05-15 | 2014-10-22 |  |  | Great River Energy | Swift County | MN |  |  | SPA - SIS | NRIS | GRE Benson - Swift Falls 69kV | 18.9 | 18.9 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J1016 | [5 empty] | NRIS | N | 50 |  | Solar | Gibson County | IN |  |  |  | 0 | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-01-06 |  | 2021-09-01 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Gibson County | IN | DPP-2018-APR | Central | PHASE 3 | NRIS | Francisco - Toyota Z75 138kV Line Tap | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2014-AUG | 0 | Withdrawn | Not Started | J379 | [5 empty] | NRIS |  | 79.14 |  | Solar | Lee County | AR | [27 empty] | Withdrawn | 2014-07-14 | 2014-10-22 |  |  | Entergy | Lee County | AR | FES-2014-AUG |  | Feasibility | NRIS | 115 kV line tap in Lee County | 79.14 | 79.14 | Solar |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2014-AUG | 0 | Withdrawn | Not Started | J380 | [5 empty] | NRIS |  | 198.9 |  | Solar | Lee County | AR | [27 empty] | Withdrawn | 2014-07-14 | 2014-10-22 |  |  | Entergy | Lee County | AR | FES-2014-AUG |  | Feasibility | NRIS | Unknown | 198.9 | 198.9 | Solar |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J1017 | [5 empty] | NRIS | N | 125 |  | Wind | Carroll County,White County | IN |  |  |  | 0 | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2018-10-03 |  | 2021-09-01 | Duke Energy | Carroll County,White County | IN | DPP-2018-APR | Central | PHASE 3 | NRIS | Springboro 138 kV Substation | 125 | 125 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J1018 | [5 empty] | NRIS | N | 150 |  | Wind | Miami County | IN |  |  |  | 0 | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2018-10-03 |  | 2021-09-01 | Duke Energy | Miami County | IN | DPP-2018-APR | Central | PHASE 3 | NRIS | Peru South East - Greentown 230 kV Line Tap | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J272 | [5 empty] | ERIS |  | 170.2 |  | Wind | Poweshiek County | IA | [27 empty] | Withdrawn | 2013-03-07 | 2014-11-05 |  |  | -- No Company -- | Poweshiek County | IA |  |  | Optional | ERIS | Parnell - Poweshiek 161 kV | 170.2 | 170.2 | Wind |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J1019 | [5 empty] | NRIS | N | 150 |  | Wind | Boone County | MO |  |  |  | 0 | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2018-10-03 |  | 2021-09-01 | Ameren Missouri | Boone County | MO | DPP-2018-APR | Central | PHASE 3 | NRIS | Overton - McCredie 345 kV Line Tap | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2013-APR | 0 | Withdrawn | Not Started | J273 | [5 empty] | ERIS |  | 149.6 |  | Wind | DeWitt County | IL | [27 empty] | Withdrawn | 2013-03-13 | 2014-11-05 |  |  | Ameren Illinois | DeWitt County | IL | FES-2013-APR |  | Feasibility | ERIS | Bloomington - Decatur 138 kV line | 149.6 | 149.6 | Wind |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1020 | [5 empty] | NRIS |  | 250 |  | Solar | Jasper County | MS | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-01-24 |  | 2022-09-01 | Cooperative Energy | Jasper County | MS | DPP-2018-APR | South | GIA | NRIS | Missionary 230kV Substation | 250 | 250 | Solar | PV Photovoltaic | Not Started |  | 250 | 250 | 0 | 0
|  |  |  | FES-2014-SEP | 0 | Withdrawn | Not Started | J393 | [5 empty] | NRIS |  | 49 |  | Solar | Arkansas County | AR | [27 empty] | Withdrawn | 2014-09-15 | 2014-12-11 |  |  | Entergy | Arkansas County | AR | FES-2014-SEP |  | Feasibility | NRIS | Unknown | 49 | 49 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2013-JUN | 0 | Withdrawn | Not Started | J283 | [5 empty] | NRIS |  | 20 |  | Wind | Cottonwood County | MN | [27 empty] | Withdrawn | 2013-05-20 | 2014-12-15 |  |  | ITC Midwest | Cottonwood County | MN | FES-2013-JUN |  | Feasibility | NRIS | Heron Lake - Storden 69kV | 20 | 20 | Wind |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | West | Withdrawn | Not Started | J356 | [5 empty] | NRIS |  | 232 |  | Gas | Polk County | IA | [27 empty] | Withdrawn | 2014-05-19 | 2014-12-15 |  |  | MidAmerican Energy Company | Polk County | IA | DPP-2014-AUG | West | DPP - SIS | NRIS | Bondurant 161 kV bus | 168 | 232 | Gas |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | West | Withdrawn | Not Started | J360 | [5 empty] | NRIS |  | 116 |  | Gas | Scott County | IA | [27 empty] | Withdrawn | 2014-05-19 | 2014-12-15 |  |  | MidAmerican Energy Company | Scott County | IA | DPP-2014-AUG | West | DPP - SIS | NRIS | Riverside Generating Station 69 kV bus | 84 | 116 | Gas |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | West | Withdrawn | Not Started | J361 | [5 empty] | NRIS |  | 116 |  | Gas | Pottawattamie County | IA | [27 empty] | Withdrawn | 2014-05-20 | 2014-12-15 |  |  | MidAmerican Energy Company | Pottawattamie County | IA | DPP-2014-AUG | West | DPP - SIS | NRIS | CBPS 69 kV bus | 84 | 116 | Gas |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | West | Withdrawn | Not Started | J280 | [5 empty] | NRIS |  | 221 |  | Gas | Goodhue County | MN | [27 empty] | Withdrawn | 2013-03-18 | 2014-12-17 |  |  | Northern States Power (Xcel Energy) | Goodhue County | MN | DPP-2014-AUG | West | Int FaS | NRIS | Hampton Corner 345 kV Substation | 207 | 221 | Gas |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2014-SEP | 0 | Withdrawn | Not Started | J398 | [5 empty] | NRIS |  | 204 |  | Gas | Marquette County | MI | [27 empty] | Withdrawn | 2014-09-15 | 2014-12-19 |  |  | American Transmission Co. LLC | Marquette County | MI | FES-2014-SEP |  | Feasibility | NRIS | National 138 kV Substation | 204 | 204 | Gas | CT Combined-Cycle Combustion ? Turbine Part | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J253 | [5 empty] | ERIS |  | 48.3 |  | Wind | Woodbury County | IA | [27 empty] | Withdrawn | 2012-09-10 | 2015-01-06 |  |  | MidAmerican Energy Company | Woodbury County | IA | SPA Parked |  | SPA - SIS | ERIS | J4 - Sioux City 69 kV | 48.3 | 48.3 | Wind |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J1021 | [5 empty] | NRIS | N | 200 |  | Wind | Piatt County | IL |  |  |  | 0 | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-01-02 |  | 2021-09-01 | Ameren Illinois | Piatt County | IL | DPP-2018-APR | Central | PHASE 3 | NRIS | Goose Creek 345kV Switchyard | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | G821 | [5 empty] | NRIS |  | 199.5 |  | Wind | Clay County | MN | [27 empty] | Withdrawn | 2007-07-19 | 2015-01-08 |  |  | Otter Tail Power Company | Clay County | MN | SPA Parked |  | SPA - SIS | NRIS | OTP Sheyenne - Audubon 230 kV | 199.5 | 199.5 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J156 | [5 empty] | NRIS |  | 185.6 |  | Wind | Marshall County | IN | [27 empty] | Withdrawn | 2010-06-28 | 2015-01-08 |  |  | Northern Indiana Public Service Company | Marshall County | IN | SPA Parked |  | SPA - SIS | NRIS | NIPSCO Burr Oak 138kV Substation | 185.6 | 185.6 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J1022 | [5 empty] | ERIS | N | 150 |  | Wind | McLean County | IL |  |  |  | 1 | 1 | 600000 | 0 | [9 empty] | 151000 | 1970000 | 0 | 1970000 | 2121000 | 13.1333 | 14.14 | 1970000 |  |  |  | Active | 2018-03-12 |  |  | 2021-08-01 | Ameren Illinois | McLean County | IL | DPP-2018-APR | Central | PHASE 3 | ERIS | Weedman Substation 138kV Bus | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 150 | 150 | 150 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J284 | [5 empty] | NRIS |  | 316 |  | Gas | Dakota County | MN | [27 empty] | Withdrawn | 2013-05-20 | 2015-01-08 |  |  | Northern States Power (Xcel Energy) | Dakota County | MN | SPA Parked |  | Feasibility | NRIS | Proposed Hampton Corner 345kV substation | 316 | 316 | Gas |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J286 | [5 empty] | ERIS |  | 198.9 |  | Wind | Audubon County, Guthrie County | IA | [27 empty] | Withdrawn | 2013-05-20 | 2015-01-08 |  |  | MidAmerican Energy Company | Audubon County, Guthrie County | IA | SPA Parked |  | Feasibility | ERIS | MEC Eclipse 345 kV Substation | 198.9 | 198.9 | Wind |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J305 | [5 empty] | NRIS |  | 50 |  | Solar | Lyon County | MN | [27 empty] | Withdrawn | 2013-11-18 | 2015-01-20 |  |  | Northern States Power (Xcel Energy) | Lyon County | MN | SPA Parked |  | Feasibility | NRIS | Unknown | 50 | 50 | Solar |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | East (ITC) | Withdrawn | Not Started | J427 | [5 empty] | NRIS |  | 110 |  | Gas | Livingston County | MI | [27 empty] | Withdrawn | 2014-11-17 | 2015-01-23 |  |  | ITC Transmission | Livingston County | MI | DPP-2015-FEB | East (ITC) | GIA | NRIS | 155 Town Line Road, Gaylord, MI | 110 | 110 | Gas | CT Combined-Combustion ? Turbine Part | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | G939 | [5 empty] | NRIS |  | 250 |  | Wind | Grant County | SD | [27 empty] | Withdrawn | 2011-09-26 | 2015-01-30 |  |  | Otter Tail Power Company | Grant County | SD | SPA Parked |  | SPA - SIS | NRIS | OTP Big Stone 230 kV Substation | 250 | 250 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1023 | [5 empty] | NRIS |  | 82 |  | Solar | Mississippi County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-29 |  | 2021-07-31 | Entergy Arkansas, LLC | Mississippi County | AR | DPP-2018-APR | South | GIA | NRIS | Osceola - Wilson 161 kV Line Tap | 82 | 82 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J377 | [5 empty] | NRIS |  | 40 |  | Solar | Bradley County | AR | [27 empty] | Withdrawn | 2014-07-14 | 2015-02-02 |  |  | Entergy | Bradley County | AR | SPA Parked |  | Feasibility | NRIS | MISO 115kV line in Zone 8 serving EAI Arkansas | 40 | 40 | Solar |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1024 | [5 empty] | NRIS | N | 200 |  | Wind | Nodaway County | MO |  |  |  | 1 | 0 | 800000 | 1510089 | [7 empty] | 12000000 |  | 0 | 10633003 | 7388443 | 22633003 | 30021446 | 113.165 | 150.1072 | 30021446 |  |  |  | Withdrawn | 2018-03-12 | 2021-03-09 |  | 2022-09-30 | MidAmerican Energy Company | Nodaway County | MO | DPP-2018-APR | West | PHASE 3 | NRIS | Maryville - Clarinda 161 kV Line Tap | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
|  |  |  | DPP-2015-FEB | East (ITC) | Withdrawn | Not Started | J271 | [5 empty] | NRIS |  | 232 |  | Gas | Montcalm County | MI | [27 empty] | Withdrawn | 2013-03-11 | 2015-02-13 |  |  | Michigan Electric Transmission Company, LLC | Montcalm County | MI | DPP-2015-FEB | East (ITC) | GIA | NRIS | Renaissance Energy Facility | 232 | 232 | Gas |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | East (ITC) | Done | Under Construction | J571 | [5 empty] | NRIS |  | 6.4 |  | Gas | Kalamazoo County | MI | [27 empty] | Done | 2016-05-06 |  | 2018-08-29 | 2018-05-31 | Michigan Electric Transmission Company, LLC | Kalamazoo County | MI | DPP-2016-AUG | East (ITC) | GIA | NRIS | Township of Comstock, County of Kalmazoo, Morrow 138kV | 6.4 | 6.4 | Gas | CT Combustion Turbine (Simple Cycle) | Under Construction | 2018-08-29 | 6.4 | 6.4 | 6.4 | 6.4
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | G775 | [5 empty] | NRIS |  | 200 |  | Wind | Hancock County | IL | [27 empty] | Withdrawn | 2007-03-27 | 2015-02-18 |  |  | Ameren Illinois | Hancock County | IL | SPA Parked |  | SPA - SIS | NRIS | Niota - Macomb 138 kV | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | G759 | [5 empty] | NRIS |  | 84.8 |  | Wind | Cottonwood County | MN | [27 empty] | Withdrawn | 2007-01-09 | 2015-03-17 |  |  | ITC Midwest | Cottonwood County | MN | SPA Parked |  | SPA - SIS | NRIS | Dotson 69kV Substation | 84.8 | 84.8 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | West | Withdrawn | Withdrawn | J097 | [5 empty] | NRIS |  | 200 |  | Wind | Des Moines County | IA | [27 empty] | Withdrawn | 2009-11-10 | 2015-04-17 |  | 2015-09-01 | ITC Midwest | Des Moines County | IA | DPP-2012-AUG | West | Network Upgrade | NRIS | ITC Midwest Denmark - Newport 161kV | 200 | 200 | Wind | WT Wind Turbine | Withdrawn | 2012-10-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | J110 | [5 empty] | NRIS |  | 7.5 |  | Biomass | Morton County | ND | [27 empty] | Done | 2010-01-14 |  | 2011-10-28 |  | Montana-Dakota Utilities Company | Morton County | ND |  |  | Feasibility | NRIS | MDU 41.6 kV transmission line at Glen Ullin between switches 6315 and 6071 | 7.5 | 7.5 | Biomass | Combined Cycle | In Service | 2011-08-15 | 0 | 0 | 0 | 0
|  |  |  | SPA-2013-AUG | 0 | Withdrawn | Not Started | G812 | [5 empty] | ERIS |  | 20 |  | Wind | Pope County | MN | [27 empty] | Withdrawn | 2007-06-21 | 2015-04-23 |  |  | Great River Energy | Pope County | MN | SPA-2013-AUG |  | SPA - SIS | ERIS | GRE Swift Falls - Gilchrest 69kV | 20 | 20 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J1025 | [5 empty] | NRIS | N | 300 |  | Wind | Knox County | MO |  |  |  | 1 | 1 | 1200000 | 2948233 | [9 empty] | 0 | 27457764 | 0 | 27457764 | 27457764 | 91.5259 | 91.5259 | 27457764 |  |  |  | Active | 2018-03-12 |  |  | 2020-09-30 | Ameren Transmission Company of Illinois | Knox County | MO | DPP-2018-APR | Central | PHASE 3 | NRIS | Zachary - Maywood 345 kV Line Tap | 300 | 300 | Wind | WT Wind Turbine | Not Started |  | 300 | 300 | 290 | 290
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J1026 | [5 empty] | NRIS | N | 400 |  | Wind | Audrain County,Ralls County | MO |  |  |  | 1 | 1 | 1600000 | 1203627 | [9 empty] | 4037000 | 14009254 | 16443844 | 14009254 | 34490098 | 35.0231 | 86.2252 | 34490098 |  |  |  | Active | 2018-03-12 |  |  | 2020-09-30 | Ameren Missouri | Audrain County,Ralls County | MO | DPP-2018-APR | Central | PHASE 3 | NRIS | Maywood - Spencer Creek 345 kV Line Tap | 400 | 400 | Wind | WT Wind Turbine | Not Started |  | 400 | 350 | 380 | 265
|  |  |  | DPP-2015-FEB | South | Withdrawn | Not Started | J433 | [5 empty] | NRIS Only |  | 1270 |  | Combined Cycle | Union County | AR | [27 empty] | Withdrawn | 2015-01-05 | 2015-04-29 |  |  | Entergy | Union County | AR | DPP-2015-FEB | South | DPP - SIS | NRIS Only | 500 kV bus at El Dorado substation | 1270 | 1270 | Combined Cycle | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J295 | [5 empty] | NRIS |  | 50 |  | Gas | Lyon County | MN | [27 empty] | Withdrawn | 2013-09-16 | 2015-05-05 |  |  | Northern States Power (Xcel Energy) | Lyon County | MN | SPA Parked |  | Feasibility | NRIS | Xcel's 69kV Lyon County Substation | 50 | 50 | Gas |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2013-AUG | J281 | Withdrawn | Withdrawn | J281 | [5 empty] | NRIS |  | 50 |  | Wind | Huron County | MI | [27 empty] | Withdrawn | 2013-05-17 | 2015-05-21 | 2014-03-25 | 2015-12-15 | ITC Transmission | Huron County | MI | DPP-2013-AUG | J281 | Optional | NRIS | Cosmo-Harvest Wind 120 kV circuit near Cosmo subst | 50 | 50 | Wind | WT Wind Turbine | Withdrawn | 2013-11-18 | 0 | 0 | 0 | 0
|  |  |  | DPP-2013-AUG | MI | Withdrawn | Withdrawn | J282 | [5 empty] | NRIS |  | 50 |  | Wind | Huron County | MI | [27 empty] | Withdrawn | 2013-05-17 | 2015-05-21 | 2014-03-25 | 2015-12-15 | ITC Transmission | Huron County | MI | DPP-2013-AUG | MI | Optional | NRIS | Cosmo-Harvest Wind 120kV circuit near Cosmo sub | 50 | 50 | Wind | WT Wind Turbine | Withdrawn | 2017-03-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J1027 | [5 empty] | NRIS | N | 150 |  | Solar | Pike County | IN |  |  |  | 1 | 1 | 600000 | 507695 | [9 empty] | 0 | 717200 | 10155153 | 717200 | 10872353 | 4.7813 | 72.4824 | 10872353 |  |  |  | Active | 2018-03-12 |  |  | 2021-01-02 | Hoosier Energy | Pike County | IN | DPP-2018-APR | Central | PHASE 3 | NRIS | Ratts 161 kV Substation | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J068 | [5 empty] | NRIS |  | 100 |  | Wind | Dickinson County | IA | [27 empty] | Withdrawn | 2009-09-17 | 2015-06-01 |  |  | ITC Midwest | Dickinson County | IA | SPA Parked |  | SPA - SIS | NRIS | ITCM Triboji - Wisdom 161kV | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | WEST | Withdrawn | Not Started | J026 | [5 empty] | NRIS |  | 50 |  | Wind | Mower County | MN | [27 empty] | Withdrawn | 2009-03-02 | 2015-06-05 |  | 2020-10-03 | ITC Midwest | Mower County | MN | DPP-2012-AUG | WEST | Network Upgrade | NRIS | Adams 161 kV Substation | 50 | 50 | Wind | WT Wind Turbine | Not Started | 2015-06-01 | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J350 | [5 empty] | NRIS |  | 50 |  | Solar | Chicot County | AR | [27 empty] | Withdrawn | 2014-05-19 | 2015-06-05 |  |  | Entergy | Chicot County | AR | SPA Parked |  | Feasibility | NRIS | Lake Village Bagby 115 kV Substation | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J1028 | [5 empty] | NRIS | N | 150 |  | Solar | Pike County | IN |  |  |  | 1 | 1 | 600000 | 1109879 | [9 empty] | 0 | 9916400 | 12045819 | 9916400 | 21962219 | 66.1093 | 146.4148 | 21962219 |  |  |  | Active | 2018-03-12 |  |  | 2021-01-02 | Hoosier Energy | Pike County | IN | DPP-2018-APR | Central | PHASE 3 | NRIS | Ratts - Victory 161 kV Line Tap | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G520 | [5 empty] | ERIS |  | 150 |  | Wind | Lyon County | MN | [27 empty] | Withdrawn | 2005-05-20 | 2015-06-08 | 2007-12-06 | 2017-08-31 | Northern States Power (Xcel Energy) | Lyon County | MN |  |  | Network Upgrade | ERIS | Lake Yankton - Lyon County 115kV | 150 | 150 | Wind | WT Wind Turbine | Withdrawn | 2006-11-01 | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J386 | [5 empty] | NRIS |  | 103 |  | Solar | Lonoke County | AR | [27 empty] | Withdrawn | 2014-09-10 | 2015-06-16 |  |  | Entergy | Lonoke County | AR | SPA Parked |  | Feasibility | NRIS | 115 kV England Substation | 103 | 103 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J389 | [5 empty] | NRIS |  | 550 |  | Gas | Rock County | WI | [27 empty] | Withdrawn | 2014-09-15 | 2015-06-17 |  |  | American Transmission Co. LLC | Rock County | WI | SPA Parked |  | Feasibility | NRIS | Unknown | 501 | 550 | Gas | CA Combined-Cycle - Steam Part | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J317 | [5 empty] | ERIS |  | 112 |  | Gas | Marquette County | MI | [27 empty] | Withdrawn | 2013-11-18 | 2015-06-22 |  |  | American Transmission Co. LLC | Marquette County | MI | SPA Parked |  | Feasibility | ERIS | Empire substation | 112 | 112 | Gas |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1029 | [5 empty] | NRIS |  | 200 |  | Solar | East Feliciana Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-03-13 |  | 2020-09-28 | Entergy Louisiana, LLC | East Feliciana Parish | LA | DPP-2018-APR | South | GIA | NRIS | Fancy Point 230 kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J307 | [5 empty] | NRIS |  | 201 |  | Wind | Osceola County | MI | [27 empty] | Withdrawn | 2013-11-18 | 2015-06-23 |  |  | Michigan Electric Transmission Company, LLC | Osceola County | MI | SPA Parked |  | Feasibility | NRIS | Unknown | 201 | 201 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J265 | [5 empty] | NRIS |  | 100 |  | Wind | Marshall County | IL | [27 empty] | Withdrawn | 2012-11-19 | 2015-06-25 |  |  | Ameren Illinois | Marshall County | IL | SPA Parked |  | SPA - SIS | NRIS | 3 miles SE of Toluca, IL | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | East (ITC) | Withdrawn | Not Started | J423 | [5 empty] | NRIS |  | 125 |  | Gas | Wayne County | MI | [27 empty] | Withdrawn | 2014-11-17 | 2015-06-26 |  |  | ITC Transmission | Wayne County | MI | DPP-2015-FEB | East (ITC) | Int FaS | NRIS | Trenton Channel Power Plant | 125 | 125 | Gas | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | East (ITC) | Withdrawn | Not Started | J424 | [5 empty] | NRIS |  | 120 |  | Gas | Wayne County | MI | [27 empty] | Withdrawn | 2014-11-17 | 2015-06-26 |  |  | ITC Transmission | Wayne County | MI | DPP-2015-FEB | East (ITC) | Int FaS | NRIS | Trenton Channel Power Plant | 120 | 120 | Gas | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | West | Done | In Service | J112 | [5 empty] | ERIS |  | 4.94 |  | Wind | Winona County | MN | [27 empty] | Done | 2010-01-25 |  | 2013-09-16 | 2011-10-30 | ITC Midwest | Winona County | MN | DPP-2012-AUG | West | DPP - SIS | ERIS | Utica - Lewiston 69 kV | 4.94 | 4.94 | Wind | WT Wind Turbine | In Service | 2009-07-14 | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J300 | [5 empty] | NRIS |  | 60 |  | Wind | Mackinac County | MI | [27 empty] | Withdrawn | 2013-11-18 | 2015-06-27 |  |  | American Transmission Co. LLC | Mackinac County | MI | SPA Parked |  | Feasibility | NRIS | Existing Pine River Substation | 60 | 60 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G390 | [5 empty] | NRIS |  | 100 |  | Gas | Sherburne County | MN | [27 empty] | Withdrawn | 2003-11-03 | 2015-06-29 | 2007-10-25 | 2012-03-15 | Great River Energy | Sherburne County | MN |  |  | Network Upgrade | NRIS | Elk River 230 kV substation | 100 | 100 | Gas | CT Combustion Turbine (Simple Cycle) | Withdrawn | 2012-05-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G531 | [5 empty] | NRIS |  | 68 |  | Coal | Mercer County | ND | [27 empty] | Withdrawn | 2005-07-01 | 2015-06-29 | 2009-07-15 | 2012-04-01 | Great River Energy | Mercer County | ND |  |  | Network Upgrade | NRIS | GRE Stanton Station | 68 | 68 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, | Withdrawn | 2011-06-01 | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J370 | [5 empty] | NRIS |  | 50 |  | Solar | Jackson County | AR | [27 empty] | Withdrawn | 2014-06-12 | 2015-06-29 |  |  | Entergy | Jackson County | AR | SPA Parked |  | Feasibility | NRIS | Cash-Newport AB 161 kV line | 50 | 50 | Solar |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Done | Under Construction | J1030 | [5 empty] | ERIS |  | 150 |  | Solar | Polk County | TX | [21 empty] | 0 | 0 |  |  |  |  | Done | 2018-03-12 |  | 2020-10-22 | 2021-09-01 | Entergy Texas, Inc. | Polk County | TX | DPP-2018-APR | South | GIA | ERIS | Poco - Menard 138kV Line Tao | 150 | 150 | Solar | PV Photovoltaic | Under Construction | 2023-01-23 | 150 | 0 | 150 | 0
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J1031 | [5 empty] | NRIS | N | 150 |  | Wind | Henry County | IN |  |  |  | 0 | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-01-07 |  | 2020-10-01 | Duke Energy Indiana | Henry County | IN | DPP-2018-APR | Central | PHASE 3 | NRIS | Fall Creek - New Castle 138 kV Line Tap | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J297 | [5 empty] | NRIS |  | 150 |  | Wind | O'Brien County | IA | [27 empty] | Withdrawn | 2013-10-09 | 2015-07-09 |  |  | MidAmerican Energy Company | O'Brien County | IA | SPA Parked |  | Feasibility | NRIS | on 345kV O'Brien to Webster Line | 150 | 150 | Wind |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | West | Withdrawn | Not Started | J409 | [5 empty] | NRIS |  | 150 |  | Wind | Fayette County | IA | [27 empty] | Withdrawn | 2014-11-14 | 2015-07-17 |  |  | ITC Midwest | Fayette County | IA | DPP-2015-FEB | West | DPP - SIS | NRIS | Hazelton to Windsor 161 kV line | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2015-12-31 | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J252 | [5 empty] | ERIS |  | 39.09 |  | Wind | Audubon County | IA | [27 empty] | Withdrawn | 2012-09-10 | 2015-07-21 |  |  | MidAmerican Energy Company | Audubon County | IA | SPA Parked |  | SPA - SIS | ERIS | Audobon 69 kV Substation | 39.09 | 39.09 | Wind |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | Central | Withdrawn | Not Started | J332 | [5 empty] | ERIS |  | 90 |  | Gas | Posey County | IN | [27 empty] | Withdrawn | 2014-05-16 | 2015-07-23 |  |  | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Posey County | IN | DPP-2014-AUG | Central | DPP - SIS | ERIS | Point Substation | 83 | 90 | Gas |  | Not Started | 2016-10-31 | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J150 | [5 empty] | NRIS |  | 99 |  | Wind | Mountrail County | ND | [27 empty] | Withdrawn | 2010-06-28 | 2015-08-10 |  |  | Montana-Dakota Utilities Company | Mountrail County | ND | SPA Parked |  | SPA - SIS | NRIS | MDU Stanely 115 kV | 99 | 99 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J261 | [5 empty] | NRIS |  | 100 |  | Wind | Montgomery County | IN | [27 empty] | Withdrawn | 2012-11-16 | 2015-08-10 |  |  | Duke Energy Corporation | Montgomery County | IN | SPA Parked |  | SPA - SIS | NRIS | Linden - Crawfordsville 138 kV | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1032 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Wabasha County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2021-10-31 | Northern States Power (Xcel Energy) | Wabasha County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Briggs Rd. - N. Rochester 345 kV Line Tap | 50 | 50 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J1033 | [5 empty] | NRIS | N | 50 |  | Battery Storage | Stoddard County | MO |  |  |  | 1 | 0 | 200000 | 236568 | [9 empty] | 436000 | 3054500 | 335070 | 3054500 | 3825570 | 61.09 | 76.5114 | 3825570 |  |  |  | Withdrawn | 2018-03-12 | 2021-03-10 |  | 2021-10-31 | Ameren Missouri | Stoddard County | MO | DPP-2018-APR | Central | PHASE 3 | NRIS | Stoddard - Morely 161 kV Line Tap | 50 | 50 | Battery Storage | BS Battery Storage | Not Started |  | 50 | 50 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J323 | [5 empty] | ERIS |  | 19.79 |  | Wind | St. Mary | LA | [27 empty] | Withdrawn | 2014-01-14 | 2015-08-10 |  |  | CLECO Corporation | St. Mary | LA | SPA Parked |  | Feasibility | ERIS | Ivanhoe Substation | 19.79 | 19.79 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J260 | [5 empty] | NRIS |  | 100 |  | Wind | Ford County | IL | [27 empty] | Withdrawn | 2012-11-16 | 2015-08-11 |  |  | Ameren Illinois | Ford County | IL | SPA Parked |  | SPA - SIS | NRIS | Paxton East 138kV Substation | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J1034 | [5 empty] | NRIS | N | 225 |  | Solar | Stoddard County | MO |  |  |  | 1 | 1 | 900000 | 0 | [9 empty] | 1959000 | 3054500 | 1507815 | 3054500 | 6521315 | 13.5756 | 28.9836 | 6521315 |  |  |  | Active | 2018-03-12 |  |  | 2021-10-31 | Ameren Missouri | Stoddard County | MO | DPP-2018-APR | Central | PHASE 3 | NRIS | Stoddard - Morley 161kV Line Tap | 225 | 225 | Solar | PV Photovoltaic | Not Started |  | 225 | 225 | 225 | 225
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J296 | [5 empty] | ERIS |  | 69.3 |  | Wind | Presque Isle County | MI | [27 empty] | Withdrawn | 2013-09-18 | 2015-08-11 |  |  | Michigan Electric Transmission Company, LLC | Presque Isle County | MI | SPA Parked |  | Feasibility | ERIS | Unknown | 69.3 | 69.3 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2014-JUN | 0 | Withdrawn | Not Started | J335 | [5 empty] | NRIS |  | 551 |  | Gas | Calumet County | WI | [27 empty] | Withdrawn | 2014-05-16 | 2015-09-03 |  |  | American Transmission Co. LLC | Calumet County | WI | FES-2014-JUN |  | Feasibility | NRIS | WPS Forest Junction 345 kV substation | 477 | 551 | Gas |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2014-JUN | 0 | Withdrawn | Not Started | J336 | [5 empty] | NRIS |  | 845 |  | Gas | Calumet County | WI | [27 empty] | Withdrawn | 2014-05-16 | 2015-09-03 |  |  | American Transmission Co. LLC | Calumet County | WI | FES-2014-JUN |  | Feasibility | NRIS | WPS Forest Junciton 345 kV substation | 835 | 845 | Gas |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J1035 | [5 empty] | NRIS | N | 75 |  | Solar | Washington County | IL |  |  |  | 0 | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2018-10-15 |  | 2021-07-01 | Ameren Illinois | Washington County | IL | DPP-2018-APR | Central | PHASE 3 | NRIS | Fayetteville - Marigold 138 kV Line Tap | 75 | 75 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2014-JUN | 0 | Withdrawn | Not Started | J337 | [5 empty] | NRIS |  | 551 |  | Gas | Winnebago County | WI | [27 empty] | Withdrawn | 2014-05-16 | 2015-09-03 |  |  | American Transmission Co. LLC | Winnebago County | WI | FES-2014-JUN |  | Feasibility | NRIS | North Appleton - Fitzgerald 345 kV line | 477 | 551 | Gas |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2014-JUN | 0 | Withdrawn | Not Started | J338 | [5 empty] | NRIS |  | 845 |  | Gas | Winnebago County | WI | [27 empty] | Withdrawn | 2014-05-16 | 2015-09-03 |  |  | American Transmission Co. LLC | Winnebago County | WI | FES-2014-JUN |  | Feasibility | NRIS | North Appleton - Fitzgerald 345 kV lin e | 835 | 845 | Gas |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA-2012-AUG | 0 | Withdrawn | Not Started | G817 | [5 empty] | ERIS |  | 5.9 |  | Wind | Grant County | MN | [27 empty] | Withdrawn | 2007-07-16 | 2015-09-23 |  |  | Missouri River Energy Services (MRES) | Grant County | MN | SPA-2012-AUG |  | SPA - SIS | ERIS | MRES Elbow Lake - Brandon 115kV | 5.9 | 5.9 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1036 | [5 empty] | NRIS |  | 130 |  | Solar | Cottonwood County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-02-15 |  | 2020-09-01 | Xcel Energy | Cottonwood County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Lakefield Generation SW 345kV Substation | 130 | 130 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2014-DEC | 0 | Withdrawn | Not Started | J425 | [5 empty] | NRIS |  | 999 |  | Gas | St. Charles Parish | LA | [27 empty] | Withdrawn | 2014-11-17 | 2015-09-23 |  |  | Entergy | St. Charles Parish | LA | FES-2014-DEC |  | Feasibility | NRIS | Waterford 230 kV substation | 999 | 999 | Gas | ST, CT | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | South | Withdrawn | Not Started | J636 | [5 empty] | NRIS |  | 52 |  | Hydro | Rapides Parish | LA | [27 empty] | Withdrawn | 2016-05-09 | 2017-06-20 |  | 2016-05-31 | CLECO Corporation | Rapides Parish | LA | DPP-2017-FEB | South | GIA | NRIS | Shady Oaks - Coughlin 138kV Line | 52 | 52 | Hydro | PS Hydraulic Turbine - Reversible (pumped storage) | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1037 | [5 empty] | NRIS |  | 15 |  | Battery Storage | Murray County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-15 |  | 2021-10-01 | Great River Energy | Murray County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Moon Lake 69kV Substation | 15 | 15 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1038 | [5 empty] | ERIS |  | 32.5 |  | Solar | Grant County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2020-09-01 | Otter Tail Power Company | Grant County | MN | DPP-2018-APR | West | PHASE 3 | ERIS | Grant Co. - E. Fergus Falls - Hoot Lake 115 kV Line Tap | 32.5 | 32.5 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-AUG | East (ITC) | Withdrawn | Not Started | J452 | [5 empty] | NRIS |  | 150 |  | Wind | Sanilac County | MI | [27 empty] | Withdrawn | 2015-05-15 | 2015-10-09 |  |  | ITC Transmission | Sanilac County | MI | DPP-2015-AUG | East (ITC) | DPP - SIS | NRIS | Sandusky 120 kV Substation | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-FEB | East (ATC) | Withdrawn | Withdrawn | J293 | [5 empty] | NRIS |  | 496 |  | Gas | Outagamie County | WI | [27 empty] | Withdrawn | 2013-09-10 | 2015-10-19 | 2015-06-11 | 2018-03-15 | American Transmission Co. LLC | Outagamie County | WI | DPP-2014-FEB | East (ATC) | DPP - SIS | NRIS | Fox River 345 kV substation | 475 | 496 | Gas |  | Withdrawn | 2016-11-01 | 0 | 0 | 0 | 0
|  |  |  | FES-2015-SEP | 0 | Withdrawn | Not Started | J480 | [5 empty] | ERIS |  | 1240 |  | Gas | Cherokee County | TX | [27 empty] | Withdrawn | 2015-09-14 | 2015-11-05 |  |  | Entergy | Cherokee County | TX | FES-2015-SEP |  | Feasibility | ERIS | Entergy Grimes 345 kV Substation (BUSNUMBER 334028) | 1095 | 1240 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA-2012-AUG | 0 | Withdrawn | Not Started | G818 | [5 empty] | ERIS |  | 20 |  | Wind | Grant County | MN | [27 empty] | Withdrawn | 2007-07-16 | 2015-11-09 |  |  | Missouri River Energy Services (MRES) | Grant County | MN | SPA-2012-AUG |  | SPA - SIS | ERIS | MRES Grant Co. - Morris 115 kV | 20 | 20 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J251 | [5 empty] | NRIS |  | 27.5 |  | Wind | Ramsey County | ND | [27 empty] | Withdrawn | 2012-09-10 | 2015-11-09 |  |  | Otter Tail Power Company | Ramsey County | ND | SPA Parked |  | SPA - SIS | NRIS | OTP 41.6 kV Oberon Substation | 27.5 | 27.5 | Wind |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | South | Withdrawn | Not Started | J417 | [5 empty] | NRIS |  | 43 |  | Waste Heat Recovery | Calcasieu | LA | [27 empty] | Withdrawn | 2014-11-17 | 2015-11-13 |  |  | Entergy | Calcasieu | LA | DPP-2015-FEB | South | Int FaS | NRIS | Entergy 230 kV Graywood substation Big Lake Road | 43 | 43 | Waste Heat Recovery | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J1039 | [5 empty] | NRIS | N | 50 |  | Battery Storage | Warren County | MO |  |  |  | 1 | 0 | 200000 | 409074 | [9 empty] | 0 | 4906500 | 877614 | 4906500 | 5784114 | 98.13 | 115.6823 | 5784114 |  |  |  | Withdrawn | 2018-03-12 | 2021-03-10 |  | 2021-10-31 | Ameren Missouri | Warren County | MO | DPP-2018-APR | Central | PHASE 3 | NRIS | Enon - Montogomery 345kV Line Tap | 50 | 50 | Battery Storage | BS Battery Storage | Not Started |  | 50 | 50 | 0 | 0
|  |  |  | DPP-2018-APR | West | Active | Not Started | J1040 |  |  | Scoping Calls - Aasawari | Orsted |  | NRIS | N | 250 |  | Wind | McIntosh County | ND |  |  |  | 1 | 1 | 1000000 | 6723874 | [7 empty] | 465966 | 167518 | 2323563 | 163530056 | 0 | 163996022 | 166487103 | 655.9841 | 665.9484 | 166487103 |  |  |  | Active | 2018-03-12 |  |  | 2021-09-01 | Montana-Dakota Utilities Co. | McIntosh County | ND | DPP-2018-APR | West | PHASE 3 | NRIS | Wishek Junction 230 kV Substation | 250 | 250 | Wind | WT Wind Turbine | Not Started |  | 250 | 250 | 250 | 250
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1041 | [5 empty] | NRIS |  | 20 |  | Battery Storage | Jackson County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2021-10-31 | ITC Midwest | Jackson County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Brewster - Heron Lake 161 kV Line | 20 | 20 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ATC) | Active | Not Started | J1042 | [5 empty] | NRIS | N | 200 |  | Solar | Walworth County | WI |  |  |  | 1 | 1 | 800000 | 258992 | [9 empty] | 1950000 | 750098 | 13825209 | 750098 | 16525307 | 3.7505 | 82.6265 | 16525307 |  |  |  | Active | 2018-03-09 |  |  | 2021-09-01 | American Transmission Co. LLC | Walworth County | WI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | North Lake Geneva 138kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 200 | 200 | 180 | 180
|  |  |  | DPP-2014-AUG | West | Withdrawn | Withdrawn | J309 | [5 empty] | NRIS |  | 20 |  | Solar | Yellow Medicine County | MN | [27 empty] | Withdrawn | 2013-11-18 | 2015-11-17 |  | 2018-09-30 | Northern States Power (Xcel Energy) | Yellow Medicine County | MN | DPP-2014-AUG | West | Int FaS | NRIS | Xcel Yellow Medicine - Minnesota Valley 69 kV line | 20 | 20 | Solar |  | Withdrawn | 2016-10-01 | 0 | 0 | 0 | 0
|  |  |  | FES-2014-JUN | 0 | Withdrawn | Not Started | J346 | [5 empty] | NRIS |  | 201 |  | Wind | Nodaway County | MO | [27 empty] | Withdrawn | 2014-05-19 | 2015-12-14 |  |  | MidAmerican Energy Company | Nodaway County | MO | FES-2014-JUN |  | Feasibility | NRIS | 161 Maryville-Clarinda line | 201 | 201 | Wind |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Active | Not Started | J1043 | [5 empty] | NRIS |  | 374.4 |  | Wind | Montcalm County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2018-03-12 |  |  | 2021-06-13 | Michigan Electric Transmission Company, LLC | Montcalm County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Vergennes - Nelson Rd 345 kV Line Tap | 374.4 | 374.4 | Wind | WT Wind Turbine | Not Started | 2024-05-31 | 374.4 | 374.4 | 374.4 | 374.4
|  |  |  | FES-2014-JUN | 0 | Withdrawn | Not Started | J347 | [5 empty] | NRIS |  | 30 |  | Solar | Craighead County | AR | [27 empty] | Withdrawn | 2014-05-19 | 2015-12-14 |  |  | Entergy | Craighead County | AR | FES-2014-JUN |  | Feasibility | NRIS | Unknown | 30 | 30 | Solar |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-FEB | West | Withdrawn | Not Started | J303 | [5 empty] | NRIS |  | 20 |  | Solar | Murray County | MN | [27 empty] | Withdrawn | 2013-11-18 | 2015-12-15 |  | 2018-12-31 | Northern States Power (Xcel Energy) | Murray County | MN | DPP-2014-FEB | West | Network Upgrade | NRIS | Xcel Hadley 69 kV Substation | 20 | 20 | Solar |  | Not Started | 2016-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | East (ITC) | Withdrawn | Not Started | J421 | [5 empty] | NRIS Only |  | 32 |  | Nuclear | Monroe County | MI | [27 empty] | Withdrawn | 2014-11-17 | 2015-12-21 |  | 2015-09-01 | ITC Transmission | Monroe County | MI | DPP-2015-FEB | East (ITC) | Int FaS | NRIS Only | Enrico Fermi Energy Center | 32 | 32 | Nuclear | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | East (ITC) | Withdrawn | Not Started | J422 | [5 empty] | NRIS Only |  | 30 |  | Gas | St. Clair County | MI | [27 empty] | Withdrawn | 2014-11-17 | 2015-12-21 |  | 2015-09-01 | ITC Transmission | St. Clair County | MI | DPP-2015-FEB | East (ITC) | Int FaS | NRIS Only | Greenwood Energy Center | 30 | 30 | Gas | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2015-NOV | 0 | Withdrawn | Not Started | J509 | [5 empty] | NRIS |  | 326.9 |  | Gas | Dickey County | ND | [27 empty] | Withdrawn | 2015-11-16 | 2015-12-30 |  |  | Otter Tail Power Company | Dickey County | ND | FES-2015-NOV |  | Feasibility | NRIS | Ellendale Township 129N, Range 63W | 321.9 | 326.9 | Gas | CT Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2014-JUN | 0 | Withdrawn | Not Started | J331 | [5 empty] | ERIS |  | 338 |  | Gas | Calcasieu | LA | [27 empty] | Withdrawn | 2014-05-16 | 2016-01-06 |  |  | Entergy | Calcasieu | LA | FES-2014-JUN |  | Feasibility | ERIS | New Entergy Michigan Substation | 284 | 338 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ATC) | Withdrawn | Not Started | J1044 | [5 empty] | NRIS | N | 200 |  | Solar | Walworth County | WI |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-10-24 |  | 2022-09-01 | American Transmission Co. LLC | Walworth County | WI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | North Lake Geneva - Sugar Creek - Burlington 138kV Line Tap | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2014-JUN | 0 | Withdrawn | Not Started | J341 | [5 empty] | NRIS |  | 50 |  | Solar | Chisago County | MN | [27 empty] | Withdrawn | 2014-05-19 | 2016-01-06 |  |  | Xcel Energy | Chisago County | MN | FES-2014-JUN |  | Feasibility | NRIS | Unknown | 50 | 50 | Solar |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2014-JUN | 0 | Withdrawn | Not Started | J352 | [5 empty] | NRIS |  | 362 |  | Gas | Dickinson County | MI | [27 empty] | Withdrawn | 2014-05-19 | 2016-01-06 |  |  | American Transmission Co. LLC | Dickinson County | MI | FES-2014-JUN |  | Feasibility | NRIS | Unknown | 342 | 362 | Gas |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2014-JUN | 0 | Withdrawn | Not Started | J353 | [5 empty] | NRIS |  | 725 |  | Gas | Dickinson County | MI | [27 empty] | Withdrawn | 2014-05-19 | 2016-01-06 |  |  | American Transmission Co. LLC | Dickinson County | MI | FES-2014-JUN |  | Feasibility | NRIS | Unknown | 690 | 725 | Gas |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA-2014-NOV | 0 | Withdrawn | Not Started | J378 | [5 empty] | NRIS |  | 79.14 |  | Solar | Lonoke County | AR | [27 empty] | Withdrawn | 2014-07-14 | 2016-01-12 |  |  | Entergy | Lonoke County | AR | SPA-2014-NOV |  | SPA - SIS | NRIS | Lonoke East 115 kV substation | 79.14 | 79.14 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Active | Not Started | J1045 | [5 empty] | NRIS | N | 20 |  | Battery Storage | Murray County | MN |  |  |  | 1 | 1 | 80000 | 120333 | [7 empty] | 0 | 17686 | 0 | 9901 |  | 9901 | 27587 | 0.49505 | 1.3794 | 27587 |  |  |  | Active | 2018-03-12 |  |  | 2021-10-31 | Northern States Power (Xcel Energy) | Murray County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Fenton - Chanarambie 115kV Line Tap | 20 | 20 | Battery Storage | BS Battery Storage | Not Started |  | 20 | 20 | 20 | 20
|  |  |  | DPP-2013-AUG | West | Withdrawn | Not Started | J288 | [5 empty] | NRIS |  | 40 |  | Wind | Kandiyohi County, Meeker County | MN | [27 empty] | Withdrawn | 2013-07-08 | 2016-01-25 |  | 2018-11-01 | Northern States Power (Xcel Energy) | Kandiyohi County, Meeker County | MN | DPP-2013-AUG | West | DPP - SIS | NRIS | Atwater-Grove City 69kV line 0.8 miles no of GRE Atwater Sub | 40 | 40 | Wind | WT Wind Turbine | Not Started | 2019-07-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-FEB | West | Withdrawn | Not Started | J532 | [5 empty] | NRIS |  | 50 |  | Solar | Cass County,Montgomery County | IA | [27 empty] | Withdrawn | 2015-11-16 | 2016-02-17 |  |  | MidAmerican Energy Company | Cass County,Montgomery County | IA | DPP-2016-FEB | West | GIA | NRIS | Red Oak â€“ Coburg 69kV Line | 50 | 50 | Solar | PV Photovoltaic | Not Started | 2016-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1046 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Washtenaw County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-11-21 |  | 2020-10-31 | ITC Transmission | Washtenaw County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Majestic - Lemoyne 345 kV Line Tap | 50 | 50 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ATC) | Withdrawn | Not Started | J1047 | [5 empty] | NRIS | N | 200 |  | Solar | Walworth County | WI |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-10-24 |  | 2022-09-01 | American Transmission Co. LLC | Walworth County | WI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | North Lake Geneva - Sugar Creek - Burlington 138kV Line Tap | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2014-SEP | 0 | Withdrawn | Not Started | J383 | [5 empty] | NRIS |  | 571 |  | Gas | Manitowoc County | WI | [27 empty] | Withdrawn | 2014-08-18 | 2016-03-18 |  | 2019-05-31 | American Transmission Co. LLC | Manitowoc County | WI | FES-2014-SEP |  | Feasibility | NRIS | Unknown | 470 | 571 | Gas | CS Combined-Cycle Single Shaft - Combustion turbine and steam turbine share a single generator | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1048 | [5 empty] | NRIS |  | 250 |  | Wind | Mecosta County,Montcalm County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-03-28 |  | 2020-09-01 | Michigan Electric Transmission Company, LLC | Mecosta County,Montcalm County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Vergennes - Nelson Road 345kV Line Tap | 250 | 250 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1049 | [5 empty] | NRIS |  | 250 |  | Solar | Forrest County | MS | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-29 |  | 2022-09-01 | Cooperative Energy | Forrest County | MS | DPP-2018-APR | South | GIA | NRIS | Purvis 161 kV Substation | 250 | 250 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2014-DEC | 0 | Withdrawn | Not Started | J404 | [5 empty] | NRIS |  | 1063 |  | Gas | Jefferson Parish | LA | [27 empty] | Withdrawn | 2014-11-12 | 2016-03-18 |  | 2020-05-01 | Entergy | Jefferson Parish | LA | FES-2014-DEC |  | Feasibility | NRIS | One miles south of EES Nine Mile Point substation in Bridge City | 1078 | 1063 | Gas | CA Combined-Cycle - Steam Part | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | 0 | Withdrawn | Withdrawn | G359 | [5 empty] | ERIS |  | 150 |  | Wind | Dickey County | ND | [27 empty] | Withdrawn | 2004-03-27 | 2016-04-03 | 2010-04-27 | 2012-12-01 | Montana-Dakota Utilities Company | Dickey County | ND | Pre-Transition SIS |  | DPP - SIS | ERIS | MDU 230 kV system near Ellendale | 150 | 150 | Wind | WT Wind Turbine | Withdrawn | 2006-05-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Active | Not Started | J1050 |  |  | Scoping Calls - Kevin Godly | Apex |  | NRIS | N | 225 |  | Wind | Boone County,Hamilton County | IA |  |  |  | 1 | 1 | 900000 | 0 | [7 empty] | 0 | 2000000 | 0 | 439861 | 18345 | 439861 | 2458206 | 1.9549 | 10.9254 | 2458206 |  |  |  | Active | 2018-03-12 |  |  | 2022-06-03 | ITC Midwest | Boone County,Hamilton County | IA | DPP-2018-APR | West | PHASE 3 | NRIS | Doud Tap 161 kV Substation | 225 | 225 | Wind | WT Wind Turbine | Not Started |  | 225 | 225 | 0 | 0
|  |  |  | Pre-Transition SIS | 0 | Withdrawn | Withdrawn | G867 | [5 empty] | NRIS |  | 1563 |  | Nuclear | Monroe County | MI | [27 empty] | Withdrawn | 2007-09-25 | 2016-04-14 | 2010-04-23 | 2020-12-31 | ITC Transmission | Monroe County | MI | Pre-Transition SIS |  | Network Upgrade | NRIS | Fermi Nuclear Plant | 1563 | 1563 | Nuclear | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | Withdrawn | 2010-05-31 | 0 | 0 | 0 | 0
|  |  |  | FES-2015-JAN | 0 | Withdrawn | Not Started | J430 | [5 empty] | NRIS |  | 26 |  | Wood | Marquette County | MI | [27 empty] | Withdrawn | 2014-12-11 | 2016-04-26 |  | 2016-10-01 | American Transmission Co. LLC | Marquette County | MI | FES-2015-JAN |  | Feasibility | NRIS | ATC 69kV Sawyer line | 26 | 26 | Wood | ST Steam Turbine (including nuclear, geothermal and solar steam, excluding combined-cycle) | Not Started | 2017-09-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ATC) | Withdrawn | Not Started | J1051 | [5 empty] | NRIS | N | 50 |  | Battery Storage | Jefferson County | WI |  |  |  | 1 | 0 | 200000 | 887940 | [9 empty] | 896378 | 6009313 | 5531570 | 6009313 | 12437261 | 120.1863 | 248.7452 | 12437261 |  |  |  | Withdrawn | 2018-03-12 | 2020-05-19 |  | 2021-10-31 | American Transmission Co. LLC | Jefferson County | WI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | Concord 138kV Substation | 50 | 50 | Battery Storage | BS Battery Storage | Not Started |  | 50 | 50 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1052 | [5 empty] | NRIS |  | 100 |  | Solar | Jackson County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-03-27 |  | 2020-09-01 | Michigan Electric Transmission Company, LLC | Jackson County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Beecher - Seamless East 138kV Line Tap | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ATC) | Withdrawn | Not Started | J1053 | [5 empty] | NRIS | N | 300 |  | Solar | Jefferson County | WI |  |  |  | 1 | 0 | 1200000 | 1969396 | [9 empty] | 12022954 | 6009313 | 22121983 | 6009313 | 40154250 | 20.031 | 133.8475 | 40154250 |  |  |  | Withdrawn | 2018-03-12 | 2020-05-19 |  | 2021-10-31 | American Transmission Co. LLC | Jefferson County | WI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | Concord SW YD 138 kV Substation | 300 | 300 | Solar | PV Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1054 | [5 empty] | NRIS |  | 30 |  | Battery Storage | Goodhue County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2021-10-31 | Northern States Power (Xcel Energy) | Goodhue County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Cannon Falls 115kV Substation | 30 | 30 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Under Construction | J1055 | [5 empty] | NRIS | N | 144 |  | Wind | Mason County | IL |  |  |  | 1 | 1 | 576000 | 0 | [9 empty] | 149800 | 1156000 | 0 | 1156000 | 1305800 | 8.0278 | 9.0681 | 1305800 |  |  |  | Active | 2018-03-12 |  |  | 2020-09-30 | Ameren Illinois | Mason County | IL | DPP-2018-APR | Central | PHASE 3 | NRIS | Mason Substation 138 kV Bus | 144 | 144 | Wind | WT Wind Turbine | Under Construction | 2020-10-15 | 144 | 144 | 144 | 144
|  |  |  | DPP-2015-AUG | West | Withdrawn | Not Started | J330 | [5 empty] | NRIS |  | 24.75 |  | Solar | Lyon County | MN | [27 empty] | Withdrawn | 2014-05-15 | 2016-05-19 |  | 2017-10-01 | Northern States Power (Xcel Energy) | Lyon County | MN | DPP-2015-AUG | West | DPP - SIS | NRIS | Tracy - Walnut Grove 69 kV | 24.39 | 24.75 | Solar | PV Photovoltaic | Not Started | 2019-06-01 | 0 | 0 | 0 | 0
|  |  |  | FES-2014-DEC | 0 | Withdrawn | Not Started | J402 | [5 empty] | NRIS |  | 991 |  | Gas | Orleans Parish | LA | [27 empty] | Withdrawn | 2014-11-10 | 2016-06-15 |  | 2019-03-01 | Entergy | Orleans Parish | LA | FES-2014-DEC |  | Feasibility | NRIS | Unknown | 991 | 991 | Gas | CA Combined-Cycle - Steam Part | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-JUN-2015 | 0 | Withdrawn | Not Started | J462 | [5 empty] | NRIS |  | 598.4 |  | Wind | Emmet County | IA | [27 empty] | Withdrawn | 2015-05-18 | 2016-06-15 |  | 2016-09-30 | ITC Midwest | Emmet County | IA | FES-JUN-2015 |  | Feasibility | NRIS | Unknown | 598.4 | 598.4 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1056 | [5 empty] | NRIS |  | 200 |  | Wind | Monroe County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-11-21 |  | 2020-10-31 | ITC Transmission | Monroe County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Lulu - Monroe 345 kV Line Tap | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1057 | [5 empty] | NRIS |  | 125 |  | Solar | Jackson County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2021-10-31 | ITC Midwest | Jackson County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Brewster - Heron Lake 161 kV Line | 125 | 125 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2015-JUN | 0 | Withdrawn | Not Started | J463 | [5 empty] | NRIS |  | 200 |  | Solar | Montgomery County | IL | [27 empty] | Withdrawn | 2015-05-18 | 2016-06-15 |  | 2016-09-30 | Ameren Illinois | Montgomery County | IL | FES-2015-JUN |  | Feasibility | NRIS | Unknown | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J1058 | [5 empty] | NRIS | N | 300 |  | Solar | Lake County | IN |  |  |  | 1 | 1 | 1200000 | 300000 | [9 empty] | 6280000 | 24582234 | 0 | 24582234 | 30862234 | 81.9408 | 102.8741 | 30862234 |  |  |  | Active | 2018-03-12 |  |  | 2021-10-31 | Northern Indiana Public Service Company | Lake County | IN | DPP-2018-APR | Central | PHASE 3 | NRIS | Schahfer-St. John 345kV Line Tap | 300 | 300 | Solar | PV Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
|  |  |  | DPP-2016-AUG | East (ITC) | Withdrawn | Not Started | J572 | [5 empty] | NRIS |  | 150 |  | Combined Cycle | Manistee County | MI | [27 empty] | Withdrawn | 2016-05-09 | 2018-10-05 |  | 2019-06-01 | Michigan Electric Transmission Company, LLC | Manistee County | MI | DPP-2016-AUG | East (ITC) | GIA | NRIS | Filler City JCT 138kV | 150 | 150 | Combined Cycle | Combined Cycle | Not Started |  | 150 | 150 | 150 | 150
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J1059 | [5 empty] | NRIS | N | 300 |  | Solar | Cape Girardeau County | MO |  |  |  | 0 | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-01-07 |  | 2021-10-31 | Ameren Missouri | Cape Girardeau County | MO | DPP-2018-APR | Central | PHASE 3 | NRIS | Kelso - Lutesville 345 kV Line Tap | 300 | 300 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2015-JUN | 0 | Withdrawn | Not Started | J464 | [5 empty] | NRIS |  | 200 |  | Solar | St. Tammany Parish | LA | [27 empty] | Withdrawn | 2015-05-18 | 2016-06-15 |  | 2016-09-30 | Entergy | St. Tammany Parish | LA | FES-2015-JUN |  | Feasibility | NRIS | Unknown | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Done | Under Construction | J1060 | [5 empty] | NRIS |  | 500 |  | Solar | St. Francis County | AR | [21 empty] | 0 | 0 |  |  |  |  | Done | 2018-03-12 |  | 2020-08-19 | 2021-10-31 | Entergy Arkansas, LLC | St. Francis County | AR | DPP-2018-APR | South | GIA | NRIS | West Memphis - Keo 500 kV Line Tap | 500 | 500 | Solar | PV Photovoltaic | Under Construction | 2023-05-01 | 500 | 500 | 450 | 400
|  |  |  | DPP-2015-AUG | South | Withdrawn | Not Started | J465 | [5 empty] | NRIS |  | 44.1 |  | Waste Heat Recovery | St. Mary Parish | LA | [27 empty] | Withdrawn | 2015-05-18 | 2016-06-17 |  | 2017-10-01 | CLECO Corporation | St. Mary Parish | LA | DPP-2015-AUG | South | Int FaS | NRIS | North Bend 138 kV Substation | 44.1 | 44.1 | Waste Heat Recovery | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1061 | [5 empty] | NRIS |  | 300 |  | Solar | Wabasha County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2021-10-31 | Northern States Power (Xcel Energy) | Wabasha County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Briggs Rd - N. Rochester 345 kV Line Tap | 300 | 300 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Active | Not Started | J1062 | [5 empty] | NRIS |  | 200 |  | Solar | Washtenaw County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2018-03-12 |  |  | 2021-10-31 | ITC Transmission | Washtenaw County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Majestic - Lemoyne 345 kV Line Tap | 200 | 200 | Solar | PV Photovoltaic | Not Started | 2023-06-01 | 150 | 150 | 150 | 150
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J1063 | [5 empty] | NRIS | N | 195 |  | Solar | Clinton County | IN |  |  |  | 1 | 1 | 1200000 | 4996500 | [9 empty] | 5655000 | 24214951 | 18954200 | 24214951 | 48824151 | 124.1792 | 250.3803 | 48824151 |  |  |  | Active | 2018-03-12 |  |  | 2022-10-31 | Duke Energy | Clinton County | IN | DPP-2018-APR | Central | PHASE 3 | NRIS | New London - Frankfort 230kV Line Tap | 195 | 195 | Solar | PV Photovoltaic | Not Started |  | 195 | 195 | 195 | 195
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1064 | [5 empty] | NRIS |  | 200 |  | Wind | Ionia County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-11-21 |  | 2020-10-31 | Michigan Electric Transmission Company, LLC | Ionia County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Marquette - Vergennes 138 kV Line Tap | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2013-APR | 0 | Withdrawn | Not Started | J277 | [5 empty] | NRIS |  | 150 |  | Wind | Iroquois County | IL | [27 empty] | Withdrawn | 2013-03-18 | 2016-06-23 |  | 2014-09-01 | -- No Company -- | Iroquois County | IL | FES-2013-APR |  | Feasibility | NRIS | Schaffer Substation | 150 | 150 | Wind |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1065 | [5 empty] | NRIS |  | 200 |  | Wind | Gratiot County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-11-21 |  | 2020-10-31 | Michigan Electric Transmission Company, LLC | Gratiot County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Alma - Vestaburg 138kV Line Tap | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J1066 | [5 empty] | External NRIS | N | 44 |  | Wind | Pike County | IL |  |  |  | 0 | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2018-05-17 |  | 2019-07-31 | Prairie Power, Inc. | Pike County | IL | DPP-2018-APR | Central | PHASE 3 | External NRIS | El Dara Junction - Pittsfield 69 kV Line Tap | 44 | 44 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J1067 | [5 empty] | NRIS | N | 240 |  | Solar | Jasper County,Pulaski County | IN |  |  |  | 1 | 1 | 960000 | 540000 | [9 empty] | 0 | 22837834 | 0 | 22837834 | 22837834 | 95.1576 | 95.1576 | 22837834 |  |  |  | Active | 2018-03-12 |  |  | 2022-09-01 | Northern Indiana Public Service Company | Jasper County,Pulaski County | IN | DPP-2018-APR | Central | PHASE 3 | NRIS | Reynolds - Burr Oak 345kV Line | 240 | 240 | Solar | PV Photovoltaic | Not Started |  | 240 | 240 | 240 | 240
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1068 | [5 empty] | NRIS |  | 200 |  | Wind | Washtenaw County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-11-21 |  | 2020-10-31 | ITC Transmission | Washtenaw County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Dorset 120 kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J1069 | [5 empty] | NRIS | N | 200 |  | Wind | Jasper County,Pulaski County | IN |  |  |  | 1 | 1 | 800000 | 0 | [9 empty] | 0 | 1102243 | 0 | 1102243 | 1102243 | 5.5112 | 5.5112 | 1102243 |  |  |  | Active | 2018-03-12 |  |  | 2022-09-01 | Northern Indiana Public Service Company | Jasper County,Pulaski County | IN | DPP-2018-APR | Central | PHASE 3 | NRIS | Reynolds 345kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 200 | 200 | 200 | 200
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1070 | [5 empty] | NRIS |  | 100 |  | Solar | Washington County | MS | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-29 |  | 2021-09-15 | Entergy Mississippi, LLC | Washington County | MS | DPP-2018-APR | South | GIA | NRIS | SE Greenville 115kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | East (ITC) | Withdrawn | Not Started | J408 | [5 empty] | NRIS |  | 200 |  | Wind | Sanilac County | MI | [27 empty] | Withdrawn | 2014-11-14 | 2016-06-30 |  | 2016-10-01 | ITC Transmission | Sanilac County | MI | DPP-2015-FEB | East (ITC) | Int FaS | NRIS | Banner 345 kV substation | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2018-09-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Active | Not Started | J1071 | [5 empty] | NRIS |  | 100 |  | Solar | Oceana County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2018-03-12 |  |  | 2021-01-20 | Michigan Electric Transmission Company, LLC | Oceana County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Donaldson 138 kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 100 | 100 | 100 | 100
|  |  |  | DPP-2018-APR | West | Active | Not Started | J1072 | [5 empty] | NRIS | N | 150 |  | Solar | Mower County | MN |  |  |  | 1 | 1 | 600000 | 80963 | [7 empty] | 0 | 71345 | 0 | 2764007 |  | 2764007 | 2835352 | 18.9023 | 18.9023 | 2835352 |  |  |  | Active | 2018-03-12 |  |  | 2020-09-01 | Northern States Power (Xcel Energy) | Mower County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Adams 345 kV Substation | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1073 | [5 empty] | NRIS |  | 300 |  | Solar | Iberville Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-29 |  | 2021-09-15 | Entergy Louisiana, LLC | Iberville Parish | LA | DPP-2018-APR | South | GIA | NRIS | Webre 500 kV Substation | 300 | 300 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | 0 | Withdrawn | Not Started | J236 | [5 empty] | NRIS |  | 2400 |  | High Voltage DC | White County | IN | [27 empty] | Withdrawn | 2011-12-08 | 2016-07-15 |  | 2018-08-01 | Northern Indiana Public Service Company | White County | IN | SPA Parked |  | SPA - SIS | NRIS | NIPSCO Reynolds 345/765 kV Substation | 2400 | 2400 | High Voltage DC | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J1074 | [5 empty] | NRIS | N | 200 |  | Solar | Gibson County | IN |  |  |  | 1 | 1 | 800000 | 1805435 | [9 empty] | 2531000 | 1216300 | 26798315 | 1216300 | 30545615 | 6.0815 | 152.7281 | 30545615 |  |  |  | Active | 2018-03-12 |  |  | 2021-01-02 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Gibson County | IN | DPP-2018-APR | Central | PHASE 3 | NRIS | Francisco 138 kV sub | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
|  |  |  | FES-2015-SEP | 0 | Withdrawn | Not Started | J471 | [5 empty] | NRIS |  | 50 |  | Solar | Wayne County | MI | [27 empty] | Withdrawn | 2015-08-19 | 2016-07-15 |  | 2016-11-01 | ITC Transmission | Wayne County | MI | FES-2015-SEP |  | Feasibility | NRIS | ITC 120 kV Dayton substation | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1075 | [5 empty] | NRIS |  | 350 |  | Wind | Cass County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2018-11-01 |  | 2020-09-01 | Michigan Electric Transmission Company, LLC | Cass County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Argenta - Weeds Lake - Hiple 345kV Line Tap | 350 | 350 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Done | Under Construction | J1076 | [5 empty] | NRIS |  | 200 |  | Solar | St. James Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Done | 2018-03-12 |  | 2021-01-06 | 2021-09-15 | Entergy Louisiana, LLC | St. James Parish | LA | DPP-2018-APR | South | GIA | NRIS | Vacherie Sub 230 kV Substation | 200 | 200 | Solar | PV Photovoltaic | Under Construction | 2022-09-01 | 200 | 200 | 200 | 200
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1077 | [5 empty] | NRIS |  | 250 |  | Wind | Cass County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2018-11-01 |  | 2020-09-01 | Michigan Electric Transmission Company, LLC | Cass County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Argenta - Weeds Lake - Hiple 345kV Line Tap | 250 | 250 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1078 | [5 empty] | NRIS |  | 300 |  | Solar | Mississippi County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-29 |  | 2021-09-15 | Entergy Arkansas, LLC | Mississippi County | AR | DPP-2018-APR | South | GIA | NRIS | San Souci 500 kV Substation | 300 | 300 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1079 | [5 empty] | NRIS |  | 200 |  | Solar | St. Charles Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-29 |  | 2021-09-15 | Entergy Louisiana, LLC | St. Charles Parish | LA | DPP-2018-APR | South | GIA | NRIS | Waterford 1&2 230 kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J1080 | [5 empty] | NRIS | N | 99 |  | Wind | DeWitt County,McLean County | IL |  |  |  | 0 | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-03-22 |  | 2020-09-01 | Ameren Illinois | DeWitt County,McLean County | IL | DPP-2018-APR | Central | PHASE 3 | NRIS | Brokaw - Clinton 345kV Line Tap | 99 | 99 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1081 | [5 empty] | NRIS |  | 300 |  | Wind | Polk County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-03-28 |  | 2020-09-01 | Otter Tail Power Company | Polk County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Winger 115kV Substation | 300 | 300 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1082 | [5 empty] | NRIS |  | 400 |  | Wind | Grundy County,Mercer County | MO | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-03-28 |  | 2020-09-01 | Ameren Missouri | Grundy County,Mercer County | MO | DPP-2018-APR | West | PHASE 3 | NRIS | Zachary 345 kV Substation | 400 | 400 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-AUG | MI | Done | In Service | J122 | [5 empty] | ERIS |  | 60 |  | Wind | Huron County | MI | [27 empty] | Done | 2010-04-15 |  | 2012-05-22 | 2012-12-07 | ITC Transmission | Huron County | MI | DPP-2010-AUG | MI | Network Upgrade | ERIS | adjacent to Rapson Rd, N. Finkel Rd and Lection Line Rd | 60 | 60 | Wind | WT Wind Turbine | In Service | 2012-09-30 | 0 | 0 | 0 | 0
|  |  |  | SPA-2013-MAR | 0 | Withdrawn | Not Started | G628 | [5 empty] | ERIS |  | 32 |  | Wind | Brown County | MN | [27 empty] | Withdrawn | 2006-05-02 | 2016-07-25 |  | 2007-12-01 | ITC Midwest | Brown County | MN | SPA-2013-MAR |  | SPA - SIS | ERIS | ITC Midwest Comfrey - Mountain Lake 69 kV | 32 | 32 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1083 | [5 empty] | NRIS |  | 70 |  | Solar | Eaton County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-12-02 |  | 2021-09-01 | Michigan Electric Transmission Company, LLC | Eaton County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Oneida138kV Substation | 70 | 70 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Active | Not Started | J1084 | [5 empty] | NRIS |  | 150 |  | Solar | Clinton County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2018-03-12 |  |  | 2020-09-01 | ITC Midwest | Clinton County | IA | DPP-2018-APR | West | PHASE 3 | NRIS | Rock Creek 345 kV Substation | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
|  |  |  | DPP-2018-APR | East (ATC) | Withdrawn | Not Started | J1085 | [5 empty] | NRIS | N | 300 |  | Wind | Marathon County,Taylor County,Wood County | WI |  |  |  | 1 | 0 | 1200000 | 547326 | [9 empty] | 4061000 | 11492260 | 11400000 | 11492260 | 26953260 | 38.3075 | 89.8442 | 26953260 |  |  |  | Withdrawn | 2018-03-12 | 2020-05-19 |  | 2021-09-01 | American Transmission Co. LLC | Marathon County,Taylor County,Wood County | WI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | Gardner Park - J821 POI - Stone Lake 345 kV Line Tap | 300 | 300 | Wind | WT Wind Turbine | Not Started |  | 300 | 300 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1086 | [5 empty] | NRIS |  | 120 |  | Solar | Nobles County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2021-01-02 | ITC Midwest | Nobles County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Elk - Brewster 161 kV Line Tap | 120 | 120 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J1087 | [5 empty] | NRIS | N | 200 |  | Solar | Scott County | MO |  |  |  | 1 | 1 | 800000 | 935301 | [9 empty] | 656000 | 8322000 | 1319532 | 8322000 | 10297532 | 41.61 | 51.4877 | 10297532 |  |  |  | Active | 2018-03-12 |  |  | 2021-01-02 | Ameren Missouri | Scott County | MO | DPP-2018-APR | Central | PHASE 3 | NRIS | Miner - Kelso 161 kV Line Tap | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1088 | [5 empty] | NRIS |  | 150 |  | Solar | Shiawassee County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2021-02-04 |  | 2021-01-02 | Michigan Electric Transmission Company, LLC | Shiawassee County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Cornell - Layton 138 kV Line Tap | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
|  |  |  | DPP-2017-FEB | East (ITC) | Done | Under Construction | J646 | [5 empty] | ERIS |  | 0 |  | Landfill Gas | Macomb County | MI | [27 empty] | Done | 2016-06-16 |  | 2019-04-26 | 2010-07-01 | ITC Transmission | Macomb County | MI | DPP-2017-FEB | East (ITC) | GIA | ERIS | Carbon - connecting to ITC at Jewel, St-Clair and Spokane substations | 1.6 | 0 | Landfill Gas | OT Other | Under Construction | 2010-07-01 | 1.6 | 0 | 1.6 | 0
|  |  |  | FES-2014-DEC | 0 | Withdrawn | Not Started | J420 | [5 empty] | NRIS |  | 75 |  | Solar | Washtenaw County | MI | [27 empty] | Withdrawn | 2014-11-17 | 2016-08-23 |  | 2016-09-01 | ITC Transmission | Washtenaw County | MI | FES-2014-DEC |  | Feasibility | NRIS | Eight miles northeast of Ann Arbor, MI | 75 | 75 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1089 | [5 empty] | NRIS |  | 170 |  | Solar | Shiawassee County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2021-02-04 |  | 2021-01-02 | Michigan Electric Transmission Company, LLC | Shiawassee County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Cornell - Bell Rd 138 kV Line Tap | 170 | 170 | Solar | PV Photovoltaic | Not Started |  | 170 | 170 | 170 | 170
|  |  |  | FES-2014-DEC | 0 | Withdrawn | Not Started | J428 | [5 empty] | NRIS |  | 50 |  | Solar | Jefferson County | TX | [27 empty] | Withdrawn | 2014-11-17 | 2016-08-30 |  | 2018-01-01 | Entergy | Jefferson County | TX | FES-2014-DEC |  | Feasibility | NRIS | Bill Hill 138 kV substation | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | Central | Withdrawn | Not Started | J649 | [5 empty] | External NRIS |  | 829 |  | Nuclear | Dauphin County | PA | [27 empty] | Withdrawn | 2016-06-24 | 2017-01-31 |  | 1957-09-01 | Metropolitan Edison Company | Dauphin County | PA | DPP-2016-AUG | Central | GIA | External NRIS | Exisiting interconnection in TMI Switchyard at 220kV | 805 | 829 | Nuclear | Nuclear | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | Central | Withdrawn | Not Started | J648 | [5 empty] | External NRIS |  | 296 |  | Gas | Cook County | IL | [27 empty] | Withdrawn | 2016-06-24 | 2019-01-22 |  |  | Commonwealth Edison Company | Cook County | IL | DPP-2016-AUG | Central | GIA | External NRIS | Exisiting Interconnection in SCEP switchyard at 138kV | 296 | 296 | Gas | OT Other | Not Started |  | 296 | 296 | 296 | 296
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1090 | [5 empty] | NRIS |  | 90 |  | Solar | Ingham County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2021-02-04 |  | 2021-01-02 | Michigan Electric Transmission Company, LLC | Ingham County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Tompkins - Churchill Jct 138 kV Line Tap | 90 | 90 | Solar | PV Photovoltaic | Not Started |  | 90 | 90 | 90 | 90
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1091 | [5 empty] | NRIS |  | 150 |  | Solar | Craighead County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-29 |  | 2021-09-15 | Entergy Arkansas, LLC | Craighead County | AR | DPP-2018-APR | South | GIA | NRIS | Power Line Road 161 kV Substation | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Active | Not Started | J1092 | [5 empty] | NRIS | N | 100 |  | Solar | Saint Croix County | WI |  |  |  | 1 | 1 | 400000 | 0 | [7 empty] | 0 | 54955 | 0 | 12415962 | 0 | 12415962 | 12470917 | 124.1596 | 124.7092 | 12470917 |  |  |  | Active | 2018-03-12 |  |  | 2022-09-30 | Northern States Power (Xcel Energy) | Saint Croix County | WI | DPP-2018-APR | West | PHASE 3 | NRIS | Three Lakes 115 kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 100 | 100 | 100 | 100
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1093 | [5 empty] | NRIS |  | 200 |  | Solar | Desha County,Drew County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-29 |  | 2021-09-15 | Entergy Arkansas, LLC | Desha County,Drew County | AR | DPP-2018-APR | South | GIA | NRIS | Reed Switch 115kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J1094 | [5 empty] | NRIS | N | 150 |  | Solar | Washington County | IL |  |  |  | 1 | 1 | 600000 | 27877 | [9 empty] | 0 | 7653000 | 1227725 | 7653000 | 8880725 | 51.02 | 59.2048 | 8880725 |  |  |  | Active | 2018-03-12 |  |  | 2021-01-02 | Ameren Illinois | Washington County | IL | DPP-2018-APR | Central | PHASE 3 | NRIS | Prest 138kV Switching Station | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1095 | [5 empty] | NRIS |  | 300 |  | Solar | DeSoto County | MS | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-29 |  | 2021-09-15 | Entergy Mississippi, LLC | DeSoto County | MS | DPP-2018-APR | South | GIA | NRIS | Twinkletown 230kV Substation | 300 | 300 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J1096 | [5 empty] | NRIS | N | 150 |  | Solar | Saline County | IL |  |  |  | 1 | 1 | 600000 | 200000 | [9 empty] | 0 | 6422000 | 0 | 6422000 | 6422000 | 42.8133 | 42.8133 | 6422000 |  |  |  | Active | 2018-03-12 |  |  | 2021-01-02 | Ameren Illinois | Saline County | IL | DPP-2018-APR | Central | PHASE 3 | NRIS | Norris City North - Muddy 138 kV Line | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1097 | [5 empty] | NRIS |  | 500 |  | Solar | Lonoke County,Pulaski County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-29 |  | 2021-09-15 | Entergy Arkansas, LLC | Lonoke County,Pulaski County | AR | DPP-2018-APR | South | GIA | NRIS | KEO EHV 500 kV Substation | 500 | 500 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2015-NOV | 0 | Withdrawn | Not Started | J487 | [5 empty] | NRIS |  | 999 |  | Combined Cycle | San Jacinto County | TX | [27 empty] | Withdrawn | 2015-10-23 | 2016-09-01 |  | 2020-10-01 | Entergy | San Jacinto County | TX | FES-2015-NOV |  | Feasibility | NRIS | San Jacinto 230kV Substation | 923 | 999 | Combined Cycle | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2014-DEC | 0 | Withdrawn | Not Started | J413 | [5 empty] | NRIS |  | 243 |  | Gas | Marquette County | MI | [27 empty] | Withdrawn | 2014-11-14 | 2016-09-13 |  | 2017-06-01 | American Transmission Co. LLC | Marquette County | MI | FES-2014-DEC |  | Feasibility | NRIS | Unknown | 218 | 243 | Gas | ST, CT | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1098 | [5 empty] | NRIS | N | 40 |  | Solar | Jackson County | MN |  |  |  | 1 | 0 | 160000 | 225567 | [7 empty] | 0 | 250853 | 0 | 96800000 | 10000000 | 96800000 | 107050853 | 2420 | 2676.2713 | 107050853 |  |  |  | Withdrawn | 2018-03-12 | 2021-03-09 |  | 2022-09-30 | Northern States Power (Xcel Energy) | Jackson County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Lakefield 345 kV Substation | 40 | 40 | Solar | PV Photovoltaic | Not Started |  | 40 | 40 | 0 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1099 | [5 empty] | NRIS |  | 200 |  | Solar | Iberville Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-29 |  | 2021-09-15 | Entergy Louisiana, LLC | Iberville Parish | LA | DPP-2018-APR | South | GIA | NRIS | Derrick 230 kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1100 | [5 empty] | NRIS |  | 200 |  | Solar | Grimes County | TX | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-29 |  | 2021-09-15 | Entergy Texas, Inc. | Grimes County | TX | DPP-2018-APR | South | GIA | NRIS | Grimes 345 kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ATC) | Active | Not Started | J1101 | [5 empty] | NRIS | N | 20 |  | Battery Storage | Manitowoc County | WI |  |  |  | 1 | 1 | 80000 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Active | 2018-03-12 |  |  | 2021-09-01 | American Transmission Co. LLC | Manitowoc County | WI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | Kewaunee 138kV Substation | 20 | 20 | Battery Storage | BS Battery Storage | Not Started |  | 20 | 20 | 20 | 20
|  |  |  | FES-2015-JUL | 0 | Withdrawn | Not Started | J470 | [5 empty] | NRIS |  | 150 |  | Wind | Marquette County | MI | [27 empty] | Withdrawn | 2015-07-13 | 2016-09-13 |  | 2018-05-01 | American Transmission Co. LLC | Marquette County | MI | FES-2015-JUL |  | Feasibility | NRIS | Unknown | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J1102 | [5 empty] | NRIS | N | 70 |  | Solar | Logan County | IL |  |  |  | 1 | 1 | 280000 | 0 | [9 empty] | 0 | 1031000 | 0 | 1031000 | 1031000 | 14.7286 | 14.7286 | 1031000 |  |  |  | Active | 2018-03-12 |  |  | 2021-06-13 | Ameren Illinois | Logan County | IL | DPP-2018-APR | Central | PHASE 3 | NRIS | Fogarty 138 kV Substation | 70 | 70 | Solar | PV Photovoltaic | Not Started |  | 70 | 70 | 70 | 70
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1103 | [5 empty] | NRIS |  | 20 |  | Battery Storage | Tuscola County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-06-30 |  | 2021-09-01 | ITC Transmission | Tuscola County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Bauer - (Kirk) - Ringle 345kV Line Tap | 20 | 20 | Battery Storage | BS Battery Storage | Not Started |  | 20 | 20 | 0 | 0
|  |  |  | DPP-2018-APR | East (ATC) | Withdrawn | Not Started | J1104 | [5 empty] | NRIS | N | 100 |  | Battery Storage | Washington County,Waukesha County | WI |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-10-24 |  | 2021-09-01 | American Transmission Co. LLC | Washington County,Waukesha County | WI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | Germantown - Bark River 138kV Line | 100 | 100 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1105 | [5 empty] | NRIS | N | 200 |  | Solar | Dakota County | MN |  |  |  | 1 | 0 | 800000 | 738148 | [7 empty] | 0 | 120483 | 0 | 18109762 | 0 | 18109762 | 18230245 | 90.5488 | 91.1512 | 18230245 |  |  |  | Withdrawn | 2018-03-12 | 2021-03-09 |  | 2020-09-01 | Northern States Power (Xcel Energy) | Dakota County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Hampton Corners 345 kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
|  |  |  | FES-2014-DEC | 0 | Withdrawn | Not Started | J403 | [5 empty] | NRIS |  | 49.9 |  | Gas | Dakota County | MN | [27 empty] | Withdrawn | 2014-11-12 | 2016-09-14 |  | 2016-03-31 | Northern States Power (Xcel Energy) | Dakota County | MN | FES-2014-DEC |  | Feasibility | NRIS | Unknown | 49.9 | 49.9 | Gas | CC (cogen) | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2014-DEC | 0 | Withdrawn | Not Started | J410 | [5 empty] | NRIS |  | 300 |  | Wind | Fayette County | IA | [27 empty] | Withdrawn | 2014-11-14 | 2016-09-14 |  | 2016-10-01 | ITC Midwest | Fayette County | IA | FES-2014-DEC |  | Feasibility | NRIS | Hazelton 345 kV substation | 300 | 300 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1106 | [5 empty] | NRIS | N | 414 |  | Wind | Redwood County | MN |  |  |  | 1 | 0 | 1656000 | 4314168 | [7 empty] | 0 | 307898 | 0 | 157774968 | 0 | 157774968 | 158082866 | 381.099 | 381.8427 | 158082866 |  |  |  | Withdrawn | 2018-03-12 | 2021-03-09 |  | 2021-08-01 | Great River Energy | Redwood County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Lyon County - Cedar Mountain 345 kV Circuit 2 Line | 414 | 414 | Wind | WT Wind Turbine | Not Started |  | 414 | 414 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J1107 | [5 empty] | NRIS | N | 200 |  | Solar | Cape Girardeau County | MO |  |  |  | 1 | 1 | 800000 | 704358 | [9 empty] | 447000 | 9813000 | 1358952 | 9813000 | 11618952 | 49.065 | 58.0948 | 11618952 |  |  |  | Active | 2018-03-12 |  |  | 2021-09-01 | Ameren Missouri | Cape Girardeau County | MO | DPP-2018-APR | Central | PHASE 3 | NRIS | Kelso - Lutesville 345 kV Line Tap | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1108 | [5 empty] | NRIS |  | 150 |  | Solar | Douglas County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2021-06-13 | Missouri River Energy Services (MRES) | Douglas County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Alexandria 345 kV Substation | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1109 | [5 empty] | NRIS |  | 207 |  | Wind | Cass County | ND | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2021-08-01 | Northern States Power (Xcel Energy) | Cass County | ND | DPP-2018-APR | West | PHASE 3 | NRIS | Bison 345kV Substation | 207 | 207 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Active | Not Started | J1110 |  |  | Scoping Calls - Anton Ptak | EDF |  | NRIS | N | 100 |  | Solar | Mower County | MN |  |  |  | 1 | 1 | 400000 | 0 | [7 empty] | 0 | 4416785 | 0 | 5165437 | 0 | 5165437 | 9582222 | 51.6544 | 95.8222 | 9582222 |  |  |  | Active | 2018-03-12 |  |  | 2021-09-15 | SMMPA | Mower County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | North Austin 161 kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 100 | 100 | 100 | 100
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J1111 | [5 empty] | NRIS | N | 150 |  | Solar | Jackson County | IL |  |  |  | 1 | 0 | 600000 | 824911 | [9 empty] | 0 | 20227000 | 1028551 | 20227000 | 21255551 | 134.8467 | 141.7037 | 21255551 |  |  |  | Withdrawn | 2018-03-12 | 2021-03-10 |  | 2021-01-02 | Southern Illinois Power Cooperative | Jackson County | IL | DPP-2018-APR | Central | PHASE 3 | NRIS | Campbell Hill - Jackson 161 kV Line Tap | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J1112 | [5 empty] | NRIS | N | 150 |  | Solar | Kosciusko County | IN |  |  |  | 1 | 0 | 800000 | 0 | [9 empty] | 0 | 4326378 | 0 | 4326378 | 4326378 | 28.8425 | 28.8425 | 4326378 |  |  |  | Withdrawn | 2018-03-12 | 2021-03-10 |  | 2021-09-15 | Northern Indiana Public Service Company | Kosciusko County | IN | DPP-2018-APR | Central | PHASE 3 | NRIS | Leesburg 138kV Substation | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1113 | [5 empty] | NRIS |  | 85 |  | Solar | Sunflower County | MS | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-29 |  | 2022-09-01 | Entergy Mississippi, LLC | Sunflower County | MS | DPP-2018-APR | South | GIA | NRIS | Delta - Ruleville 115kV Line Tap | 85 | 85 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2014-SEP | 0 | Withdrawn | Not Started | J388 | [5 empty] | NRIS |  | 800 |  | Gas | Vermilion County | IL | [27 empty] | Withdrawn | 2014-09-15 | 2016-09-15 |  | 2018-12-31 | Ameren Illinois | Vermilion County | IL | FES-2014-SEP |  | Feasibility | NRIS | 345 kV Ameren line at Vermilion Power Plant | 748 | 800 | Gas | CA Combined-Cycle - Steam Part | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2014-AUG | 0 | Withdrawn | Not Started | J368 | [5 empty] | NRIS |  | 200 |  | Solar | Lee County | AR | [27 empty] | Withdrawn | 2014-05-30 | 2016-09-16 |  | 2016-10-01 | Entergy | Lee County | AR | FES-2014-AUG |  | Feasibility | NRIS | Unknown | 200 | 200 | Solar |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2014-AUG | 0 | Withdrawn | Not Started | J369 | [5 empty] | NRIS |  | 393 |  | Gas | Newton County | TX | [27 empty] | Withdrawn | 2014-05-30 | 2016-09-16 |  | 2017-03-01 | Entergy | Newton County | TX | FES-2014-AUG |  | Feasibility | NRIS | Unknown | 337 | 393 | Gas |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | Central | Withdrawn | Under Construction | J375 | [5 empty] | ERIS |  | 124 |  | Wind | Ford County | IL | [27 empty] | Withdrawn | 2014-07-07 | 2016-10-25 |  | 2017-06-02 | Ameren Illinois | Ford County | IL | DPP-2015-FEB | Central | Network Upgrade | ERIS | Gibson City South Substation 138 kV | 124 | 124 | Wind |  | Under Construction | 2015-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1114 | [5 empty] | NRIS |  | 200 |  | Wind | Plymouth County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2021-09-15 | MidAmerican Energy Company | Plymouth County | IA | DPP-2018-APR | West | PHASE 3 | NRIS | J506 Substation on Raun - Highland 345 kV Line | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J1115 | [5 empty] | NRIS | N | 200 |  | Wind | Macon County | IL |  |  |  | 1 | 1 | 800000 | 280000 | [9 empty] | 9681700 | 9847000 | 0 | 9847000 | 19528700 | 49.235 | 97.6435 | 19528700 |  |  |  | Active | 2018-03-12 |  |  | 2021-09-01 | Ameren Illinois | Macon County | IL | DPP-2018-APR | Central | PHASE 3 | NRIS | Latham - Oreana 345kV Line | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 200 | 200 | 200 | 200
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J1116 | [5 empty] | NRIS | N | 100 |  | Wind | Hancock County | IN |  |  |  | 0 | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2018-10-03 |  | 2021-09-01 | Duke Energy Corporation | Hancock County | IN | DPP-2018-APR | Central | PHASE 3 | NRIS | Greensboro - Greenfield 138 kV Line Tap | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1117 | [5 empty] | NRIS |  | 80 |  | Solar | Ingham County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-05-30 |  | 2021-09-01 | Michigan Electric Transmission Company, LLC | Ingham County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Green 138kV Substation | 80 | 80 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J1118 | [5 empty] | NRIS | N | 150 |  | Wind | Piatt County | IL |  |  |  | 0 | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2018-10-03 |  | 2021-09-01 | Ameren Illinois | Piatt County | IL | DPP-2018-APR | Central | PHASE 3 | NRIS | Mahomet - Weedman 138 kV Line Tap | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1120 | [5 empty] | NRIS |  | 145 |  | Wind | Jefferson County | TX | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-23 |  | 2021-09-01 | Entergy Texas, Inc. | Jefferson County | TX | DPP-2018-APR | South | GIA | NRIS | Big Hill CO - Bayou Farms CO 138 kV Line Tap | 145 | 145 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ATC) | Withdrawn | Not Started | J1121 | [5 empty] | NRIS | N | 200 |  | Solar | Marathon County | WI |  |  |  | 1 | 0 | 800000 | 521010 | [9 empty] | 10349000 | 11492261 | 7600000 | 11492261 | 29441261 | 57.4613 | 147.2063 | 29441261 |  |  |  | Withdrawn | 2018-03-12 | 2020-05-19 |  | 2021-09-01 | American Transmission Co. LLC | Marathon County | WI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | Stone Lake - (Pershing) - Gardner Park 345 kV Line Tap | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1122 | [5 empty] | NRIS | N | 200 |  | Wind | Pottawattamie County | IA |  |  |  | 1 | 0 | 800000 | 1350268 | [7 empty] | 0 | 0 | 0 | 14036304 | 144859 | 14036304 | 14181163 | 70.1815 | 70.9058 | 14181163 |  |  |  | Withdrawn | 2018-03-12 | 2021-03-09 |  | 2022-09-01 | MidAmerican Energy Company | Pottawattamie County | IA | DPP-2018-APR | West | PHASE 3 | NRIS | Council Bluffs - Fallow Avenue 345 kV Line Tap | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
|  |  |  | FES-2015-JUN | 0 | Withdrawn | Not Started | J461 | [5 empty] | NRIS |  | 299.2 |  | Wind | Tama County | IA | [27 empty] | Withdrawn | 2015-05-18 | 2016-11-02 |  | 2016-09-30 | ITC Midwest | Tama County | IA | FES-2015-JUN |  | Feasibility | NRIS | Unknown | 299.2 | 299.2 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J1123 | [5 empty] | NRIS | N | 150 |  | Wind | Audrain County | MO |  |  |  | 0 | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-01-02 |  | 2021-09-01 | Ameren Missouri | Audrain County | MO | DPP-2018-APR | Central | PHASE 3 | NRIS | Spencer Creek 345 kV Substation | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Active | Not Started | J1124 |  |  | Scoping Calls - Anton Ptak | EDF |  | NRIS | N | 100 |  | Solar | Olmsted County | MN |  |  |  | 1 | 1 | 400000 | 0 | [7 empty] | 0 | 51717 | 0 | 4051078 | 0 | 4051078 | 4102795 | 40.5108 | 41.0279 | 4102795 |  |  |  | Active | 2018-03-12 |  |  | 2021-09-15 | SMMPA | Olmsted County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Byron 345kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 100 | 100 | 100 | 100
|  |  |  | DPP-2018-APR | South | Done | Under Construction | J1125 | [5 empty] | NRIS |  | 135 |  | Solar | Cross County | AR | [21 empty] | 0 | 0 |  |  |  |  | Done | 2018-03-12 |  | 2020-08-12 | 2021-07-31 | Entergy Arkansas, LLC | Cross County | AR | DPP-2018-APR | South | GIA | NRIS | Wynne South - Wynne East AECC 161 kV Line Tap | 135 | 135 | Solar | PV Photovoltaic | Under Construction | 2023-03-01 | 135 | 135 | 135 | 135
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1126 | [5 empty] | NRIS |  | 1.1 |  | Wind | Tuscola County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2018-11-01 |  | 2020-09-01 | ITC Transmission | Tuscola County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | ITC Bauer - Grassmere - Rapson (Kirk Sub) 345kV Substation | 1.1 | 1.1 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ATC) | Withdrawn | Not Started | J1127 | [5 empty] | NRIS | N | 49.9 |  | Solar | Green County | WI |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-10-25 |  | 2021-01-02 | American Transmission Co. LLC | Green County | WI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | Albany - Bass Creek 138 kV Line Tap | 49.9 | 49.9 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J685 | [5 empty] | NRIS |  | 30 |  | Gas | Clark County | AR | [27 empty] | Withdrawn | 2016-07-11 | 2017-07-21 |  | 2017-12-01 | Entergy | Clark County | AR | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 30 | 30 | Gas | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1128 | [5 empty] | NRIS | N | 150 |  | Solar | Freeborn County | MN |  |  |  | 1 | 0 | 600000 | 1338204 | [7 empty] | 0 | 7878179 | 0 | 18950622 | 0 | 18950622 | 26828801 | 126.3375 | 178.8587 | 26828801 |  |  |  | Withdrawn | 2018-03-12 | 2021-03-09 |  | 2021-01-02 | SMMPA | Freeborn County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Hayward - Murphy Creek 161 kV Line Tap | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
|  |  |  | DPP-2018-APR | East (ATC) | Withdrawn | Not Started | J1129 | [5 empty] | NRIS | N | 65 |  | Solar | Rock County | WI |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-10-25 |  | 2021-01-02 | American Transmission Co. LLC | Rock County | WI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | Paddock - Townline Rd 138 kV Line Tap | 65 | 65 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-FEB | West | Withdrawn | Not Started | J497 | [5 empty] | NRIS |  | 170 |  | Wind | Benton County | IA | [27 empty] | Withdrawn | 2015-11-13 | 2016-11-17 |  | 2017-07-01 | ITC Midwest | Benton County | IA | DPP-2016-FEB | West | GIA | NRIS | ITC 161 kV Dysart substation | 170 | 170 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Active | Not Started | J1131 |  |  | Scoping Calls - Amit Ranjan | Alliant |  | NRIS |  | 100 |  | Solar | Scott County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2018-03-12 |  |  | 2023-10-01 | MidAmerican Energy Company | Scott County | IA | DPP-2018-APR | West | PHASE 3 | NRIS | Sub 56 Davenport 161 kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 100 | 100 | 100 | 100
|  |  |  | DPP-2015-FEB | East (ATC) | Withdrawn | Not Started | J394 | [5 empty] | NRIS |  | 327 |  | Combined Cycle | Marquette County | MI | [27 empty] | Withdrawn | 2014-09-15 | 2016-11-21 |  | 2016-12-15 | American Transmission Co. LLC | Marquette County | MI | DPP-2015-FEB | East (ATC) | DPP - SIS | NRIS | National 138 kV Substation | 280 | 327 | Combined Cycle | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Active | Not Started | J1132 | [5 empty] | NRIS | N | 50 |  | Solar | Union County | IA |  |  |  | 1 | 1 | 200000 | 330511 | [7 empty] | 0 | 0 | 1988000 | 230544 | 3748353 | 230544 | 5966897 | 4.6109 | 119.3379 | 5966897 |  |  |  | Active | 2018-03-12 |  |  | 2023-10-01 | ITC Midwest | Union County | IA | DPP-2018-APR | West | PHASE 3 | NRIS | Creston East 69 kV Substation | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 50 | 50 | 50 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1133 | [5 empty] | NRIS |  | 100 |  | Solar | Richland Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2018-10-01 |  | 2021-08-11 | Entergy Louisiana, LLC | Richland Parish | LA | DPP-2018-APR | South | GIA | NRIS | Dunn - Oakridge 115kV Line Tap | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1134 | [5 empty] | NRIS |  | 100 |  | Solar | White County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2018-06-05 |  | 2021-08-11 | Entergy Arkansas, LLC | White County | AR | DPP-2018-APR | South | GIA | NRIS | Griffithville - Searcy Price 115 kV Line Tap | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA-2013-NOV | 0 | Withdrawn | Not Started | G637 | [5 empty] | ERIS |  | 20 |  | Wind | Traverse County | MN | [27 empty] | Withdrawn | 2006-05-16 | 2016-12-13 |  | 2007-10-01 | Otter Tail Power Company | Traverse County | MN | SPA-2013-NOV |  | SPA - SIS | ERIS | OTP Graceville - Wapton 115 kV | 20 | 20 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Active | Not Started | J1135 | [5 empty] | NRIS |  | 50 |  | Solar | Des Moines County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2018-03-12 |  |  | 2021-10-01 | ITC Midwest | Des Moines County | IA | DPP-2018-APR | West | PHASE 3 | NRIS | Huntwoods 69 kV substation | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 50 | 50 | 50 | 50
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1136 | [5 empty] | NRIS |  | 100 |  | Solar | Hinds County | MS | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2018-06-05 |  | 2021-08-11 | Entergy Mississippi, LLC | Hinds County | MS | DPP-2018-APR | South | GIA | NRIS | Tinnin Road 230kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1137 | [5 empty] | NRIS |  | 100 |  | Solar | Jackson County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-28 |  | 2021-09-30 | Entergy Arkansas, LLC | Jackson County | AR | DPP-2018-APR | South | GIA | NRIS | Swifton - Hoxie South 161 kV Line Tap | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ATC) | Withdrawn | Not Started | J1138 | [5 empty] | NRIS | N | 70 |  | Wind | Baraga County | MI |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2018-12-07 |  | 2020-09-23 | American Transmission Co. LLC | Baraga County | MI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | M38 138 kV Substation | 70 | 70 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG/DPP-2017-FEB | East (UP) | Done | In Service | J703 | [5 empty] | NRIS |  | 128.1 |  | Gas | Marquette County | MI | [27 empty] | Done | 2016-09-08 |  |  | 2019-03-01 | American Transmission Co. LLC | Marquette County | MI | DPP-2016-AUG/DPP-2017-FEB | East (UP) | GIA | NRIS | Huron 138kV Substation -looping Lines FREG11 (National to Freeman) & Goose Lake (PI to Empire) | 128.1 | 128.1 | Gas | IC Internal Combustion (diesel, piston) Engine | In Service | 2018-12-01 | 128.1 | 128.1 | 128.1 | 128.1
|  |  |  | DPP-2016-AUG/DPP-2017-FEB | East (UP) | Done | In Service | J704 | [5 empty] | NRIS |  | 54.9 |  | Gas | Baraga County | MI | [27 empty] | Done | 2016-09-08 |  |  | 2019-03-01 | American Transmission Co. LLC | Baraga County | MI | DPP-2016-AUG/DPP-2017-FEB | East (UP) | GIA | NRIS | M38 Substation 138kV | 54.9 | 54.9 | Gas | IC Internal Combustion (diesel, piston) Engine | In Service | 2018-12-01 | 54.9 | 54.9 | 54.9 | 54.9
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J1139 | [5 empty] | NRIS | N | 150 |  | Solar | Champaign County | IL |  |  |  | 1 | 1 | 600000 | 0 | [9 empty] | 41861500 | 290000 | 0 | 290000 | 42151500 | 1.9333 | 281.01 | 42151500 |  |  |  | Active | 2018-03-12 |  |  | 2020-10-31 | Ameren Illinois | Champaign County | IL | DPP-2018-APR | Central | PHASE 3 | NRIS | Sidney Substation 138 kV Bus | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 135 | 135
|  |  |  | SPA-2015-MAY | 0 | Withdrawn | Not Started | J093 | [5 empty] | NRIS |  | 50 |  | Wind | Greene County | IA | [27 empty] | Withdrawn | 2009-10-28 | 2017-01-10 |  | 2010-07-31 | MidAmerican Energy Company | Greene County | IA | SPA-2015-MAY |  | SPA - SIS | NRIS | MEC Drager - Grand Junction 161 kV | 50 | 50 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | R58 | [5 empty] | NRIS |  | 3 |  | Wind | Pottawattamie County | IA | [27 empty] | Withdrawn | 2009-04-08 | 2017-01-10 |  | 2008-12-31 | MidAmerican Energy Company | Pottawattamie County | IA |  |  | SPA - SIS | NRIS | MEC Teakwood (Walnut) 161kV Substation | 3 | 3 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1140 | [5 empty] | NRIS | N | 80 |  | Solar | Benton County | MN |  |  |  | 1 | 0 | 400000 | 969933 | [7 empty] | 0 | 49820 | 0 | 46446170 | 0 | 46446170 | 46495990 | 580.5771 | 581.1999 | 46495990 |  |  |  | Withdrawn | 2018-03-12 | 2021-03-09 |  | 2020-08-01 | Minnesota Power | Benton County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Platte River 115 kV Substation | 80 | 80 | Solar | PV Photovoltaic | Not Started |  | 80 | 80 | 0 | 0
|  |  |  | SPA-2014-NOV | West | Withdrawn | Not Started | R59 | [5 empty] | NRIS |  | 28 |  | Wind | Wright County | IA | [27 empty] | Withdrawn | 2009-04-08 | 2017-01-10 |  | 2010-06-30 | MidAmerican Energy Company | Wright County | IA | SPA-2014-NOV | West | SPA - SIS | NRIS | Wall Lake (Century) - expansion | 28 | 28 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Active | Not Started | J1142 | [5 empty] | NRIS |  | 20 |  | Solar | St. James Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2018-03-12 |  |  | 2020-06-01 | Entergy Louisiana, LLC | St. James Parish | LA | DPP-2018-APR | South | GIA | NRIS | Vacherie 230kV Substation | 20 | 20 | Solar | PV Photovoltaic | Not Started | 2020-07-01 | 20 | 20 | 20 | 20
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1143 | [5 empty] | NRIS |  | 100 |  | Solar | Morrison County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2020-08-01 | Minnesota Power | Morrison County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Blanchard - Little Falls 115 kV Line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Done | Under Construction | J1144 | [5 empty] | NRIS |  | 96 |  | Solar | Covington County,Lamar County | MS | [21 empty] | 0 | 0 |  |  |  |  | Done | 2018-03-12 |  | 2020-09-10 | 2021-09-01 | Cooperative Energy | Covington County,Lamar County | MS | DPP-2018-APR | South | GIA | NRIS | Moselle - Columbia 161kV Line Tap | 96 | 96 | Solar | PV Photovoltaic | Under Construction | 2022-06-01 | 96 | 96 | 96 | 96
|  |  |  | DPP-2017-FEB | Central | Withdrawn | Not Started | J708 | [5 empty] | NRIS |  | 847 |  | Combined Cycle | Posey County | IN | [27 empty] | Withdrawn | 2016-09-09 | 2019-05-02 |  | 2022-06-01 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Posey County | IN | DPP-2017-FEB | Central | GIA | NRIS | AB Brown 138 kV sub | 847 | 847 | Combined Cycle | Combined Cycle | Not Started | 2019-07-01 | 847 | 847 | 847 | 847
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J1145 | [5 empty] | NRIS | N | 250 |  | Solar | Callaway County | MO |  |  |  | 1 | 1 | 1000000 | 388122 | [9 empty] | 1865000 | 9855000 | 3672284 | 9855000 | 15392284 | 39.42 | 61.5691 | 15392284 |  |  |  | Active | 2018-03-12 |  |  | 2021-04-01 | Ameren Missouri | Callaway County | MO | DPP-2018-APR | Central | PHASE 3 | NRIS | Overton - (McCrede) - Montgomery 345 kV Line Tap | 250 | 250 | Solar | PV Photovoltaic | Not Started |  | 250 | 250 | 250 | 250
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1147 | [5 empty] | ERIS |  | 100 |  | Solar | St. Francis County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-01-24 |  | 2021-09-30 | Entergy Arkansas, LLC | St. Francis County | AR | DPP-2018-APR | South | GIA | ERIS | Moses - McCrory 161 kV Line tap | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 100 | 0 | 0 | 0
|  |  |  | SPA-2014-NOV | West | Withdrawn | Not Started | R60 | [5 empty] | NRIS |  | 54 |  | Wind | Sac County | IA | [27 empty] | Withdrawn | 2009-04-08 | 2017-01-10 |  | 2010-06-30 | MidAmerican Energy Company | Sac County | IA | SPA-2014-NOV | West | SPA - SIS | NRIS | Clipper (Intrepid) - expansion | 54 | 54 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1149 | [5 empty] | NRIS |  | 200 |  | Solar | Yellow Medicine County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2021-11-15 | Northern States Power (Xcel Energy) | Yellow Medicine County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Hazel Creek 230 kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J1148 | [5 empty] | NRIS | N | 54 |  | Gas | Posey County | IN |  |  |  | 0 | 0 | [22 empty] | Withdrawn | 2018-03-12 | 2020-01-07 |  | 2022-06-01 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Posey County | IN | DPP-2018-APR | Central | PHASE 3 | NRIS | AB Brown 138 kV Substation | 54 | 54 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J1150 | [5 empty] | NRIS | N | 30 |  | Wind | Miami County | IN |  |  |  | 0 | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2018-08-10 |  | 2020-09-30 | Duke Energy Indiana | Miami County | IN | DPP-2018-APR | Central | PHASE 3 | NRIS | Deedsville 345 kV Substation | 30 | 30 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ATC) | Active | Not Started | J1153 | [5 empty] | NRIS | N | 150 |  | Solar | Sheboygan County | WI |  |  |  | 1 | 1 | 600000 | 0 | [9 empty] | 12579000 | 4106408 | 0 | 4106408 | 16685408 | 27.3761 | 111.2361 | 16685408 |  |  |  | Active | 2018-03-12 |  |  | 2021-04-01 | American Transmission Co. LLC | Sheboygan County | WI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | Holland 138 kV Substation | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
|  |  |  | DPP-2018-APR | East (ATC) | Active | Not Started | J1154 | [5 empty] | NRIS | N | 75 |  | Solar | Jefferson County | WI |  |  |  | 1 | 1 | 800000 | 0 | [9 empty] | 0 | 0 | 5994932 | 0 | 5994932 | 0 | 79.9324 | 5994932 |  |  |  | Active | 2018-03-12 |  |  | 2021-04-01 | American Transmission Co. LLC | Jefferson County | WI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | Jefferson 138 kV Substation | 75 | 75 | Solar | PV Photovoltaic | Not Started |  | 75 | 75 | 75 | 75
|  |  |  | DPP-2018-APR | South | Done | Under Construction | J1155 | [5 empty] | NRIS |  | 150 |  | Solar | Mississippi County | AR | [21 empty] | 0 | 0 |  |  |  |  | Done | 2018-03-12 |  | 2020-08-12 | 2020-06-01 | Entergy Arkansas, LLC | Mississippi County | AR | DPP-2018-APR | South | GIA | NRIS | Driver 230 kV Substation | 150 | 150 | Solar | PV Photovoltaic | Under Construction | 2022-09-01 | 150 | 150 | 150 | 150
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1156 | [5 empty] | NRIS |  | 150 |  | Solar | Crittenden County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-28 |  | 2020-06-01 | Entergy Arkansas, LLC | Crittenden County | AR | DPP-2018-APR | South | GIA | NRIS | Kuhn Rd. - Parkin 161 kV line tap | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1157 | [5 empty] | NRIS |  | 100 |  | Solar | Hinds County | MS | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-28 |  | 2020-06-01 | Entergy Mississippi, LLC | Hinds County | MS | DPP-2018-APR | South | GIA | NRIS | Tinnin Road 230 kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Done | Under Construction | J1158 | [5 empty] | NRIS |  | 70 |  | Solar | St. James Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Done | 2018-03-12 |  | 2020-12-07 | 2020-06-01 | Entergy Louisiana, LLC | St. James Parish | LA | DPP-2018-APR | South | GIA | NRIS | Vacherie 230 kV Substation | 70 | 70 | Solar | PV Photovoltaic | Under Construction | 2022-12-01 | 70 | 70 | 70 | 70
|  |  |  | SPA-2014-NOV | West | Withdrawn | Not Started | R62 | [5 empty] | NRIS |  | 300 |  | Wind | Greene County | IA | [27 empty] | Withdrawn | 2009-04-08 | 2017-01-10 |  | 2010-12-31 | MidAmerican Energy Company | Greene County | IA | SPA-2014-NOV | West | SPA - SIS | NRIS | Grimes - Lehigh 345 kV | 300 | 300 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-AUG | West | Withdrawn | Not Started | J454 | [5 empty] | NRIS Only |  | 18.9 |  | Wind | Lyon County | MN | [27 empty] | Withdrawn | 2015-05-18 | 2017-01-17 |  | 2016-03-01 | Missouri River Energy Services (MRES) | Lyon County | MN | DPP-2015-AUG | West | DPP - SIS | NRIS Only | MMU Southwest Substation | 18.9 | 18.9 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1159 | [5 empty] | NRIS |  | 100 |  | Solar | Walker County | TX | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-28 |  | 2020-06-01 | Entergy Texas, Inc. | Walker County | TX | DPP-2018-APR | South | GIA | NRIS | Mount Zion 138 kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ATC) | Withdrawn | Not Started | J1160 | [5 empty] | NRIS | N | 100.23 |  | Solar | Adams County,Wood County | WI |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-01-31 |  | 2021-10-01 | American Transmission Co. LLC | Adams County,Wood County | WI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | Sand Lake - Port Edwards 138 kV Line Tap | 100.23 | 100.23 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J1152 | [5 empty] | NRIS | N | 200 |  | Solar | Hancock County,Shelby County | IN |  |  |  | 1 | 1 | 800000 | 242500 | [9 empty] | 3909000 | 0 | 2181818 | 0 | 6090818 | 0 | 30.4541 | 6090818 |  |  |  | Active | 2018-03-12 |  |  | 2021-04-01 | Indianapolis Power & Light Company | Hancock County,Shelby County | IN | DPP-2018-APR | Central | PHASE 3 | NRIS | Gwynneville - Sunnyside 345 kV Line Tap | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
|  |  |  | DPP-2017-FEB | Central | Done | Under Construction | J734 | [5 empty] | NRIS Only |  | 57.1 |  | Gas | Ford County | IL | [27 empty] | Done | 2016-11-10 |  | 2019-02-19 | 2017-06-01 | Ameren Illinois | Ford County | IL | DPP-2017-FEB | Central | GIA | NRIS Only | Gibson City South Substation | 57.1 | 57.1 | Gas | CT Combustion Turbine (Simple Cycle) | Under Construction | 2017-09-01 | 11.5 | 11.5 | 11.5 | 11.5
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1162 | [5 empty] | NRIS |  | 80 |  | Solar | Jefferson County | TX | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-28 |  | 2020-06-01 | Entergy Texas, Inc. | Jefferson County | TX | DPP-2018-APR | South | GIA | NRIS | Jacinto - China 230 kV Line Tap | 80 | 80 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1163 | [5 empty] | NRIS |  | 120 |  | Solar | Quitman County,Tunica County | MS | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-28 |  | 2020-06-01 | Entergy Mississippi, LLC | Quitman County,Tunica County | MS | DPP-2018-APR | South | GIA | NRIS | Crenshaw - Tunica 115kv Line Tap | 120 | 120 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Active | Not Started | J1164 |  |  | Scoping Calls - Devon Pherson | Geronimo |  | NRIS | N | 80 |  | Solar | Rock County | MN |  |  |  | 1 | 1 | 800000 | 3874879 | [7 empty] | 0 | 756133 | 0 | 6923598 | 0 | 6923598 | 7679731 | 86.545 | 95.9966 | 7679731 |  |  |  | Active | 2018-03-12 |  |  | 2021-08-01 | ITC Midwest | Rock County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Magnolia 161 kV Substation | 80 | 80 | Solar | PV Photovoltaic | Not Started |  | 80 | 80 | 80 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1165 | [5 empty] | NRIS |  | 150 |  | Solar | Jefferson Davis Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-28 |  | 2020-06-01 | Entergy Louisiana, LLC | Jefferson Davis Parish | LA | DPP-2018-APR | South | GIA | NRIS | LC Bulk - Henning 138 kV Line Tap | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1166 | [5 empty] | NRIS |  | 50 |  | Solar | Acadia Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-28 |  | 2020-06-01 | Entergy Louisiana, LLC | Acadia Parish | LA | DPP-2018-APR | South | GIA | NRIS | Bayou Cove - Richard 138 kV Line Tap | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1167 | [5 empty] | NRIS |  | 50 |  | Solar | St. Francis County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-01-14 |  | 2020-06-01 | Entergy Arkansas, LLC | St. Francis County | AR | DPP-2018-APR | South | GIA | NRIS | AECC Forrest City West 161 kV Substation | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-AUG | MI | Done | In Service | J132 | [5 empty] | NRIS |  | 125 |  | Wind | Gratiot County | MI | [27 empty] | Done | 2010-05-13 |  | 2011-12-22 | 2012-12-01 | Michigan Electric Transmission Company, LLC | Gratiot County | MI | DPP-2010-AUG | MI | Network Upgrade | NRIS | METC Nelson Road - Goss 345 kV | 125 | 125 | Wind | WT Wind Turbine | In Service | 2007-04-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1168 | [5 empty] | NRIS |  | 80 |  | Solar | Liberty County | TX | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-28 |  | 2020-06-01 | Entergy Texas, Inc. | Liberty County | TX | DPP-2018-APR | South | GIA | NRIS | Pintail 138 kV Substation | 80 | 80 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Active | Not Started | J1169 | [5 empty] | NRIS | N | 50 |  | Solar | McCook County | SD |  |  |  | 1 | 1 | 200000 | 293034 | [7 empty] | 0 | 1965718 | 0 | 5496551 | 0 | 5496551 | 7462269 | 109.931 | 149.2454 | 7462269 |  |  |  | Active | 2018-03-12 |  |  | 2021-08-31 | Northern States Power (Xcel Energy) | McCook County | SD | DPP-2018-APR | West | PHASE 3 | NRIS | Grant 115 kV Substation | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 50 | 50 | 50 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1170 | [5 empty] | NRIS |  | 200 |  | Solar | Cass County | ND | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2021-08-01 | Northern States Power (Xcel Energy) | Cass County | ND | DPP-2018-APR | West | PHASE 3 | NRIS | Bison 345 kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ATC) | Active | Not Started | J1171 | [5 empty] | NRIS | N | 100 |  | Solar | Dodge County | WI |  |  |  | 1 | 1 | 400000 | 0 | [9 empty] | 670000 | 1521698 | 5097259 | 1521698 | 7288957 | 15.217 | 72.8896 | 7288957 |  |  |  | Active | 2018-03-12 |  |  | 2021-08-01 | American Transmission Co. LLC | Dodge County | WI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | Butternut 138 kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 100 | 100 | 100 | 100
|  |  |  | DPP-2018-APR | East (ITC) | Active | Not Started | J1172 | [5 empty] | NRIS |  | 50 |  | Solar | Genesee County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2018-03-12 |  |  | 2021-07-01 | Michigan Electric Transmission Company, LLC | Genesee County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Dort - Garfield 138 kV Line Tap | 50 | 50 | Solar | PV Photovoltaic | Not Started | 2023-08-01 | 50 | 50 | 50 | 50
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1173 | [5 empty] | NRIS |  | 80 |  | Solar | Lenawee County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-06-30 |  | 2019-12-01 | Consumers Energy Company | Lenawee County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Raisin - METC Tap 138kV Line Tap | 80 | 80 | Solar | PV Photovoltaic | Not Started |  | 80 | 80 | 0 | 0
|  |  |  | DPP-2018-APR | West | Active | Not Started | J1174 | [5 empty] | NRIS | N | 165 |  | Solar | Worth County | IA |  |  |  | 1 | 1 | 1200000 | 996501 | [7 empty] | 0 | 8521061 | 9959 | 12469083 | 0 | 12469083 | 21000103 | 75.5702 | 127.2734 | 21000103 |  |  |  | Active | 2018-03-12 |  |  | 2021-10-31 | ITC Midwest | Worth County | IA | DPP-2018-APR | West | PHASE 3 | NRIS | Ledyard - Colby 345 kV Line Tap | 165 | 165 | Solar | PV Photovoltaic | Not Started |  | 165 | 165 | 165 | 165
|  |  |  | DPP-2018-APR | West | Active | Not Started | J1175 | [5 empty] | NRIS | N | 165 |  | Wind | Worth County | IA |  |  |  | 1 | 1 | 1200000 | 1390809 | [7 empty] | 0 | 8521061 | 19918 | 19144001 | 0 | 19144001 | 27684980 | 116.0242 | 167.7878 | 27684980 |  |  |  | Active | 2018-03-12 |  |  | 2021-10-31 | ITC Midwest | Worth County | IA | DPP-2018-APR | West | PHASE 3 | NRIS | Ledyard - Colby 345kV Line Tap | 165 | 165 | Wind | WT Wind Turbine | Not Started |  | 165 | 165 | 165 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1176 | [5 empty] | NRIS |  | 145 |  | Wind | Cerro Gordo County,Worth County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-15 |  | 2021-10-31 | ITC Midwest | Cerro Gordo County,Worth County | IA | DPP-2018-APR | West | PHASE 3 | NRIS | Lime Creek 161 kV Substation | 145 | 145 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1177 | [5 empty] | NRIS |  | 300 |  | Wind | Schuyler County | MO | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2020-09-30 | Ameren Transmission Company of Illinois | Schuyler County | MO | DPP-2018-APR | West | PHASE 3 | NRIS | Hughes 345 kV Switching Station (J541 POI) | 300 | 300 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | J034 | [5 empty] | NRIS |  | 175 |  | Wind | Logan County | IL | [27 empty] | Withdrawn | 2009-03-12 | 2017-01-25 | 2012-08-10 | 2014-12-31 | Ameren Illinois | Logan County | IL |  |  | Network Upgrade | NRIS | Fogarty 138 kV Substation | 175 | 175 | Wind | WT Wind Turbine | Withdrawn | 2010-11-30 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Active | Not Started | J1178 | [5 empty] | NRIS |  | 65 |  | Solar | Eaton County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2018-03-12 |  |  | 2020-07-01 | Michigan Electric Transmission Company, LLC | Eaton County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Oneida 138 kV Substation | 65 | 65 | Solar | PV Photovoltaic | Not Started | 2023-08-01 | 65 | 65 | 65 | 65
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1179 | [5 empty] | NRIS |  | 300 |  | Solar | Chisago County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2021-10-31 | Northern States Power (Xcel Energy) | Chisago County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Rush City - Red Rock 230 kV Line Tap | 300 | 300 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J1161 | [5 empty] | NRIS | N | 100.23 |  | Solar | Scott County | MO |  |  |  | 0 | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-01-07 |  | 2021-10-01 | Ameren Missouri | Scott County | MO | DPP-2018-APR | Central | PHASE 3 | NRIS | Miner - Kelso 161 kV Line Tap | 100.23 | 100.23 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Active | Not Started | J1181 | [5 empty] | NRIS | N | 200 |  | Wind | Chickasaw County | IA |  |  |  | 1 | 1 | 800000 | 629023 | [7 empty] | 0 | 76301 | 4952823 | 17731384 | 0 | 17731384 | 22760508 | 88.6569 | 113.8025 | 22760508 |  |  |  | Active | 2018-03-12 |  |  | 2021-10-31 | ITC Midwest | Chickasaw County | IA | DPP-2018-APR | West | PHASE 3 | NRIS | Hazleton - Mitchell county 345 kV line | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 200 | 200 | 200 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J1180 | [5 empty] | NRIS | N | 75 |  | Solar | Clark County | IL |  |  |  | 1 | 1 | 300000 | 880000 | [9 empty] | 0 | 15006000 | 0 | 15006000 | 15006000 | 200.08 | 200.08 | 15006000 |  |  |  | Active | 2018-03-12 |  |  | 2020-08-14 | Ameren Illinois | Clark County | IL | DPP-2018-APR | Central | PHASE 3 | NRIS | Casey West - Sullivan 345 kV Line | 75 | 75 | Solar | PV Photovoltaic | Not Started |  | 75 | 75 | 75 | 75
|  |  |  | DPP-2018-APR | East (ATC) | Active | Not Started | J1183 | [5 empty] | ERIS | E | 1.35 |  | Solar | Delta County | MI |  |  |  | 1 | 1 | 5400 | [13 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Active | 2018-03-12 |  |  | 2019-01-31 | American Transmission Co. LLC | Delta County | MI | DPP-2018-APR | East (ATC) | PHASE 3 | ERIS | Heritage Garden substation | 1.35 | 1.35 | Solar | PV Photovoltaic | Not Started |  | 1.35 | 0 | 1.35 | 0
|  |  |  | DPP-2018-APR | South | Done | Under Construction | J1184 | [5 empty] | NRIS |  | 50 |  | Solar | Washington Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Done | 2018-03-12 |  | 2020-10-09 | 2020-06-01 | Entergy Louisiana, LLC | Washington Parish | LA | DPP-2018-APR | South | GIA | NRIS | Lagen Holton-Franklinton 115kV Line Tap | 50 | 50 | Solar | PV Photovoltaic | Under Construction | 2021-04-09 | 50 | 50 | 50 | 50
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1185 | [5 empty] | NRIS |  | 200 |  | Wind | Putnam County | MO | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-04-24 |  | 2020-09-30 | Ameren Missouri | Putnam County | MO | DPP-2018-APR | West | PHASE 3 | NRIS | Adair - Appanoose 161 kV Line Tap | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1186 | [5 empty] | NRIS |  | 100 |  | Solar | San Jacinto County | TX | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-28 |  | 2020-06-01 | Entergy Texas, Inc. | San Jacinto County | TX | DPP-2018-APR | South | GIA | NRIS | Pelican Road - Shepard 138 kV Line Tap | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J1187 | [5 empty] | NRIS | N | 151.8 |  | Wind | Mercer County | ND |  |  |  | 1 | 0 | 607200 | 1627631 | [7 empty] | 318142 | 97955 | 5776437 | 4520117 | 38100000 | 4838259 | 48812651 | 31.8726 | 321.559 | 48812651 |  |  |  | Withdrawn | 2018-03-12 | 2021-03-09 |  | 2022-05-01 | Great River Energy | Mercer County | ND | DPP-2018-APR | West | PHASE 3 | NRIS | Stanton 230 kV Substation | 151.8 | 151.8 | Wind | WT Wind Turbine | Not Started |  | 151.8 | 151.8 | 0 | 0
|  |  |  | DPP-2018-APR | East (ATC) | Active | Not Started | J1188 | [5 empty] | NRIS | N | 50 |  | Solar | Rock County | WI |  |  |  | 1 | 1 | 200000 | 135899 | [9 empty] | 760211 | 1362993 | 4703137 | 1362993 | 6826341 | 27.2599 | 136.5268 | 6826341 |  |  |  | Active | 2018-03-12 |  |  | 2021-08-31 | American Transmission Co. LLC | Rock County | WI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | Sheepskin 69 kV Substation | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 50 | 50 | 50 | 50
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J1182 | [5 empty] | NRIS | N | 250 |  | Solar | Adair County | MO |  |  |  | 1 | 1 | 0 | 390083 | [9 empty] | 2098000 | 1367000 | 0 | 1367000 | 3465000 | 5.468 | 13.86 | 3465000 |  |  |  | Active | 2018-03-12 |  |  | 2021-11-15 | Ameren Transmission Company of Illinois | Adair County | MO | DPP-2018-APR | Central | PHASE 3 | NRIS | Zachary Substation 345 kV Bus | 250 | 250 | Solar | PV Photovoltaic | Not Started |  | 250 | 250 | 250 | 250
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1190 | [5 empty] | NRIS |  | 200 |  | Solar | Clinton County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-01-22 |  |  | 2023-10-01 | ITC Midwest | Clinton County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Calamus East 161 kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1191 | [5 empty] | NRIS |  | 64 |  | Solar | Boone County | MO | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-02-04 |  |  | 2022-07-31 | City of Columbia, MO | Boone County | MO | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Bolstad 69 kV Substation | 64 | 64 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA-2015-MAY | 0 | Withdrawn | Not Started | J445 | [5 empty] | NRIS |  | 2 |  | High Voltage DC | Gratiot County | MI | [27 empty] | Withdrawn | 2015-05-13 | 2017-02-01 |  | 2015-12-01 | Michigan Electric Transmission Company, LLC | Gratiot County | MI | SPA-2015-MAY |  | SPA - SIS | NRIS | Nelson Road - Goss 345kV | 2 | 2 | High Voltage DC | BS Battery Storage | Not Started | 2017-06-19 | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1192 | [5 empty] | NRIS |  | 35 |  | Solar | Eaton County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-03-25 |  |  | 2021-07-01 | Michigan Electric Transmission Company, LLC | Eaton County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Oneida 138kV Substation | 35 | 35 | Solar | PV Photovoltaic | Not Started |  | 35 | 35 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1194 | [5 empty] | NRIS |  | 225.2 |  | Wind | Midland County,Saginaw County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-24 |  |  | 2021-10-01 | Michigan Electric Transmission Company, LLC | Midland County,Saginaw County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Murphy 138 kV Substation | 225.2 | 225.2 | Wind | WT Wind Turbine | Not Started | 2021-11-01 | 225.2 | 225.2 | 0 | 0
|  |  |  | FES-2015-JUN | 0 | Withdrawn | Not Started | J451 | [5 empty] | NRIS |  | 500 |  | Gas | Oakland County | MI | [27 empty] | Withdrawn | 2015-05-15 | 2017-02-21 |  | 2018-01-01 | ITC Transmission | Oakland County | MI | FES-2015-JUN |  | Feasibility | NRIS | Unknown | 450 | 500 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Withdrawn | Not Started | J1195 | [5 empty] | NRIS |  | 150.4 |  | Wind | Branch County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-24 | 2020-01-03 |  | 2021-10-01 | Michigan Electric Transmission Company, LLC | Branch County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Wagner 138 kV Substation | 150.4 | 150.4 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1196 | [5 empty] | NRIS |  | 200 |  | Solar | Sanilac County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-25 |  |  | 2022-08-29 | ITC Transmission | Sanilac County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Greenwood - Rapson (Banner) 345 kV Line Tap | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1197 | [5 empty] | NRIS |  | 75 |  | Battery Storage | LaSalle County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-25 |  |  | 2021-06-15 | Ameren Illinois | LaSalle County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Oglesby 138kV Substation | 75 | 75 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2015-NOV | 0 | Withdrawn | Not Started | J536 | [5 empty] | NRIS |  | 100 |  | Solar | Pottawattamie County | IA | [27 empty] | Withdrawn | 2015-11-16 | 2017-02-21 |  | 2017-09-30 | MidAmerican Energy Company | Pottawattamie County | IA | FES-2015-NOV |  | Feasibility | NRIS | Unknown | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1198 | [5 empty] | NRIS |  | 51.8 |  | Hybrid | Jasper County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-25 |  |  | 2021-06-15 | Ameren Illinois | Jasper County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Newton 345kV Substation | 51.8 | 51.8 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2015-NOV | 0 | Withdrawn | Not Started | J539 | [5 empty] | NRIS |  | 999 |  | Gas | Newton County | TX | [27 empty] | Withdrawn | 2015-11-16 | 2017-02-21 |  | 2019-01-01 | Entergy | Newton County | TX | FES-2015-NOV |  | Feasibility | NRIS | Unknown | 999 | 999 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1199 | [5 empty] | NRIS |  | 20 |  | Hybrid | Fulton County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-25 |  |  | 2021-06-15 | Ameren Illinois | Fulton County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Duck Creek 345kV Substation | 20 | 20 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1200 | [5 empty] | NRIS |  | 24.2 |  | Hybrid | Putnam County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-25 |  |  | 2021-06-15 | Ameren Illinois | Putnam County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Hennepin 138kV Substation | 24.2 | 24.2 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1201 | [5 empty] | NRIS |  | 44.2 |  | Hybrid | Montgomery County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-25 |  |  | 2021-06-15 | Ameren Illinois | Montgomery County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Coffeen 345kV Substation | 44.2 | 44.2 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1202 | [5 empty] | NRIS |  | 68.4 |  | Hybrid | Randolph County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-25 |  |  | 2021-06-15 | Ameren Illinois | Randolph County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Baldwin Plant 345kV Switchyard - Baldwin Unit 2 | 68.4 | 68.4 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1203 | [5 empty] | NRIS |  | 125 |  | Solar | Genesee County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-25 |  |  | 2022-06-01 | Michigan Electric Transmission Company, LLC | Genesee County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Thetford 345kV Substation | 125 | 125 | Solar | PV Photovoltaic | Not Started |  | 125 | 125 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1204 | [5 empty] | NRIS |  | 199.3 |  | Solar | Cumberland County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-26 |  |  | 2022-06-01 | Ameren Illinois | Cumberland County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Casey West 345kV Substation | 199.3 | 199.3 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1205 |  |  | Scoping Calls, Tim Kopp EPE | EPE Consulting |  | NRIS | N | 125 |  | Solar | Allen Parish,Assumption Parish | LA |  |  |  | 1 | 1 | 500000 | 3475319 | [9 empty] | 0 | 10094000 | 33716350 | 10094000 | 43810350 | 80.752 | 350.4828 | 43810350 |  |  |  | Active | 2019-04-26 |  |  | 2021-10-31 | CLECO Corporation | Allen Parish,Assumption Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Centennial - West Bay 138kV Line | 125 | 125 | Solar | PV Photovoltaic | Not Started |  | 125 | 125 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1208 | [5 empty] | NRIS |  | 80 |  | Solar | Saline County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-27 |  |  | 2023-10-31 | Ameren Illinois | Saline County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Muddy - Crab Orchard 138 kV line | 80 | 80 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | Central | Withdrawn | In Service | J372 | [5 empty] | External NRIS |  | 1373 |  | Nuclear | Rock Island County | IL | [27 empty] | Withdrawn | 2014-06-24 | 2017-02-22 | 2016-02-26 | 2017-06-01 | Commonwealth Edison Company | Rock Island County | IL | DPP-2014-AUG | Central | DPP - SIS | External NRIS | Quad Cities Substation | 1364.3 | 1373 | Nuclear |  | In Service | 2019-03-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | East (ATC) | Done | In Service | J760 | [5 empty] | NRIS |  | 30 |  | Gas | Rock County | WI | [27 empty] | Done | 2016-11-14 |  | 2019-03-27 | 2019-04-08 | American Transmission Co. LLC | Rock County | WI | DPP-2017-FEB | East (ATC) | GIA | NRIS | New Kitty Hawk 345kV substation | 30 | 30 | Gas | CT Combustion Turbine (Simple Cycle) | In Service |  | 30 | 30 | 30 | 30
| Oriole Solar is a energy consulting company filed in 2019 | file:///C:/Users/omo0g6y/Downloads/Preview.pdf |  | DPP-2019-Cycle | Central | Active | Not Started | J1209 | [5 empty] | NRIS |  | 80 |  | Solar | Saline County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-27 |  |  | 2023-10-31 | Ameren Illinois | Saline County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Muddy - Crab Orchard 138kV Line | 80 | 80 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA-2012-AUG | 0 | Withdrawn | Not Started | J032 | [5 empty] | ERIS |  | 4.94 |  | Wind | Watonwan County | MN | [27 empty] | Withdrawn | 2009-03-11 | 2017-02-28 |  | 2010-11-30 | Northern States Power (Xcel Energy) | Watonwan County | MN | SPA-2012-AUG |  | SPA - SIS | ERIS | Sveadahl - Butterfield 69kV | 4.94 | 4.94 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1210 | [5 empty] | NRIS |  | 50 |  | Solar | Iosco County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-27 |  |  | 2023-10-31 | Michigan Electric Transmission Company, LLC | Iosco County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Whittemore - Twining 138kV Line | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 50 | 50 | 0 | 0
|  |  |  | SPA-2012-NOV | 0 | Withdrawn | Not Started | J058 | [5 empty] | ERIS |  | 4.94 |  | Wind | Cottonwood County | MN | [27 empty] | Withdrawn | 2009-07-27 | 2017-02-28 |  | 2011-09-01 | ITC Midwest | Cottonwood County | MN | SPA-2012-NOV |  | SPA - SIS | ERIS | Bingham Lake - Moutain Lake 69kV | 4.94 | 4.94 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Withdrawn | Not Started | J1211 | [5 empty] | NRIS |  | 50 |  | Solar | Isabella County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-27 | 2021-02-11 |  | 2023-10-31 | Consumers Energy Company | Isabella County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Vernon - METC Tap 138kV Line | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2015-NOV | 0 | Withdrawn | Not Started | J494 | [5 empty] | NRIS |  | 484 |  | Gas | Cass County | ND | [27 empty] | Withdrawn | 2015-11-12 | 2017-03-01 |  | 2022-05-01 | Northern States Power (Xcel Energy) | Cass County | ND | FES-2015-NOV |  | Feasibility | NRIS | Xcel's Bison 345 kV substation | 484 | 484 | Gas | CT Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
|  |  | Bayou Teche Solar from 1803 2020 PPAs | 0 | 0 | Done | In Service | J787 | [5 empty] | NRIS |  | 0 |  | Gas | Manistee County | MI | [27 empty] | Done | 2016-12-22 |  | 2017-01-03 | 2018-06-01 | Consumers Energy Transmission Owner | Manistee County | MI |  |  | DPP - SIS | NRIS | filer city substation | 0 | 0 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2019-09-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1212 | [5 empty] | NRIS |  | 60 |  | Solar | Murray County | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-27 |  |  | 2023-10-31 | Northern States Power (Xcel Energy) | Murray County | MN | DPP-2019-Cycle | West | PHASE 1 | NRIS | Chanarambie-Ellsborough 115kV Line | 60 | 60 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ATC) | Active | Not Started | J1214 | [5 empty] | NRIS |  | 300 |  | Solar | Dane County | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-27 |  |  | 2022-10-30 | American Transmission Co. LLC | Dane County | WI | DPP-2019-Cycle | East (ATC) | PHASE 2 | NRIS | Rockdale 345 kV Substation | 300 | 300 | Solar | PV Photovoltaic | Not Started |  | 300 | 300 | 0 | 0
|  |  |  | DPP-2016-FEB | South | Withdrawn | Not Started | J518 | [5 empty] | NRIS |  | 49.5 |  | Solar | Calcasieu,Calcasieu Parish,Jefferson Davis Parish | LA | [27 empty] | Withdrawn | 2015-11-16 | 2017-03-01 |  | 2017-11-01 | Entergy | Calcasieu,Calcasieu Parish,Jefferson Davis Parish | LA | DPP-2016-FEB | South | GIA | NRIS | tapping on Lake Charles -Jennings 138 kV line | 49.5 | 49.5 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1215 | [5 empty] | NRIS | N | 200 |  | Solar | Arkansas County | AR |  |  |  | 1 | 1 | 800000 | 4252878 | [9 empty] | 902000 | 13149000 | 317794 | 13149000 | 14368794 | 65.745 | 71.844 | 14368794 |  |  |  | Active | 2019-04-27 |  |  | 2022-10-30 | Entergy Arkansas, LLC | Arkansas County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS | Stuttgart Ricuskey - Woodward 230 kV | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 155 | 155 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1216 | [5 empty] | NRIS |  | 250 |  | Solar | Washington County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-27 |  |  | 2023-10-30 | Ameren Illinois | Washington County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Ashley 138 kV Substation | 250 | 250 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | J792 | [5 empty] | NRIS |  | 0 |  | Gas | Washington Parish | LA | [27 empty] | Done | 2017-05-15 |  | 2017-05-23 | 2020-02-15 | Entergy | Washington Parish | LA |  |  | Out of Cycle | NRIS | 230 kV Adams Creek Switchyard | 0 | 0 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2021-03-21 | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1217 | [5 empty] | NRIS | N | 200 |  | Solar | St. Landry Parish | LA |  |  |  | 1 | 1 | 800000 | 6670422 | [9 empty] | 0 | 8978660 | 59851714 | 8978660 | 68830374 | 44.8933 | 344.1519 | 68830374 |  |  |  | Active | 2019-04-27 |  |  | 2022-10-30 | CLECO Corporation | St. Landry Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Ville Platte - West Fork 230 kV Line Tap | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1218 | [5 empty] | NRIS |  | 200 |  | Solar | Muscatine County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-27 |  |  | 2023-10-30 | MidAmerican Energy Company | Muscatine County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Sub 92 345 kV | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1219 | [5 empty] | NRIS | N | 100 |  | Solar | Tangipahoa Parish | LA |  |  |  | 1 | 1 | 400000 | 350977 | [9 empty] | 0 | 5946000 | 0 | 5946000 | 5946000 | 59.46 | 59.46 | 5946000 |  |  |  | Active | 2019-04-27 |  |  | 2022-10-30 | Entergy Louisiana, LLC | Tangipahoa Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Chicken Farm - Amite 115 kV Line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 100 | 100 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1220 | [5 empty] | NRIS | N | 200 |  | Solar | Rapides Parish | LA |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-27 | 2020-08-04 |  | 2022-10-30 | CLECO Corporation | Rapides Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Rapides - Rodemacher 230 kV Line Tap | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1221 | [5 empty] | NRIS |  | 150 |  | Solar | Wadena County | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-27 |  |  | 2023-10-30 | Great River Energy | Wadena County | MN | DPP-2019-Cycle | West | PHASE 1 | NRIS | Wing River- Riverton 230kV line | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1222 | [5 empty] | NRIS |  | 200 |  | Solar | Ralls County | MO | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-27 |  |  | 2022-10-30 | Ameren Missouri | Ralls County | MO | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Spencer Creek 345 kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1223 | [5 empty] | NRIS | N | 150 |  | Solar | Pike County | MS |  |  |  | 1 | 1 | 600000 | 151444 | [9 empty] | 0 | 13688000 | 0 | 13688000 | 13688000 | 91.2533 | 91.2533 | 13688000 |  |  |  | Active | 2019-04-27 |  |  | 2023-10-30 | Entergy Mississippi, LLC | Pike County | MS | DPP-2019-Cycle | South | PHASE 2 | NRIS | Colonial Pipeline - Kentwood 115 kV Line | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 75 | 75 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ITC) | Withdrawn | Not Started | J812 | [5 empty] | NRIS |  | 1217 |  | Combined Cycle | Van Buren County | MI | [27 empty] | Withdrawn | 2017-06-16 | 2017-10-26 |  | 2017-06-16 | Michigan Electric Transmission Company, LLC | Van Buren County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Covert - Palisades 345kV Line | 1108 | 1217 | Combined Cycle | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-AUG | South | Withdrawn | Not Started | J429 | [5 empty] | NRIS |  | 100 |  | Wind | Jefferson County | TX | [27 empty] | Withdrawn | 2014-11-17 | 2017-03-09 |  | 2018-05-31 | Entergy | Jefferson County | TX | DPP-2015-AUG | South | DPP - SIS | NRIS | tap on Big Hill â€“Bayou farm 138 kV line | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2016-09-30 | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1224 | [5 empty] | NRIS |  | 170 |  | Solar | Washtenaw County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-27 |  |  | 2022-10-30 | ITC Transmission | Washtenaw County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Majestic - Milan 345 kV Line Tap | 170 | 170 | Solar | PV Photovoltaic | Not Started |  | 170 | 170 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1225 | [5 empty] | NRIS |  | 160 |  | Solar | Washington County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-27 |  |  | 2023-09-29 | Ameren Illinois | Washington County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Ashley-Turkey Hill Line 1482, between the Okawville and North Nashville substations | 160 | 160 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1226 | [5 empty] | NRIS |  | 200 |  | Solar | Lenawee County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-27 |  |  | 2023-09-29 | Michigan Electric Transmission Company, LLC | Lenawee County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Morocco 345 kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1227 | [5 empty] | NRIS |  | 125 |  | Solar | Spencer County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-27 |  |  | 2023-09-29 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Spencer County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Dubois - FB Culley 138 kV Line Tap | 125 | 125 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Withdrawn | Not Started | J1228 | [5 empty] | NRIS |  | 100 |  | Solar | Faribault County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-27 | 2019-11-05 |  | 2023-09-29 | ITC Midwest | Faribault County | MN | DPP-2019-Cycle | West | PHASE 1 | NRIS | Huntley 161 kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1230 | [5 empty] | NRIS |  | 40 |  | Battery Storage | Wadena County | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-27 |  |  | 2023-10-30 | Great River Energy | Wadena County | MN | DPP-2019-Cycle | West | PHASE 1 | NRIS | Wing River- Riverton 230kV line | 40 | 40 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Withdrawn | Not Started | J802 | [5 empty] | NRIS |  | 1244 |  | Combined Cycle | Vermillion County | IN | [27 empty] | Withdrawn | 2017-06-16 | 2018-05-22 |  | 2020-09-01 | Duke Energy Corporation | Vermillion County | IN | DPP-2017-AUG | Central | GIA | NRIS | Cayuga 345 kV Substation | 1244 | 1244 | Combined Cycle | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1231 | [5 empty] | NRIS |  | 125 |  | Solar | Lyon County | KY | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-28 |  |  | 2022-09-01 | Big Rivers Electric Corporation | Lyon County | KY | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Barkley - Caldwell 161kV Line | 125 | 125 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1232 | [5 empty] | NRIS |  | 99 |  | Solar | Coles County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | Ameren Illinois | Coles County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Chesterville - Mattoon West 138kV Line | 99 | 99 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1233 | [5 empty] | NRIS |  | 32.5 |  | Battery Storage | Pike County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-10-30 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Pike County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Cato 138 kV Substation | 32.5 | 32.5 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J810 | [5 empty] | NRIS |  | 145.5 |  | Gas | Audubon County | IA | [27 empty] | Withdrawn | 2017-06-16 | 2018-08-31 |  | 2023-04-01 | MidAmerican Energy Company | Audubon County | IA | DPP-2017-AUG | West | PHASE 3 | NRIS | Atlantic to Adair 161 kV line | 139.6 | 145.5 | Gas | CT Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1234 | [5 empty] | NRIS |  | 100 |  | Solar | Knox County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-10-31 | Duke Energy Indiana | Knox County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Edwardsport - Washington Mun, Linton 138kV Line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1235 | [5 empty] | NRIS |  | 50 |  | Solar | Knox County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-10-31 | Duke Energy Indiana | Knox County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Edwardsport - Washington Mun, Linton 138kV Line | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1236 | [5 empty] | NRIS |  | 50 |  | Battery Storage | St. Landry Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-08-04 |  | 2022-10-30 | CLECO Corporation | St. Landry Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Ville Platte - West Form 230 kV Line Tap | 50 | 50 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J863 | [5 empty] | NRIS |  | 220 |  | Gas | Dakota County | MN | [27 empty] | Withdrawn | 2017-06-16 | 2018-12-18 |  | 2021-01-01 | Northern States Power (Xcel Energy) | Dakota County | MN | DPP-2017-AUG | West | PHASE 3 | NRIS | Rosemount - Nininger 115kV Line | 220 | 220 | Gas | CT Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Withdrawn | Not Started | J1237 | [5 empty] | NRIS |  | 175 |  | Solar | Washtenaw County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-01-03 |  | 2022-09-01 | ITC Transmission | Washtenaw County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Majestic - Milan 345kV Line | 175 | 175 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1238 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Rapides Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-08-04 |  | 2022-10-30 | CLECO Corporation | Rapides Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Rapides - Rodemacher 230 kV Line Tap | 50 | 50 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA Parked | West | Withdrawn | Not Started | G696 | [5 empty] | NRIS |  | 50 |  | Wind | Cass County | ND | [27 empty] | Withdrawn | 2011-04-12 | 2017-04-04 |  | 2008-05-01 | Otter Tail Power Company | Cass County | ND | SPA Parked | West | SPA - SIS | NRIS | OTP Buffalo 115 kV Substation | 50 | 50 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1239 |  |  | Scoping Calls, Karthik | RWE |  | NRIS | N | 100 |  | Solar | Ouachita Parish | LA |  |  |  | 1 | 1 | 400000 | 4016325 | [9 empty] | 0 | 3802000 | 2582309 | 3802000 | 6384309 | 38.02 | 63.8431 | 6384309 |  |  |  | Active | 2019-04-29 |  |  | 2023-04-01 | Entergy Louisiana, LLC | Ouachita Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Rilla 115 kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 100 | 70 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Withdrawn | Not Started | J1240 | [5 empty] | NRIS |  | 135 |  | Solar | Audrain County | MO | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2019-11-01 |  | 2022-09-01 | Ameren Missouri | Audrain County | MO | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Spencer Creek 345kV Substation | 135 | 135 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1241 | [5 empty] | NRIS |  | 200 |  | Solar | Jefferson County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-09-01 | Ameren Illinois | Jefferson County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | West Mt Vernon - Xenia 345kV Line | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-APR | East (UP) | Withdrawn | Withdrawn | J061 | [5 empty] | NRIS |  | 70 |  | Wind | Delta County | MI | [27 empty] | Withdrawn | 2009-07-27 | 2017-04-20 | 2012-02-07 | 2013-12-31 | American Transmission Co. LLC | Delta County | MI | DPP-2010-APR | East (UP) | Network Upgrade | NRIS | ATC Line west of Indian Lake | 70 | 70 | Wind | WT Wind Turbine | Withdrawn | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1242 | [5 empty] | External NRIS |  | 25 |  | Solar | Hancock County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-05-15 | Ameren Illinois | Hancock County | IL | DPP-2019-Cycle | Central | PHASE 1 | External NRIS | Hamilton Line 796 Tap to Audrian 69kV Line | 25 | 25 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  | CMS Energy is holding company of Consumers in MI, but may be filing this queue under it's O&M business for developers | DPP-2019-Cycle | Central | Active | Not Started | J1243 | [5 empty] | External NRIS |  | 25 |  | Solar | McDonough County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-05-15 | Ameren Illinois | McDonough County | IL | DPP-2019-Cycle | Central | PHASE 1 | External NRIS | Macomb West #2 - Blandlnsville Tap 69kV Line | 25 | 25 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ATC) | Active | Not Started | J1244 | [5 empty] | NRIS |  | 38.4 |  | Wind | Houghton County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-09-15 | American Transmission Co. LLC | Houghton County | MI | DPP-2019-Cycle | East (ATC) | PHASE 2 | NRIS | Winona - Toivola - Portage Tap - Atlantic Mine 69kV Line | 38.4 | 38.4 | Wind | WT Wind Turbine | Not Started |  | 38.4 | 38.4 | 0 | 0
|  |  |  | FES-2015-MAR | 0 | Withdrawn | Not Started | J435 | [5 empty] | NRIS |  | 1170 |  | Gas | Eau Claire County | WI | [27 empty] | Withdrawn | 2015-03-12 | 2017-04-25 |  | 2019-06-01 | Northern States Power (Xcel Energy) | Eau Claire County | WI | FES-2015-MAR |  | Feasibility | NRIS | Eau Clair substation at Arpin-Eau Clair 345 line | 1185 | 1170 | Gas | CS Combined-Cycle Single Shaft - Combustion turbine and steam turbine share a single generator | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1245 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Arkansas County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-08-04 |  | 2022-10-30 | Entergy Arkansas, LLC | Arkansas County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS | Stuttgart Ricuskey - Woodward 230 kV | 50 | 50 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1248 | [5 empty] | NRIS |  | 100 |  | Solar | Calhoun County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-08-01 | Michigan Electric Transmission Company, LLC | Calhoun County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Marshall - Black Stone 138 kV line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 100 | 100 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1250 | [5 empty] | NRIS |  | 35 |  | Battery Storage | Clay County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-08-04 |  | 2022-10-30 | Entergy Arkansas, LLC | Clay County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS | Datto-Corning North 161 kV line | 35 | 35 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ATC) | Active | Not Started | J1251 | [5 empty] | NRIS |  | 100 |  | Solar | Marquette County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-10-30 | American Transmission Co. LLC | Marquette County | MI | DPP-2019-Cycle | East (ATC) | PHASE 2 | NRIS | Arnold - Perkins 138 kV Line Tap | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 100 | 100 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ATC) | Withdrawn | Not Started | J1252 | [5 empty] | NRIS |  | 20 |  | Battery Storage | Marquette County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2021-02-08 |  | 2022-10-30 | American Transmission Co. LLC | Marquette County | MI | DPP-2019-Cycle | East (ATC) | PHASE 2 | NRIS | Arnold - Perkins 138 kV Line Tap | 20 | 20 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ATC) | Active | Not Started | J1253 | [5 empty] | NRIS |  | 100 |  | Solar | Fond du Lac County | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-08-01 | American Transmission Co. LLC | Fond du Lac County | WI | DPP-2019-Cycle | East (ATC) | PHASE 2 | NRIS | South Fond Du Lac to Fitzgerald 345 kV line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 100 | 100 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1254 | [5 empty] | NRIS |  | 150 |  | Solar | Knox County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-10-31 | Duke Energy Indiana | Knox County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Merom - Gibson - Wheatland 345kV Line | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1255 | [5 empty] | NRIS |  | 200 |  | Solar | Ionia County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-10-30 | Michigan Electric Transmission Company, LLC | Ionia County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Marquette - Vergennes 138 kV Line Tap | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 100 | 100 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Withdrawn | Not Started | J1256 | [5 empty] | NRIS |  | 150 |  | Solar | Washtenaw County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-05-06 |  | 2022-10-30 | ITC Transmission | Washtenaw County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Dorset 120 kV Substation | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1257 | [5 empty] | NRIS |  | 20 |  | Battery Storage | Tangipahoa Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-10-30 | Entergy Louisiana, LLC | Tangipahoa Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Chicken Farm - Amite 115 kV Line | 20 | 20 | Battery Storage | BS Battery Storage | Not Started |  | 20 | 20 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1258 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Lonoke County | AR | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-10-30 | Entergy Arkansas, LLC | Lonoke County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS | KEO EHV 500 kV Substation | 50 | 50 | Battery Storage | BS Battery Storage | Not Started |  | 50 | 50 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1259 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Pike County | MS | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-08-04 |  | 2022-10-30 | Entergy Mississippi, LLC | Pike County | MS | DPP-2019-Cycle | South | PHASE 2 | NRIS | Colonial Pipeline - Kentwood 115 kV Line | 50 | 50 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1260 | [5 empty] | NRIS | N | 164 |  | Solar | Desha County | AR |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-08-05 |  | 2021-10-01 | Entergy Arkansas, LLC | Desha County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS | Dumas - Reed 115kV Line | 164 | 164 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1261 | [5 empty] | NRIS | N | 90 |  | Solar | Monroe County | AR |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-08-05 |  | 2021-10-01 | Entergy Arkansas, LLC | Monroe County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS | Clarendon - Brinkley East 115kV Line | 90 | 90 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA-2015-NOV | 0 | Withdrawn | Not Started | J324 | [5 empty] | NRIS |  | 36.24 |  | Hydro | Grant Parish | LA | [27 empty] | Withdrawn | 2014-03-10 | 2017-05-08 |  | 2017-10-01 | CLECO Corporation | Grant Parish | LA | SPA-2015-NOV |  | SPA - SIS | NRIS | Central LA Electric Co 230 kV line | 36.24 | 36.24 | Hydro |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1263 | [5 empty] | NRIS |  | 408.6 |  | Hybrid | Clark County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-01-01 | Ameren Illinois | Clark County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Casey - Kansas West 345kV Line | 408.6 | 408.6 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | J142 | [5 empty] | NRIS |  | 59.69 |  | Gas | Wood County | WI | [27 empty] | Done | 2010-06-14 |  | 2011-03-14 | 2011-03-31 | American Transmission Co. LLC | Wood County | WI |  |  | SPA - SIS | NRIS | Arpin - Hume 115kV | 55.2 | 59.69 | Gas | CT Combustion Turbine (Simple Cycle) | In Service |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | South | Withdrawn | Not Started | J516 | [5 empty] | NRIS |  | 100 |  | Solar | St. James Parish | LA | [27 empty] | Withdrawn | 2015-11-16 | 2017-05-16 |  | 2017-11-01 | Entergy | St. James Parish | LA | DPP-2016-AUG | South | GIA | NRIS | Vacherie Substation 230kV | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1265 | [5 empty] | NRIS |  | 43 |  | Solar | LaGrange County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | Northern Indiana Public Service Company | LaGrange County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Wolcottville - South Milford 69kV Line | 43 | 43 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1266 | [5 empty] | NRIS |  | 99 |  | Solar | Marion County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | Ameren Illinois | Marion County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Kinmundy - Salem 138kV Line | 99 | 99 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1267 | [5 empty] | NRIS | N | 135 |  | Solar | Cross County | AR |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-08-06 |  | 2022-05-01 | Entergy Arkansas, LLC | Cross County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS | Fisher - Cherry Valley 161kV Line | 135 | 135 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1268 | [5 empty] | NRIS |  | 150 |  | Solar | Lincoln County | MO | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-11-30 | Ameren Missouri | Lincoln County | MO | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Pike - Troy 161kV Line | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  | https://www.calpinesolutions.com/ | Retail energy provider, don't seem to developer projects themselves | DPP-2019-Cycle | Central | Active | Not Started | J1269 | [5 empty] | NRIS |  | 100 |  | Hybrid | Warrick County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Warrick County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Elliott 69kV Substation | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1270 | [5 empty] | NRIS |  | 200 |  | Wind | Palo Alto County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-09-29 | MidAmerican Energy Company | Palo Alto County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Kossuth - O'Brien 345 kV Line Tap | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1271 | [5 empty] | NRIS |  | 100 |  | Battery Storage | Vanderburgh County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Vanderburgh County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Oak Grove 138kV Substation | 100 | 100 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1272 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Vanderburgh County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Vanderburgh County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Angel Mound 138kV Substation | 50 | 50 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Withdrawn | Not Started | J1273 | [5 empty] | NRIS |  | 100 |  | Solar | Marshall County,Starke County | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2019-11-05 |  | 2023-09-29 | Northern Indiana Public Service Company | Marshall County,Starke County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Burr Oak - East Winnamac 138 kV Line Tap | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | J143 | [5 empty] | NRIS |  | 40 |  | Coal | Ontonagon County | MI | [27 empty] | Done | 2010-06-23 |  | 2011-03-08 |  | Upper Peninsula Power Company | Ontonagon County | MI |  |  | Feasibility | NRIS | ATC White Pine 69 kV Substation | 40 | 40 | Coal | Combined Cycle | In Service |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1274 | [5 empty] | NRIS |  | 100 |  | Hybrid | Posey County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Posey County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Point 69kV Substation | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1275 | [5 empty] | NRIS |  | 100 |  | Solar | Henderson County | KY | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-10-30 | Big Rivers Electric Corporation | Henderson County | KY | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Henderson 161 kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1276 | [5 empty] | NRIS |  | 100 |  | Hybrid | Posey County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Posey County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Point 69kV Substation | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1277 | [5 empty] | NRIS | N | 130 |  | Solar | Liberty County | TX |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-08-04 |  | 2022-10-30 | Entergy Texas, Inc. | Liberty County | TX | DPP-2019-Cycle | South | PHASE 2 | NRIS | Pintail 138 kV Substation | 130 | 130 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1278 | [5 empty] | NRIS | N | 100 |  | Solar | Polk County | TX |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-08-05 |  | 2022-03-01 | Entergy Texas, Inc. | Polk County | TX | DPP-2019-Cycle | South | PHASE 2 | NRIS | Corrigan Bulk - Staley 138kV Line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1279 | [5 empty] | NRIS | N | 100 |  | Solar | Hardin County | TX |  |  |  | 1 | 1 | 400000 | 3212224 | [9 empty] | 0 | 15446000 | 41435794 | 15446000 | 56881794 | 154.46 | 568.8179 | 56881794 |  |  |  | Active | 2019-04-29 |  |  | 2022-03-01 | Entergy Texas, Inc. | Hardin County | TX | DPP-2019-Cycle | South | PHASE 2 | NRIS | Rye - Cypress 138kV Line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 100 | 100 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1280 | [5 empty] | NRIS | N | 100 |  | Solar | Monroe County | AR |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-08-05 |  | 2022-03-01 | Entergy Arkansas, LLC | Monroe County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS | Brinkley East - Clarendon 115kV Line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ITC) | Withdrawn | Not Started | J914 | [5 empty] | NRIS |  | 30 |  | Gas | Manistee County | MI | [27 empty] | Withdrawn | 2017-06-16 | 2019-01-09 |  | 2019-10-01 | Michigan Electric Transmission Company, LLC | Manistee County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Filer City 138 kV Substation | 30 | 30 | Gas | CT Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ITC) | Withdrawn | Not Started | J936 | [5 empty] | NRIS |  | 535 |  | Combined Cycle | Calhoun County | MI | [27 empty] | Withdrawn | 2017-06-16 | 2019-01-09 |  | 2020-05-01 | Michigan Electric Transmission Company, LLC | Calhoun County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Argenta - Tompkins 345kV Line Tap | 507 | 535 | Combined Cycle | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1281 |  |  | Scoping Calls, Jeff Hudson | Urban Grid |  | NRIS | N | 75 |  | Solar | Ashley County | AR |  |  |  | 1 | 1 | 300000 | 1828655 | [9 empty] | 0 | 11779000 | 2331278 | 11779000 | 14110278 | 157.0533 | 188.137 | 14110278 |  |  |  | Active | 2019-04-29 |  |  | 2022-03-01 | Entergy Arkansas, LLC | Ashley County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS | Crossett - Monticello East 115kV Line | 75 | 75 | Solar | PV Photovoltaic | Not Started |  | 75 | 75 | 0 | 0
|  |  |  | SPA-2015-MAY | 0 | Withdrawn | Not Started | J270 | [5 empty] | NRIS |  | 197.8 |  | Wind | Newton County | IN | [27 empty] | Withdrawn | 2013-03-07 | 2017-05-23 |  | 2018-09-15 | Northern Indiana Public Service Company | Newton County | IN | SPA-2015-MAY |  | SPA - SIS | NRIS | NIPSCO Thayer - Schafer 138 kV | 197.8 | 197.8 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1282 | [5 empty] | NRIS | N | 200 |  | Solar | Beauregard Parish | LA |  |  |  | 1 | 1 | 800000 | 8857952 | [9 empty] | 0 | 11249146 | 90439234 | 11249146 | 101688380 | 56.2457 | 508.4419 | 101688380 |  |  |  | Active | 2019-04-29 |  |  | 2022-03-01 | CLECO Corporation | Beauregard Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Cooper - Penton Road 230kV Line | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1284 | [5 empty] | NRIS |  | 250 |  | Solar | Linn County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-10-30 | ITC Midwest | Linn County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Duane Arnold - Tiffin (MEC) 345 kV Line Tap | 250 | 250 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1285 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Linn County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-10-30 | ITC Midwest | Linn County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Duane Arnold - Tiffin (MEC) 345 kV Line Tap | 50 | 50 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1286 | [5 empty] | NRIS | N | 150 |  | Solar | Evangeline Parish | LA |  |  |  | 1 | 1 | 600000 | 5978388 | [9 empty] | 0 | 2426089 | 68527633 | 2426089 | 70953722 | 16.1739 | 473.0248 | 70953722 |  |  |  | Active | 2019-04-29 |  |  | 2022-10-30 | CLECO Corporation | Evangeline Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Manuel 138 kV Substation | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 125 | 125 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1287 | [5 empty] | NRIS | N | 50 |  | Solar | Tunica County | MS |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-08-05 |  | 2022-07-01 | Entergy Mississippi, LLC | Tunica County | MS | DPP-2019-Cycle | South | PHASE 2 | NRIS | Tunica - Crenshaw 115kV Line | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1289 | [5 empty] | NRIS |  | 200 |  | Wind | Morgan County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-04-20 | Ameren Illinois | Morgan County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Turner 345kV Switching Station | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1290 | [5 empty] | NRIS |  | 25 |  | Battery Storage | Evangeline Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-08-04 |  | 2022-10-30 | CLECO Corporation | Evangeline Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Manuel 138 kV Substation | 25 | 25 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1291 | [5 empty] | NRIS | N | 100 |  | Solar | Catahoula Parish | LA |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-01-14 |  | 2022-10-30 | Entergy Louisiana, LLC | Catahoula Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Standard - Red Gum 115 kV Line Tap | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1292 | [5 empty] | NRIS |  | 198 |  | Wind | Ionia County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-05-01 | Michigan Electric Transmission Company, LLC | Ionia County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Thompson Road 138kV Substation | 198 | 198 | Wind | WT Wind Turbine | Not Started |  | 198 | 198 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1293 | [5 empty] | NRIS |  | 25 |  | Battery Storage | Lee County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-08-04 |  | 2022-10-30 | Entergy Arkansas, LLC | Lee County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS | Brinkley East - Moro 115 kV Line Tap | 25 | 25 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2010-AUG | IL-MO | Done | In Service | J145 | [5 empty] | NRIS |  | 14 |  | Hydro | Miller County | MO | [27 empty] | Done | 2010-06-25 |  | 2012-06-28 | 2012-08-14 | Ameren Missouri | Miller County | MO | DPP-2010-AUG | IL-MO | DPP - SIS | NRIS | Osage Power Plant | 14 | 14 | Hydro | OT Other | In Service | 2004-06-07 | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1294 |  |  | Scoping Calls, Neil Burbure | EN Engineering |  | NRIS | N | 99 |  | Solar | Sunflower County | MS |  |  |  | 1 | 1 | 396000 | 1831523 | [9 empty] | 902000 | 12015000 | 4189107 | 12015000 | 17106107 | 121.3636 | 172.789 | 17106107 |  |  |  | Active | 2019-04-29 |  |  | 2022-06-01 | Entergy Mississippi, LLC | Sunflower County | MS | DPP-2019-Cycle | South | PHASE 2 | NRIS | Indianola - Cleveland 115kV Line | 99 | 99 | Solar | PV Photovoltaic | Not Started |  | 99 | 99 | 0 | 0
|  |  |  | SPA-2015-MAY | 0 | Withdrawn | Not Started | J275 | [5 empty] | NRIS |  | 700 |  | Gas | Midland County | MI | [27 empty] | Withdrawn | 2013-03-14 | 2017-05-31 |  | 2015-10-01 | Michigan Electric Transmission Company, LLC | Midland County | MI | SPA-2015-MAY |  | SPA - SIS | NRIS | METC Tittabawasse 345kV Substation | 700 | 700 | Gas | CT Combined-Cycle Combustion ? Turbine Part | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1295 | [5 empty] | NRIS |  | 280 |  | Solar | Gibson County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-12-01 | Duke Energy Indiana | Gibson County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Gibson - Francisco 345kV Line | 280 | 280 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1296 | [5 empty] | NRIS |  | 200 |  | Solar | Gibson County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-12-01 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Gibson County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Francisco 138kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1297 | [5 empty] | NRIS |  | 170 |  | Solar | Shiawassee County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-12-01 | Michigan Electric Transmission Company, LLC | Shiawassee County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Cornell - Bell Road 138 kV Line | 170 | 170 | Solar | PV Photovoltaic | Not Started |  | 170 | 170 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1298 | [5 empty] | NRIS |  | 150 |  | Solar | Freeborn County | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-12-01 | SMMPA | Freeborn County | MN | DPP-2019-Cycle | West | PHASE 1 | NRIS | Hayward - Murphy Creek 161kV Line | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1299 | [5 empty] | NRIS |  | 200 |  | Solar | Scott County | MO | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-12-01 | Ameren Missouri | Scott County | MO | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Miner - Kelso 161kV Line | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1300 | [5 empty] | NRIS |  | 120 |  | Solar | Nobles County | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-12-01 | ITC Midwest | Nobles County | MN | DPP-2019-Cycle | West | PHASE 1 | NRIS | Brewster - Elk 161kV Line | 120 | 120 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1301 | [5 empty] | NRIS |  | 150 |  | Solar | Washington County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-12-01 | Ameren Illinois | Washington County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Prest 138kV Switching Station | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2015-SEP | 0 | Withdrawn | Not Started | J479 | [5 empty] | NRIS |  | 462 |  | Gas | Grimes County | TX | [27 empty] | Withdrawn | 2015-09-14 | 2017-06-06 |  | 2018-09-30 | Entergy | Grimes County | TX | FES-2015-SEP |  | Feasibility | NRIS | Grimes substation, 345 kV bus | 442 | 462 | Gas | OT Other | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1302 | [5 empty] | NRIS |  | 150 |  | Solar | Saline County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-12-01 | Ameren Illinois | Saline County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Muddy - Norris City 138kV Line | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1303 | [5 empty] | NRIS |  | 150 |  | Solar | Jackson County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-12-01 | Southern Illinois Power Cooperative | Jackson County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Campbell Hill - Jackson 161kV Line | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ATC) | Active | Not Started | J1304 | [5 empty] | NRIS |  | 65 |  | Solar | Rock County | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-12-01 | American Transmission Co. LLC | Rock County | WI | DPP-2019-Cycle | East (ATC) | PHASE 2 | NRIS | Paddock - Townline Road 138kV Line | 65 | 65 | Solar | PV Photovoltaic | Not Started |  | 65 | 65 | 0 | 0
|  |  |  | FES-2015-MAR | 0 | Withdrawn | Not Started | J434 | [5 empty] | NRIS |  | 1170 |  | Gas | Vermillion County | IN | [27 empty] | Withdrawn | 2015-03-12 | 2017-06-08 |  | 2019-06-01 | Duke Energy Corporation | Vermillion County | IN | FES-2015-MAR |  | Feasibility | NRIS | Cayuga 345 substation 345 kv bus | 1185 | 1170 | Gas | CS Combined-Cycle Single Shaft - Combustion turbine and steam turbine share a single generator | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ATC) | Active | Not Started | J1305 | [5 empty] | NRIS |  | 49.9 |  | Solar | Green County | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-12-01 | American Transmission Co. LLC | Green County | WI | DPP-2019-Cycle | East (ATC) | PHASE 2 | NRIS | Albany - Bass Creek 138kV Line | 49.9 | 49.9 | Solar | PV Photovoltaic | Not Started |  | 49.9 | 49.9 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1306 | [5 empty] | NRIS |  | 200 |  | Solar | Perry County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-12-01 | Ameren Illinois | Perry County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Pickneyville - St John 230kV Line | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1307 | [5 empty] | NRIS |  | 150 |  | Solar | Eaton County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-12-01 | Michigan Electric Transmission Company, LLC | Eaton County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Oneida - Battle Creek 345kV Line | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1308 | [5 empty] | NRIS |  | 300 |  | Solar | Posey County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-12-01 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Posey County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | AB Brown - Gibson 345kV Line | 300 | 300 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1309 | [5 empty] | NRIS | N | 129.9 |  | Solar | Arkansas County | AR |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2019-09-12 |  | 2021-09-30 | Entergy Arkansas, LLC | Arkansas County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS | Gillett 115 kV Substation | 129.9 | 129.9 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1310 | [5 empty] | NRIS |  | 125 |  | Solar | Jackson County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-06-30 | Michigan Electric Transmission Company, LLC | Jackson County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Blackstone - Marshall 138 kV Line | 125 | 125 | Solar | PV Photovoltaic | Not Started |  | 125 | 125 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1311 | [5 empty] | NRIS |  | 150 |  | Solar | St. Clair County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-06-30 | Ameren Illinois | St. Clair County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Fayetteville Bee Hollow Road 138 kV Substation | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ITC) | Withdrawn | Not Started | J841 | [5 empty] | NRIS |  | 725 |  | Combined Cycle | Saginaw County | MI | [27 empty] | Withdrawn | 2017-06-16 | 2020-01-24 |  | 2020-04-01 | Michigan Electric Transmission Company, LLC | Saginaw County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Orr RD 138 kV Substation | 702 | 725 | Combined Cycle | Combined Cycle | Not Started |  | 725 | 725 | 725 | 702
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1312 | [5 empty] | NRIS |  | 50 |  | Solar | McCook County | SD | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-06-30 | Northern States Power (Xcel Energy) | McCook County | SD | DPP-2019-Cycle | West | PHASE 1 | NRIS | Grant 115 kV Substation | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1313 | [5 empty] | NRIS |  | 100 |  | Solar | Greene County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-06-30 | ITC Midwest | Greene County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | 161kV bus at Karma substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1314 | [5 empty] | NRIS |  | 100 |  | Solar | Polk County | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-06-30 | Dairyland Power Cooperative | Polk County | WI | DPP-2019-Cycle | West | PHASE 1 | NRIS | Apple River 161 kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1315 | [5 empty] | NRIS |  | 600 |  | Wind | Cottonwood County,Murray County,Redwood County | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-06-30 | Northern States Power (Xcel Energy) | Cottonwood County,Murray County,Redwood County | MN | DPP-2019-Cycle | West | PHASE 1 | NRIS | Lyon County - Cedar Mountain 345 kV Line Tap | 600 | 600 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ATC) | Active | Not Started | J1316 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Kenosha County | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-10-30 | American Transmission Co. LLC | Kenosha County | WI | DPP-2019-Cycle | East (ATC) | PHASE 2 | NRIS | Paris 138 kV Substation | 50 | 50 | Battery Storage | BS Battery Storage | Not Started |  | 50 | 50 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Withdrawn | Not Started | J1317 | [5 empty] | NRIS |  | 150 |  | Wind | Sanilac County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-01-03 |  | 2022-10-01 | ITC Transmission | Sanilac County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Bennet 120kV Substation | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1318 | [5 empty] | NRIS |  | 25 |  | Solar | Rush County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | Duke Energy Indiana | Rush County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Rushville 69kV Substation | 25 | 25 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1319 | [5 empty] | NRIS |  | 117.5 |  | Wind | Huron County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-09-30 | ITC Transmission | Huron County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Rapson 120kV Substation | 117.5 | 117.5 | Wind | WT Wind Turbine | Not Started |  | 117.5 | 117.5 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1320 | [5 empty] | NRIS |  | 150 |  | Solar | Branch County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2019-04-20 | Michigan Electric Transmission Company, LLC | Branch County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Coldwater - Batavia 138kV Line | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1321 | [5 empty] | NRIS |  | 65 |  | Battery Storage | Story County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-10-30 | MidAmerican Energy Company | Story County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | O'Brien - Kossuth 345 kV Line Tap | 65 | 65 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Withdrawn | Not Started | J1322 | [5 empty] | NRIS |  | 200 |  | Solar | Eaton County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2021-01-26 |  | 2022-04-20 | Michigan Electric Transmission Company, LLC | Eaton County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Battle Creek - Oneida 345kV Tap | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1323 | [5 empty] | NRIS |  | 25 |  | Battery Storage | LaGrange County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-10-30 | Northern Indiana Public Service Company | LaGrange County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Lagrange 138 kV Substation | 25 | 25 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ITC) | Withdrawn | Withdrawn | J937 | [5 empty] | NRIS |  | 535 |  | Combined Cycle | Calhoun County | MI | [27 empty] | Withdrawn | 2017-06-16 | 2020-10-21 | 2020-06-11 | 2020-05-01 | Michigan Electric Transmission Company, LLC | Calhoun County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Argenta - Tompkins 345kV Line Tap | 507 | 535 | Combined Cycle | Combined Cycle | Withdrawn | 2022-12-29 | 535 | 535 | 535 | 507
|  |  |  | DPP-2019-Cycle | Central | Withdrawn | Not Started | J1324 | [5 empty] | NRIS |  | 150 |  | Solar | Montgomery County | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-05-11 |  | 2022-04-20 | Ameren Illinois | Montgomery County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Midway 138kV Substation | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1325 | [5 empty] | NRIS |  | 200 |  | Solar | Rock County | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-06-30 | ITC Midwest | Rock County | MN | DPP-2019-Cycle | West | PHASE 1 | NRIS | Magnolia 161 kV substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ATC) | Done | Under Construction | J732 | [5 empty] | NRIS |  | 561.5 |  | Combined Cycle | Douglas County | WI | [27 empty] | Done | 2017-06-16 |  | 2020-07-29 | 2021-06-08 | American Transmission Co. LLC | Douglas County | WI | DPP-2017-AUG | East (ATC) | GIA | NRIS | Arrowhead - Stone Lake 345kV Line | 527.8 | 561.5 | Combined Cycle | Combined Cycle | Under Construction | 2023-11-10 | 561.5 | 561.5 | 561.5 | 561.5
|  |  |  | DPP-2019-Cycle | East (ATC) | Active | Not Started | J1326 | [5 empty] | NRIS |  | 75 |  | Battery Storage | Dane County | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-10-30 | American Transmission Co. LLC | Dane County | WI | DPP-2019-Cycle | East (ATC) | PHASE 2 | NRIS | Rockdale 345 kV Substation | 75 | 75 | Battery Storage | BS Battery Storage | Not Started |  | 75 | 75 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Withdrawn | Not Started | J1327 | [5 empty] | NRIS |  | 20 |  | Battery Storage | Ionia County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2021-02-08 |  | 2022-10-30 | Michigan Electric Transmission Company, LLC | Ionia County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Marquette - Vergennes 138 kV Line Tap | 20 | 20 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1328 | [5 empty] | NRIS |  | 100 |  | Solar | Grant County | SD | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-04-20 | Otter Tail Power Company | Grant County | SD | DPP-2019-Cycle | West | PHASE 1 | NRIS | Big Stone South 345kV Sub | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ITC) | Done | Under Construction | J793 | [5 empty] | NRIS |  | 1175 |  | Combined Cycle | St. Clair County | MI | [27 empty] | Done | 2017-06-16 |  | 2020-10-26 | 2021-05-14 | ITC Transmission | St. Clair County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Belle River - Fitz #2 345 kV Line Tap | 1175 | 1175 | Combined Cycle | Combined Cycle | Under Construction | 2021-05-14 | 1209 | 1209 | 1209 | 1175
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1329 | [5 empty] | NRIS |  | 20 |  | Battery Storage | Washtenaw County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-10-30 | ITC Transmission | Washtenaw County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Majestic - Milan 345 kV Line Tap | 20 | 20 | Battery Storage | BS Battery Storage | Not Started |  | 20 | 20 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1330 | [5 empty] | NRIS |  | 200 |  | Solar | Randolph County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-04-20 | Ameren Illinois | Randolph County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Baldwin 345kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1331 | [5 empty] | NRIS |  | 100 |  | Solar | St. Clair County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-06-30 | ITC Transmission | St. Clair County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Greenwood 120 kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 100 | 100 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1332 | [5 empty] | NRIS |  | 200 |  | Solar | Jasper County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-04-20 | Northern Indiana Public Service Company | Jasper County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Schahfer 345kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1333 | [5 empty] | NRIS |  | 199.5 |  | Hybrid | Jasper County,Starke County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | Northern Indiana Public Service Company | Jasper County,Starke County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Schahfer - Burr Oak 345kV Line | 199.5 | 199.5 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2015-NOV | 0 | Withdrawn | Not Started | J507 | [5 empty] | NRIS |  | 16.7 |  | Solar | Pulaski County | AR | [27 empty] | Withdrawn | 2015-11-13 | 2017-06-16 |  | 2016-12-01 | Entergy | Pulaski County | AR | FES-2015-NOV |  | Feasibility | NRIS | Unknown | 16.7 | 16.7 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1334 | [5 empty] | NRIS |  | 199.5 |  | Hybrid | Jasper County,Starke County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | Northern Indiana Public Service Company | Jasper County,Starke County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Schahfer - Burr Oak 345kV Line | 199.5 | 199.5 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1335 | [5 empty] | NRIS |  | 199.5 |  | Hybrid | Jasper County,Starke County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | Northern Indiana Public Service Company | Jasper County,Starke County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Schahfer - Burr Oak 345kV Line | 199.5 | 199.5 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1336 | [5 empty] | NRIS |  | 199.5 |  | Hybrid | Jasper County,Starke County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | Northern Indiana Public Service Company | Jasper County,Starke County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Schahfer 345 kV Substation | 199.5 | 199.5 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1337 | [5 empty] | NRIS |  | 300 |  | Solar | Sherburne County | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-06-30 | Northern States Power (Xcel Energy) | Sherburne County | MN | DPP-2019-Cycle | West | PHASE 1 | NRIS | Sherburne County 345 kV substation | 300 | 300 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1338 | [5 empty] | NRIS |  | 150 |  | Wind | Audrain County | MO | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-15 | Ameren Missouri | Audrain County | MO | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Spencer Creek - Montgomery 345 kV Line Tap | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1339 | [5 empty] | NRIS |  | 199.5 |  | Hybrid | Jasper County,Starke County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | Northern Indiana Public Service Company | Jasper County,Starke County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Schahfer 345kV Substation | 199.5 | 199.5 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1340 | [5 empty] | NRIS |  | 199.5 |  | Hybrid | Jasper County,Starke County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | Northern Indiana Public Service Company | Jasper County,Starke County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Schahfer 345kV Substation | 199.5 | 199.5 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1341 | [5 empty] | NRIS |  | 398 |  | Wind | Buchanan County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | ITC Midwest | Buchanan County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Hazleton 345kV Substation | 398 | 398 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2015-NOV | 0 | Withdrawn | Not Started | J491 | [5 empty] | NRIS |  | 20 |  | Solar | Bartholomew County | IN | [27 empty] | Withdrawn | 2015-11-12 | 2017-06-19 |  | 2017-05-01 | Duke Energy Corporation | Bartholomew County | IN | FES-2015-NOV |  | Feasibility | NRIS | connection to 69 kV Duke line feeding Flat Rock substation | 20 | 20 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1342 | [5 empty] | NRIS |  | 99 |  | Solar | Starke County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-06-30 | Northern Indiana Public Service Company | Starke County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Starke 138kV Substation | 99 | 99 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Withdrawn | Not Started | J1343 | [5 empty] | NRIS |  | 96 |  | Solar | Cerro Gordo County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-03-05 |  | 2022-09-15 | ITC Midwest | Cerro Gordo County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Emery - Lime Creek 161 kV Line Tap | 96 | 96 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Withdrawn | Not Started | J1344 | [5 empty] | NRIS |  | 48 |  | Solar | Mills County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-03-05 |  | 2022-09-15 | MidAmerican Energy Company | Mills County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Hastings 69 kV Substation | 48 | 48 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2015-NOV | 0 | Withdrawn | Not Started | J492 | [5 empty] | NRIS |  | 20 |  | Solar | Montgomery County | IN | [27 empty] | Withdrawn | 2015-11-12 | 2017-06-19 |  | 2017-05-01 | Duke Energy Corporation | Montgomery County | IN | FES-2015-NOV |  | Feasibility | NRIS | connection to 69 kV Duke line feeding Cherry Grove substation | 20 | 20 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ATC) | Active | Not Started | J1345 | [5 empty] | NRIS |  | 25 |  | Battery Storage | Dodge County | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-10-01 | American Transmission Co. LLC | Dodge County | WI | DPP-2019-Cycle | East (ATC) | PHASE 2 | NRIS | North Beaver Dam 69kV Substation | 25 | 25 | Battery Storage | BS Battery Storage | Not Started |  | 25 | 25 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1347 |  |  | Scoping Calls, Jared hibshman | EDP |  | ERIS | E | 175 |  | Solar | Scott County | MS |  |  |  | 1 | 1 | 800000 | 1822322 | [9 empty] | 14200000 | 12910000 | 0 | 12910000 | 27110000 | 73.7714 | 154.9143 | 12910000 |  |  |  | Active | 2019-04-26 |  |  | 2022-08-01 | Entergy Mississippi, LLC | Scott County | MS | DPP-2019-Cycle | South | PHASE 2 | ERIS | Pelahatchie - Scott 115 kV Line Tap | 175 | 175 | Solar | PV Photovoltaic | Not Started |  | 175 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1348 | [5 empty] | NRIS |  | 200 |  | Solar | Vermillion County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-04-20 | Duke Energy Indiana | Vermillion County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Cayuga - Sugar Creek 345kV Line | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1349 | [5 empty] | NRIS |  | 335 |  | Hybrid | Cottonwood County | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-04-20 | Northern States Power (Xcel Energy) | Cottonwood County | MN | DPP-2019-Cycle | West | PHASE 1 | NRIS | Crandall 345 kV Substation | 335 | 335 | Hybrid | Solar/Wind | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1350 | [5 empty] | NRIS |  | 150 |  | Solar | Monroe County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-04-20 | Michigan Electric Transmission Company, LLC | Monroe County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Milan â€“ Monroe â€“ Morocco 345 kV Point | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1351 | [5 empty] | NRIS | N | 120 |  | Solar | Madison Parish | LA |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-08-05 |  | 2022-08-01 | Entergy Louisiana, LLC | Madison Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Tallulah - Delhi 115kV Line Tap | 120 | 120 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J916 | [5 empty] | NRIS |  | 2 |  | Diesel | Cottonwood County | MN | [27 empty] | Withdrawn | 2017-06-16 | 2021-01-29 |  | 2020-07-06 | ITC Midwest | Cottonwood County | MN | DPP-2017-AUG | West | PHASE 3 | NRIS | Mountain Lake 69kV Substation | 2 | 2 | Diesel | CT Combustion Turbine (Simple Cycle) | Not Started |  | 2 | 2 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1352 | [5 empty] | NRIS |  | 100 |  | Solar | Montgomery County | MO | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-04-20 | Ameren Missouri | Montgomery County | MO | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Spencer Creek - Montgomery 345kV Line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1353 | [5 empty] | NRIS |  | 150 |  | Battery Storage | Lake County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-05-30 | Northern Indiana Public Service Company | Lake County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Green Acres138kV Subtation | 150 | 150 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1354 | [5 empty] | NRIS |  | 146 |  | Battery Storage | Decatur County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-05-30 | Hoosier Energy | Decatur County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Decatur County 138kV Switching Station | 146 | 146 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1355 | [5 empty] | NRIS |  | 160 |  | Battery Storage | LaPorte County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-05-30 | Northern Indiana Public Service Company | LaPorte County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Stillwell 138kV Subtation | 160 | 160 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1356 | [5 empty] | NRIS |  | 160 |  | Solar | Martin County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-05-30 | Duke Energy Indiana | Martin County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Whitfield 138kV Substation | 160 | 160 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1357 | [5 empty] | NRIS |  | 150 |  | Battery Storage | Madison County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-05-30 | Duke Energy Indiana | Madison County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Madison 138 KV SUBSTATION | 150 | 150 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1358 | [5 empty] | NRIS |  | 125 |  | Battery Storage | LaPorte County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-05-30 | Northern Indiana Public Service Company | LaPorte County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Luchtman 138kV Substation | 125 | 125 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ATC) | Done | In Service | J831 | [5 empty] | NRIS |  | 48 |  | Combined Cycle | Ozaukee County | WI | [27 empty] | Done | 2017-06-16 |  | 2019-11-12 | 2017-06-16 | American Transmission Co. LLC | Ozaukee County | WI | DPP-2017-AUG | East (ATC) | GIA | NRIS | Port Washington Generating Switchyard 138 kV | 40 | 48 | Combined Cycle | Combined Cycle | In Service | 2019-10-28 | 48 | 48 | 48 | 48
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1360 | [5 empty] | NRIS |  | 300 |  | Wind | Piatt County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-04-20 | Ameren Illinois | Piatt County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Goose Creek 345kV Switchyard | 300 | 300 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1361 |  |  | Scoping Calls, Laura Klein | Oriole Solar (consulting company) |  | NRIS | N | 50 |  | Solar | Washington Parish | LA |  |  |  | 1 | 1 | 200000 | 200480 | [9 empty] | 0 | 1364000 | 0 | 1364000 | 1364000 | 27.28 | 27.28 | 1364000 |  |  |  | Active | 2019-04-29 |  |  | 2021-10-31 | Entergy Louisiana, LLC | Washington Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Lagen Holton - Franklinton 115kV Line (J1184) | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 50 | 50 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Withdrawn | Not Started | J1362 | [5 empty] | NRIS |  | 150 |  | Solar | Muskegon County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-02-13 |  | 2021-08-27 | Michigan Electric Transmission Company, LLC | Muskegon County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Kenowa - Ludington 345 kV Line Tap | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1363 | [5 empty] | NRIS |  | 150 |  | Solar | Audrain County | MO | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-26 |  |  | 2022-07-15 | Ameren Missouri | Audrain County | MO | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Spencer Creek - Montgomery 345 kV Line Tap | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1364 | [5 empty] | NRIS | N | 150 |  | Solar | Crittenden County | AR |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-08-05 |  | 2022-07-15 | Entergy Arkansas, LLC | Crittenden County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS | Marked Tree - Marion 161 kV Line tap | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1365 | [5 empty] | NRIS |  | 169.4 |  | Wind | Tama County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | ITC Midwest | Tama County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Traer 161-kV Substation | 169.4 | 169.4 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Withdrawn | Not Started | J1366 | [5 empty] | NRIS |  | 200 |  | Wind | Eau Claire County | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-04-02 |  | 2022-09-01 | Northern States Power (Xcel Energy) | Eau Claire County | WI | DPP-2019-Cycle | West | PHASE 1 | NRIS | Tremval - Seven Mile 161 kV Line Tap | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1367 | Bayou Teche Solar |  | 1803 2020 PPA Filing & Scoping Call MIGHT be Sudipto Bhowmik from iBV Energy |  | PPA w/ 1803 in 2020 | NRIS | N | 95 |  | Solar | St. Mary,St. Mary Parish | LA |  |  |  | 1 | 1 | 380000 | 923623 | [9 empty] | 0 | 3650000 | 7314765 | 3650000 | 10964765 | 38.4211 | 115.4186 | 10964765 |  |  |  | Active | 2019-04-29 |  |  | 2021-07-01 | CLECO Corporation | St. Mary,St. Mary Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Caneland 230kV Substation | 95 | 95 | Solar | PV Photovoltaic | Not Started |  | 95 | 95 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1368 |  |  | Scoping Calls, Jason Ausmus | Lightsource BP |  | NRIS | N | 200 |  | Solar | Pointe Coupee,Pointe Coupee Parish | LA |  |  |  | 1 | 1 | 800000 | 5418271 | [9 empty] | 0 | 7500000 | 42700207 | 7500000 | 50200207 | 37.5 | 251.001 | 50200207 |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | Entergy Louisiana, LLC | Pointe Coupee,Pointe Coupee Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Fancy Point - Waterloo 230 kV Line | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 200 | 130 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1369 | [5 empty] | NRIS |  | 100 |  | Solar | Dubois County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Dubois County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Dubois - Culley 138 kV Line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1371 | [5 empty] | NRIS |  | 150 |  | Wind | Yellow Medicine County | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-08-01 | Otter Tail Power Company | Yellow Medicine County | MN | DPP-2019-Cycle | West | PHASE 1 | NRIS | Astoria 345kV Substation | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1372 |  |  | Scoping Calls, Jason Ausmus | Lightsource BP |  | NRIS | N | 100 |  | Solar | Pointe Coupee,Pointe Coupee Parish | LA |  |  |  | 1 | 1 | 400000 | 3084135 | [9 empty] | 0 | 7500000 | 21350104 | 7500000 | 28850104 | 75 | 288.501 | 28850104 |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | Entergy Louisiana, LLC | Pointe Coupee,Pointe Coupee Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Fancy Point - Waterloo 230 kV Line (J1368 POI) | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 100 | 65 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1373 |  |  | Scoping Calls, Jason Ausmus | Lightsource BP |  | NRIS | N | 95 |  | Solar | White County | AR |  |  |  | 1 | 1 | 380000 | 2117528 | [9 empty] | 0 | 10453000 | 0 | 10453000 | 10453000 | 110.0316 | 110.0316 | 10453000 |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | Entergy Arkansas, LLC | White County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS | Griffithville - Searcy Price 115 kV Line Tap | 95 | 95 | Solar | PV Photovoltaic | Not Started |  | 95 | 80.75 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ATC) | Active | Not Started | J1374 | [5 empty] | NRIS |  | 95 |  | Wind | Grant County | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-08-01 | American Transmission Co. LLC | Grant County | WI | DPP-2019-Cycle | East (ATC) | PHASE 2 | NRIS | ATC Ebenezer Sub on Lancaster-Eden 138kv line | 95 | 95 | Wind | WT Wind Turbine | Not Started |  | 67.2 | 67.2 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1375 | [5 empty] | NRIS |  | 100 |  | Solar | Muskegon County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-09-29 | Michigan Electric Transmission Company, LLC | Muskegon County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Du Pont - Cobb -White Lake 138kv | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 100 | 100 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1376 | [5 empty] | NRIS |  | 100 |  | Wind | Cooper County | MO | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-15 | Ameren Missouri | Cooper County | MO | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Barnett - Georgetown Overton 161 kV Line Tap | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ATC) | Active | Not Started | J1377 | [5 empty] | NRIS |  | 98.56 |  | Solar | Rock County | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-15 | American Transmission Co. LLC | Rock County | WI | DPP-2019-Cycle | East (ATC) | PHASE 2 | NRIS | Wempletown - Rockdale 345kV Line Tap | 98.56 | 98.56 | Solar | PV Photovoltaic | Not Started |  | 98.56 | 98.56 | 0 | 0
|  |  |  | DPP-2017-FEB | South | Withdrawn | Not Started | J508 | [5 empty] | NRIS |  | 42.7 |  | Gas | Clark County | AR | [27 empty] | Withdrawn | 2015-11-16 | 2017-07-17 |  | 2017-04-01 | Entergy | Clark County | AR | DPP-2017-FEB | South | GIA | NRIS | tap 115 kV line betwwen W Arkadelphia sub and Delarc sub at 3.85 miles from West Arkadelphia substation | 42.7 | 42.7 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1378 | [5 empty] | NRIS |  | 200 |  | Solar | Fountain County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-10-01 | Duke Energy Indiana | Fountain County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Veedersburg West 230 kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1379 | [5 empty] | NRIS |  | 200 |  | Solar | Montcalm County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-10-01 | Michigan Electric Transmission Company, LLC | Montcalm County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Eureka - Vestaburg 138 kV Line Tap | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
|  |  |  | DPP-2017-AUG | South | Done | Under Construction | J868 | [5 empty] | NRIS |  | 37.2 |  | Hydro | Concordia Parish | LA | [27 empty] | Done | 2017-06-16 |  | 2020-03-05 |  | Entergy | Concordia Parish | LA | DPP-2017-AUG | South | GIA | NRIS | Plantation 115 kV Substation | 37.2 | 37.2 | Hydro | OT Other | Under Construction | 1990-12-03 | 0 | 25.33 | 0 | 23.5
|  |  | Unfavorable location due to high ERIS and NRIS | DPP-2019-Cycle | South | Withdrawn | Not Started | J1380 | [5 empty] | NRIS | N | 200 |  | Solar | Beauregard Parish | LA |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-07-17 |  | 2023-10-01 | CLECO Corporation | Beauregard Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Cooper - Penton 230 kV Line | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-FEB | East (ITC) | Withdrawn | Not Started | J496 | [5 empty] | NRIS |  | 151.8 |  | Wind | Sanilac County | MI | [27 empty] | Withdrawn | 2015-11-13 | 2017-07-19 |  | 2017-09-15 | ITC Transmission | Sanilac County | MI | DPP-2016-FEB | East (ITC) | GIA | NRIS | J321 substation (new breaker position or the J321 gen-tie) | 151.8 | 151.8 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA-2015-MAY | 0 | Withdrawn | Not Started | J190 | [5 empty] | NRIS |  | 100 |  | Wind | Ottawa County | MI | [27 empty] | Withdrawn | 2010-12-21 | 2017-07-21 |  | 2012-12-15 | Michigan Electric Transmission Company, LLC | Ottawa County | MI | SPA-2015-MAY |  | SPA - SIS | NRIS | Kenowa 345kV Substation | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2019-07-01 | 0 | 0 | 0 | 0
|  |  |  | SPA-2015-NOV | 0 | Withdrawn | Not Started | J304 | [5 empty] | NRIS |  | 20 |  | Solar | Dakota County | MN | [27 empty] | Withdrawn | 2013-11-18 | 2017-07-21 |  | 2016-09-01 | Northern States Power (Xcel Energy) | Dakota County | MN | SPA-2015-NOV |  | SPA - SIS | NRIS | NSP 69 kV Miesville Tap-Byllesby | 20 | 20 | Solar |  | Not Started |  | 0 | 0 | 0 | 0
| NEER |  | NEER Project | DPP-2019-Cycle | Central | Active | Not Started | J1381 | [5 empty] | NRIS |  | 200 |  | Solar | Howard County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-10-01 | Duke Energy Indiana | Howard County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Greentown 230 kV substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J306 | [5 empty] | NRIS |  | 101 |  | Wind | Traverse County, Wexford | MN | [27 empty] | Withdrawn | 2013-11-18 | 2017-07-21 |  | 2016-09-01 | Michigan Electric Transmission Company, LLC | Traverse County, Wexford | MN |  |  | SPA - SIS | NRIS | Unknown | 101 | 101 | Wind |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1382 | [5 empty] | NRIS |  | 150 |  | Solar | Clark County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | Ameren Illinois | Clark County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Hutsonville - Neoga 138 kV Line tap | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA-2015-NOV | 0 | Withdrawn | Not Started | J312 | [5 empty] | NRIS |  | 201 |  | Wind | Clinton County | IN | [27 empty] | Withdrawn | 2013-11-18 | 2017-07-21 |  | 2017-09-01 | Duke Energy Corporation | Clinton County | IN | SPA-2015-NOV |  | SPA - SIS | NRIS | Duke Energy 230 kV Thorntown-Kokomo | 201 | 201 | Wind |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA-2015-NOV | 0 | Withdrawn | Not Started | J313 | [5 empty] | NRIS |  | 201 |  | Wind | Montgomery County | IN | [27 empty] | Withdrawn | 2013-11-18 | 2017-07-21 |  | 2017-09-01 | Duke Energy Corporation | Montgomery County | IN | SPA-2015-NOV |  | SPA - SIS | NRIS | Unknown | 201 | 201 | Wind |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2014-SEP | 0 | Withdrawn | Not Started | J387 | [5 empty] | NRIS |  | 103 |  | Solar | Independence County | AR | [27 empty] | Withdrawn | 2014-09-10 | 2017-07-21 |  | 2016-11-01 | Entergy | Independence County | AR | FES-2014-SEP |  | Feasibility | NRIS | 161 kV Independence Substation | 103 | 103 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA-2014-NOV | MI-UP | Withdrawn | Not Started | J397 | [5 empty] | NRIS |  | 153 |  | Gas | Marquette County | MI | [27 empty] | Withdrawn | 2014-09-15 | 2017-07-21 |  | 2016-10-31 | American Transmission Co. LLC | Marquette County | MI | SPA-2014-NOV | MI-UP | SPA - SIS | NRIS | Arnold 138 kV Substation | 153 | 153 | Gas | CT Combined-Cycle Combustion ? Turbine Part | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2015-JUN | 0 | Withdrawn | Not Started | J448 | [5 empty] | NRIS |  | 202 |  | Wind | Mitchell County | IA | [27 empty] | Withdrawn | 2015-05-15 | 2017-07-21 |  | 2017-09-15 | ITC Midwest | Mitchell County | IA | FES-2015-JUN |  | Feasibility | NRIS | New substation adjacent to ITC's Barton Wind - Adams 161 kv line | 202 | 202 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2015-JUN | 0 | Withdrawn | Not Started | J450 | [5 empty] | NRIS |  | 200 |  | Wind | Huron County | MI | [27 empty] | Withdrawn | 2015-05-15 | 2017-07-21 |  | 2016-02-01 | ITC Transmission | Huron County | MI | FES-2015-JUN |  | Feasibility | NRIS | ITC Rapson-Banner 345 kV line | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1383 | [5 empty] | NRIS |  | 150 |  | Solar | Fulton County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | Ameren Illinois | Fulton County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Ipava 138 kV Substation | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2015-NOV | 0 | Withdrawn | Not Started | J517 | [5 empty] | NRIS |  | 100 |  | Solar | Jefferson County, Liberty County | TX | [27 empty] | Withdrawn | 2015-11-16 | 2017-07-21 |  | 2017-11-01 | Entergy | Jefferson County, Liberty County | TX | FES-2015-NOV |  | Feasibility | NRIS | Unknown | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1384 | [5 empty] | NRIS | N | 200 |  | Solar | Evangeline Parish | LA |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-07-22 |  | 2022-04-30 | CLECO Corporation | Evangeline Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Ville Platte - West Fork 230 kV Line | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1385 | [5 empty] | NRIS |  | 100 |  | Solar | Hendricks County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | Duke Energy Indiana | Hendricks County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Stilesville 138 kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2015-NOV | 0 | Withdrawn | Not Started | J519 | [5 empty] | NRIS |  | 200 |  | Wind | Audubon County | IA | [27 empty] | Withdrawn | 2015-11-16 | 2017-07-21 |  | 2017-09-30 | MidAmerican Energy Company | Audubon County | IA | FES-2015-NOV |  | Feasibility | NRIS | MEC Atlantic substation, 161 kV bus | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2015-NOV | 0 | Withdrawn | Not Started | J520 | [5 empty] | NRIS |  | 100 |  | Wind | Pipestone County | MN | [27 empty] | Withdrawn | 2015-11-16 | 2017-07-21 |  | 2017-09-30 | Northern States Power (Xcel Energy) | Pipestone County | MN | FES-2015-NOV |  | Feasibility | NRIS | Unknown | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2015-NOV | 0 | Withdrawn | Not Started | J521 | [5 empty] | NRIS |  | 100 |  | Wind | Huron County | MI | [27 empty] | Withdrawn | 2015-11-16 | 2017-07-21 |  | 2017-09-01 | ITC Transmission | Huron County | MI | FES-2015-NOV |  | Feasibility | NRIS | Harvest Wind tap on Cosmo-Bad Axe 120 kV line | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1386 | [5 empty] | NRIS |  | 100 |  | Solar | Lake County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | Northern Indiana Public Service Company | Lake County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Green Acres 138 kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
| NEER |  |  | DPP-2017-AUG | South | Done | In Service | J888 | [5 empty] | NRIS |  | 25 |  | Gas | George County | MS | [27 empty] | Done | 2017-06-16 |  | 2019-08-19 | 2019-01-01 | South Mississippi Electric Power Association | George County | MS | DPP-2017-AUG | South | GIA | NRIS | Benndale 69kV Substation | 25 | 25 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2019-07-22 | 25 | 25 | 25 | 25
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1387 | [5 empty] | ERIS |  | 60 |  | Solar | Jasper County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-12-31 | Northern Indiana Public Service Company | Jasper County | IN | DPP-2019-Cycle | Central | PHASE 1 | ERIS | Circuit 6958 69 kV Line Tap | 60 | 60 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1388 | [5 empty] | ERIS |  | 150 |  | Solar | Gibson County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-12-31 | Duke Energy Indiana | Gibson County | IN | DPP-2019-Cycle | Central | PHASE 1 | ERIS | Oakland City - Old Ben Coal 138 kV Line Tap | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  | Relatively high upgrades + land and gen-tie tough + coastal | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1389 | [5 empty] | NRIS |  | 120 |  | Solar | Saginaw County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | Michigan Electric Transmission Company, LLC | Saginaw County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Murphy Station - Nelson Road 345 kV Line tap | 120 | 120 | Solar | PV Photovoltaic | Not Started |  | 120 | 120 | 0 | 0
|  |  | Unfavorable location due to high ERIS and NRIS | DPP-2019-Cycle | Central | Active | Not Started | J1390 | [5 empty] | NRIS |  | 150 |  | Solar | Bartholomew County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | Duke Energy Indiana | Bartholomew County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Gallagher Station - Columbus 230 kV Line Tap | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1391 | [5 empty] | NRIS |  | 100 |  | Solar | Dubois County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Dubois County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Duff 138 kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1392 | [5 empty] | NRIS |  | 100 |  | Solar | LaGrange County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-10-30 | Northern Indiana Public Service Company | LaGrange County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Lagrange 138 kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  | Unfavorable location due to high ERIS and NRIS | DPP-2019-Cycle | Central | Active | Not Started | J1393 | [5 empty] | NRIS |  | 130 |  | Solar | Pike County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-10-30 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Pike County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Cato 138 kV Substation | 130 | 130 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Withdrawn | Not Started | J1394 | [5 empty] | NRIS |  | 150 |  | Solar | Shiawassee County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2021-02-08 |  | 2021-12-01 | Michigan Electric Transmission Company, LLC | Shiawassee County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Cornell - Layton138kV Line | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1395 | [5 empty] | NRIS |  | 200 |  | Solar | Lyon County | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-09-01 | Northern States Power (Xcel Energy) | Lyon County | MN | DPP-2019-Cycle | West | PHASE 1 | NRIS | Nest Lake - Lyon County 345 kV Line Tap | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1396 | [5 empty] | NRIS |  | 150 |  | Solar | Pike County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-12-01 | Hoosier Energy | Pike County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Ratts-Victory 161kV Line | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ATC) | Withdrawn | Not Started | J1397 | [5 empty] | NRIS |  | 25 |  | Solar | Juneau County | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-05-18 |  | 2022-10-30 | Dairyland Power Cooperative | Juneau County | WI | DPP-2019-Cycle | East (ATC) | PHASE 2 | NRIS | Whistling Wings 69 kV Substation | 25 | 25 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1398 | [5 empty] | NRIS |  | 150 |  | Solar | Pike County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-12-01 | Hoosier Energy | Pike County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Ratts 161kV Substation | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1399 | [5 empty] | NRIS |  | 90 |  | Solar | Ingham County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-12-01 | Michigan Electric Transmission Company, LLC | Ingham County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Delhi - Churchill - Tompkins 138kV Line | 90 | 90 | Solar | PV Photovoltaic | Not Started |  | 90 | 90 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1400 | [5 empty] | NRIS | N | 150 |  | Wind | Crittenden County | AR |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-07-30 |  | 2021-08-01 | Entergy Arkansas, LLC | Crittenden County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS | Marked Tree - Marion 161 kV Line Tap | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1401 | [5 empty] | NRIS |  | 150 |  | Solar | Branch County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-12-01 | Michigan Electric Transmission Company, LLC | Branch County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Batavia - Wagner 138kV Line | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1402 |  |  | Scoping Calls - Aaron Martin | CMS Energy |  | NRIS |  | 0 |  | Battery Storage | Jackson County | AR | [21 empty] | #DIV/0! | #DIV/0! |  |  |  |  | Active | 2019-04-29 |  |  | 2021-08-01 | Entergy Arkansas, LLC | Jackson County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS | Cash - Newport AB161kV Line | 0 | 0 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1403 | [5 empty] | NRIS |  | 200 |  | Solar | Ionia County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-09-01 | Michigan Electric Transmission Company, LLC | Ionia County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Marquette 138 kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1404 | [5 empty] | NRIS | N | 167 |  | Wind | Sunflower County | MS |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-07-23 |  | 2022-10-01 | Entergy Mississippi, LLC | Sunflower County | MS | DPP-2019-Cycle | South | PHASE 2 | NRIS | Drew 115kV Substation | 167 | 167 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1405 | [5 empty] | NRIS |  | 140 |  | Solar | Greene County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | Duke Energy Indiana | Greene County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Sanborn - Linton 138 kV Line Tap | 140 | 140 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Withdrawn | Not Started | J1406 | [5 empty] | NRIS |  | 25.2 |  | Wind | Muskegon County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-02-07 |  | 2021-09-03 | Michigan Electric Transmission Company, LLC | Muskegon County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Kenowa - Ludington 345 kV Line Tap | 25.2 | 25.2 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1407 | [5 empty] | NRIS |  | 100 |  | Solar | Porter County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | Northern Indiana Public Service Company | Porter County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | South Valparaiso 138 kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1408 | [5 empty] | NRIS |  | 100 |  | Hybrid | Macoupin County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-06-15 | Ameren Illinois | Macoupin County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Virden South 138kV Substation | 100 | 100 | Hybrid | Solar/Wind/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Active | Not Started | J953 | [5 empty] | External NRIS |  | 2 |  | Diesel | Johnson County | IA | [27 empty] | Active | 2018-03-08 |  |  | 2006-01-01 | ITC Midwest | Johnson County | IA | DPP-2018-APR | West | PHASE 3 | External NRIS | AMIL.IOW_AFRYT | 1.83 | 2 | Diesel | IC Internal Combustion (diesel, piston) Engine | Not Started |  | 1.83 | 2 | 1.83 | 2
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1409 | [5 empty] | NRIS |  | 25 |  | Battery Storage | Henderson County | KY | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-10-30 | Big Rivers Electric Corporation | Henderson County | KY | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Henderson 161 kV Substation | 25 | 25 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J1189 | [5 empty] | NRIS | N | 5 |  | Battery Storage | Brown County,Martin County | IN |  |  |  | 1 | 1 | 20000 | 8493 | [9 empty] | 0 | 0 | 284936 | 0 | 284936 | 0 | 56.9872 | 284936 |  |  |  | Active | 2018-03-12 |  |  | 2019-01-01 | Duke Energy Indiana | Brown County,Martin County | IN | DPP-2018-APR | Central | PHASE 3 | NRIS | Crane Solar 69kV Substation | 5 | 5 | Battery Storage | BS Battery Storage | Not Started |  | 4.95 | 4.95 | 4.95 | 4.95
|  |  |  | DPP-2019-Cycle | East (ATC) | Active | Not Started | J1410 | [5 empty] | NRIS |  | 300 |  | Solar | Dane County | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-10-30 | American Transmission Co. LLC | Dane County | WI | DPP-2019-Cycle | East (ATC) | PHASE 2 | NRIS | N. Madison 345 kV Substation | 300 | 300 | Solar | PV Photovoltaic | Not Started |  | 300 | 300 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ATC) | Active | Not Started | J1411 | [5 empty] | NRIS |  | 75 |  | Battery Storage | Dane County | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-10-30 | American Transmission Co. LLC | Dane County | WI | DPP-2019-Cycle | East (ATC) | PHASE 2 | NRIS | N. Madison 345 kV Substation | 75 | 75 | Battery Storage | BS Battery Storage | Not Started |  | 75 | 75 | 0 | 0
| NEER |  | NEER Project | DPP-2019-Cycle | Central | Withdrawn | Not Started | J1412 | [5 empty] | NRIS |  | 250 |  | Solar | Porter County | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-04-15 |  | 2023-10-30 | Northern Indiana Public Service Company | Porter County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Lake George - Schahfer GEN STA 345 kV Line Tap | 250 | 250 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1413 | [5 empty] | NRIS |  | 300 |  | Solar | Howard County,Mitchell County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-10-30 | ITC Midwest | Howard County,Mitchell County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Hazleton - Mitchell County 345 kV Line tap | 300 | 300 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1414 | [5 empty] | NRIS | N | 150 |  | Solar | Clay County | AR |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-08-04 |  | 2022-10-30 | Entergy Arkansas, LLC | Clay County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS | Datto-Corning North 161 kV line | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1415 | [5 empty] | NRIS | N | 250 |  | Solar | Lonoke County | AR |  |  |  | 1 | 1 | 1000000 | 0 | [9 empty] | 0 | 1959500 | 0 | 1959500 | 1959500 | 7.838 | 7.838 | 1959500 |  |  |  | Active | 2019-04-29 |  |  | 2023-10-30 | Entergy Arkansas, LLC | Lonoke County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS | KEO EHV 500 kV Substation | 250 | 250 | Solar | PV Photovoltaic | Not Started |  | 250 | 250 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1416 | [5 empty] | NRIS |  | 149 |  | Solar | Worth County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-10-30 | ITC Midwest | Worth County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Worth County - Glenworth 161 kV Line tap | 149 | 149 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1417 | [5 empty] | NRIS |  | 75 |  | Battery Storage | Worth County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-10-30 | ITC Midwest | Worth County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Ledyard - Colby 345 kV Line Tap | 75 | 75 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Withdrawn | Not Started | J1418 | [5 empty] | NRIS |  | 100 |  | Solar | Pulaski County | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-01-02 |  | 2021-12-01 | Ameren Illinois | Pulaski County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Joppa-Joppa North Bus 161kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1419 | [5 empty] | NRIS |  | 250 |  | Solar | Greene County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | Duke Energy Indiana | Greene County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Edwardsport - Amo 345 kV Line Tap | 250 | 250 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Withdrawn | Not Started | J1420 | [5 empty] | NRIS |  | 48 |  | Solar | Rock Island County | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-03-05 |  | 2022-09-15 | MidAmerican Energy Company | Rock Island County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Sub #107 69 kV Substation | 48 | 48 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1421 | [5 empty] | NRIS | N | 300 |  | Solar | East Feliciana Parish | LA |  |  |  | 1 | 1 | 1200000 | 1553225 | [9 empty] | 0 | 34600000 | 0 | 34600000 | 34600000 | 115.3333 | 115.3333 | 34600000 |  |  |  | Active | 2019-04-29 |  |  | 2021-10-20 | Entergy Louisiana, LLC | East Feliciana Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Moler 230 kV Substation | 300 | 300 | Solar | PV Photovoltaic | Not Started |  | 300 | 300 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1422 | [5 empty] | NRIS |  | 150 |  | Hybrid | Edwards County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-10-20 | Ameren Illinois | Edwards County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Albion - Olney 138 kV Line Tap | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Withdrawn | Not Started | J1423 | [5 empty] | NRIS |  | 100 |  | Solar | Ottawa County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-06-11 |  | 2022-04-20 | Michigan Electric Transmission Company, LLC | Ottawa County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Campbell - Blendon 138kV Line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1424 | [5 empty] | NRIS | N | 200 |  | Solar | Beauregard Parish | LA |  |  |  | 1 | 1 | 800000 | 8439655 | [9 empty] | 0 | 11478660 | 90618429 | 11478660 | 102097089 | 57.3933 | 510.4854 | 102097089 |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | CLECO Corporation | Beauregard Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Cooper - Penton Road 230kV Line | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1426 | [5 empty] | NRIS |  | 100 |  | Solar | Benton County | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | Great River Energy | Benton County | MN | DPP-2019-Cycle | West | PHASE 1 | NRIS | Benton County 115kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1427 | [5 empty] | NRIS |  | 400 |  | Wind | Benton County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | ITC Midwest | Benton County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Duane Arnold 345kV Substation | 400 | 400 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1428 | [5 empty] | NRIS |  | 200 |  | Solar | Cass County | ND | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | Otter Tail Power Company | Cass County | ND | DPP-2019-Cycle | West | PHASE 1 | NRIS | Buffalo 345kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  | Entergy wants projects in this parish. Developer will determine if they keep this. | DPP-2019-Cycle | East (ATC) | Withdrawn | Not Started | J1429 | [5 empty] | NRIS |  | 24 |  | Battery Storage | Juneau County | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-05-18 |  | 2022-10-30 | Dairyland Power Cooperative | Juneau County | WI | DPP-2019-Cycle | East (ATC) | PHASE 2 | NRIS | Whistiling Wings 69 kV Substation | 24 | 24 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1430 | [5 empty] | NRIS |  | 100 |  | Solar | Calhoun County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | Michigan Electric Transmission Company, LLC | Calhoun County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Verona - Foundary 138kV Line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 100 | 100 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1431 | [5 empty] | NRIS | N | 200 |  | Solar | St. James Parish | LA |  |  |  | 1 | 1 | 800000 | 3382034 | [9 empty] | 0 | 608000 | 8678439 | 608000 | 9286439 | 3.04 | 46.4322 | 9286439 |  |  |  | Active | 2019-04-29 |  |  | 2021-06-01 | Entergy Louisiana, LLC | St. James Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Vacherie 230kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 90 | 90 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1432 | [5 empty] | NRIS |  | 250 |  | Wind | Clinton County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | ITC Midwest | Clinton County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Salem - Rock Creek 345kV Line | 250 | 250 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1433 | [5 empty] | NRIS | N | 50 |  | Solar | Washington Parish | LA |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2019-10-22 |  | 2021-06-01 | Entergy Louisiana, LLC | Washington Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Lagen Holton-Franklinton 115kV (J1184) | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1434 | [5 empty] | NRIS | N | 100 |  | Solar | Monroe County | AR |  |  |  | 1 | 1 | 400000 | 1921525 | [9 empty] | 792000 | 0 | 211598 | 0 | 1003598 | 0 | 10.036 | 1003598 |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | Entergy Arkansas, LLC | Monroe County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS | J907 230kV Sub, Brinkley East - Aubrey 230 kV Line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 100 | 100 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1435 | [5 empty] | NRIS |  | 100 |  | Battery Storage | Dubuque County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | ITC Midwest | Dubuque County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Center Grove 161kV Substation | 100 | 100 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1436 |  |  | Scoping Calls, Jacob Pundyk | AES |  | ERIS | E | 50 |  | Solar | Morehouse Parish | LA |  |  |  | 1 | 1 | 200000 | 157619 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Active | 2019-04-29 |  |  | 2022-11-15 | Entergy Louisiana, LLC | Morehouse Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Oak Ridge 115 kV Substation | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 50 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1437 | [5 empty] | NRIS | N | 180 |  | Wind | Carroll County | AR |  |  |  | 1 | 1 | 720000 | 0 | [9 empty] | 500000 | 2500000 | 0 | 2500000 | 3000000 | 13.8889 | 16.6667 | 3000000 |  |  |  | Active | 2019-04-29 |  |  | 2021-04-30 | Arkansas Electric Coop Corp | Carroll County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS | AECC Dry Creek 161kV Switchyard Station | 180 | 180 | Wind | WT Wind Turbine | Not Started |  | 180 | 180 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1438 | [5 empty] | NRIS |  | 100 |  | Solar | Fayette County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | ITC Midwest | Fayette County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Windsor - Hazelton 161kV Line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1439 | [5 empty] | NRIS |  | 40 |  | Battery Storage | Tunica County | MS | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-08-04 |  | 2022-10-30 | Entergy Mississippi, LLC | Tunica County | MS | DPP-2019-Cycle | South | PHASE 2 | NRIS | Lula - Tunica 115 kV Line | 40 | 40 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1440 | [5 empty] | NRIS | N | 160 |  | Solar | Tunica County | MS |  |  |  | 1 | 1 | 650000 | 2419980 | [9 empty] | 946000 | 12064000 | 379113 | 12064000 | 13389113 | 75.4 | 83.682 | 13389113 |  |  |  | Active | 2019-04-29 |  |  | 2023-10-30 | Entergy Mississippi, LLC | Tunica County | MS | DPP-2019-Cycle | South | PHASE 2 | NRIS | Lula - Tunica 115 kV Line | 160 | 160 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1441 | [5 empty] | NRIS | N | 200 |  | Solar | Terrebonne Parish | LA |  |  |  | 1 | 1 | 800000 | 3675142 | [9 empty] | 0 | 3255000 | 19621561 | 3255000 | 22876561 | 16.275 | 114.3828 | 22876561 |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | Entergy Louisiana, LLC | Terrebonne Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Schriever 230 kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
|  |  |  | DPP-2012-AUG | MI | Done | In Service | J161 | [5 empty] | NRIS |  | 155 |  | Wind | Tuscola County | MI | [27 empty] | Done | 2010-08-31 |  | 2013-06-21 | 2014-10-31 | ITC Transmission | Tuscola County | MI | DPP-2012-AUG | MI | DPP - SIS | NRIS | Bauer - Rapson 345 kV | 155 | 155 | Wind | WT Wind Turbine | In Service | 2012-04-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1442 | [5 empty] | NRIS | N | 165 |  | Solar | Polk County | TX |  |  |  | 1 | 1 | 660000 | 5668331 | [10 empty] | 13578000 | 44284120 | 13578000 | 57862120 | 82.2909 | 350.6795 | 57862120 |  |  |  | Active | 2019-04-29 |  |  | 2023-10-30 | Entergy Texas, Inc. | Polk County | TX | DPP-2019-Cycle | South | PHASE 2 | NRIS | Rich (SHECO) - Livingston 138 kV Line Tap | 165 | 165 | Solar | PV Photovoltaic | Not Started |  | 105 | 105 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1443 | [5 empty] | NRIS | N | 100 |  | Solar | Union County | AR |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-01-14 |  | 2023-10-30 | Entergy Arkansas, LLC | Union County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS | Texas Eastern F SS - Strong SS 115 kV Line Tap | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1444 | [5 empty] | NRIS |  | 200 |  | Solar | Linn County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2015-08-01 | ITC Midwest | Linn County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Duane Arnold 345kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1445 | [5 empty] | NRIS |  | 100 |  | Solar | Benton County | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | Northern States Power (Xcel Energy) | Benton County | MN | DPP-2019-Cycle | West | PHASE 1 | NRIS | Mayhew Lake 115kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1446 | [5 empty] | NRIS |  | 150 |  | Battery Storage | Wright County | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | Northern States Power (Xcel Energy) | Wright County | MN | DPP-2019-Cycle | West | PHASE 1 | NRIS | Lake Pulaski 115kV Substation | 150 | 150 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1447 | [5 empty] | NRIS |  | 250 |  | Solar | Porter County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-09-01 | Northern Indiana Public Service Company | Porter County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Schahfer - Green Acres 345kV Line | 250 | 250 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1448 | [5 empty] | NRIS |  | 150 |  | Solar | Caldwell County | KY | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | Big Rivers Electric Corporation | Caldwell County | KY | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Hopkins - Caldwell County - Barkely 161kV Line | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Withdrawn | Not Started | J1449 | [5 empty] | NRIS |  | 100 |  | Solar | Monroe County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2021-02-10 |  | 2022-08-01 | Michigan Electric Transmission Company, LLC | Monroe County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Morocco 138kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1450 | [5 empty] | NRIS |  | 150 |  | Solar | Webster County | KY | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | Big Rivers Electric Corporation | Webster County | KY | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Hopkins - Reid161kV Line | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Withdrawn | Not Started | J1451 | [5 empty] | NRIS |  | 25 |  | Battery Storage | Washtenaw County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-26 | 2020-05-06 |  | 2022-10-30 | ITC Transmission | Washtenaw County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Dorset 120 kV Substation | 25 | 25 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1452 | [5 empty] | NRIS | N | 200 |  | Solar | Red River Parish | LA |  |  |  | 1 | 1 | 800000 | 2311132 | [10 empty] | 10250000 | 5261535 | 10250000 | 15511535 | 51.25 | 77.5577 | 15511535 |  |  |  | Active | 2019-04-29 |  |  | 2022-10-30 | CLECO Corporation | Red River Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Carroll - Mansfield 138 kV Line Tap | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 75 | 75 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1453 | [5 empty] | NRIS |  | 188.3 |  | Wind | Mason County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-04-30 | Ameren Illinois | Mason County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Havana - Shockey 138 kV Line Tap | 188.3 | 188.3 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1454 | [5 empty] | NRIS |  | 58.5 |  | Wind | Mason County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-04-30 | Ameren Illinois | Mason County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Mason 138 kV Substation | 58.5 | 58.5 | Wind | WT Wind Turbine | Not Started | 2021-08-18 | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1455 | [5 empty] | NRIS | N | 150 |  | Solar | St. Mary,St. Mary Parish | LA |  |  |  | 1 | 1 | 600000 | 1957465 | [10 empty] | 10814000 | 12033496 | 10814000 | 22847496 | 72.0933 | 152.3166 | 22847496 |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | CLECO Corporation | St. Mary,St. Mary Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Teche - Morbihan 138kV Line | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1456 | [5 empty] | NRIS |  | 300 |  | Wind | Sheridan County | ND | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-09-01 | Otter Tail Power Company | Sheridan County | ND | DPP-2019-Cycle | West | PHASE 1 | NRIS | Harvey - Underwood 230 kV Line Tap | 300 | 300 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1457 | [5 empty] | NRIS |  | 200 |  | Solar | Vermillion County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-06-30 | Duke Energy Indiana | Vermillion County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Sugar Creek - Cayuga 345 kV Line Tap | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1458 | [5 empty] | NRIS | N | 200 |  | Solar | Washington County | MS |  |  |  | 1 | 1 | 800000 | 3839272 | [9 empty] | 858000 | 4380000 | 13572412 | 4380000 | 18810412 | 21.9 | 94.0521 | 18810412 |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | Entergy Mississippi, LLC | Washington County | MS | DPP-2019-Cycle | South | PHASE 2 | NRIS | Ray Braswell - Tinnin - Gerald Andrus 230kV Line | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 200 | 170 | 0 | 0
|  |  |  | DPP-2018-APR | South | Done | In Service | J1146 | [5 empty] | NRIS |  | 10 |  | Coal | Mississippi County | AR | [27 empty] | Done | 2018-03-12 |  | 2020-08-12 | 2019-01-04 | Entergy Arkansas, LLC | Mississippi County | AR | DPP-2018-APR | South | GIA | NRIS | San Souci 500 kV Substation | 10 | 10 | Coal | Combined Cycle | In Service | 2020-10-10 | 10 | 10 | 10 | 10
|  |  |  | DPP-2019-Cycle | East (ATC) | Active | Not Started | J1460 | [5 empty] | NRIS |  | 200 |  | Solar | Rock County | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-06-30 | American Transmission Co. LLC | Rock County | WI | DPP-2019-Cycle | East (ATC) | PHASE 2 | NRIS | Sunrise 138 kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1461 | [5 empty] | NRIS |  | 50 |  | Solar | Carver County | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | Northern States Power (Xcel Energy) | Carver County | MN | DPP-2019-Cycle | West | PHASE 1 | NRIS | McLeod - Blue Lake 230kV Line | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1462 | [5 empty] | NRIS | N | 150 |  | Solar | Acadia Parish | LA |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-08-06 |  | 2022-08-01 | Entergy Louisiana, LLC | Acadia Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Acadia - Scanlan 138kV Line | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1463 | [5 empty] | NRIS | N | 150 |  | Solar | West Baton Rouge Parish | LA |  |  |  | 1 | 1 | 600000 | 2934367 | [11 empty] | 22427269 | 0 | 22427269 | 0 | 149.5151 | 22427269 |  |  |  | Active | 2019-04-29 |  |  | 2021-10-20 | Entergy Louisiana, LLC | West Baton Rouge Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Addis - Big Cajun 230 kV Line Tap (J639) | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 150 | 45 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1464 | [5 empty] | NRIS |  | 592.8 |  | Solar | Macoupin County,Morgan County,Sangamon County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-04-30 | Ameren Transmission Company of Illinois | Macoupin County,Morgan County,Sangamon County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Meredosia - Austin 345 kV Line tap | 592.8 | 592.8 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1465 | [5 empty] | NRIS | N | 150 |  | Solar | Pointe Coupee Parish | LA |  |  |  | 1 | 1 | 600000 | 3130304 | [10 empty] | 15000000 | 32493325 | 15000000 | 47493325 | 100 | 316.6222 | 47493325 |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | Entergy Louisiana, LLC | Pointe Coupee Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Livonia 138 kV Substation | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1466 | [5 empty] | NRIS |  | 250 |  | Solar | Henderson County | KY | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | Big Rivers Electric Corporation | Henderson County | KY | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Reid 161 kV Substation | 250 | 250 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1467 | [5 empty] | NRIS |  | 150 |  | Wind | Fayette County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | ITC Midwest | Fayette County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | ITC 161kV Windsor - Hazleton 161kV Line | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1468 | [5 empty] | NRIS |  | 100 |  | Battery Storage | Dakota County | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | Northern States Power (Xcel Energy) | Dakota County | MN | DPP-2019-Cycle | West | PHASE 1 | NRIS | West Hastings 115kV Substation | 100 | 100 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1469 | [5 empty] | NRIS | N | 200 |  | Solar | Crittenden County | AR |  |  |  | 0 | [17 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-08-06 |  | 2022-08-01 | Entergy Arkansas, LLC | Crittenden County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS | Marion - Marked Tree 161kV Line | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1470 | [5 empty] | NRIS Only |  | 30 |  | Wind | Benton County,Warren County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2019-04-30 | Duke Energy Indiana | Benton County,Warren County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS Only | Cayuga CT 345kV Substation | 30 | 30 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1471 | [5 empty] | NRIS |  | 200 |  | Solar | Lee County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | ITC Midwest | Lee County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | ITC 161kV Wever Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1472 | [5 empty] | NRIS |  | 100 |  | Solar | Jackson County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | Michigan Electric Transmission Company, LLC | Jackson County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Leoni - Parr Raod 138kV line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 100 | 100 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1473 | [5 empty] | NRIS |  | 100 |  | Solar | Chisago County | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-01 | Northern States Power (Xcel Energy) | Chisago County | MN | DPP-2019-Cycle | West | PHASE 1 | NRIS | Lawrence Creek - Shafer 115kV Line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1474 | [5 empty] | NRIS |  | 200 |  | Solar | Chippewa County | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-07-01 | Northern States Power (Xcel Energy) | Chippewa County | WI | DPP-2019-Cycle | West | PHASE 1 | NRIS | Pine Lake - Eagle Point 115kV Line | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1475 | [5 empty] | NRIS |  | 75 |  | Solar | Clark County | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-04-18 | Ameren Illinois | Clark County | IL | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Casey West - Sullivan 345 kV Line Tap | 75 | 75 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1476 | [5 empty] | NRIS |  | 25 |  | Battery Storage | Union County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-10-01 | ITC Midwest | Union County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Creston East 69 kV Substation (J1132) | 25 | 25 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1477 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Scott County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-10-01 | MidAmerican Energy Company | Scott County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Sub 56 161 kV Substation (J1131) | 50 | 50 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1478 | [5 empty] | NRIS |  | 25 |  | Battery Storage | Des Moines County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-10-01 | ITC Midwest | Des Moines County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Huntwoods 69 kV substation (J1135) | 25 | 25 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
| NEER |  | NEER Project | DPP-2019-Cycle | West | Active | Not Started | J1479 | [5 empty] | NRIS |  | 100 |  | Battery Storage | Des Moines County | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-10-01 | ITC Midwest | Des Moines County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Burlington 161 kV Substation | 100 | 100 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Withdrawn | Not Started | J1480 | [5 empty] | NRIS |  | 70 |  | Wind | Black Hawk County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-04-14 |  | 2020-08-04 | MidAmerican Energy Company | Black Hawk County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Shawlis - Electric Farms 161kV Line | 70 | 70 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1481 | [5 empty] | NRIS |  | 200 |  | Solar | Howard County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-15 | Duke Energy Indiana | Howard County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Greentown 230 kV substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1482 | [5 empty] | NRIS |  | 150 |  | Solar | White County | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-08-15 | Northern Indiana Public Service Company | White County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Monticello - Springboro 138 kV Line Tap | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1141 | [5 empty] | NRIS |  | 17 |  | Gas | Manistee County | MI | [27 empty] | Withdrawn | 2018-03-12 | 2018-09-07 |  | 2019-10-01 | Michigan Electric Transmission Company, LLC | Manistee County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Filer - BoxbdJ - Stronach 138kV Line Tap | 17 | 17 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ATC) | Active | Not Started | J1483 | [5 empty] | ERIS |  | 99 |  | Wind | Iowa County | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2023-10-30 | American Transmission Co. LLC | Iowa County | WI | DPP-2019-Cycle | East (ATC) | PHASE 2 | ERIS | Hill Valley 345 kV Substation | 99 | 99 | Wind | WT Wind Turbine | Not Started |  | 99 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1484 | [5 empty] | NRIS |  | 25 |  | Battery Storage | Union County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-01-14 |  | 2023-10-30 | Entergy Arkansas, LLC | Union County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS | Texas Eastern F SS - Strong SS 115 kV Line Tap | 25 | 25 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1485 | [5 empty] | NRIS |  | 250 |  | Wind | Deuel County | SD | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2022-10-30 | Otter Tail Power Company | Deuel County | SD | DPP-2019-Cycle | West | PHASE 1 | NRIS | Astoria 345 kV Substation (J493/J510) | 250 | 250 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ATC) | Withdrawn | Not Started | J1486 | [5 empty] | NRIS |  | 2.5 |  | Battery Storage | Waupaca County | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2019-04-29 | 2020-03-17 |  | 2021-12-31 | American Transmission Co. LLC | Waupaca County | WI | DPP-2019-Cycle | East (ATC) | PHASE 2 | NRIS | Harrison North 138kV Substation | 2.5 | 2.5 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1487 | [5 empty] | NRIS |  | 120 |  | Wind | Freeborn County | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2019-04-29 |  |  | 2021-05-01 | ITC Midwest | Freeborn County | MN | DPP-2019-Cycle | West | PHASE 1 | NRIS | Freeborn 161kV substation | 120 | 120 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1491 | [5 empty] | NRIS |  | 200 |  | Battery Storage | Marion | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-06-23 | 2021-02-12 |  | 2022-12-15 | Indianapolis Power & Light Company | Marion | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | IPL EW Stout North Yard 138 kV Substation | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1492 | [5 empty] | NRIS |  | 150 |  | Battery Storage | Kent | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-06-24 |  |  | 2023-08-15 | Michigan Electric Tranmission Company LLC | Kent | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Gaines 138kV | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1493 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Hubbard | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-06-24 | 2021-01-05 |  | 2023-10-15 | Great River Energy | Hubbard | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | Hubbard 115kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1494 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Chisago | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-06-24 |  |  | 2023-10-15 | Northern States Power (Xcel Energy) | Chisago | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | Chisago 115kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1495 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Goodhue | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-06-24 |  |  | 2023-10-15 | Northern States Power (Xcel Energy) | Goodhue | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | North Rochester 161kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1496 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Olmsted | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-06-24 |  |  | 2023-10-15 | Southern Minnesota Municipal Power Agency | Olmsted | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | Byron 161kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1497 | [5 empty] | NRIS |  | 125 |  | Solar | Jefferson | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-06-25 |  |  | 2024-10-30 | American Transmission Co. LLC | Jefferson | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Concord 138 kV | 125 | 125 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1498 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Murray | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-06-25 |  |  | 2023-09-01 | Northern States Power (Xcel Energy) | Murray | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | Chanarambie 115 kV Substation | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1499 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Union | AR | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-12-22 |  |  | 2023-09-01 | Entergy Arkansas LLC | Union | AR | DPP-2020-Cycle | South | PHASE 1 | NRIS | El Dorado East - Sterlington 115 kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1500 | #REF! |  |  |  |  | NRIS |  | 150 |  | Solar | George | MS | [5 empty] | SE Greene Co 230kV substation | Cooperative Energy | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-12-23 |  |  | 2023-10-30 | Cooperative Energy | George | MS | DPP-2020-Cycle | South | PHASE 1 | NRIS | SE Greene Co 230kV substation | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1501 | [5 empty] | NRIS |  | 0 |  | Battery Storage | Sangamon | IL | [21 empty] | #DIV/0! | #DIV/0! |  |  |  |  | Withdrawn | 2020-07-06 | 2021-03-09 |  | 2023-08-31 | Ameren Illinois | Sangamon | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Auburn North 138kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1502 | [5 empty] | NRIS |  | 225 |  | Solar | Juneau | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-06 |  |  | 2023-03-31 | American Transmission Co. LLC | Juneau | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Briggs Road - North Madison 345KV | 225 | 225 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1503 | [5 empty] | NRIS |  | 150 |  | Solar | Faribault | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-06-29 |  |  | 2024-10-31 | ITC Midwest | Faribault | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | Huntley 345 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1504 | [5 empty] | NRIS |  | 150 |  | Solar | Faribault | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-06-29 |  |  | 2024-10-31 | ITC Midwest | Faribault | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | Huntley 345 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Withdrawn | Not Started | J1505 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Washington | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-06-29 | 2020-12-22 |  | 2023-09-01 | Entergy Louisiana LLC | Washington | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Talisheek - Bogalusa 230 kV Line | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Withdrawn | Not Started | J1506 | [5 empty] | NRIS |  | 100 |  | Solar | Washington | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-06-29 | 2020-12-22 |  | 2023-09-01 | Entergy Louisiana LLC | Washington | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Barkers Corner - Bogalusa 230 kV Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Withdrawn | Not Started | J1507 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Washington | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-06-29 | 2020-12-22 |  | 2023-09-01 | Entergy Louisiana LLC | Washington | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Barkers Corner - Bogalusa 230 kV Line | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  | Drop, Jefferson Davis was impacted with the hurricanes impacting the transmission system. On a standoff on repairs. | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1508 | [5 empty] | NRIS |  | 98.9 |  | Wind | Marathon | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-11 |  |  | 2023-09-01 | American Transmission Co. LLC | Marathon | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | B-54 Wien to McMillan 115KV | 98.9 | 98.9 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1509 | #REF! |  |  |  |  | NRIS |  | 100 |  | Solar | Leflore | MS | [5 empty] | Greenwood - Pickens 115 kV | Entergy Mississippi LLC | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-12-23 |  |  | 2023-09-01 | Entergy Mississippi LLC | Leflore | MS | DPP-2020-Cycle | South | PHASE 1 | NRIS | Greenwood - Pickens 115 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1510 | [5 empty] | NRIS |  | 100 |  | Solar | Wood | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-06-30 |  |  | 2023-10-01 | American Transmission Co. LLC | Wood | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Arpin 345kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1511 | [5 empty] | NRIS |  | 26 |  | Solar | Chisago | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-01 | 2021-01-05 |  | 2023-08-31 | Northern States Power (Xcel Energy) | Chisago | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | Scandia to Lawrence Creek 69kV | 26 | 26 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1512 | [5 empty] | NRIS |  | 98.9 |  | Wind | Lafayette | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-23 |  |  | 2023-09-01 | American Transmission Co. LLC | Lafayette | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Darlington 138KV | 98.9 | 98.9 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1513 | [5 empty] | NRIS |  | 300 |  | Solar | Waupaca | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-01 |  |  | 2023-10-01 | American Transmission Co. LLC | Waupaca | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Highway 22 B3 345kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1514 | #REF! |  |  |  |  | NRIS |  | 100 |  | Solar | Mississippi | AR | [5 empty] | Driver 230kV | Entergy Arkansas LLC | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-07-01 |  |  | 2023-08-31 | Entergy Arkansas LLC | Mississippi | AR | DPP-2020-Cycle | South | PHASE 1 | NRIS | Driver 230kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Withdrawn | Not Started | J1515 | [5 empty] | NRIS |  | 200 |  | Solar | Midland | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-01 | 2021-01-23 |  | 2023-10-01 | Michigan Electric Tranmission Company LLC | Midland | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Tittabawassee to Murphy 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1516 | [5 empty] | NRIS |  | 100 |  | Solar | St. Clair | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-01 |  |  | 2023-10-01 | ITC Transmission | St. Clair | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Fitz 120kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1517 | [5 empty] | NRIS |  | 40 |  | Battery Storage | Vermillion | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-03-11 |  |  | 2023-10-02 | Duke Energy Indiana | Vermillion | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Hillsdale North 230 kV | 40 | 40 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J1119 | [5 empty] | NRIS |  | 600 |  | Gas | Jackson County | MI | [27 empty] | Withdrawn | 2018-03-12 | 2019-06-10 |  | 2021-01-01 | Michigan Electric Transmission Company, LLC | Jackson County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Tompkins 345 kV Substation | 600 | 600 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1518 | [5 empty] | NRIS |  | 185 |  | Solar | Vermillion | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-03-11 |  |  | 2023-10-06 | Duke Energy Indiana | Vermillion | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Hillsdale North 230 kV | 185 | 185 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1519 | [5 empty] | NRIS |  | 200 |  | Solar | Bollinger | MO | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-02 |  |  | 2023-03-31 | Ameren Missouri | Bollinger | MO | DPP-2020-Cycle | Central | PHASE 1 | NRIS | St. Francois to Lutesville 345 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1520 | [5 empty] | NRIS |  | 135 |  | Solar | Worth | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-06 |  |  | 2024-10-31 | ITC Midwest | Worth | IA | DPP-2020-Cycle | West | PHASE 1 | NRIS | Ledyard - Colby 345 kV | 135 | 135 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1521 | [5 empty] | NRIS |  | 199.5 |  | Wind | Day | SD | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-06 |  |  | 2022-10-31 | Otter Tail Power Company | Day | SD | DPP-2020-Cycle | West | PHASE 1 | NRIS | Big Stone to Ellendale (BS3ELR) 345kV (J933) | 199.5 | 199.5 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Withdrawn | Not Started | J1522 | [5 empty] | NRIS |  | 200 |  | Solar | Muskegon | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-06 | 2020-11-30 |  | 2023-10-01 | Michigan Electric Tranmission Company LLC | Muskegon | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Grassmere 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1523 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Leflore | MS | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-12-23 |  |  | 2023-09-01 | Entergy Mississippi LLC | Leflore | MS | DPP-2020-Cycle | South | PHASE 1 | NRIS | Greenwood - Pickens 115 kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1524 | [5 empty] | NRIS |  | 200 |  | Solar | Pipestone | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-06 | 2020-11-02 |  | 2023-08-31 | Northern States Power (Xcel Energy) | Pipestone | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | Buffalo Ridge to Pipestone 115kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1525 | [5 empty] | NRIS |  | 200 |  | Solar | Huron | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-06 |  |  | 2023-10-01 | ITC Transmission | Huron | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Grassmere 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1526 | [5 empty] | NRIS |  | 200 |  | Solar | St. Clair | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-06 |  |  | 2023-10-01 | ITC Transmission | St. Clair | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Greenwood 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1527 | [5 empty] | NRIS |  | 200 |  | Solar | Ottawa | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-06 |  |  | 2023-04-01 | Michigan Electric Tranmission Company LLC | Ottawa | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Kenowa 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1528 | [5 empty] | NRIS |  | 0 |  | Battery Storage | Dunn | WI | [21 empty] | #DIV/0! | #DIV/0! |  |  |  |  | Active | 2020-07-06 |  |  | 2024-06-06 | Northern States Power (Xcel Energy) | Dunn | WI | DPP-2020-Cycle | West | PHASE 1 | NRIS | EAU CLAIRE (ENDPOINT A) TO AS KING (ENDPOINT B) 345 KV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1529 | [5 empty] | NRIS |  | 50 |  | Solar | Carroll | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-06 |  |  | 2023-09-15 |  | Carroll | IA | DPP-2020-Cycle | West | PHASE 1 | NRIS | Tap Carroll (635320) - Auburn (635328) 69 kV line at about midpoint | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1530 | [5 empty] | NRIS |  | 50 |  | Solar | Mills | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-06 |  |  | 2023-09-15 |  | Mills | IA | DPP-2020-Cycle | West | PHASE 1 | NRIS | Tap Hastings (635033) - Macedonia (635069) 69 kV line at about midpoint | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1531 | [5 empty] | NRIS |  | 200 |  | Solar | Sherburne | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-06 | 2020-10-09 |  | 2023-05-01 | Northern States Power (Xcel Energy) | Sherburne | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | Sheroc Substation 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1532 | [5 empty] | NRIS |  | 50 |  | Solar | Page | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-06 |  |  | 2023-09-15 |  | Page | IA | DPP-2020-Cycle | West | PHASE 1 | NRIS | Clarinda-Coburg 69 kV | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1533 | [5 empty] | NRIS |  | 200 |  | Solar | Adams | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-06 |  |  | 2024-06-01 | MidAmerican Energy Company | Adams | IA | DPP-2020-Cycle | West | PHASE 1 | NRIS | Creston-Adams County 161kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1534 | [5 empty] | NRIS |  | 100 |  | Solar | Olmsted | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-06 |  |  | 2023-06-01 | Southern Minnesota Municipal Power Agency | Olmsted | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | Byron 345kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1535 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Knox | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-07 | 2021-03-15 |  | 2023-09-01 | Duke Energy Indiana | Knox | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Edwardsport - Peabody Tap 138 kV Line | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Withdrawn | Not Started | J1536 | [5 empty] | NRIS |  | 150 |  | Wind | Isabella | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-07 | 2020-11-24 |  | 2024-10-31 | Michigan Electric Tranmission Company LLC | Isabella | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Summerton (1) 138 kV | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1537 | [5 empty] | NRIS |  | 150 |  | Solar | Genesee | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-12-29 |  |  | 2024-07-04 | Michigan Electric Transmission Company LLC | Genesee | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Thetford #1 - Dort 138kV T-Line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Withdrawn | Not Started | J1538 | [5 empty] | NRIS |  | 268 |  | Solar | Livingston | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-07 | 2020-09-16 |  | 2023-04-20 | Entergy Louisiana LLC | Livingston | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Hammond - Coly 230 kV | 268 | 268 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1539 | #REF! |  |  |  |  | NRIS |  | 146 |  | Solar | West Baton Rouge | LA | [5 empty] | J683 POI 138 kV | Entergy Louisiana LLC |  |  |  |  | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-07-07 |  |  | 2023-04-20 | Entergy Louisiana LLC | West Baton Rouge | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | J683 POI 138 kV | 146 | 146 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1540 | [5 empty] | NRIS |  | 200 |  | Solar | Cass | ND | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-10-19 | 2021-01-06 |  | 2024-06-01 | Northern States Power (Xcel Energy) | Cass | ND | DPP-2020-Cycle | West | PHASE 1 | NRIS | Bison-Alexandria 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Withdrawn | Not Started | J1541 | [5 empty] | NRIS |  | 200 |  | Solar | Calcasieu | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-07 | 2020-09-18 |  | 2023-10-01 | Entergy Louisiana LLC | Calcasieu | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Donaldsonville 230kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1542 | #REF! |  |  |  |  | NRIS |  | 200 |  | Solar | St. James | LA | [5 empty] | Thibodaux - Vacherie 230kV | Entergy Louisiana LLC |  |  |  |  | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-07-07 |  |  | 2023-10-01 | Entergy Louisiana LLC | St. James | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Thibodaux - Vacherie 230kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Withdrawn | Not Started | J1543 | [5 empty] | NRIS |  | 200 |  | Solar | Grand Traverse | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-07 | 2020-09-18 |  | 2023-10-01 | Michigan Electric Tranmission Company LLC | Grand Traverse | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Ludington to Keystone 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1130 | [5 empty] | NRIS |  | 1110 |  | Gas | Warren County | MS | [27 empty] | Withdrawn | 2018-03-12 | 2019-08-29 |  | 2023-05-01 | Entergy Mississippi, LLC | Warren County | MS | DPP-2018-APR | South | GIA | NRIS | Baxter Wilson SES 115/500 kV Sw YD | 966 | 1110 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J1151 | [5 empty] | NRIS |  | 252 |  | Gas | Ascension Parish | LA | [27 empty] | Withdrawn | 2018-03-12 | 2019-08-29 |  | 2020-09-01 | Entergy Louisiana, LLC | Ascension Parish | LA | DPP-2018-APR | South | GIA | NRIS | Brittany 230kV Substation | 219 | 252 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1544 | [5 empty] | NRIS |  | 200 |  | Solar | Morton | ND | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-19 |  |  | 2023-09-01 | Montana-Dakota Utilities Company | Morton | ND | DPP-2020-Cycle | West | PHASE 1 | NRIS | Mandan BN-Northwest Mandan 115kV Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Withdrawn | Not Started | J1545 | [5 empty] | NRIS |  | 0 |  | Battery Storage | Morehouse | LA | [21 empty] | #DIV/0! | #DIV/0! |  |  |  |  | Withdrawn | 2020-12-08 | 2020-12-21 |  | 2024-01-15 | Entergy Louisiana LLC | Morehouse | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Crossett North to North Bastrop 115 kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Withdrawn | Not Started | J1546 | [5 empty] | NRIS |  | 150 |  | Solar | Monroe | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-08 | 2020-11-24 |  | 2023-10-31 | ITC Transmission | Monroe | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Milan - Monroe 345 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1547 | [5 empty] | NRIS |  | 250 |  | Solar | Franklin,Hardin | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-08 | 2020-10-01 |  | 2023-09-01 | ITC Midwest | Franklin,Hardin | IA | DPP-2020-Cycle | West | PHASE 1 | NRIS | Killdeer to Blackhawk 345kV Line Tap | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1548 | [5 empty] | NRIS |  | 200 |  | Solar | Putnam | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-08 | 2020-12-18 |  | 2024-06-01 | Duke Energy Indiana | Putnam | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Amo-Edwardsport IGCC 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1549 | [5 empty] | NRIS |  | 125 |  | Solar | Clinton | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-08 | 2020-10-08 |  | 2024-06-01 | ITC Midwest | Clinton | IA | DPP-2020-Cycle | West | PHASE 1 | NRIS | Rock Creek-DeWitt 161kV line | 125 | 125 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | West | Done | In Service | J171 | [5 empty] | NRIS |  | 7 |  | Biomass | Swift County | MN | [27 empty] | Done | 2010-10-12 |  | 2015-05-27 | 2011-09-30 | Great River Energy | Swift County | MN | DPP-2012-AUG | West | DPP - SIS | NRIS | Benson 115kV Substation | 7 | 7 | Biomass | Combined Cycle | In Service | 2010-04-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1550 | [5 empty] | NRIS |  | 200 |  | Solar | Branch | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-12-29 |  |  | 2024-07-04 | Michigan Electric Transmission Company LLC | Branch | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Batavia - Tap Kinderhook distribution station, 138kV Transmission Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Withdrawn | Not Started | J1551 | [5 empty] | NRIS |  | 195 |  | Solar | Morehouse | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-12-08 | 2020-12-21 |  | 2024-01-15 | Entergy Louisiana LLC | Morehouse | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Crossett North to North Bastrop 115 kV | 195 | 195 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1552 | [5 empty] | NRIS |  | 100 |  | Solar | Jackson | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-11-20 |  |  | 2023-09-01 | Michigan Electric Transmission Company LLC | Jackson | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Blackstone to Marshall 138kV (J1310 POI) | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1553 | [5 empty] | NRIS |  | 150 |  | Solar | Clinton | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-09 |  |  | 2023-09-15 | Michigan Electric Tranmission Company LLC | Clinton | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Bingham West 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Withdrawn | Not Started | J1554 | [5 empty] | NRIS |  | 150 |  | Solar | Ionia | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-09 | 2020-11-24 |  | 2023-09-15 | Michigan Electric Tranmission Company LLC | Ionia | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | American Bumper Junction to David Junction 138Kv | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Withdrawn | Not Started | J1555 | [5 empty] | NRIS |  | 100 |  | Solar | Hillsdale | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-09 | 2020-11-24 |  | 2023-09-15 | Michigan Electric Tranmission Company LLC | Hillsdale | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Moore Road Substation 138kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Withdrawn | Not Started | J1556 | [5 empty] | NRIS |  | 200 |  | Solar | Ottawa | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-09 | 2021-02-23 |  | 2023-09-15 | Michigan Electric Tranmission Company LLC | Ottawa | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Northern Fibre 138kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1557 | [5 empty] | NRIS |  | 293 |  | Wind | Sanilac | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-01 |  |  | 2023-08-31 | ITC Transmission | Sanilac | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Greenwood to Banner 345 kV Line | 293 | 293 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1558 | #REF! |  |  |  |  | NRIS |  | 200 |  | Solar | Pope | AR | [5 empty] | Moreland - St. Vincent 161kV line | Entergy Arkansas LLC | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2021-01-14 |  |  | 2023-04-01 | Entergy Arkansas LLC | Pope | AR | DPP-2020-Cycle | South | PHASE 1 | NRIS | Moreland - St. Vincent 161kV line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1559 | #REF! |  |  |  |  | NRIS |  | 200 |  | Solar | Conway | AR | [5 empty] | Morrilton East Substation (161kV bus) | Entergy Arkansas LLC | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2021-01-14 |  |  | 2023-04-01 | Entergy Arkansas LLC | Conway | AR | DPP-2020-Cycle | South | PHASE 1 | NRIS | Morrilton East Substation (161kV bus) | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1560 | #REF! |  |  |  |  | NRIS |  | 200 |  | Solar | Iberia | LA | [5 empty] | Patoutville Substation (138kV bus) | CLECO Corporation |  |  |  |  | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2021-02-17 |  |  | 2023-04-01 | CLECO Corporation | Iberia | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Patoutville Substation (138kV bus) | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1561 | #REF! |  |  |  |  | NRIS |  | 150 |  | Solar | Acadia | LA | [5 empty] | Richard 138kV | Entergy Louisiana LLC |  |  |  |  | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-07-09 |  |  | 2023-10-30 | Entergy Louisiana LLC | Acadia | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Richard 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1562 | Blytheville |  |  |  |  | NRIS |  | 200 |  | Solar | Mississippi | AR | [5 empty] | Blytheville I-55 to AECC Blytheville North 161kV | Entergy Arkansas LLC | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2021-02-19 |  |  | 2023-09-01 | Entergy Arkansas LLC | Mississippi | AR | DPP-2020-Cycle | South | PHASE 1 | NRIS | Blytheville I-55 to AECC Blytheville North 161kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1563 | [5 empty] | NRIS |  | 200 |  | Solar | Montgomery | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-09 |  |  | 2023-04-01 | Duke Energy Indiana | Montgomery | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Wabash River - Whitesville 230kV line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1564 | #REF! |  |  |  |  | NRIS |  | 100 |  | Solar | Washington | LA | [5 empty] | Talisheek - Bogalusa 230 kV Line | Entergy Louisiana LLC |  |  |  |  | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-12-23 |  |  | 2023-09-01 | Entergy Louisiana LLC | Washington | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Talisheek - Bogalusa 230 kV Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1565 | [5 empty] | NRIS |  | 200 |  | Solar | Lawrence | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-03-11 |  |  | 2023-04-01 | Duke Energy Indiana | Lawrence | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Bedford - Columbus 345kV line (Line #34517) | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1566 | [5 empty] | NRIS |  | 150 |  | Solar | Martin | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-09 |  |  | 2023-09-01 | Southern Minnesota Municipal Power Agency | Martin | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | Rutland Substation 161kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1567 | [5 empty] | NRIS |  | 150 |  | Solar | Outagamie | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-03-12 |  |  | 2023-10-01 | American Transmission Co. LLC | Outagamie | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Werner West 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1568 | [5 empty] | NRIS |  | 100 |  | Solar | Renville | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-09 | 2021-01-05 |  | 2023-08-31 | Northern States Power (Xcel Energy) | Renville | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | Franklin 115kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1569 | [5 empty] | NRIS |  | 44 |  | Solar | Pierce | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-09 | 2021-01-05 |  | 2023-08-31 | Northern States Power (Xcel Energy) | Pierce | WI | DPP-2020-Cycle | West | PHASE 1 | NRIS | Red Wing to Herbert 69kV (Redwing - Bay City - Esdaile - Herbert) | 44 | 44 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J955 | [5 empty] | NRIS | N | 1165 |  | Gas | Sangamon County | IL |  |  |  | 1 | 1 | 4660000 | 0 | [9 empty] | 26318100 | 884000 | 0 | 884000 | 27202100 |  |  | 27202100 |  |  |  | Active | 2018-03-08 |  |  | 2021-11-01 | Ameren Transmission Company of Illinois | Sangamon County | IL | DPP-2018-APR | Central | PHASE 3 | NRIS | Austin Substation 345kV Bus | 1040 | 1165 | Gas | Combined Cycle | Not Started |  | 1165 | 1165 | 1165 | 1165
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1570 | [5 empty] | NRIS |  | 200 |  | Solar | Rock | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-09 | 2020-10-08 |  | 2023-09-01 | ITC Midwest | Rock | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | Magnolia 161 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1571 | [5 empty] | NRIS |  | 200 |  | Solar | Lenawee | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-09 |  |  | 2023-09-15 | Michigan Electric Tranmission Company LLC | Lenawee | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Morocco to Beecher 138kV (Ckt 1) | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1572 | [5 empty] | NRIS |  | 150 |  | Hybrid | Faribault | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-09 |  |  | 2023-10-15 | Northern States Power (Xcel Energy) | Faribault | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | Huntley to Blue Earth 161kV | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1573 | [5 empty] | NRIS |  | 250 |  | Solar | Portage | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-09 |  |  | 2023-09-01 | American Transmission Co. LLC | Portage | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Plover 115kV | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1574 | [5 empty] | NRIS |  | 99 |  | Hybrid | West Carroll | LA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-09 |  |  | 2023-08-01 | Entergy Louisiana LLC | West Carroll | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Darnell 115kV | 99 | 99 | Hybrid | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1575 | [5 empty] | NRIS |  | 70 |  | Wind | Kittson,Marshall | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-10 |  |  | 2025-12-01 | Otter Tail Power Company | Kittson,Marshall | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | 115 kV transmission line from Warsaw to Donaldson owned by Otter Tail Power Company | 70 | 70 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1576 | #REF! |  |  |  |  | NRIS |  | 200 |  | Solar | Washington | LA | [5 empty] | Angie to Adams Creek 230 kV | Entergy Louisiana LLC |  |  |  |  | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2021-02-17 |  |  | 2024-01-15 | Entergy Louisiana LLC | Washington | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Angie to Adams Creek 230 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1577 | #REF! |  |  |  |  | NRIS |  | 100 |  | Solar | Grant | AR | [5 empty] | Hardin West SS (Endpoint A) to Sheridan (Endpoint B) 115 kV | Entergy Arkansas LLC | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-12-21 |  |  | 2024-01-15 | Entergy Arkansas LLC | Grant | AR | DPP-2020-Cycle | South | PHASE 1 | NRIS | Hardin West SS (Endpoint A) to Sheridan (Endpoint B) 115 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1578 | [5 empty] | NRIS |  | 200 |  | Solar | Johnson | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-17 |  |  | 2023-04-01 | Duke Energy Indiana | Johnson | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Columbus -Greenwood Clark Twp 230kV line (Circuit ID 23019) | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-FEB | East (ITC) | Withdrawn | Not Started | J537 | [5 empty] | NRIS |  | 200 |  | Wind | Sanilac County | MI | [27 empty] | Withdrawn | 2015-11-16 | 2017-07-27 |  | 2017-10-01 | ITC Transmission | Sanilac County | MI | DPP-2016-FEB | East (ITC) | GIA | NRIS | 1.5 miles south of Banner 345 kV substation | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1579 | [5 empty] | NRIS |  | 200 |  | Solar | Edwards | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-01-13 |  |  | 2023-04-01 | Ameren Illinois | Edwards | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Albion-Crossville 138kV Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | J174 | [5 empty] | NRIS |  | 43.75 |  | Gas | Jefferson County | WI | [27 empty] | Done | 2010-11-12 |  | 2011-08-08 |  | American Transmission Co. LLC | Jefferson County | WI |  |  | Feasibility | NRIS | ATC University Substation | 43.75 | 43.75 | Gas | Combined Cycle | In Service | 2011-09-30 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Withdrawn | Not Started | J1580 | [5 empty] | NRIS |  | 100 |  | Solar | Ottawa | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-11-24 | 2020-11-30 |  | 2023-10-01 | Michigan Electric Transmission Company LLC | Ottawa | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Cobb - Archer Junction 138kV #2 | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1581 | [5 empty] | NRIS |  | 200 |  | Solar | Nobles | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-10 |  |  | 2023-09-01 | Northern States Power (Xcel Energy) | Nobles | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | Nobles County 345 kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1582 | [5 empty] | NRIS |  | 160 |  | Solar | St. Croix | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-17 |  |  | 2024-06-06 | Northern States Power (Xcel Energy) | St. Croix | WI | DPP-2020-Cycle | West | PHASE 1 | NRIS | Pine Lake to Three Lakes 115 kV | 160 | 160 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1583 | #REF! |  |  |  |  | NRIS |  | 200 |  | Solar | Iberville | LA | [5 empty] | Donaldsonville - Evergreen 230kV | Entergy Louisiana LLC |  |  |  |  | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-07-10 |  |  | 2023-10-01 | Entergy Louisiana LLC | Iberville | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Donaldsonville - Evergreen 230kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Withdrawn | Not Started | J1584 | [5 empty] | NRIS |  | 150 |  | Solar | Calcasieu | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-10 | 2020-09-18 |  | 2023-10-01 | Entergy Louisiana LLC | Calcasieu | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Toomey 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1585 | [5 empty] | NRIS |  | 200 |  | Solar | Moniteau | MO | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-10 |  |  | 2023-04-01 | Ameren Missouri | Moniteau | MO | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Apache Tap - Barnett 161kV line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1586 | [5 empty] | NRIS |  | 499 |  | Hybrid | Calhoun | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-10 |  |  | 2023-09-30 | Michigan Electric Tranmission Company LLC | Calhoun | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Argenta to Tompkins 345kV line | 499 | 499 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1587 | [5 empty] | NRIS |  | 100 |  | Solar | Muskegon | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-19 |  |  | 2023-09-01 | ITC Transmission | Muskegon | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Du Pont to Cobb 138 KV (J1375 POI) | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1588 | [5 empty] | NRIS |  | 200 |  | Solar | Cass | ND | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-10 |  |  | 2023-09-01 | Northern States Power (Xcel Energy) | Cass | ND | DPP-2020-Cycle | West | PHASE 1 | NRIS | Bison 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1589 | [5 empty] | NRIS |  | 150 |  | Solar | Clinton | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-11-24 |  |  | 2022-12-15 | Michigan Electric Transmission Company LLC | Clinton | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Hubbardston - Tech Drive 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1590 | [5 empty] | NRIS |  | 200 |  | Wind | Plymouth | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-10 |  |  | 2024-10-30 | MidAmerican Energy Company | Plymouth | IA | DPP-2020-Cycle | West | PHASE 1 | NRIS | O'Brien - Raun 345 kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1591 | [5 empty] | NRIS |  | 150 |  | Solar | Clay | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-10 |  |  | 2023-09-01 | Duke Energy Indiana | Clay | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Staunton 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1592 | #REF! |  |  |  |  | NRIS |  | 200 |  | Solar | Pope | AR | [5 empty] | MORRILTON EAST - Atkins 161 kV | Entergy Arkansas LLC | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2021-02-17 |  |  | 2023-04-01 | Entergy Arkansas LLC | Pope | AR | DPP-2020-Cycle | South | PHASE 1 | NRIS | MORRILTON EAST - Atkins 161 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1593 | [5 empty] | NRIS |  | 200 |  | Solar | Rush | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-10 |  |  | 2024-10-30 | Duke Energy Indiana | Rush | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Greensboro-Gwynneville 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1594 | [5 empty] | NRIS |  | 200 |  | Wind | Clark | SD | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-10 |  |  | 2023-08-01 | Otter Tail Power Company | Clark | SD | DPP-2020-Cycle | West | PHASE 1 | NRIS | Big Stone to Ellendale 345 kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Withdrawn | Not Started | J1595 | [5 empty] | NRIS |  | 100 |  | Solar | St. Martin | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-12-08 | 2021-01-05 |  | 2023-08-31 | Entergy Louisiana LLC | St. Martin | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Kirk 138kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-FEB | West | Withdrawn | Not Started | J490 | [5 empty] | NRIS |  | 60 |  | Wind | 0 | SD | [27 empty] | Withdrawn | 2015-11-11 | 2017-09-01 |  | 2017-10-01 | Montana-Dakota Utilities Company |  | SD | DPP-2016-FEB | West | GIA | NRIS | The McIntosh Substation located 0.5 miles due North of the intersection of Route 31 and Route 12, located just off Route 31. The referenced intersection is 0.73 miles NE of the city center of McIntosh, SD. | 60 | 60 | Wind | WT Wind Turbine | Not Started |  | 60 | 60 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Withdrawn | Not Started | J1596 | [5 empty] | NRIS |  | 100 |  | Solar | Waushara | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-10 | 2021-02-24 |  | 2023-10-15 | American Transmission Co. LLC | Waushara | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Sand Lake 138kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-FEB | West | Withdrawn | Withdrawn | J501 | [5 empty] | NRIS |  | 500 |  | Wind | Hancock County,Kossuth County | IA | [27 empty] | Withdrawn | 2015-11-13 | 2017-09-01 |  | 2017-07-01 | MidAmerican Energy Company | Hancock County,Kossuth County | IA | DPP-2016-FEB | West | GIA | NRIS | MEC 345 kV Kossuth County substation | 500 | 500 | Wind | WT Wind Turbine | Withdrawn | 2017-09-30 | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-FEB | West | Withdrawn | Not Started | J531 | [5 empty] | NRIS |  | 200 |  | Wind | Chickasaw County | IA | [27 empty] | Withdrawn | 2015-11-16 | 2017-09-01 |  | 2017-10-01 | ITC Midwest | Chickasaw County | IA | DPP-2016-FEB | West | GIA | NRIS | Hazleton-Adams 345kV Line | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1597 | [5 empty] | NRIS |  | 75 |  | Solar | Wadena | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-12-18 |  |  | 2023-09-01 | Great River Energy | Wadena | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | Wing River Substation 230kV | 75 | 75 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1598 | #REF! |  |  |  |  | NRIS |  | 325 |  | Solar | Calcasieu | LA | [5 empty] | Solac - Chalkley 230kV | Entergy Louisiana LLC |  |  |  |  | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-07-10 |  |  | 2023-09-15 | Entergy Louisiana LLC | Calcasieu | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Solac - Chalkley 230kV | 325 | 325 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1599 | [5 empty] | NRIS |  | 100 |  | Hybrid | Iberia | LA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-10 |  |  | 2023-09-01 | CLECO Corporation | Iberia | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Morbihan - Hopkins 138kV | 100 | 100 | Hybrid | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA-2014-MAY | 0 | Withdrawn | Not Started | PQ0001 | [5 empty] | 0 |  | 0 |  | High Voltage DC | Ralls County | MO | [27 empty] | Withdrawn | 2012-09-10 | 2017-09-07 |  | 2018-10-31 | Ameren Missouri | Ralls County | MO | SPA-2014-MAY |  | SPA - SIS |  | Maywood - Spencer Creek 345kV Substation | 0 | 0 | High Voltage DC |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-AUG | East (ITC) | Withdrawn | Not Started | J264 | [5 empty] | NRIS |  | 120.75 |  | Wind | Shiawassee County | MI | [27 empty] | Withdrawn | 2012-11-16 | 2017-10-02 |  | 2014-10-15 | Michigan Electric Transmission Company, LLC | Shiawassee County | MI | DPP-2015-AUG | East (ITC) | DPP - SIS | NRIS | Bingham - Cornell 138 kV | 120.75 | 120.75 | Wind | WT Wind Turbine | Not Started | 2021-05-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1600 | [5 empty] | NRIS |  | 40 |  | Solar | Meade | KY | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-03-12 |  |  | 2022-10-31 | Big Rivers Electric Corporation | Meade | KY | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Flaherty Tap to Custer 69kV | 40 | 40 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-AUG | West | Withdrawn | Withdrawn | J298 | [5 empty] | NRIS |  | 300 |  | Wind | Tama County | IA | [27 empty] | Withdrawn | 2013-11-13 | 2017-10-12 |  | 2015-09-01 | ITC Midwest | Tama County | IA | DPP-2015-AUG | West | DPP - SIS | NRIS | ITCM Dysart 161 kV Substation | 300 | 300 | Wind |  | Withdrawn | 2016-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1601 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Marion | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2021-03-04 | 2021-03-15 |  | 2023-09-01 | Duke Energy Indiana | Marion | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Merom - Gibson Station Tap 345 kV Line | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1602 | [5 empty] | NRIS |  | 25 |  | Battery Storage | Ouachita | LA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-10 |  |  | 2023-04-01 | Entergy Louisiana LLC | Ouachita | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Rilla 115kV substation (Same as J1239) | 25 | 25 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1603 | [5 empty] | NRIS |  | 200 |  | Solar | Otsego | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-10 |  |  | 2023-09-15 | Michigan Electric Tranmission Company LLC | Otsego | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Vantyle 138kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1604 | [5 empty] | NRIS |  | 50 |  | Solar | Henderson | KY | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-10 |  |  | 2023-08-31 | Henderson Municipal Power & Light | Henderson | KY | DPP-2020-Cycle | Central | PHASE 1 | NRIS | HMPL Substation #7 69kV | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1605 | [5 empty] | NRIS |  | 200 |  | Solar | Sherburne | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-10 |  |  | 2023-09-01 | Northern States Power (Xcel Energy) | Sherburne | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | Sherburne 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | South | Withdrawn | Not Started | J319 | [5 empty] | NRIS |  | 500 |  | High Voltage DC | Pope County | AR | [27 empty] | Withdrawn | 2013-12-19 | 2018-01-08 |  | 2018-11-01 | Entergy | Pope County | AR | DPP-2015-FEB | South | DPP - SIS | NRIS | Entergy AR ANO-Pleasant Hill 500 kV line | 500 | 500 | High Voltage DC |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1606 | [5 empty] | NRIS |  | 200 |  | Solar | Fountain | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-10 | 2020-12-15 |  | 2023-06-01 | Duke Energy Indiana | Fountain | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Attica 230kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1607 | [5 empty] | NRIS |  | 0 |  | Battery Storage | Grant | AR | [21 empty] | #DIV/0! | #DIV/0! |  |  |  |  | Active | 2020-12-21 |  |  | 2024-01-15 | Entergy Arkansas LLC | Grant | AR | DPP-2020-Cycle | South | PHASE 1 | NRIS | Hardin West SS to Sheridan 115 kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Withdrawn | Not Started | J1608 | [5 empty] | NRIS |  | 100 |  | Solar | Ingham | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-10 | 2020-11-24 |  | 2023-09-15 | Michigan Electric Tranmission Company LLC | Ingham | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Tihart to Lovejoy Junction 138kv | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1609 | [5 empty] | NRIS |  | 125 |  | Solar | St. Joseph | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-10 |  |  | 2023-09-01 | Consumers Energy Company | St. Joseph | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Simpson 138kV | 125 | 125 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1610 | [5 empty] | NRIS |  | 100 |  | Solar | Sangamon | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-03-12 |  |  | 2023-08-31 | Ameren Illinois | Sangamon | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Auburn North to Chatham Main 138kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1611 | [5 empty] | NRIS |  | 174 |  | Solar | Morrison | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-13 |  |  | 2023-09-01 | Minnesota Power (Allete Inc) | Morrison | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | Langola 115kV Tap | 174 | 174 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1612 | #REF! |  |  |  |  | NRIS |  | 100 |  | Solar | Union | AR | [5 empty] | El Dorado East - Sterlington 115 kV | Entergy Mississippi LLC | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-12-22 |  |  | 2023-09-01 | Entergy Mississippi LLC | Union | AR | DPP-2020-Cycle | South | PHASE 1 | NRIS | El Dorado East - Sterlington 115 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1613 | [5 empty] | NRIS |  | 400 |  | Wind | Cass | ND | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-13 |  |  | 2023-08-01 | Northern States Power (Xcel Energy) | Cass | ND | DPP-2020-Cycle | West | PHASE 1 | NRIS | Bison Substation 345 kV | 400 | 400 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1614 | [5 empty] | NRIS |  | 250 |  | Solar | Muskegon | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-13 |  |  | 2024-02-15 | Michigan Electric Tranmission Company LLC | Muskegon | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | White Road - Four Mile 138kV line | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1615 | [5 empty] | NRIS |  | 150 |  | Solar | Oconto | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-13 |  |  | 2023-10-01 | American Transmission Co. LLC | Oconto | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Morgan 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1616 | [5 empty] | NRIS |  | 200 |  | Solar | Knox | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-13 |  |  | 2023-08-31 | Duke Energy Indiana | Knox | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Amo to Edwardsport 345KV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1617 | [5 empty] | NRIS |  | 200 |  | Solar | Vermilion | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-13 | 2020-12-18 |  | 2023-09-15 | Ameren Illinois | Vermilion | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Bunsonville 138kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1618 | #REF! |  |  |  |  | NRIS |  | 200 |  | Solar | Ascension | LA | [5 empty] | ST. JAMES - WELCOME 230KV | Entergy Louisiana LLC |  |  |  |  | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2021-02-17 |  |  | 2023-04-01 | Entergy Louisiana LLC | Ascension | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | ST. JAMES - WELCOME 230KV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1619 | [5 empty] | NRIS |  | 160 |  | Solar | Henderson,Webster | KY | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-13 |  |  | 2023-09-01 | Big Rivers Electric Corporation | Henderson,Webster | KY | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Reid Switchyard 161kV | 160 | 160 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1620 | [5 empty] | NRIS |  | 125 |  | Solar | Pipestone | MN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-13 |  |  | 2023-09-01 | Northern States Power (Xcel Energy) | Pipestone | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | Pipestone to Split Rock 115kV | 125 | 125 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1621 | [5 empty] | NRIS |  | 400 |  | Wind | McPherson | SD | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-13 |  |  | 2023-09-01 | Otter Tail Power Company | McPherson | SD | DPP-2020-Cycle | West | PHASE 1 | NRIS | Big Stone South to Ellendale 345kV | 400 | 400 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1622 | [5 empty] | NRIS |  | 100 |  | Solar | Sheridan | ND | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-13 |  |  | 2024-06-01 | Otter Tail Power Company | Sheridan | ND | DPP-2020-Cycle | West | PHASE 1 | NRIS | Harvey-Underwood 230kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1623 | [5 empty] | NRIS |  | 200 |  | Solar | Orange | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-13 | 2020-12-18 |  | 2024-06-01 | Duke Energy Indiana | Orange | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Mitchell Lost River 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1624 | [5 empty] | NRIS |  | 100 |  | Solar | Bartholomew | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-12-29 |  |  | 2024-08-04 | Duke Energy Indiana | Bartholomew | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Columbus Denois Cr - Columbus 345 230 kV Transmission Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-FEB | West | Withdrawn | Not Started | J489 | [5 empty] | ERIS |  | 151.8 |  | Wind | Grant County,Roberts County | SD | [27 empty] | Withdrawn | 2015-11-11 | 2018-03-26 |  | 2018-09-03 | Otter Tail Power Company | Grant County,Roberts County | SD | DPP-2016-FEB | West | GIA | ERIS | 345 kV at new Tap on proposed MVP Big Stone to Ellendale line | 151.8 | 151.8 | Wind | WT Wind Turbine | Not Started |  | 151.8 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1625 | [5 empty] | NRIS |  | 150 |  | Solar | Tipton | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-12-29 |  |  | 2024-08-05 | Duke Energy Indiana | Tipton | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Kokomo - Tipton 230kV Transmission line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-FEB | West | Withdrawn | Not Started | J525 | [5 empty] | NRIS |  | 50 |  | Solar | Murray County | MN | [27 empty] | Withdrawn | 2015-11-16 | 2018-03-26 |  | 2017-09-30 | Great River Energy | Murray County | MN | DPP-2016-FEB | West | GIA | NRIS | Lake Wilson - Hadley 69 kV line | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 33 | 33 | 0 | 0
|  |  |  | DPP-2018-APR | West | Active | Not Started | J963 | [5 empty] | NRIS |  | 9 |  | Diesel | Cedar County | IA | [27 empty] | Active | 2018-03-12 |  |  | 2017-01-01 | ITC Midwest | Cedar County | IA | DPP-2018-APR | West | PHASE 3 | NRIS | Bennett (CIPCO) - Graham 69 Kv Line Tap | 9 | 9 | Diesel | IC Internal Combustion (diesel, piston) Engine | Not Started |  | 9 | 9 | 9 | 9
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1626 | [5 empty] | NRIS |  | 150 |  | Solar | Fayette | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-12-29 |  |  | 2024-08-05 | Ameren Illinois | Fayette | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Ramsey East 138kV bus | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1627 | [5 empty] | NRIS |  | 200 |  | Wind | White | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-14 | 2020-12-18 |  | 2022-08-31 | Northern Indiana Public Service Company | White | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Reynolds 345KV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1628 | [5 empty] | NRIS |  | 200 |  | Wind | White | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-14 | 2020-12-18 |  | 2022-08-31 | Northern Indiana Public Service Company | White | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Goodland to Reynolds 138KV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1629 | [5 empty] | NRIS |  | 200 |  | Solar | Columbia | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-12-29 |  |  | 2024-07-18 | American Transmission Co. LLC | Columbia | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Columbia SW YD(ALTE) - South Fond Du Lac SW YD 345 KV T-Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1630 | #REF! |  |  |  |  | NRIS |  | 150 |  | Solar | Madison | MS | [5 empty] | Gerald Andrus-Tinnin Road 230 kV | Entergy Mississippi LLC | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-07-14 |  |  | 2023-10-31 | Entergy Mississippi LLC | Madison | MS | DPP-2020-Cycle | South | PHASE 1 | NRIS | Gerald Andrus-Tinnin Road 230 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
Bayou Chicot Solar? |  |  |  | DPP-2020-Cycle | East (ATC) | Withdrawn | Not Started | J1631 | [5 empty] | NRIS |  | 200 |  | Wind | Clark | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-14 | 2020-11-24 |  | 2023-09-15 | American Transmission Co. LLC | Clark | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Stonelake to Gardner Park 345kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1632 | [5 empty] | NRIS |  | 200 |  | Solar | Caldwell | KY | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-14 |  |  | 2023-09-01 | Big Rivers Electric Corporation | Caldwell | KY | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Caldwell County - Barkley 161kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1633 | [5 empty] | NRIS |  | 0 |  | Battery Storage | Beauregard | LA | [21 empty] | #DIV/0! | #DIV/0! |  |  |  |  | Active | 2020-10-28 |  |  | 2022-03-01 | CLECO Corporation | Beauregard | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Cooper Switching - Penton Road 230 kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1634 | #REF! |  |  |  |  | NRIS |  | 100 |  | Solar | Beauregard | LA | [5 empty] | Cooper - Penton Road 230kV (J1282) | CLECO Corporation |  |  |  |  | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-07-14 |  |  | 2022-03-01 | CLECO Corporation | Beauregard | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Cooper - Penton Road 230kV (J1282) | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | East (ITC) | Withdrawn | Not Started | J444 | [5 empty] | NRIS |  | 235 |  | Gas | Wayne County | MI | [27 empty] | Withdrawn | 2015-05-07 | 2018-04-12 |  | 2017-01-31 | ITC Transmission | Wayne County | MI | DPP-2017-FEB | East (ITC) | GIA | NRIS | Waterman/Navarre 230kV | 235 | 235 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1635 | [5 empty] | NRIS |  | 100 |  | Battery Storage | Branch | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-11-13 |  |  | 2022-02-01 | Michigan Electric Transmission Company LLC | Branch | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | 138kV Michigan Ave to Newton | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1636 | [5 empty] | NRIS |  | 44 |  | Solar | Pike | MO | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-14 |  |  | 2023-09-01 | Ameren Missouri | Pike | MO | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Peno Creek Substation 161kV | 44 | 44 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1637 | [5 empty] | NRIS |  | 150 |  | Solar | Knox | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-14 |  |  | 2023-09-01 | Duke Energy Indiana | Knox | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Wheatland Substation 345kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1638 | [5 empty] | NRIS |  | 150 |  | Solar | Hancock | KY | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-14 |  |  | 2023-09-01 | Big Rivers Electric Corporation | Hancock | KY | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Skillman Substation 161kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1639 | [5 empty] | NRIS |  | 100 |  | Battery Storage | Lenawee | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-11-13 |  |  | 2022-02-01 | Michigan Electric Transmission Company LLC | Lenawee | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | 345kV Allen Junction to Morocco | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Withdrawn | Not Started | J1640 | [5 empty] | NRIS |  | 200 |  | Solar | Hinds | MS | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-14 | 2020-09-22 |  | 2023-10-31 | Entergy Mississippi LLC | Hinds | MS | DPP-2020-Cycle | South | PHASE 1 | NRIS | Beech Grove - Ray Braswell 115 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1641 | [5 empty] | NRIS |  | 150 |  | Solar | Greene | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-15 |  |  | 2023-09-01 | Hoosier Energy REC Inc | Greene | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Worthington Substation 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | CS5 | Withdrawn | Withdrawn | G620 | [5 empty] | ERIS |  | 19 |  | Wind | Goodhue County | MN | [27 empty] | Withdrawn | 2006-04-17 | 2018-04-20 | 2008-04-25 | 2018-12-31 | Northern States Power (Xcel Energy) | Goodhue County | MN |  | CS5 | DPP - SIS | ERIS | Kenyon - Dodge 69 kV | 19 | 19 | Wind | WT Wind Turbine | Withdrawn | 2009-12-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1642 | [5 empty] | NRIS |  | 200 |  | Hybrid | Spencer | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-15 |  |  | 2023-10-15 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana Inc. | Spencer | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | North East (Castle) - Culley 138kV | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Withdrawn | Not Started | J1643 | [5 empty] | NRIS |  | 50 |  | Solar | Genesee | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-15 | 2020-11-30 |  | 2023-10-01 | Michigan Electric Tranmission Company LLC | Genesee | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Delaney 138kV | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Withdrawn | Not Started | J1193 | [5 empty] | NRIS |  | 103.1 |  | Gas | Morton County | ND | [27 empty] | Withdrawn | 2019-04-22 | 2020-04-28 |  | 2023-10-01 | Montana-Dakota Utilities Co. | Morton County | ND | DPP-2019-Cycle | West | PHASE 1 | NRIS | Heskitt 115 kV Switchyard | 103.1 | 103.1 | Gas | CT Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1644 | #REF! |  |  |  |  | NRIS |  | 150 |  | Solar | St. Landry | LA | [5 empty] | Champagne 138kV | Entergy Louisiana LLC |  |  |  |  | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-07-15 |  |  | 2023-10-01 | Entergy Louisiana LLC | St. Landry | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Champagne 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1645 | [5 empty] | NRIS |  | 80 |  | Solar | Renville | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-12-23 | 2020-11-19 |  | 2023-09-01 | Great River Energy | Renville | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | Panther 230kV Substation | 80 | 80 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1646 | [5 empty] | NRIS |  | 150 |  | Solar | Newton | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-15 |  |  | 2023-10-01 | Northern Indiana Public Service Company | Newton | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Morrison Ditch 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1647 | [5 empty] | NRIS |  | 150 |  | Solar | Chippewa | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-15 | 2020-11-19 |  | 2023-09-01 | Northern States Power (Xcel Energy) | Chippewa | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | Maynard XMSN 115kV Substation | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Withdrawn | Not Started | J1648 | [5 empty] | NRIS |  | 10 |  | Hybrid | Searcy | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-15 | 2020-11-24 |  | 2021-08-15 | Entergy Arkansas LLC | Searcy | AR | DPP-2020-Cycle | South | PHASE 1 | NRIS | Searcy Price 161kV | 10 | 10 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1649 | [5 empty] | NRIS |  | 60 |  | Solar | McCracken | KY | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-03-12 |  |  | 2022-10-31 | Big Rivers Electric Corporation | McCracken | KY | DPP-2020-Cycle | Central | PHASE 1 | NRIS | McCracken County to Shell 69kV | 60 | 60 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1650 | [5 empty] | NRIS |  | 200 |  | Solar | Logan | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-16 | 2020-12-18 |  | 2023-09-15 | Ameren Illinois | Logan | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Latham 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1651 | [5 empty] | NRIS |  | 149.5 |  | Solar | Logan | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-12-16 |  |  | 2023-08-31 | Ameren Illinois | Logan | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Howlett 138 kV Substation | 149.5 | 149.5 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
| NEER |  | NEER Project | DPP-2020-Cycle | Central | Active | Not Started | J1652 | [5 empty] | NRIS |  | 116 |  | Solar | Champaign | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-03-09 |  |  | 2023-09-15 | Ameren Illinois | Champaign | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Sidney 138kV | 116 | 116 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1653 | [5 empty] | NRIS |  | 150 |  | Solar | Tazewell | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-16 |  |  | 2023-09-15 | Ameren Illinois | Tazewell | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | San Jose Rail 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1654 | [5 empty] | NRIS |  | 200 |  | Solar | Genesee | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-17 |  |  | 2023-09-01 | Michigan Electric Transmission Company LLC | Genesee | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Goss-Thetford 345kV Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1655 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Jefferson | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-16 |  |  | 2022-09-15 | Ameren Illinois | Jefferson | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | West Mt Vernon - Xenia 345kV Line (J1241) | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1207 | [5 empty] | NRIS |  | 50 |  | Gas | Branch County | MI | [27 empty] | Active | 2019-04-26 |  |  | 2021-04-01 | Michigan Electric Transmission Company, LLC | Branch County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Newton 138kV Substation | 50 | 50 | Gas | CT Combustion Turbine (Simple Cycle) | Not Started |  | 50 | 49.5 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1656 | [5 empty] | NRIS |  | 412 |  | Hybrid | Vermilion | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-03-12 |  |  | 2023-08-31 | Ameren Illinois | Vermilion | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Sydney to Bunsonville 345kV Line | 412 | 412 | Hybrid | Solar/Wind | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1657 | [5 empty] | NRIS |  | 100 |  | Solar | St. Croix | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-16 |  |  | 2022-08-01 | Northern States Power (Xcel Energy) | St. Croix | WI | DPP-2020-Cycle | West | PHASE 1 | NRIS | Pine Lake to Apple River 161 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1658 | [5 empty] | NRIS |  | 180 |  | Solar | Hillsdale | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-23 |  |  | 2023-09-01 | Michigan Electric Transmission Company LLC | Hillsdale | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Coldwater to Moore Road 138kV Line | 180 | 180 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Withdrawn | Not Started | J1206 | [5 empty] | NRIS |  | 50 |  | Gas | Branch County | MI | [27 empty] | Withdrawn | 2019-04-26 | 2021-02-10 |  | 2021-04-01 | Michigan Electric Transmission Company, LLC | Branch County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Newton 138kV Substation | 50 | 50 | Gas | CT Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1659 | [5 empty] | NRIS |  | 100 |  | Battery Storage | Washtenaw | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-11-13 |  |  | 2022-02-01 | ITC Transmission | Washtenaw | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | 120 kV Dorset | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  | Drop | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1660 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Genesee | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-19 |  |  | 2023-09-01 | Michigan Electric Transmission Company LLC | Genesee | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Goss-Thetford 345kV Line | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Withdrawn | Not Started | J1661 | [5 empty] | NRIS |  | 200 |  | Solar | Lapeer | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-16 | 2021-02-23 |  | 2023-09-01 | ITC Transmission | Lapeer | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Imlay Pump 120kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1662 | [5 empty] | NRIS |  | 200 |  | Solar | Newton | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-16 | 2020-12-18 |  | 2023-08-31 | Northern Indiana Public Service Company | Newton | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Goodland Substation 138kV (Bus Name: 17Goodland) | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | West | Done | In Service | J183 | [5 empty] | NZIS |  | 200 |  | Wind | Rock County | MN | [27 empty] | Done | 2010-11-15 |  | 2016-03-23 | 2012-12-31 | Northern States Power (Xcel Energy) | Rock County | MN | DPP-2012-AUG | West | DPP - SIS | NZIS | Split Rock Substation | 200 | 200 | Wind | WT Wind Turbine | In Service |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1213 | [5 empty] | NRIS |  | 60 |  | Hydro | Iron County | MO | [27 empty] | Active | 2019-04-27 |  |  | 2022-12-31 | Ameren Missouri | Iron County | MO | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Taum Sauk 138kV Switchyard, Bus 1 & 2 | 60 | 60 | Hydro | Hydroelectric | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1663 | [5 empty] | NRIS |  | 200 |  | Solar | Ottawa | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-16 |  |  | 2023-09-15 | Michigan Electric Tranmission Company LLC | Ottawa | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Argenta to Tallmadge 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  | Don't drop because in St. Landry | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1664 | [5 empty] | NRIS |  | 200 |  | Solar | St. Clair | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-23 |  |  | 2023-09-01 | ITC Transmission | St. Clair | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Carrigan 120kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1665 | [5 empty] | NRIS |  | 50 |  | Battery Storage | St. Clair | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-23 |  |  | 2023-09-01 | ITC Transmission | St. Clair | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Carrigan 120kV Substation | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1666 | [5 empty] | NRIS |  | 300 |  | Wind | Ingham | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-16 |  |  | 2023-04-20 | Michigan Electric Tranmission Company LLC | Ingham | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Oneida - Majestic 345 kV | 300 | 300 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1667 | [5 empty] | NRIS |  | 200 |  | Wind | Isabella,Midland | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-23 |  |  | 2023-04-20 | Michigan Electric Transmission Company LLC | Isabella,Midland | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | NRIS | Bard Rd to Clare Junction 138 kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1668 | #REF! |  |  |  |  | NRIS |  | 194 |  | Solar | Iberville | LA | [5 empty] | Donaldsonville - Evergreen 230 kV | Entergy Louisiana LLC |  |  |  |  | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-07-16 |  |  | 2023-04-20 | Entergy Louisiana LLC | Iberville | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Donaldsonville - Evergreen 230 kV | 194 | 194 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1669 | #REF! |  |  |  |  | ERIS |  | 165 |  | Solar | Jefferson Davis | LA | [5 empty] | LC Bulk to Henning 138kV Line (Circuit 28) | Entergy Louisiana LLC |  |  |  |  | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-12-22 |  |  | 2023-09-01 | Entergy Louisiana LLC | Jefferson Davis | LA | DPP-2020-Cycle | South | PHASE 1 | ERIS | LC Bulk to Henning 138kV Line (Circuit 28) | 165 | 165 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1670 | #REF! |  |  |  |  | NRIS |  | 50 |  | Solar | Mississippi | AR | [5 empty] | Crooked Lake 161kV at J586 POI | Entergy Arkansas LLC | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-12-23 |  |  | 2022-08-31 | Entergy Arkansas LLC | Mississippi | AR | DPP-2020-Cycle | South | PHASE 1 | NRIS | Crooked Lake 161kV at J586 POI | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1671 | #REF! |  |  |  |  | ERIS |  | 150 |  | Solar | Walker | TX | [5 empty] | Rocky Creek to Lewis Creek 230kV | Entergy Texas Inc | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-12-23 |  |  | 2023-08-31 | Entergy Texas Inc | Walker | TX | DPP-2020-Cycle | South | PHASE 1 | ERIS | Rocky Creek to Lewis Creek 230kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1672 | #REF! |  |  |  |  | NRIS |  | 150 |  | Solar | Hinds | MS | [5 empty] | Tinnin Road 230kV | Entergy Mississippi LLC | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-07-16 |  |  | 2023-08-31 | Entergy Mississippi LLC | Hinds | MS | DPP-2020-Cycle | South | PHASE 1 | NRIS | Tinnin Road 230kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1673 | #REF! |  |  |  |  | NRIS |  | 200 |  | Solar | Sabine | LA | [5 empty] | Fisher to Mansfield Compressor 230 kV | CLECO Corporation |  |  |  |  | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-12-21 |  |  | 2024-01-15 | CLECO Corporation | Sabine | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Fisher to Mansfield Compressor 230 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Withdrawn | Not Started | J1674 | [5 empty] | NRIS |  | 250 |  | Hybrid | St. Tammany | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-12-08 | 2020-12-21 |  | 2023-08-02 | Entergy Louisiana LLC | St. Tammany | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Talisheek - North Slidell 230kV Line | 250 | 250 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1675 | [5 empty] | NRIS |  | 250 |  | Wind | Edgar | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-12-23 | 2021-02-12 |  | 2023-12-15 | Ameren Transmission Company of Illinois | Edgar | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Kansas 345kV | 250 | 250 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1676 | [5 empty] | NRIS |  | 300 |  | Wind | McLean | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-03-11 |  |  | 2023-04-20 | Ameren Illinois | McLean | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Brokaw - Clinton 345 kV line | 300 | 300 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1677 | [5 empty] | NRIS |  | 180 |  | Solar | Macon | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-03-12 |  |  | 2023-04-20 | Ameren Illinois | Macon | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Leghorn 345 kV | 180 | 180 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1678 | [5 empty] | NRIS |  | 74.7 |  | Battery Storage | Miami | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-16 |  |  | 2023-08-01 | Duke Energy Indiana | Miami | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Deedsville 345 kV | 74.7 | 74.7 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1679 | [5 empty] | NRIS |  | 125 |  | Solar | Clay | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-17 |  |  | 2023-04-20 | Ameren Illinois | Clay | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Xenia - West Mt Vernon 345 kV | 125 | 125 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | Pre-Transition SIS | CS5 | Withdrawn | Withdrawn | G549 | [5 empty] | NRIS |  | 20 |  | Wind | Pope County | MN | [27 empty] | Withdrawn | 2005-09-21 | 2018-06-26 | 2012-03-13 | 2018-12-31 | Great River Energy | Pope County | MN | Pre-Transition SIS | CS5 | DPP - SIS | NRIS | Next to Williams Substation (69 kV) | 20 | 20 | Wind | WT Wind Turbine | Withdrawn | 2008-12-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1680 | [5 empty] | NRIS |  | 100 |  | Solar | Cass | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-17 |  |  | 2023-04-20 | Duke Energy Indiana | Cass | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | 345 kV Walton Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1229 | [5 empty] | NRIS |  | 50 |  | Hydro | Muscatine County | IA | [27 empty] | Active | 2019-04-29 |  |  | 2023-10-30 | MidAmerican Energy Company | Muscatine County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Sub 92 345 kV Substation | 50 | 50 | Hydro | Hydroelectric | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1681 | [5 empty] | NRIS |  | 200 |  | Solar | Maries | MO | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-17 |  |  | 2024-10-31 | Ameren Missouri | Maries | MO | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Bland to Franks 345kV line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1682 | [5 empty] | NRIS |  | 300 |  | Solar | Boone | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-17 | 2020-12-18 |  | 2024-10-01 | Duke Energy Indiana | Boone | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Hortonville to Whitestown 345 kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | WEST | Done | In Service | J191 | [5 empty] | NRIS |  | 101.2 |  | Wind | Cass County | IA | [27 empty] | Done | 2010-12-28 |  | 2015-05-04 | 2011-12-22 | MidAmerican Energy Company | Cass County | IA | DPP-2012-AUG | WEST | Network Upgrade | NRIS | Rolling Hills 345 kV Substation | 101.2 | 101.2 | Wind | WT Wind Turbine | In Service | 2012-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1683 | [5 empty] | NRIS |  | 75 |  | Battery Storage | Porter | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-17 | 2020-12-14 |  | 2023-08-01 | Northern Indiana Public Service Company | Porter | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Babcock - Lake George 345 kV | 75 | 75 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1684 | [5 empty] | NRIS |  | 200 |  | Solar | Starke | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-17 |  |  | 2023-04-20 | Northern Indiana Public Service Company | Starke | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | ROLLIN SCHAFER -BURR OAK 345KV LINE | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Withdrawn | Not Started | J1685 | [5 empty] | NRIS |  | 250 |  | Hybrid | Ascension,Assumption | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-17 | 2020-09-24 |  | 2023-09-30 | Entergy Louisiana LLC | Ascension,Assumption | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Donaldsonville to Evergreen 230kV line | 250 | 250 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1686 | [5 empty] | NRIS |  | 100 |  | Hybrid | Evangeline | LA | [5 empty] | Coughlin - Plaisance 138 kV | CLECO Corporation | [14 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-17 |  |  | 2023-09-04 | CLECO Corporation | Evangeline | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Coughlin - Plaisance 138 kV | 100 | 100 | Hybrid | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | Central | Done | In Service | J196 | [5 empty] | NRIS |  | 50 |  | Wind | Vermilion County | IL | [27 empty] | Done | 2011-02-07 |  | 2013-09-09 | 2014-12-31 | Ameren Illinois | Vermilion County | IL | DPP-2012-AUG | Central | DPP - SIS | NRIS | Vermillion 138 kV Substation | 50 | 50 | Wind | WT Wind Turbine | In Service | 2013-11-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1687 | [5 empty] | NRIS |  | 160 |  | Solar | Decatur | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-12-22 |  |  | 2023-09-15 | Hoosier Energy REC Inc | Decatur | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Decatur Switching Station 161kv | 160 | 160 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1688 | [5 empty] | NRIS |  | 200 |  | Solar | Champaign | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-17 | 2020-10-02 |  | 2023-09-15 | Ameren Illinois | Champaign | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Rising 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1689 | [5 empty] | NRIS |  | 150 |  | Solar | Henry | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-17 | 2020-12-18 |  | 2023-09-15 | Duke Energy Indiana | Henry | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Cadiz 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | West | Done | In Service | J200 | [5 empty] | NRIS |  | 99 |  | Gas | Morton County | ND | [27 empty] | Done | 2011-02-15 |  | 2012-07-30 | 2014-05-20 | Montana-Dakota Utilities Company | Morton County | ND | DPP-2012-AUG | West | DPP - SIS | NRIS | RM Heskett Station 115 kV & 41.6 kV | 75 | 99 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2016-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2013-FEB | East (ITC) | Done | In Service | J201 | [5 empty] | NRIS |  | 20 |  | Wind | Bay County | MI | [27 empty] | Done | 2011-02-16 |  | 2013-09-04 | 2012-12-01 | Michigan Electric Transmission Company, LLC | Bay County | MI | DPP-2013-FEB | East (ITC) | DPP - SIS | NRIS | METC Manning 138kV Substation | 20 | 20 | Wind | WT Wind Turbine | In Service | 2013-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | MI | Done | In Service | J202 | [5 empty] | NRIS |  | 101 |  | Wind | Tuscola County | MI | [27 empty] | Done | 2011-02-16 |  | 2013-05-01 | 2013-11-30 | ITC Transmission | Tuscola County | MI | DPP-2012-AUG | MI | DPP - SIS | NRIS | ITC Atlanta - Tuscola 115 kV | 101 | 101 | Wind | WT Wind Turbine | In Service | 2014-10-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1246 |  |  | Scoping Calls, Julie Friedberg | Kindle Energy |  | NRIS |  | 725.2 |  | Gas | Iberville Parish | LA | [27 empty] | Active | 2019-04-29 |  |  | 2023-10-31 | Entergy Louisiana, LLC | Iberville Parish | LA | DPP-2019-Cycle | South | PHASE 2 | NRIS | Bayou Labutte 500kV Substation | 725.2 | 725.2 | Gas | Combined Cycle | Not Started |  | 705 | 705 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Withdrawn | Not Started | J414 | [5 empty] | NRIS |  | 120 |  | Wind | Freeborn County | MN | [27 empty] | Withdrawn | 2014-11-14 | 2018-10-12 |  | 2019-07-01 | ITC Midwest | Freeborn County | MN | DPP-2016-AUG | West | GIA | NRIS | Freeborn 161kV Substation on the Hayword - Freeborn - Winnebago 161kV line | 120 | 120 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Withdrawn | Not Started | J415 | [5 empty] | NRIS |  | 200 |  | Wind | Franklin County | IA | [27 empty] | Withdrawn | 2014-11-14 | 2018-10-12 |  | 2019-07-01 | MidAmerican Energy Company | Franklin County | IA | DPP-2016-AUG | West | GIA | NRIS | New 345 kV Switchyard on the ROW of the proposed 345 kV Emery - Blackhawk line (MVP4) | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Withdrawn | Not Started | J439 | [5 empty] | NRIS |  | 500 |  | Wind | Emmet County | IA | [27 empty] | Withdrawn | 2015-03-16 | 2018-10-12 |  | 2016-12-01 | MidAmerican Energy Company | Emmet County | IA | DPP-2016-AUG | West | GIA | NRIS | Dickens, IA 51333 at O'Brien to Kossuth 345 kV | 500 | 500 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Withdrawn | Not Started | J459 | [5 empty] | NRIS |  | 200 |  | Wind | Grant County | SD | [27 empty] | Withdrawn | 2015-05-18 | 2018-10-12 |  | 2017-09-30 | Otter Tail Power Company | Grant County | SD | DPP-2016-AUG | West | GIA | NRIS | Big Stone Brookings 345kV | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Withdrawn | Not Started | J511 | [5 empty] | NRIS |  | 200 |  | Wind | Oliver County | ND | [27 empty] | Withdrawn | 2015-11-16 | 2018-10-12 |  | 2017-09-01 | Great River Energy | Oliver County | ND | DPP-2016-AUG | West | GIA | NRIS | GRE Stanton Substation 230 kV bus, Stanton ND | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2017-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1247 |  |  | Scoping Calls, Carl St. Cin | Apex Power |  | ERIS |  | 16.98 |  | Waste Heat Recovery | St. Mary,St. Mary Parish | LA | [27 empty] | Active | 2019-04-29 |  |  | 2020-08-01 | CLECO Corporation | St. Mary,St. Mary Parish | LA | DPP-2019-Cycle | South | PHASE 2 | ERIS | Ivanhoe 138kV Substation | 16.98 | 16.98 | Waste Heat Recovery | CC (cogen) | Not Started | 2021-10-31 | 30.98 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1690 | [5 empty] | NRIS |  | 125 |  | Solar | Henry | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-17 | 2021-03-15 |  | 2023-09-15 | Duke Energy Indiana | Henry | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Lewisville 138kV | 125 | 125 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1249 |  |  | Scoping Calls, Bret Hariel | Cooperative Energy |  | NRIS |  | 600 |  | Gas | Lamar County | MS | [27 empty] | Active | 2019-04-29 |  |  | 2022-03-01 | Cooperative Energy | Lamar County | MS | DPP-2019-Cycle | South | PHASE 2 | NRIS | Morrow 161 kV Substation | 600 | 600 | Gas | Combined Cycle | Not Started |  | 600 | 600 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1691 | [5 empty] | NRIS |  | 200 |  | Solar | Sullivan | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-17 |  |  | 2023-06-01 | Hoosier Energy REC Inc | Sullivan | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Merom 345kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1692 | [5 empty] | NRIS |  | 65 |  | Battery Storage | Cass | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-17 | 2020-12-03 |  | 2023-06-01 | Duke Energy Indiana | Cass | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Walton 345 kV Substation | 65 | 65 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1693 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Chippewa | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-17 | 2020-11-19 |  | 2023-09-01 | Northern States Power (Xcel Energy) | Chippewa | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | Maynard XMSN 115kV Substation | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1694 | [5 empty] | NRIS |  | 100 |  | Solar | Lawrence | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-17 | 2020-12-18 |  | 2024-06-01 | Duke Energy Indiana | Lawrence | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Lost River 345kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1695 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Perry | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-19 |  |  | 2023-09-01 | Ameren Illinois | Perry | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Aster 138kV Substation (Rebuild of North Coulterville 138kV) | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1696 | [5 empty] | NRIS |  | 150 |  | Solar | Henderson | KY | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-17 |  |  | 2023-10-01 | Big Rivers Electric Corporation | Henderson | KY | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Reid 161kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Active | Not Started | J1262 | [5 empty] | ERIS |  | 25 |  | Gas | Wayne County | MI | [27 empty] | Active | 2019-04-29 |  |  | 2019-06-01 | ITC Transmission | Wayne County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | ERIS | Waterman 120kV Substation | 25 | 25 | Gas | Combined Cycle | Not Started |  | 25 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1697 | [5 empty] | NRIS |  | 200 |  | Solar | Jackson | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-03-11 |  |  | 2023-04-01 | Duke Energy Indiana | Jackson | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Bedford - Seymour 138kV line (Line#13829) | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Withdrawn | Not Started | J1698 | [5 empty] | NRIS |  | 150 |  | Hybrid | St. Tammany | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-12-08 | 2020-12-21 |  | 2023-08-02 | Entergy Louisiana LLC | St. Tammany | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Talisheek - North Slidell 230kV Line | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1699 | [5 empty] | NRIS |  | 43 |  | Solar | Shelby | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-12-23 |  |  | 2024-10-01 | Hoosier Energy REC Inc | Shelby | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | HE Lewis Creek 69 kV | 43 | 43 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1700 | [5 empty] | NRIS |  | 288 |  | Solar | Johnson | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-17 | 2020-10-22 |  | 2023-04-30 | Duke Energy Indiana | Johnson | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | FRANKLIN 230KV | 288 | 288 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1701 | [5 empty] | NRIS |  | 200 |  | Wind | McDonough | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-03-09 |  |  | 2023-09-15 | Ameren Illinois | McDonough | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Macomb to Ipava 138kV line | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1702 | [5 empty] | NRIS |  | 300 |  | Wind | Macon,Shelby | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-17 | 2020-12-14 |  | 2023-04-20 | Ameren Transmission Company of Illinois | Macon,Shelby | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Faraday 345 kV | 300 | 300 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1703 | [5 empty] | NRIS |  | 74 |  | Solar | Webster | KY | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-12-23 |  |  | 2023-09-01 | Big Rivers Electric Corporation | Webster | KY | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Reid to Hopkins County 161kV | 74 | 74 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | MI | Done | In Service | J226 | [5 empty] | NRIS |  | 70 |  | Hydro | Mason County | MI | [27 empty] | Done | 2011-09-27 |  | 2013-06-19 | 2015-05-22 | Michigan Electric Transmission Company, LLC | Mason County | MI | DPP-2012-AUG | MI | DPP - SIS | NRIS | Ludington Substation | 70 | 70 | Hydro | PS Hydraulic Turbine - Reversible (pumped storage) | In Service | 2013-01-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | MI | Done | In Service | J227 | [5 empty] | NRIS |  | 70 |  | Hydro | Mason County | MI | [27 empty] | Done | 2011-09-27 |  | 2013-06-19 | 2016-05-27 | Michigan Electric Transmission Company, LLC | Mason County | MI | DPP-2012-AUG | MI | DPP - SIS | NRIS | Ludington Substation | 70 | 70 | Hydro | PS Hydraulic Turbine - Reversible (pumped storage) | In Service | 2015-09-30 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | MI | Done | Under Construction | J228 | [5 empty] | NRIS |  | 70 |  | Hydro | Mason County | MI | [27 empty] | Done | 2011-09-27 |  | 2013-06-19 | 2017-05-26 | Michigan Electric Transmission Company, LLC | Mason County | MI | DPP-2012-AUG | MI | DPP - SIS | NRIS | Ludington Substation | 70 | 70 | Hydro | PS Hydraulic Turbine - Reversible (pumped storage) | Under Construction | 2014-05-24 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | MI | Done | In Service | J229 | [5 empty] | NRIS |  | 70 |  | Hydro | Mason County | MI | [27 empty] | Done | 2011-09-27 |  | 2013-06-19 | 2017-05-26 | Michigan Electric Transmission Company, LLC | Mason County | MI | DPP-2012-AUG | MI | DPP - SIS | NRIS | Ludington Substation | 70 | 70 | Hydro | PS Hydraulic Turbine - Reversible (pumped storage) | In Service | 2015-05-22 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | MI | Done | Under Construction | J230 | [5 empty] | NRIS |  | 70 |  | Hydro | Mason County | MI | [27 empty] | Done | 2011-09-27 |  | 2013-06-19 | 2018-05-25 | Michigan Electric Transmission Company, LLC | Mason County | MI | DPP-2012-AUG | MI | DPP - SIS | NRIS | Ludington Substation | 70 | 70 | Hydro | PS Hydraulic Turbine - Reversible (pumped storage) | Under Construction | 2016-05-27 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | MI | Done | In Service | J231 | [5 empty] | NRIS |  | 70 |  | Hydro | Mason County | MI | [27 empty] | Done | 2011-09-27 |  | 2013-06-19 | 2019-05-24 | Michigan Electric Transmission Company, LLC | Mason County | MI | DPP-2012-AUG | MI | DPP - SIS | NRIS | Ludington Substation | 70 | 70 | Hydro | PS Hydraulic Turbine - Reversible (pumped storage) | In Service | 2017-05-26 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | 0 | Done | In Service | J232 | [5 empty] | NRIS |  | 35 |  | Coal | Randolph County | IL | [27 empty] | Done | 2011-11-09 |  | 2013-11-01 | 2013-09-01 | Ameren Illinois | Randolph County | IL | DPP-2012-AUG |  | Network Upgrade | NRIS | Baldwin Station | 35 | 35 | Coal | Combined Cycle | In Service | 2018-05-25 | 0 | 0 | 0 | 0
|  |  |  | DPP-2013-AUG | West | Done | In Service | J233 | [5 empty] | NRIS |  | 700 |  | Combined Cycle | Marshall County | IA | [27 empty] | Done | 2011-11-14 |  | 2016-01-20 | 2016-03-01 | ITC Midwest | Marshall County | IA | DPP-2013-AUG | West | Network Upgrade | NRIS | ITC Midwest Marshalltown 161 (Sutherland) Substation | 635 | 700 | Combined Cycle | CT Combined-Cycle Combustion ? Turbine Part | In Service | 2018-06-28 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1704 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Shelby | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-19 |  |  | 2023-09-01 | Duke Energy Indiana | Shelby | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Gwynneville 345kV Substation | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | J235 | [5 empty] | NRIS |  | 110 |  | Wind | Huron County | MI | [27 empty] | Done | 2011-11-15 |  | 2013-05-30 | 2015-03-31 | ITC Transmission | Huron County | MI |  |  | Optional | NRIS | Bauer - Rapson 345 kV | 110 | 110 | Wind | WT Wind Turbine | In Service | 2016-05-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Withdrawn | Not Started | J1705 | [5 empty] | NRIS |  | 200 |  | Solar | Columbia | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-17 | 2021-02-23 |  | 2024-02-20 | American Transmission Co. LLC | Columbia | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | South Fond du Lac (Endpoint A) to Columbia (Endpoint B) 345 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1706 | [5 empty] | NRIS |  | 100 |  | Solar | Green | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-17 |  |  | 2025-06-01 | American Transmission Co. LLC | Green | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | North Monroe 138 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | Central | Done | In Service | J238 | [5 empty] | NRIS |  | 725 |  | Gas | Morgan County | IN | [27 empty] | Done | 2012-01-09 |  | 2013-08-29 | 2017-04-30 | Indianapolis Power & Light Company | Morgan County | IN | DPP-2012-AUG | Central | DPP - SIS | NRIS | Eagle Valley 138kV Substation | 725 | 725 | Gas | Combined Cycle | In Service | 2018-08-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2013-FEB | Central | Done | Withdrawn | J239 | [5 empty] | NRIS |  | 200 |  | Coal | Morgan County | IL | [27 empty] | Done | 2012-01-09 |  | 2015-06-04 | 2019-12-27 | Ameren Illinois | Morgan County | IL | DPP-2013-FEB | Central | Network Upgrade | NRIS | Merdosia Unit 4 | 200 | 200 | Coal | Combined Cycle | Withdrawn | 2019-05-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1707 | [5 empty] | NRIS |  | 72 |  | Solar | Dubois | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-17 |  |  | 2023-04-20 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana Inc. | Dubois | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | DUFF 345KV | 72 | 72 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | East (ATC) | Done | In Service | J241 | [5 empty] | NRIS |  | 3.7 |  | Hydro | Florence County | WI | [27 empty] | Done | 2012-04-02 |  | 2013-05-08 | 2016-04-01 | American Transmission Co. LLC | Florence County | WI | DPP-2012-AUG | East (ATC) | DPP - SIS | NRIS | Twin Falls Substation | 3.7 | 3.7 | Hydro | OT Other | In Service |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | MI | Done | In Service | J242 | [5 empty] | NRIS |  | 12.8 |  | Landfill Gas | Macomb County | MI | [27 empty] | Done | 2012-05-04 |  | 2013-02-11 | 2011-10-14 | ITC Transmission | Macomb County | MI | DPP-2012-AUG | MI | DPP - SIS | NRIS | Jewell - Spokane - St. Claire 120 kV | 12.8 | 12.8 | Landfill Gas | IC Internal Combustion (diesel, piston) Engine | In Service | 2016-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1708 | [5 empty] | NRIS |  | 75 |  | Solar | Grant | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-17 |  |  | 2025-06-01 | American Transmission Co. LLC | Grant | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | J947 Interconnection Substation | 75 | 75 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1709 | [5 empty] | NRIS |  | 100 |  | Battery Storage | Grimes | TX | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-12-23 |  |  | 2022-02-01 | Entergy Texas Inc | Grimes | TX | DPP-2020-Cycle | South | PHASE 1 | NRIS | 138 kV Grimes | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1710 | #REF! |  |  |  |  | NRIS |  | 300 |  | Solar | Lee | AR | [5 empty] | Entergy Keo-Memphis 500kV Line Tap | Entergy Arkansas LLC | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-12-23 |  |  | 2023-09-13 | Entergy Arkansas LLC | Lee | AR | DPP-2020-Cycle | South | PHASE 1 | NRIS | Entergy Keo-Memphis 500kV Line Tap | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-FEB | East (ITC) | Done | In Service | J246 | [5 empty] | NRIS |  | 7 |  | Wind | Gratiot County | MI | [27 empty] | Done | 2012-05-21 |  | 2014-09-22 | 2014-10-17 | Michigan Electric Transmission Company, LLC | Gratiot County | MI | DPP-2014-FEB | East (ITC) | DPP - SIS | NRIS | Nelson Road - Goss 345 kV | 7 | 7 | Wind | WT Wind Turbine | In Service | 2015-06-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Withdrawn | Not Started | J1711 | [5 empty] | NRIS |  | 100 |  | Solar | Green | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-20 | 2020-11-30 |  | 2023-09-01 | American Transmission Co. LLC | Green | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | North Monroe 138kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | PQ0002 | [5 empty] | NRIS |  | 2000 |  | High Voltage DC | Cerro Gordo County | IA | [27 empty] | Withdrawn | 2015-08-11 | 2018-12-11 |  | 2021-12-31 | ITC Midwest | Cerro Gordo County | IA |  |  |  | NRIS | Killdeer 345 kV Substation | 2000 | 2000 | High Voltage DC | OT Other | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | West | Done | In Service | J249 | [5 empty] | NRIS Only |  | 180 |  | Wind | Dickey County | ND | [27 empty] | Done | 2012-07-02 |  | 2013-12-12 |  | Montana-Dakota Utilities Company | Dickey County | ND | DPP-2012-AUG | West | DPP - SIS | NRIS Only | MDU Tatanka Substation | 180 | 180 | Wind | WT Wind Turbine | In Service | 2012-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1712 | [5 empty] | NRIS |  | 300 |  | Solar | Perry | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-20 |  |  | 2022-12-15 | Ameren Illinois | Perry | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | North Coulterville - COMM 345kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1713 | [5 empty] | NRIS |  | 147.19 |  | Wind | Macon | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-20 | 2021-02-12 |  | 2022-08-01 | Ameren Transmission Company of Illinois | Macon | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Faraday (138 kV) | 147.19 | 147.19 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1714 | [5 empty] | NRIS |  | 100 |  | Solar | Fayette | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-19 |  |  | 2023-09-01 | Ameren Illinois | Fayette | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Ramsey East 138kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1715 | [5 empty] | NRIS |  | 145 |  | Solar | Decatur | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-21 | 2020-12-18 |  | 2023-09-15 | Hoosier Energy REC Inc | Decatur | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | HE Westport 138kV | 145 | 145 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1716 | [5 empty] | NRIS |  | 100 |  | Solar | Fond du Lac | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-19 |  |  | 2022-08-01 | American Transmission Co. LLC | Fond du Lac | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Fitzgerald to South Fond Du Lac 345 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2013-FEB | Central | Done | In Service | J256 | [5 empty] | ERIS |  | 8 |  | Gas | Marshall County | IN | [27 empty] | Done | 2012-10-15 |  | 2014-05-28 | 2014-09-01 | Northern Indiana Public Service Company | Marshall County | IN | DPP-2013-FEB | Central | Int FaS | ERIS | NIPSCO Plymouth 69kV | 8 | 8 | Gas | IC Internal Combustion (diesel, piston) Engine | In Service | 2015-10-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1717 | [5 empty] | NRIS |  | 150 |  | Solar | Decatur | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-21 | 2020-12-18 |  | 2023-09-15 | Duke Energy Indiana | Decatur | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Greensburg 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Not Started | J258 | [5 empty] | NRIS |  | 1 |  | Diesel | Stearns County | MN | [27 empty] | Done | 2012-10-30 |  | 2012-11-20 | 2013-04-01 | -- No Company -- | Stearns County | MN |  |  |  | NRIS | Melrose East 69kV Substation | 1 | 1 | Diesel | IC Internal Combustion (diesel, piston) Engine | Not Started | 2013-07-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1718 | [5 empty] | NRIS |  | 200 |  | Wind | Vermilion | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-21 | 2020-09-18 |  | 2023-09-15 | Ameren Illinois | Vermilion | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Bunsonville 345kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1719 | [5 empty] | NRIS |  | 100 |  | Solar | Waushara | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-23 |  |  | 2023-09-01 | American Transmission Co. LLC | Waushara | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Sand Lake 138kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1720 | [5 empty] | NRIS |  | 99 |  | Solar | Columbia | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-12-29 |  |  | 2024-05-20 | American Transmission Co. LLC | Columbia | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Fountain Prairie -North Randolph 138kV Transmission Line | 99 | 99 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2013-FEB | West | Done | In Service | J262 | [5 empty] | NRIS |  | 100 |  | Wind | Stutsman County | ND | [27 empty] | Done | 2013-01-07 |  | 2014-12-07 | 2015-11-30 | Otter Tail Power Company | Stutsman County | ND | DPP-2013-FEB | West | Network Upgrade | NRIS | OTP Jamestown 345/115 kV substation | 100 | 100 | Wind | WT Wind Turbine | In Service | 2014-10-27 | 0 | 0 | 0 | 0
|  |  |  | DPP-2013-FEB | West | Done | In Service | J263 | [5 empty] | NRIS |  | 100 |  | Wind | Stutsman County | ND | [27 empty] | Done | 2013-01-07 |  | 2014-12-07 | 2015-11-30 | Otter Tail Power Company | Stutsman County | ND | DPP-2013-FEB | West | Network Upgrade | NRIS | OTP Jamestown 345/115 kV Substation | 100 | 100 | Wind | WT Wind Turbine | In Service | 2014-10-27 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1721 | [5 empty] | NRIS |  | 175.12 |  | Solar | Vigo | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-03-12 |  |  | 2023-06-01 | Duke Energy Indiana | Vigo | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Vigo-Worthington 138kV | 175.12 | 175.12 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1722 | #REF! |  |  |  |  | NRIS |  | 100 |  | Solar | Lonoke | AR | [5 empty] | Galloway - Remigton 115kV Transmission Line | Entergy Arkansas LLC | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-12-29 |  |  | 2024-02-09 | Entergy Arkansas LLC | Lonoke | AR | DPP-2020-Cycle | South | PHASE 1 | NRIS | Galloway - Remigton 115kV Transmission Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1723 | [5 empty] | NRIS |  | 10 |  | Battery Storage | Cross | AR | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-21 |  |  | 2023-04-01 | Entergy Arkansas LLC | Cross | AR | DPP-2020-Cycle | South | PHASE 1 | NRIS | Wynne East to Wynne South 161kV line (J1125 sub) | 10 | 10 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1724 | [5 empty] | NRIS |  | 150 |  | Solar | LaPorte | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-03-09 |  |  | 2023-09-15 | Northern Indiana Public Service Company | LaPorte | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | LNG - STILLWELL 138kV line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1725 | [5 empty] | NRIS |  | 100 |  | Wind | Tazewell | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-21 |  |  | 2024-09-01 | Ameren Illinois | Tazewell | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | San Jose Rail Switching Station 138KV | 100 | 100 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1726 | [5 empty] | NRIS |  | 200 |  | Solar | Pulaski | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-21 |  |  | 2023-10-01 | Northern Indiana Public Service Company | Pulaski | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Reynolds - Burr 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1727 | [5 empty] | NRIS |  | 33.75 |  | Wind | Hancock | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-21 | 2020-10-08 |  | 2023-12-01 | ITC Midwest | Hancock | IA | DPP-2020-Cycle | West | PHASE 1 | NRIS | Lime Creek 161kV | 33.75 | 33.75 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1728 | [5 empty] | NRIS Only |  | 39 |  | Wind | Story | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-21 | 2020-10-08 |  | 2023-12-01 | ITC Midwest | Story | IA | DPP-2020-Cycle | West | PHASE 1 | NRIS Only | Story County Substation 161kV | 39 | 39 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1729 | [5 empty] | NRIS Only |  | 43 |  | Wind | Hancock | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-21 | 2020-10-08 |  | 2023-12-01 | ITC Midwest | Hancock | IA | DPP-2020-Cycle | West | PHASE 1 | NRIS Only | Lime Creek 161kV | 43 | 43 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1730 | [5 empty] | NRIS |  | 300 |  | Solar | Dunn | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-21 |  |  | 2024-06-06 | Northern States Power (Xcel Energy) | Dunn | WI | DPP-2020-Cycle | West | PHASE 1 | NRIS | Eau Claire to AS King 345 kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2013-AUG | West | Done | In Service | J274 | [5 empty] | NRIS |  | 100 |  | Wind | Madison County | IA | [27 empty] | Done | 2013-03-14 |  | 2015-01-09 | 2014-08-18 | MidAmerican Energy Company | Madison County | IA | DPP-2013-AUG | West | Network Upgrade | NRIS | Winterset. - Creston 161 kV | 100 | 100 | Wind | WT Wind Turbine | In Service | 2014-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1731 | [5 empty] | NRIS |  | 100 |  | Battery Storage | Madison | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2021-03-01 | 2021-03-12 |  | 2022-02-01 | Indianapolis Power Light Company | Madison | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Noblesville to Fall Creek 345 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-FEB | Central | Done | Withdrawn | J276 | [5 empty] | NRIS Only |  | 150 |  | Wind | Iroquois County | IL | [27 empty] | Done | 2013-03-18 |  | 2015-02-19 | 2019-12-31 | Ameren Illinois | Iroquois County | IL | DPP-2014-FEB | Central | DPP - SIS | NRIS Only | Sheldon South | 150 | 150 | Wind | BS Battery Storage | Withdrawn | 2014-08-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1732 | [5 empty] | NRIS |  | 98.4 |  | Solar | Columbia | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-19 |  |  | 2024-12-31 | American Transmission Co. LLC | Columbia | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | LEWISTON ACEC A03-TRIENDA (138KV ) | 98.4 | 98.4 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2013-AUG | West | Done | In Service | J278 | [5 empty] | NRIS |  | 200 |  | Wind | Mower County | MN | [27 empty] | Done | 2013-03-18 |  | 2014-07-17 | 2015-10-15 | Great River Energy | Mower County | MN | DPP-2013-AUG | West | Network Upgrade | NRIS | 161 kV bus at the Pleasant Valley Station | 200 | 200 | Wind | WT Wind Turbine | In Service | 2014-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2013-AUG | West | Done | In Service | J279 | [5 empty] | NRIS |  | 30 |  | Coal | Woodbury County | IA | [27 empty] | Done | 2013-03-18 |  | 2016-01-19 | 2016-01-01 | MidAmerican Energy Company | Woodbury County | IA | DPP-2013-AUG | West | Network Upgrade | NRIS | Raun 345 kV Substation | 30 | 30 | Coal | ST Steam Turbine (including nuclear, geothermal and solar steam, | In Service | 2016-11-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1733 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Allamakee | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-21 |  |  | 2025-06-01 | ITC Midwest | Allamakee | IA | DPP-2020-Cycle | West | PHASE 1 | NRIS | Lansing 161 kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1734 | [5 empty] | NRIS |  | 150 |  | Solar | Lee | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-21 |  |  | 2025-06-01 | ITC Midwest | Lee | IA | DPP-2020-Cycle | West | PHASE 1 | NRIS | Wever 161 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1735 | [5 empty] | NRIS |  | 75 |  | Solar | Rock | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-17 |  |  | 2025-06-01 | American Transmission Co. LLC | Rock | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | J1304 POI 138 kV Substation | 75 | 75 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1736 | [5 empty] | NRIS |  | 100 |  | Solar | Dubois | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-21 |  |  | 2023-08-31 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana Inc. | Dubois | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Duff 138kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1737 | [5 empty] | NRIS |  | 210 |  | Solar | 0 | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-21 |  |  | 2023-04-20 | Duke Energy Indiana |  | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Gwynville 345 kV | 210 | 210 | Solar |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | West | Done | In Service | J285 | [5 empty] | NRIS |  | 250 |  | Wind | O'Brien County | IA | [27 empty] | Done | 2013-05-20 |  | 2016-05-09 | 2016-10-01 | MidAmerican Energy Company | O'Brien County | IA | DPP-2014-AUG | West | DPP - SIS | NRIS | Proposed O'Brien County 345kV substation | 250 | 250 | Wind | WT Wind Turbine | In Service | 2017-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1738 | [5 empty] | NRIS |  | 20 |  | Hybrid | McPherson | SD | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-21 | 2020-12-02 |  | 2023-05-15 | Montana-Dakota Utilities Company | McPherson | SD | DPP-2020-Cycle | West | PHASE 1 | NRIS | Leola Substation 41.6kV | 20 | 20 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Withdrawn | Not Started | J1739 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Waushara | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2021-02-19 | 2021-02-23 |  | 2023-09-01 | American Transmission Co. LLC | Waushara | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Sand Lake 138kV Substation | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1740 | [5 empty] | NRIS |  | 100 |  | Solar | Walworth | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-21 |  |  | 2023-09-01 | American Transmission Co. LLC | Walworth | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | University to Mukwanago 138kV Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | West | Done | In Service | J289 | [5 empty] | NRIS |  | 20 |  | Wind | Madison County | IA | [27 empty] | Done | 2013-07-11 |  | 2016-02-29 | 2014-08-18 | MidAmerican Energy Company | Madison County | IA | DPP-2014-AUG | West | DPP - SIS | NRIS | 161 kV sybstation on Winterset Junction to Creston 161 kV Line | 20 | 20 | Wind | WT Wind Turbine | In Service | 2013-11-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2013-AUG | West | Done | In Service | J290 | [5 empty] | NRIS |  | 150 |  | Wind | Rolette County | ND | [27 empty] | Done | 2013-08-05 |  | 2014-07-16 | 2015-10-15 | Northern States Power (Xcel Energy) | Rolette County | ND | DPP-2013-AUG | West | DPP - SIS | NRIS | 230 kV Rugby to Glenboro | 150 | 150 | Wind | WT Wind Turbine | In Service | 2014-08-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-AUG | Central | Done | In Service | J291 | [5 empty] | NRIS |  | 45 |  | Gas | Scott County | IL | [27 empty] | Done | 2013-08-12 |  | 2016-04-25 | 2016-05-13 | Prairie Power, Inc. | Scott County | IL | DPP-2015-AUG | Central | DPP - SIS | NRIS | PPI Alsey 138kV Substation | 42 | 45 | Gas | Combined Cycle | In Service | 2016-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-FEB | West | Done | In Service | J292 | [5 empty] | External NRIS |  | 3576 |  | Hydro | Churchill | 0 | [27 empty] | Done | 2013-08-13 |  | 2015-09-01 |  | Manitoba Hydro | Churchill |  | DPP-2014-FEB | West | DPP - SIS | External NRIS | Limestone, Long Spruce and Kettle Generating Statiosn | 3576 | 3576 | Hydro | HY Hydraulic Turbine (including turnbines associated with delive | In Service | 2016-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1741 | [5 empty] | NRIS |  | 270 |  | Solar | Cass | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-21 | 2020-12-03 |  | 2023-06-01 | Duke Energy Indiana | Cass | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Walton 345kV Substation | 270 | 270 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1742 | [5 empty] | NRIS |  | 294.1 |  | Solar | Porter | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-21 | 2020-12-14 |  | 2023-08-01 | Northern Indiana Public Service Company | Porter | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Babcock - Lake George 345 kV | 294.1 | 294.1 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1743 | [5 empty] | NRIS |  | 292.89 |  | Solar | Miami | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-21 |  |  | 2023-08-01 | Duke Energy Indiana | Miami | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Deedsville 345 kV Substation | 292.89 | 292.89 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1744 | [5 empty] | NRIS |  | 149.5 |  | Solar | Cumberland | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-21 |  |  | 2023-08-01 | Ameren Illinois | Cumberland | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Hutsonville - Neoga 138 kV | 149.5 | 149.5 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1745 | [5 empty] | NRIS |  | 100 |  | Solar | Winnebago | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-21 |  |  | 2025-06-01 | American Transmission Co. LLC | Winnebago | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Fitzgerald 138 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1746 | [5 empty] | NRIS |  | 150 |  | Solar | Columbia | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-21 |  |  | 2025-06-01 | American Transmission Co. LLC | Columbia | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Columbia 138 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | West | Done | Under Construction | J299 | [5 empty] | ERIS |  | 73 |  | Combined Cycle | Blue Earth County | MN | [27 empty] | Done | 2013-11-18 |  | 2016-09-08 | 2007-05-01 | Northern States Power (Xcel Energy) | Blue Earth County | MN | DPP-2015-FEB | West | DPP - SIS | ERIS | Wilmarth Substation | 0 | 73 | Combined Cycle | Combined Cycle | Under Construction | 2018-10-10 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1747 | #REF! |  |  |  |  | NRIS |  | 50 |  | Solar | Madison | MS | [5 empty] | J830 POI | Entergy Mississippi LLC | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-12-23 |  |  | 2022-02-28 | Entergy Mississippi LLC | Madison | MS | DPP-2020-Cycle | South | PHASE 1 | NRIS | J830 POI | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | East (ITC) | Done | In Service | J301 | [5 empty] | NRIS |  | 101 |  | Wind | Tuscola County | MI | [27 empty] | Done | 2013-11-18 |  | 2016-07-06 | 2015-09-01 | ITC Transmission | Tuscola County | MI | DPP-2015-FEB | East (ITC) | Int FaS | NRIS | ITCs Bauer-Rapson 345kV line | 101 | 101 | Wind | WT Wind Turbine | In Service | 2017-07-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Done | In Service | J302 | [5 empty] | NRIS |  | 101.2 |  | Wind | Emmons County,Logan County | ND | [27 empty] | Done | 2013-11-18 |  | 2019-12-16 | 2019-09-20 | Montana-Dakota Utilities Company | Emmons County,Logan County | ND | DPP-2016-AUG | West | GIA | NRIS | 230kV Heskett-Wishek | 101.2 | 101.2 | Wind | WT Wind Turbine | In Service | 2019-11-15 | 100 | 100 | 100 | 100
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1748 | #REF! |  |  |  |  | NRIS |  | 100 |  | Solar | DeSoto | MS | [5 empty] | Twinkletown 230 kV | Entergy Mississippi LLC | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-12-23 |  |  | 2023-08-15 | Entergy Mississippi LLC | DeSoto | MS | DPP-2020-Cycle | South | PHASE 1 | NRIS | Twinkletown 230 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1749 | [5 empty] | NRIS |  | 50 |  | Hybrid | West Baton Rouge | LA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-09-24 |  |  | 2022-08-01 | Entergy Louisiana LLC | West Baton Rouge | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Addis - Big Cajun 230kV | 50 | 50 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1750 | [5 empty] | NRIS |  | 149.69 |  | Solar | Marquette | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-18 |  |  | 2023-08-01 | American Transmission Co. LLC | Marquette | MI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Huron - Empire 138kV line | 149.69 | 149.69 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1751 | [5 empty] | NRIS |  | 150.5 |  | Solar | Wood | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-22 |  |  | 2023-08-01 | American Transmission Co. LLC | Wood | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | ACEC Badger West - Saratoga 138 kV | 150.5 | 150.5 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1752 | [5 empty] | NRIS |  | 148.1 |  | Solar | Portage | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-19 |  |  | 2023-08-01 | American Transmission Co. LLC | Portage | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Golden Sands 138 kV Substation | 148.1 | 148.1 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Withdrawn | Not Started | J1753 | [5 empty] | NRIS |  | 300 |  | Solar | Green | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-22 | 2020-12-01 |  | 2024-06-01 | American Transmission Co. LLC | Green | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Columbia-South Fond du Lac 345kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1754 | [5 empty] | NRIS |  | 200 |  | Wind | McHenry | ND | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-19 |  |  | 2023-04-01 | Great River Energy | McHenry | ND | DPP-2020-Cycle | West | PHASE 1 | NRIS | McHenry ND | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1755 | [5 empty] | NRIS |  | 147.19 |  | Wind | Bureau | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-22 | 2021-02-12 |  | 2022-08-01 | Ameren Illinois | Bureau | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Bureau County 138 kV | 147.19 | 147.19 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1756 | [5 empty] | NRIS |  | 309 |  | Hybrid | Shelby | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-12-23 |  |  | 2023-03-31 | Indianapolis Power Light Company | Shelby | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Gwynneville to Sunnyside 345kV | 309 | 309 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Withdrawn | Not Started | J457 | [5 empty] | NRIS |  | 150 |  | Wind | Dickey County | ND | [27 empty] | Withdrawn | 2015-05-18 | 2019-01-14 |  | 2017-09-15 | Montana-Dakota Utilities Company | Dickey County | ND | DPP-2016-AUG | West | GIA | NRIS | Merricourt Substation | 150 | 150 | Wind | WT Wind Turbine | Not Started | 2016-02-01 | 150 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1757 | [5 empty] | NRIS |  | 300 |  | Wind | Coles | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-22 | 2020-12-14 |  | 2023-04-20 | Ameren Transmission Company of Illinois | Coles | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Kansas - Faraday 345 kV | 300 | 300 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1758 | [5 empty] | NRIS |  | 42 |  | Wind | Barnes | ND | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-22 | 2020-10-08 |  | 2023-12-01 | Northern States Power (Xcel Energy) | Barnes | ND | DPP-2020-Cycle | West | PHASE 1 | NRIS | Pillsburry Substation 230kV | 42 | 42 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1759 | [5 empty] | NRIS |  | 0 |  | Battery Storage | Sabine | LA | [21 empty] | #DIV/0! | #DIV/0! |  |  |  |  | Active | 2020-12-21 |  |  | 2024-01-15 | CLECO Corporation | Sabine | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Fisher to Mansfield Compressor 230 kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | West | Done | In Service | J316 | [5 empty] | NRIS |  | 150 |  | Wind | Dickey County | ND | [27 empty] | Done | 2013-11-18 |  | 2016-08-30 | 2017-09-01 | Montana-Dakota Utilities Company | Dickey County | ND | DPP-2014-AUG | West | DPP - SIS | NRIS | MDU 230 kV Tatanka-Ellendale line | 150 | 150 | Wind | WT Wind Turbine | In Service | 2016-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1760 | #REF! |  |  |  |  | NRIS |  | 250 |  | Solar | Liberty | TX | [5 empty] | Timberland 230kV | Entergy Texas Inc | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-07-22 |  |  | 2023-10-01 | Entergy Texas Inc | Liberty | TX | DPP-2020-Cycle | South | PHASE 1 | NRIS | Timberland 230kV | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1761 | [5 empty] | External NRIS |  | 39 |  | Wind | Barnes | ND | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-22 | 2020-10-08 |  | 2023-12-01 | Northern States Power (Xcel Energy) | Barnes | ND | DPP-2020-Cycle | West | PHASE 1 | External NRIS | Maple River 230kV | 39 | 39 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Withdrawn | Not Started | J1762 | [5 empty] | NRIS |  | 22.5 |  | Solar | Iron | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-22 | 2021-02-19 |  | 2023-09-15 | American Transmission Co. LLC | Iron | MI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Crystal Falls - Aspen 69 kV | 22.5 | 22.5 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | West | Done | In Service | J320 | [5 empty] | ERIS |  | 55 |  | Gas | Ramsey County | MN | [27 empty] | Done | 2014-01-13 |  | 2016-02-16 | 2016-03-01 | Xcel Energy | Ramsey County | MN | DPP-2014-AUG | West | DPP - SIS | ERIS | Xcel's existing High Bridge 115 kV substation | 0 | 55 | Gas | Combined Cycle | In Service | 2016-11-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1763 | [5 empty] | NRIS Only |  | 33 |  | Wind | Cavalier | ND | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-22 | 2020-10-08 |  | 2023-12-01 | Otter Tail Power Company | Cavalier | ND | DPP-2020-Cycle | West | PHASE 1 | NRIS Only | Langdon Substation 115kV | 33 | 33 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1764 | [5 empty] | NRIS |  | 125 |  | Solar | Perry | MO | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-22 | 2020-12-01 |  | 2023-09-01 | Wabash Valley Power | Perry | MO | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Seminary/Perryville 138kV | 125 | 125 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1765 | [5 empty] | NRIS |  | 150 |  | Solar | Tipton | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-22 |  |  | 2023-10-01 | Duke Energy Indiana | Tipton | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Tipton Substation 230kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1766 | [5 empty] | NRIS |  | 20 |  | Hybrid | Fallon | MT | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-22 |  |  | 2023-10-15 | Montana-Dakota Utilities Company | Fallon | MT | DPP-2020-Cycle | West | PHASE 1 | NRIS | Keystone XL (Pumping station - 14) - 115kV | 20 | 20 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | East (ITC) | Done | In Service | J325 | [5 empty] | ERIS |  | 4 |  | Wind | Huron County | MI | [27 empty] | Done | 2014-03-12 |  | 2015-06-08 | 2015-06-01 | ITC Transmission | Huron County | MI | DPP-2014-AUG | East (ITC) | DPP - SIS | ERIS | ITC Minden Station | 4 | 4 | Wind | WT Wind Turbine | In Service | 2016-03-04 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1767 | [5 empty] | NRIS Only |  | 37 |  | Wind | Hancock | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-22 | 2020-10-08 |  | 2023-12-01 | ITC Midwest | Hancock | IA | DPP-2020-Cycle | West | PHASE 1 | NRIS Only | Burt to Emery 161kV | 37 | 37 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | East (ITC) | Done | In Service | J327 | [5 empty] | NRIS |  | 150 |  | Wind | Huron County | MI | [27 empty] | Done | 2014-03-17 |  | 2015-06-05 | 2016-07-15 | ITC Transmission | Huron County | MI | DPP-2014-AUG | East (ITC) | DPP - SIS | NRIS | Raphson 120kV substation | 150 | 150 | Wind | WT Wind Turbine | In Service | 2018-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | South | Done | In Service | J328 | [5 empty] | NRIS Only |  | 160 |  | Gas | Jefferson County | AR | [27 empty] | Done | 2014-03-20 |  | 2015-08-04 | 2015-08-04 | Entergy | Jefferson County | AR | DPP-2014-AUG | South | DPP - SIS | NRIS Only | 5301 Fairfield Rd, Pine Bluff, AR | 160 | 160 | Gas | CC (cogen) | In Service | 2016-08-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | West | Done | Under Construction | J329 | [5 empty] | NRIS |  | 55 |  | Hydro | Marion County | IA | [27 empty] | Done | 2014-04-17 |  | 2016-04-22 | 2017-08-01 | Cedar Falls Utilities | Marion County | IA | DPP-2014-AUG | West | DPP - SIS | NRIS | Pella West Substation | 55 | 55 | Hydro |  | Under Construction | 2019-05-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1768 | [5 empty] | NRIS |  | 200 |  | Solar | Orange | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-23 | 2020-12-18 |  | 2023-04-01 | Duke Energy Indiana | Orange | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Lost River Substation 345 | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1769 | [5 empty] | NRIS |  | 120 |  | Wind | Howard | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-03-12 |  |  | 2023-10-01 | Dairyland Power Cooperative | Howard | IA | DPP-2020-Cycle | West | PHASE 1 | NRIS | Beaver Creek to Rice 161 kV line tap (same POI as J898) | 120 | 120 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1770 | [5 empty] | ERIS |  | 150 |  | Wind | 0 | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-23 |  |  | 2024-10-31 | Ameren Illinois |  | IL | DPP-2020-Cycle | Central | PHASE 1 | ERIS | Hoopston 138kV | 150 | 150 | Wind |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | Central | Done | Retired | J333 | [5 empty] | NRIS |  | 170 |  | Coal | Vigo County | IN | [27 empty] | Done | 2014-05-16 |  | 2014-11-20 |  | Duke Energy Corporation | Vigo County | IN | DPP-2014-AUG | Central | DPP - SIS | NRIS | Wabash River 230 kV Bus | 170 | 170 | Coal | IGCC | Retired | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | Central | Done | Retired | J334 | [5 empty] | NRIS |  | 180 |  | Coal | Vigo County | IN | [27 empty] | Done | 2014-05-16 |  | 2014-11-20 |  | Duke Energy Corporation | Vigo County | IN | DPP-2014-AUG | Central | DPP - SIS | NRIS | Wabash River 138 kV Bus | 180 | 180 | Coal | IGCC | Retired | 2010-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | West | Active | Not Started | J1359 | [5 empty] | NRIS |  | 95 |  | Gas | Linn County | IA | [27 empty] | Active | 2019-04-29 |  |  | 2022-03-01 | ITC Midwest | Linn County | IA | DPP-2019-Cycle | West | PHASE 1 | NRIS | Oakridge 69 kV Substation | 95 | 95 | Gas | CT Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1771 | [5 empty] | NRIS |  | 197.3 |  | Solar | Cumberland | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-23 | 2021-03-15 |  | 2023-08-01 | Ameren Illinois | Cumberland | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Casey - Sullivan 345 kV | 197.3 | 197.3 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1772 | [5 empty] | NRIS |  | 200 |  | Solar | White | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-23 |  |  | 2023-08-31 | Northern Indiana Public Service Company | White | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Reynolds 345KV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1773 | [5 empty] | NRIS |  | 300 |  | Wind | Iowa,Lafayette | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-23 |  |  | 2024-04-15 | American Transmission Co. LLC | Iowa,Lafayette | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Hill Valley to Cardinal 345kV | 300 | 300 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | Central | Done | In Service | J339 | [5 empty] | NRIS Only |  | 96 |  | Gas | Ford County | IL | [27 empty] | Done | 2014-05-16 |  | 2016-01-14 | 1999-01-01 | Ameren Illinois | Ford County | IL | DPP-2014-AUG | Central | DPP - SIS | NRIS Only | Gibson City South Substation | 68 | 96 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2016-10-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | East (ITC) | Done | In Service | J340 | [5 empty] | NRIS |  | 100 |  | Wind | Huron County | MI | [27 empty] | Done | 2014-05-16 |  | 2015-08-26 | 2017-09-01 | ITC Transmission | Huron County | MI | DPP-2014-AUG | East (ITC) | DPP - SIS | NRIS | Harvest Wind Tap on Cosmo-Bad Axe 120 kv line | 100 | 100 | Wind | WT Wind Turbine | In Service | 2016-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1774 | [5 empty] | NRIS Only |  | 50 |  | Wind | Warren | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-23 |  |  | 2023-05-01 | Duke Energy Indiana | Warren | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS Only | Cayuga 345kV | 50 | 50 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Withdrawn | Not Started | J1775 | [5 empty] | NRIS |  | 150 |  | Solar | Calumet | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-23 | 2020-11-11 |  | 2023-12-01 | American Transmission Co. LLC | Calumet | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Forest Junction Substation 345kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | West | Done | In Service | J343 | [5 empty] | NRIS |  | 150 |  | Wind | Adams County | IA | [27 empty] | Done | 2014-05-19 |  | 2016-05-09 | 2015-10-01 | MidAmerican Energy Company | Adams County | IA | DPP-2014-AUG | West | DPP - SIS | NRIS | 161 kv substation on Creston-Clarinda line | 150 | 150 | Wind | WT Wind Turbine | In Service | 2016-08-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | West | Done | In Service | J344 | [5 empty] | NRIS |  | 169 |  | Wind | Mahaska County | IA | [27 empty] | Done | 2014-05-19 |  | 2016-06-17 | 2017-07-01 | ITC Midwest | Mahaska County | IA | DPP-2014-AUG | West | DPP - SIS | NRIS | 161 kV substation on Poweshiek-Oskaloosa line | 169 | 169 | Wind | WT Wind Turbine | In Service | 2017-10-28 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1776 | [5 empty] | NRIS Only |  | 34 |  | Wind | Osceola | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-23 | 2020-10-08 |  | 2023-12-01 | ITC Midwest | Osceola | IA | DPP-2020-Cycle | West | PHASE 1 | NRIS Only | Dickinson County Switch Yard 161kV | 34 | 34 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ATC) | Active | Not Started | J1370 | [5 empty] | NRIS |  | 50 |  | Gas | Chippewa County | MI | [27 empty] | Active | 2019-04-29 |  |  | 2021-03-01 | American Transmission Co. LLC | Chippewa County | MI | DPP-2019-Cycle | East (ATC) | PHASE 2 | NRIS | 9 Mile SW STA - Dafter 69kV Line | 50 | 50 | Gas | CT Combustion Turbine (Simple Cycle) | Not Started |  | 50 | 50 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1777 | [5 empty] | NRIS |  | 100 |  | Solar | Perry | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-23 |  |  | 2023-09-01 | Ameren Illinois | Perry | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Aster 138kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | South | Done | In Service | J348 | [5 empty] | NRIS |  | 81 |  | Solar | Arkansas County | AR | [27 empty] | Done | 2014-05-19 |  | 2015-09-14 | 2017-09-01 | Entergy | Arkansas County | AR | DPP-2014-AUG | South | Network Upgrade | NRIS | Entergy Stuttgart Rcuskey-Almyra115 kv line | 81 | 81 | Solar | BS Battery Storage | In Service | 2016-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1778 | [5 empty] | NRIS |  | 100 |  | Solar | Kenosha | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-23 |  |  | 2024-10-31 | American Transmission Co. LLC | Kenosha | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Paris 138 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1779 | [5 empty] | NRIS |  | 200 |  | Solar | Dane | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-17 |  |  | 2024-10-31 | American Transmission Co. LLC | Dane | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Rockdale 345kV substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-FEB | Central | Done | Under Construction | J351 | [5 empty] | NRIS |  | 715 |  | Gas | St. Joseph County | IN | [27 empty] | Done | 2014-05-19 |  |  | 2018-05-01 | Northern Indiana Public Service Company | St. Joseph County | IN | DPP-2016-FEB | Central | GIA | NRIS | Stillwell 345 kV | 705 | 715 | Gas | Combined Cycle | Under Construction | 2020-03-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1780 | [5 empty] | NRIS |  | 200 |  | Solar | Montgomery | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-23 |  |  | 2023-08-15 | Duke Energy Indiana | Montgomery | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Linden Tap - Crawfordsville 138kV Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1781 | [5 empty] | NRIS |  | 300 |  | Wind | Iowa,Lafayette | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-23 |  |  | 2024-04-15 | American Transmission Co. LLC | Iowa,Lafayette | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Hill Valley 345kV | 300 | 300 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | East (ITC) | Done | In Service | J354 | [5 empty] | NRIS |  | 52 |  | Wind | Huron County | MI | [27 empty] | Done | 2014-05-19 |  | 2015-07-21 | 2016-08-11 | ITC Transmission | Huron County | MI | DPP-2014-AUG | East (ITC) | DPP - SIS | NRIS | ITC Grassmere | 52 | 52 | Wind | WT Wind Turbine | In Service | 2018-04-25 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1782 | [5 empty] | NRIS |  | 150 |  | Solar | Montgomery | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-23 |  |  | 2023-09-01 | Duke Energy Indiana | Montgomery | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | WABASH RIVER GEN. STA. TO WHITESVILLE SOUTH SUB 230kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1783 | [5 empty] | NRIS |  | 150 |  | Solar | Montgomery | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-23 |  |  | 2023-09-01 | Duke Energy Indiana | Montgomery | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | WABASH RIVER GEN. STA. TO WHITESVILLE SOUTH SUB 230 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J458 | [5 empty] | NRIS |  | 200 |  | Wind | Clark County | SD | [27 empty] | Withdrawn | 2015-05-18 | 2019-04-09 |  | 2019-09-30 | Otter Tail Power Company | Clark County | SD | DPP-2017-FEB | West | GIA | NRIS | On proposed Big Stone-Ellendale 345 kV line approx. 76 miles west of Big Stone | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J522 | [5 empty] | NRIS |  | 20 |  | Battery Storage | Mower County | MN | [27 empty] | Withdrawn | 2015-11-16 | 2019-04-09 |  | 2019-09-15 | ITC Midwest | Mower County | MN | DPP-2017-FEB | West | GIA | NRIS | Adams substation at 69 kV | 20 | 20 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1784 | [5 empty] | NRIS |  | 39 |  | Solar | Henry | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-23 |  |  | 2023-09-01 | Duke Energy Indiana | Henry | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | New Castle to Hagerstown 69 kV | 39 | 39 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1785 | [5 empty] | NRIS |  | 100 |  | Solar | LaPorte | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-17 |  |  | 2024-07-12 | Northern Indiana Public Service Company | LaPorte | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Maple 69 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1786 | [5 empty] | NRIS |  | 200 |  | Solar | Sullivan | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-23 |  |  | 2023-06-01 | Hoosier Energy REC Inc | Sullivan | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Merom 345kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Withdrawn | Not Started | J1787 | [5 empty] | NRIS |  | 0 |  | Battery Storage | Hinds | MS | [21 empty] | #DIV/0! | #DIV/0! |  |  |  |  | Withdrawn | 2020-07-23 | 2020-10-08 |  | 2023-10-31 | Entergy Mississippi LLC | Hinds | MS | DPP-2020-Cycle | South | PHASE 1 | NRIS | Beech Grove - Ray Braswell 115 kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Withdrawn | Not Started | J1788 | [5 empty] | NRIS |  | 120 |  | Solar | St. Mary | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-24 | 2020-09-24 |  | 2023-02-28 | CLECO Corporation | St. Mary | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Caneland 230 kV | 120 | 120 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1789 | #REF! |  |  |  |  | NRIS |  | 5.99 |  | Solar | Monroe | AR | [5 empty] | Brinkley East to Clarendon 115 kV | Entergy Arkansas LLC | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-12-21 |  |  | 2021-10-01 | Entergy Arkansas LLC | Monroe | AR | DPP-2020-Cycle | South | PHASE 1 | NRIS | Brinkley East to Clarendon 115 kV | 5.99 | 5.99 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1790 | [5 empty] | NRIS |  | 0 |  | Battery Storage | Ashley | AR | [21 empty] | #DIV/0! | #DIV/0! |  |  |  |  | Active | 2020-10-16 |  |  | 2022-03-01 | Entergy Arkansas LLC | Ashley | AR | DPP-2020-Cycle | South | PHASE 1 | NRIS | Crossett - Monticello East 115 kV Line | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1791 | [5 empty] | NRIS |  | 0 |  | Battery Storage | Madison | MS | [21 empty] | #DIV/0! | #DIV/0! |  |  |  |  | Active | 2020-10-16 |  |  | 2023-10-31 | Entergy Mississippi LLC | Madison | MS | DPP-2020-Cycle | South | PHASE 1 | NRIS | Gerald Andrus-Tinnin Road 230 kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Withdrawn | Not Started | J1792 | [5 empty] | NRIS |  | 22.5 |  | Solar | Houghton | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-24 | 2021-02-19 |  | 2023-09-15 | American Transmission Co. LLC | Houghton | MI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | New Tap of the Ontonagan to Rockland Jct 69kV Line approx. 2.2 mi. north of Rockland Jct. | 22.5 | 22.5 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1793 | [5 empty] | NRIS |  | 75 |  | Solar | Sheboygan | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-24 |  |  | 2025-06-01 | American Transmission Co. LLC | Sheboygan | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Holland 138 kV | 75 | 75 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1794 | #REF! |  |  |  |  | ERIS |  | 150 |  | Solar | Acadia | LA | [5 empty] | Richard to Scott 138kV line | Entergy Louisiana LLC |  |  |  |  | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-12-23 |  |  | 2023-08-31 | Entergy Louisiana LLC | Acadia | LA | DPP-2020-Cycle | South | PHASE 1 | ERIS | Richard to Scott 138kV line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1795 | #REF! |  |  |  |  | ERIS |  | 100 |  | Solar | Acadia | LA | [5 empty] | Bayou Cove to Richard 138kV (Circuit 258) | Entergy Louisiana LLC |  |  |  |  | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-12-22 |  |  | 2023-08-31 | Entergy Louisiana LLC | Acadia | LA | DPP-2020-Cycle | South | PHASE 1 | ERIS | Bayou Cove to Richard 138kV (Circuit 258) | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | Central | Done | Withdrawn | J371 | [5 empty] | External NRIS |  | 2325 |  | Nuclear | Ogle County | IL | [27 empty] | Done | 2014-06-24 |  | 2016-02-26 |  | Commonwealth Edison Company | Ogle County | IL | DPP-2014-AUG | Central | DPP - SIS | External NRIS | Byron Substation | 2300 | 2325 | Nuclear | Nuclear | Withdrawn | 2016-03-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1796 | Bayout Chicot Solar |  |  |  |  | NRIS |  | 150 |  | Solar | Evangeline | LA | [5 empty] | Pine Prairie to Coughlin 138 kV | CLECO Corporation |  |  |  |  | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-08-03 |  |  | 2023-02-28 | CLECO Corporation | Evangeline | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Pine Prairie to Coughlin 138 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | South | Done | In Service | J373 | [5 empty] | NRIS Only |  | 71.5 |  | Gas | St. Mary,St. Mary Parish | LA | [27 empty] | Done | 2014-06-30 |  | 2016-02-26 | 2015-10-08 | CLECO Corporation | St. Mary,St. Mary Parish | LA | DPP-2014-AUG | South | DPP - SIS | NRIS Only | Near Morgan City Substation on 138 kV side | 64.51 | 71.5 | Gas | Combined Cycle | In Service | 2016-03-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | Central | Done | In Service | J374 | [5 empty] | External NRIS |  | 30 |  | Landfill Gas | Bucks County | PA | [27 empty] | Done | 2014-07-03 |  | 2016-02-26 |  | PECO Energy Company | Bucks County | PA | DPP-2014-AUG | Central | DPP - SIS | External NRIS | Fairless Hills Power Plant | 30 | 30 | Landfill Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2014-11-17 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1797 | #REF! |  |  |  |  | NRIS |  | 100 |  | Solar | St. John the Baptist | LA | [5 empty] | Waterford 230kV | Entergy Louisiana LLC |  |  |  |  | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-07-24 |  |  | 2023-10-31 | Entergy Louisiana LLC | St. John the Baptist | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Waterford 230kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | South | Done | In Service | J376 | [5 empty] | NRIS Only |  | 1270 |  | Gas | Union County | AR | [27 empty] | Done | 2014-07-07 |  | 2015-05-27 | 2015-05-27 | Entergy | Union County | AR | DPP-2014-AUG | South | DPP - SIS | NRIS Only | El Dorado substation | 1270 | 1270 | Gas | ST, CT | In Service | 2016-12-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1799 | [5 empty] | External NRIS |  | 100 |  | Solar | Pulaski | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-27 | 2021-02-18 |  | 2022-02-15 | Ameren Illinois | Pulaski | IL | DPP-2020-Cycle | Central | PHASE 1 | External NRIS | Joppa 345 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1800 | [5 empty] | NRIS Only |  | 25 |  | Wind | Mower | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-27 | 2020-10-08 |  | 2023-12-01 | ITC Midwest | Mower | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS Only | Adams Switch Yard 161kV | 25 | 25 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1801 | [5 empty] | NRIS Only |  | 39 |  | Wind | Story | IA | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-12-23 |  |  | 2023-12-01 | ITC Midwest | Story | IA | DPP-2020-Cycle | West | PHASE 1 | NRIS Only | Story County Substation 161kV | 39 | 39 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1802 | [5 empty] | NRIS |  | 150 |  | Solar | Marshall | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-03-09 |  |  | 2024-10-30 | Northern Indiana Public Service Company | Marshall | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Burr Oak 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1803 | [5 empty] | NRIS |  | 1.6 |  | Wind | Houghton | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-27 |  |  | 2021-09-15 | American Transmission Co. LLC | Houghton | MI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Winona-Atlantic 69 kV | 1.6 | 1.6 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2014-AUG | West | Done | In Service | J382 | [5 empty] | NRIS Only |  | 48.3 |  | Gas | Cambridge | WI | [27 empty] | Done | 2014-07-14 |  | 2016-03-14 | 2016-03-01 | American Transmission Co. LLC | Cambridge | WI | DPP-2014-AUG | West | DPP - SIS | NRIS Only | 2346 Clearview Road, Cambridge, WI | 48.3 | 48.3 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2020-05-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1804 | [5 empty] | NRIS |  | 0 |  | Battery Storage | St. Croix | WI | [21 empty] | #DIV/0! | #DIV/0! |  |  |  |  | Active | 2021-02-17 |  |  | 2024-06-06 | Northern States Power (Xcel Energy) | St. Croix | WI | DPP-2020-Cycle | West | PHASE 1 | NRIS | PINE LAKE TO THREE LAKES 115 KV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | East (ATC) | Done | Under Construction | J384 | [5 empty] | NRIS |  | 21 |  | Gas | Cambridge | WI | [27 empty] | Done | 2014-08-25 |  | 2017-01-11 | 2015-06-01 | American Transmission Co. LLC | Cambridge | WI | DPP-2015-FEB | East (ATC) | DPP - SIS | NRIS | 2346 Clearview Road, Cambridge, WI | 21 | 21 | Gas | CT Combustion Turbine (Simple Cycle) | Under Construction | 2017-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | West | Done | In Service | J385 | [5 empty] | NRIS |  | 100 |  | Solar | Chisago County | MN | [27 empty] | Done | 2014-09-02 |  | 2016-10-17 | 2016-08-15 | Northern States Power (Xcel Energy) | Chisago County | MN | DPP-2015-FEB | West | DPP - SIS | NRIS | Chisago 115 kV Substation | 100 | 100 | Solar | PV Photovoltaic | In Service | 2016-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1805 | [5 empty] | NRIS |  | 0 |  | Battery Storage | LaPorte | IN | [21 empty] | #DIV/0! | #DIV/0! |  |  |  |  | Active | 2021-02-17 |  |  | 2024-04-12 | Northern Indiana Public Service Company | LaPorte | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Maple 69 kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1806 | [5 empty] | NRIS |  | 30 |  | Battery Storage | Henry | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-27 |  |  | 2022-09-01 | Duke Energy Indiana | Henry | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Greensboro Substation 345kV | 30 | 30 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1807 | [5 empty] | NRIS |  | 150 |  | Solar | Washington | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-27 | 2020-12-18 |  | 2023-05-01 | Duke Energy Indiana | Washington | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Mount Tabor 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1808 | [5 empty] | NRIS |  | 200 |  | Solar | Barron | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-27 |  |  | 2023-02-28 | Dairyland Power Cooperative | Barron | WI | DPP-2020-Cycle | West | PHASE 1 | NRIS | Barron 161 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | East (ATC) | Done | In Service | J390 | [5 empty] | NRIS |  | 711 |  | Combined Cycle | Rock County | WI | [27 empty] | Done | 2014-09-15 |  | 2017-04-21 | 2018-04-25 | American Transmission Co. LLC | Rock County | WI | DPP-2015-FEB | East (ATC) | DPP - SIS | NRIS | Paddock - Rockdale 345 kV line | 702 | 711 | Combined Cycle | Combined Cycle | In Service | 2017-11-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Withdrawn | Not Started | J1809 | [5 empty] | NRIS |  | 62.5 |  | Solar | Houghton | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-27 | 2021-02-19 |  | 2023-08-15 | American Transmission Co. LLC | Houghton | MI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Atlantic -Silver River 138 kV | 62.5 | 62.5 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | East (ITC) | Done | In Service | J392 | [5 empty] | NRIS |  | 420.7 |  | Gas | Otsego County | MI | [27 empty] | Done | 2014-09-15 |  | 2016-03-23 | 2016-05-16 | Michigan Electric Transmission Company, LLC | Otsego County | MI | DPP-2015-FEB | East (ITC) | Int FaS | NRIS | ITC/METC 138 kV Livingston to Stover line | 383.1 | 420.7 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2015-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | East (ITC) | Done | In Service | J392 | [5 empty] | NRIS |  | 420.7 |  | Gas | Otsego County | MI | [27 empty] | Done | 2014-09-15 |  | 2016-03-23 | 2016-05-16 | Michigan Electric Transmission Company, LLC | Otsego County | MI | DPP-2015-FEB | East (ITC) | Network Upgrade | NRIS | ITC/METC 138 kV Livingston to Stover line | 383.1 | 420.7 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2015-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1810 | [5 empty] | NRIS |  | 60 |  | Hybrid | White | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-03-02 |  |  | 2023-09-01 | Northern Indiana Public Service Company | White | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Reynolds 345kV to Burr Oaks 345kV | 60 | 60 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | West | Withdrawn | Withdrawn | J441 | [5 empty] | NRIS |  | 170 |  | Wind | Dodge County | MN | [27 empty] | Withdrawn | 2015-04-15 | 2019-08-09 |  | 2018-09-01 | Northern States Power (Xcel Energy) | Dodge County | MN | DPP-2017-FEB | West | GIA | NRIS | Byron 345 kV Substation | 170 | 170 | Wind | WT Wind Turbine | Withdrawn | 2019-09-18 | 170 | 170 | 170 | 170
|  |  |  | DPP-2015-FEB | East (ATC) | Done | In Service | J395 | [5 empty] | ERIS |  | 98 |  | Wind | Lafayette County | WI | [27 empty] | Done | 2014-09-15 |  | 2017-01-30 | 2017-12-31 | American Transmission Co. LLC | Lafayette County | WI | DPP-2015-FEB | East (ATC) | Optional | ERIS | Hillman - Darlington 138 kV line | 98 | 98 | Wind | WT Wind Turbine | In Service | 2015-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-AUG | South | Done | In Service | J396 | [5 empty] | NRIS |  | 1020 |  | Gas | St. Charles Parish | LA | [27 empty] | Done | 2014-09-15 |  | 2016-12-07 | 2019-05-31 | Entergy | St. Charles Parish | LA | DPP-2015-AUG | South | Network Upgrade | NRIS | Entergy Little Gypsy Power Station | 904 | 1020 | Gas | Combined Cycle | In Service | 2019-09-30 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1811 | #REF! |  |  |  |  | NRIS |  | 150 |  | Solar | Independence | AR | [5 empty] | Independence 161 kV | Entergy Arkansas LLC | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-12-23 |  |  | 2023-10-31 | Entergy Arkansas LLC | Independence | AR | DPP-2020-Cycle | South | PHASE 1 | NRIS | Independence 161 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1812 | #REF! |  |  |  |  | NRIS |  | 294.25 |  | Wind | Chambers | TX | [5 empty] | Stowell 230 kV | Entergy Texas Inc | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-12-21 |  |  | 2024-09-01 | Entergy Texas Inc | Chambers | TX | DPP-2020-Cycle | South | PHASE 1 | NRIS | Stowell 230 kV | 294.25 | 294.25 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-AUG | West | Done | In Service | J399 | [5 empty] | NRIS |  | 232 |  | Gas | Dakota County | MN | [27 empty] | Done | 2014-10-15 |  | 2017-09-01 | 2017-10-28 | Northern States Power (Xcel Energy) | Dakota County | MN | DPP-2015-AUG | West | DPP - SIS | NRIS | Black Dog 115 kV substation | 214 | 232 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2018-02-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | West | Done | In Service | J400 | [5 empty] | NRIS |  | 62.5 |  | Solar | Lyon County | MN | [27 empty] | Done | 2014-11-10 |  | 2016-10-18 | 2016-09-30 | Northern States Power (Xcel Energy) | Lyon County | MN | DPP-2015-FEB | West | DPP - SIS | NRIS | Lyon County 115kV Substation | 62.5 | 62.5 | Solar | PV Photovoltaic | In Service | 2017-06-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | Central | Done | In Service | J401 | [5 empty] | NRIS |  | 20 |  | Battery Storage | Marion County | IN | [27 empty] | Done | 2014-11-10 |  | 2016-03-19 | 2016-03-31 | Indianapolis Power & Light Company | Marion County | IN | DPP-2015-FEB | Central | DPP - SIS | NRIS | Stout South Substation 138 | 20 | 20 | Battery Storage | BS Battery Storage | In Service | 2016-01-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1814 | [5 empty] | NRIS |  | 22.5 |  | Solar | Dickinson | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-23 |  |  | 2023-09-15 | American Transmission Co. LLC | Dickinson | MI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Nordic | 22.5 | 22.5 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1815 | [5 empty] | NRIS |  | 180 |  | Solar | Montgomery | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-28 |  |  | 2023-08-01 | Duke Energy Indiana | Montgomery | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Linden Junction - Crawfordsville 138 kV | 180 | 180 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1816 | #REF! |  |  |  |  | NRIS |  | 135 |  | Solar | Cross | AR | [5 empty] | Fisher (Endpoint A) to Cherry Valley (Endpoint B) 161 kV line | Entergy Arkansas LLC | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-12-23 |  |  | 2024-01-15 | Entergy Arkansas LLC | Cross | AR | DPP-2020-Cycle | South | PHASE 1 | NRIS | Fisher (Endpoint A) to Cherry Valley (Endpoint B) 161 kV line | 135 | 135 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | West | Done | In Service | J405 | [5 empty] | NRIS |  | 40 |  | Gas | Richland County | MT | [27 empty] | Done | 2014-11-11 |  | 2016-10-26 | 2015-12-01 | Montana-Dakota Utilities Company | Richland County | MT | DPP-2015-FEB | West | DPP - SIS | NRIS | MDUs existing Lewis & Clark Jct substation | 40 | 40 | Gas | CT Combustion Turbine (Simple Cycle) | In Service | 2017-12-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | East (ITC) | Done | In Service | J406 | [5 empty] | External NRIS |  | 4 |  | Wood | Wexford County | MI | [27 empty] | Done | 2014-11-14 |  | 2016-05-02 | 2016-03-24 | Michigan Electric Transmission Company, LLC | Wexford County | MI | DPP-2015-FEB | East (ITC) | Int FaS | External NRIS | Wexford Substation | 4 | 4 | Wood | CS Combined-Cycle Single Shaft - Combustion turbine and steam turbine share a single generator | In Service | 2018-01-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | West | Done | Under Construction | J407 | [5 empty] | NRIS |  | 200 |  | Wind | Freeborn County | MN | [27 empty] | Done | 2014-11-14 |  | 2017-03-24 | 2016-10-01 | ITC Midwest | Freeborn County | MN | DPP-2015-FEB | West | DPP - SIS | NRIS | Glenworth 161 kV | 200 | 200 | Wind | WT Wind Turbine | Under Construction | 2015-12-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1817 | [5 empty] | NRIS |  | 20 |  | Wind | Houghton | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-23 |  |  | 2021-09-15 | American Transmission Co. LLC | Houghton | MI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | ATC WInona-Atlantic Minw 69 kV tap (J1244) | 20 | 20 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1818 | #REF! |  |  |  |  | NRIS |  | 80 |  | Solar | Lafayette | LA | [5 empty] | Northeast (Moss) 69kV | Lafayette Utilities System |  |  |  |  | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-07-28 |  |  | 2023-10-01 | Lafayette Utilities System | Lafayette | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Northeast (Moss) 69kV | 80 | 80 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1819 | [5 empty] | NRIS |  | 0 |  | Battery Storage | Lee | AR | [21 empty] | #DIV/0! | #DIV/0! |  |  |  |  | Active | 2020-12-23 |  |  | 2023-09-13 | Entergy Arkansas LLC | Lee | AR | DPP-2020-Cycle | South | PHASE 1 | NRIS | Entergy Keo - West Memphis 500kV Line Tap | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | West | Done | In Service | J411 | [5 empty] | NRIS |  | 300 |  | Wind | Ida County | IA | [27 empty] | Done | 2014-11-14 |  | 2016-10-10 | 2016-07-15 | MidAmerican Energy Company | Ida County | IA | DPP-2015-FEB | West | DPP - SIS | NRIS | LeHigh - Raun 345 kV Line | 300 | 300 | Wind | WT Wind Turbine | In Service | 2014-11-18 | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-AUG | West | Done | In Service | J412 | [5 empty] | NRIS |  | 200 |  | Wind | Ida County | IA | [27 empty] | Done | 2014-11-14 |  | 2017-08-23 | 2016-10-01 | MidAmerican Energy Company | Ida County | IA | DPP-2015-AUG | West | DPP - SIS | NRIS | LeHigh - Raun 345 kV line | 200 | 200 | Wind | WT Wind Turbine | In Service | 2019-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1820 | #REF! |  |  |  |  | NRIS |  | 100 |  | Solar | Lee | AR | [5 empty] | Entergy Keo-West Memphis 500kV Line Tap | Entergy Arkansas LLC | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-12-23 |  |  | 2023-09-13 | Entergy Arkansas LLC | Lee | AR | DPP-2020-Cycle | South | PHASE 1 | NRIS | Entergy Keo-West Memphis 500kV Line Tap | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | South | Active | Not Started | J1425 |  |  | Scoping Calls - Duncan Mitchell | Calpine Energy Solutions |  | NRIS Only |  | 114 |  | Gas | Jefferson County | AR | [27 empty] | Active | 2019-04-29 |  |  | 2020-06-01 | Entergy Arkansas, LLC | Jefferson County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS Only | Pine Bluff International Paper 115 kV substation | 114 | 114 | Gas | Combined Cycle | Not Started |  | 0 | 114 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1821 | [5 empty] | NRIS |  | 0 |  | Battery Storage | Lee | AR | [21 empty] | #DIV/0! | #DIV/0! |  |  |  |  | Active | 2020-12-23 |  |  | 2023-09-13 | Entergy Arkansas LLC | Lee | AR | DPP-2020-Cycle | South | PHASE 1 | NRIS | Entergy Keo -West Memphis 500kV Line tap | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | West | Done | In Service | J416 | [5 empty] | NRIS |  | 200 |  | Wind | Franklin County | IA | [27 empty] | Done | 2014-11-14 |  | 2016-09-02 | 2019-07-01 | ITC Midwest | Franklin County | IA | DPP-2015-FEB | West | DPP - SIS | NRIS | Emery - Blackhawk 345 kV (Section of MVP4) | 200 | 200 | Wind | WT Wind Turbine | In Service | 2017-09-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Withdrawn | Not Started | J1822 | [5 empty] | NRIS |  | 200 |  | Wind | Franklin | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-29 | 2021-01-04 |  | 2023-06-01 | ITC Midwest | Franklin | IA | DPP-2020-Cycle | West | PHASE 1 | NRIS | KILLDEER3 (631199) 345 KV TO BLACKHAWK (636199) 345 kv line Tap | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Withdrawn | Not Started | J1823 | [5 empty] | NRIS |  | 62.5 |  | Solar | Houghton | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-29 | 2021-02-19 |  | 2023-09-15 | American Transmission Co. LLC | Houghton | MI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Portage (UPPCO) - Atlantic 69 kV | 62.5 | 62.5 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | East (ITC) | Done | Under Construction | J419 | [5 empty] | NRIS |  | 100 |  | Solar | Washtenaw County | MI | [27 empty] | Done | 2014-11-17 |  | 2016-06-20 | 2016-09-01 | ITC Transmission | Washtenaw County | MI | DPP-2015-FEB | East (ITC) | GIA | NRIS | Milan 120kV Substation | 100 | 100 | Solar | PV Photovoltaic | Under Construction | 2014-12-30 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1824 | [5 empty] | NRIS |  | 73.8 |  | Solar | Columbia | WI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-21 |  |  | 2024-12-31 | American Transmission Co. LLC | Columbia | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Academy 138KV | 73.8 | 73.8 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1825 | [5 empty] | NRIS |  | 100 |  | Solar | Decatur | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-29 | 2020-12-18 |  | 2024-10-01 | Duke Energy Indiana | Decatur | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Westport | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1827 | #REF! |  |  |  |  | NRIS |  | 90 |  | Solar | Morehouse | LA | [5 empty] | Bastrop tap point | Entergy Louisiana LLC |  |  |  |  | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-12-22 |  |  | 2023-10-31 | Entergy Louisiana LLC | Morehouse | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Bastrop tap point | 90 | 90 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1828 | [5 empty] | ERIS |  | 99.2 |  | Hybrid | Sangamon | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2021-03-12 | 2021-03-12 |  | 2024-08-20 | Ameren Illinois | Sangamon | IL | DPP-2020-Cycle | Central | PHASE 1 | ERIS | Austin-1 138 kV substation | 99.2 | 99.2 | Hybrid | Solar/Wind/Battery | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1829 | [5 empty] | NRIS |  | 180 |  | Solar | Shelby | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-12-23 |  |  | 2024-10-01 | Duke Energy Indiana | Shelby | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | DEI's Columbus to Clark Twp. 230 kV (one of the two 230 kV circuits going from Columbus to Five Points) | 180 | 180 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1830 | [5 empty] | NRIS |  | 200 |  | Hybrid | Pulaski | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-10-14 |  |  | 2023-09-01 | Ameren Illinois | Pulaski | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Kelso - Joppa (Massac) 345 kV line | 200 | 200 | Hybrid | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | West | Done | In Service | J426 | [5 empty] | NRIS |  | 100 |  | Wind | Pipestone County | MN | [27 empty] | Done | 2014-11-17 |  | 2016-09-22 | 2016-09-01 | Northern States Power (Xcel Energy) | Pipestone County | MN | DPP-2015-FEB | West | DPP - SIS | NRIS | Chanarambie substation 35.4 kV | 100 | 100 | Wind | WT Wind Turbine | In Service | 2018-09-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1831 | [5 empty] | NRIS |  | 200 |  | Wind | Logan,Menard | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-30 |  |  | 2023-10-31 | Ameren Illinois | Logan,Menard | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Shockey 138kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1832 | #REF! |  |  |  |  | NRIS |  | 150 |  | Solar | St. Landry | LA | [5 empty] | Plaisance 138kV | CLECO Corporation |  |  |  |  | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2020-07-30 |  |  | 2023-04-01 | CLECO Corporation | St. Landry | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Plaisance 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1835 | [5 empty] | NRIS |  | 200 |  | Wind | Spencer | IN | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-31 |  |  | 2023-06-01 | Southern Indiana Gas Electric Company d/b/a Vectren Energy Delivery of Indiana Inc | Spencer | IN | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Rockport Substation 69 KV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1836 | [5 empty] | NRIS |  | 300 |  | Solar | 0 | MO | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-31 |  |  | 2025-08-01 | Ameren Missouri |  | MO | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Callaway Plant-345 kV | 300 | 300 | Solar |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | Central | Done | In Service | J431 | [5 empty] | NRIS Only |  | 100 |  | Wind | Benton County | IN | [27 empty] | Done | 2014-12-16 |  | 2016-08-26 | 2014-12-30 | Northern Indiana Public Service Company | Benton County | IN | DPP-2015-FEB | Central | DPP - SIS | NRIS Only | Goodland 138 / 69 kV substation | 100 | 100 | Wind | WT Wind Turbine | In Service | 2017-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-FEB | West | Done | In Service | J432 | [5 empty] | NRIS |  | 98 |  | Wind | Brookings County | SD | [27 empty] | Done | 2014-12-30 |  | 2018-10-03 | 2018-09-15 | Northern States Power (Xcel Energy) | Brookings County | SD | DPP-2016-FEB | West | GIA | NRIS | Brookings 345 kV substation | 98 | 98 | Wind | WT Wind Turbine | In Service | 2019-09-01 | 98 | 98 | 98 | 0
|  |  |  | DPP-2020-Cycle | Central | Withdrawn | Not Started | J1837 | [5 empty] | NRIS |  | 200 |  | Wind | Shelby | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2020-07-31 | 2021-03-12 |  | 2023-06-01 | Ameren Illinois | Shelby | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Pana - Route 51 138kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1840 | [5 empty] | NRIS |  | 250 |  | Solar | De Witt | IL | [21 empty] | 0 | 0 |  |  |  |  | Active | 2020-07-31 |  |  | 2023-08-30 | Ameren Illinois | De Witt | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Clinton to Goose Creek-4545 345kV line | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1841 | #REF! |  |  |  |  | NRIS |  | 52 |  | Wind | Cross | AR | [5 empty] | Forrest City to Wynne S 161 KV Line | Entergy Arkansas LLC | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2021-02-21 |  |  | 2023-06-01 | Entergy Arkansas LLC | Cross | AR | DPP-2020-Cycle | South | PHASE 1 | NRIS | Forrest City to Wynne S 161 KV Line | 52 | 52 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-AUG | West | Done | Under Construction | J436 | [5 empty] | ERIS |  | 150 |  | Wind | Codington County,Grant County | SD | [27 empty] | Done | 2015-03-12 |  | 2017-12-15 | 2017-10-10 | Otter Tail Power Company | Codington County,Grant County | SD | DPP-2015-AUG | West | DPP - SIS | ERIS | Big Stone South - Ellendale 345 kV line | 150 | 150 | Wind | WT Wind Turbine | Under Construction | 2020-07-06 | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-AUG | West | Done | Under Construction | J437 | [5 empty] | ERIS |  | 150 |  | Wind | Codington County,Grant County | SD | [27 empty] | Done | 2015-03-12 |  | 2017-12-15 | 2017-10-10 | Otter Tail Power Company | Codington County,Grant County | SD | DPP-2015-AUG | West | DPP - SIS | ERIS | Big Stone South - Ellendale 345 kV line | 150 | 150 | Wind | WT Wind Turbine | Under Construction | 2020-07-06 | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-AUG | West | Done | In Service | J438 | [5 empty] | NRIS |  | 170 |  | Wind | Poweshiek County | IA | [27 empty] | Done | 2015-03-16 |  | 2017-09-05 | 2016-09-01 | MidAmerican Energy Company | Poweshiek County | IA | DPP-2015-AUG | West | DPP - SIS | NRIS | Poweshiek-Parnell 161 kV line | 170 | 170 | Wind | WT Wind Turbine | In Service | 2018-12-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1842 | #REF! |  |  |  |  | NRIS |  | 175 |  | Wind | Cross | AR | [5 empty] | Forrest City to Wynne S 161 KV | Entergy Arkansas LLC | [6 empty] | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | Active | 2021-02-21 |  |  | 2023-06-01 | Entergy Arkansas LLC | Cross | AR | DPP-2020-Cycle | South | PHASE 1 | NRIS | Forrest City to Wynne S 161 KV | 175 | 175 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-AUG | East (ITC) | Done | In Service | J440 | [5 empty] | NRIS Only |  | 52 |  | Gas | Wayne County | MI | [27 empty] | Done | 2015-03-16 |  | 2017-02-23 | 2016-01-31 | ITC Transmission | Wayne County | MI | DPP-2015-AUG | East (ITC) | DPP - SIS | NRIS Only | Consumers DIGG 230 kV substation | 52 | 52 | Gas | CS Combined-Cycle Single Shaft - Combustion turbine and steam turbine share a single generator | In Service | 2016-01-10 | 0 | 0 | 0 | 0
|  |  |  | DPP-2021-Cycle | East (ITC) | Active | Not Started | J1844 | [5 empty] | NRIS |  | 100 |  | Battery Storage | Washtenaw | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-24 |  |  | 2024-10-07 | ITC Transmission | Washtenaw | MI | DPP-2021-Cycle | East (ITC) | Study Not Started | NRIS | 19CVTRY | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-AUG | West | Done | In Service | J442 | [5 empty] | NRIS |  | 200 |  | Wind | Deuel County | SD | [27 empty] | Done | 2015-04-15 |  | 2017-08-11 | 2017-09-01 | Otter Tail Power Company | Deuel County | SD | DPP-2015-AUG | West | DPP - SIS | NRIS | Big Stone substation via a radial 230 kV line | 200 | 200 | Wind | WT Wind Turbine | In Service | 2019-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-AUG | West | Done | In Service | J443 | [5 empty] | NRIS Only |  | 41 |  | Wind | Delaware County | IA | [27 empty] | Done | 2015-05-06 |  | 2017-05-22 | 2015-12-31 | ITC Midwest | Delaware County | IA | DPP-2015-AUG | West | DPP - SIS | NRIS Only | Greely Tap | 41 | 41 | Wind | WT Wind Turbine | In Service | 2018-04-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2021-Cycle | East (ITC) | Active | Not Started | J1845 | [5 empty] | NRIS |  | 100 |  | Battery Storage | Calhoun | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2021-02-24 |  |  | 2025-10-06 | Michigan Electric Transmission Company LLC | Calhoun | MI | DPP-2021-Cycle | East (ITC) | Study Not Started | NRIS | 18BATTLC | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ITC) | Withdrawn | Not Started | J203 | [5 empty] | NRIS |  | 200 |  | Wind | Sanilac County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-09 |  | 2012-09-01 | ITC Transmission | Sanilac County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Greenwood - Banner 345kV Line Tap | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | Central | Done | Under Construction | J446 | [5 empty] | NRIS |  | 200 |  | Wind | Clinton County | IN | [27 empty] | Done | 2015-05-13 |  | 2018-11-15 | 2019-12-31 | Duke Energy Corporation | Clinton County | IN | DPP-2016-AUG | Central | GIA | NRIS | Frankfort-New London 230 kV | 200 | 200 | Wind | WT Wind Turbine | Under Construction | 2020-09-01 | 200 | 200 | 200 | 200
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J310 | [5 empty] | NRIS |  | 200 |  | Wind | Dodge County,Steele County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-02-11 |  | 2017-09-01 | Southern Minnesota Municipal Power Agency | Dodge County,Steele County | MN | DPP-2017-AUG | West | PHASE 3 | NRIS | West Owatonna-AL Corn Dist-Byron 161kV Line | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J418 | [5 empty] | NRIS |  | 100 |  | Solar | Polk County | TX | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-07 |  | 2016-11-01 | Entergy | Polk County | TX | DPP-2017-AUG | South | GIA | NRIS | Rich - Livingston 138kV Line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-AUG | West | Done | In Service | J449 | [5 empty] | NRIS |  | 202 |  | Wind | Mitchell County | IA | [27 empty] | Done | 2015-05-15 |  | 2017-06-26 | 2017-09-15 | ITC Midwest | Mitchell County | IA | DPP-2015-AUG | West | DPP - SIS | NRIS | Pioneer Prairie I substation | 202 | 202 | Wind | WT Wind Turbine | In Service | 2018-10-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J447 | [5 empty] | NRIS |  | 150 |  | Wind | Cerro Gordo County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-10-24 |  | 2021-07-01 | ITC Midwest | Cerro Gordo County | IA | DPP-2017-AUG | West | PHASE 3 | NRIS | Emery 161 kV Substation | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Withdrawn | Not Started | J467 | [5 empty] | NRIS |  | 102 |  | Wind | Douglas County | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-08 |  | 2017-11-15 | Ameren Illinois | Douglas County | IL | DPP-2017-AUG | Central | GIA | NRIS | Sidnay-Kansas 345kV Line | 102 | 102 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Withdrawn | Not Started | J478 | [5 empty] | NRIS |  | 200 |  | Wind | Clinton County | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-04-17 |  | 2018-07-01 | Duke Energy Corporation | Clinton County | IN | DPP-2017-AUG | Central | GIA | NRIS | Thorntown - New London - Kokomo 230kV Line | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
|  |  |  | DPP-2015-AUG | Central | Done | In Service | J453 | [5 empty] | ERIS |  | 16.75 |  | Solar | Martin County | IN | [27 empty] | Done | 2015-05-18 |  | 2016-06-06 | 2016-08-31 | Duke Energy Corporation | Martin County | IN | DPP-2015-AUG | Central | DPP - SIS | ERIS | Duke Crane South â€“ Crane Junction 69kV | 17.25 | 16.75 | Solar | OT Other | In Service | 2019-06-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J502 | [5 empty] | NRIS |  | 100 |  | Solar | Orange County | TX | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-07 |  | 2019-09-01 | Entergy | Orange County | TX | DPP-2017-AUG | South | GIA | NRIS | McLewis 230 kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-AUG | West | Done | In Service | J455 | [5 empty] | ERIS |  | 300 |  | Wind | Clay County | IA | [27 empty] | Done | 2015-05-18 |  | 2017-08-23 | 2018-10-10 | MidAmerican Energy Company | Clay County | IA | DPP-2015-AUG | West | DPP - SIS | ERIS | Kossuth â€“ Obrien 345 kV line | 300 | 300 | Wind | WT Wind Turbine | In Service | 2018-09-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | Central | Done | In Service | J456 | [5 empty] | NRIS |  | 150 |  | Wind | McDonough County | IL | [27 empty] | Done | 2015-05-18 |  | 2018-09-26 | 2017-01-09 | Ameren Illinois | McDonough County | IL | DPP-2016-AUG | Central | GIA | NRIS | 138 kV Niota-Macomb Northeast Line just south of Sciota, IL | 150 | 150 | Wind | WT Wind Turbine | In Service | 2019-12-01 | 150 | 150 | 150 | 150
|  |  |  | DPP-2016-AUG | West | Done | In Service | J541 | [5 empty] | NRIS | N | 400 |  | Wind | Schuyler County | MO |  |  |  | 1 | 1 | 1513856 | 11213124 | [9 empty] | 3380000 | 34555897 | 0 | 34555897 | 37935897 | 86.3897 | 94.8397 | 37935897 |  |  |  | Done | 2016-01-11 |  | 2019-08-16 | 2020-04-30 | Ameren Transmission Company of Illinois | Schuyler County | MO | DPP-2016-AUG | West | GIA | NRIS | Zachary-Ottumwa 345 kV line | 400 | 400 | Wind | WT Wind Turbine | In Service | 2020-04-01 | 400 | 400 | 400 | 400
|  |  |  | DPP-2016-AUG | South | Done | Not Started | J544 | [5 empty] | NRIS |  | 98.1 |  | Solar | Morehouse Parish | LA | [5 empty] | Galion 115kV Substation | [15 empty] | 0 | 0 |  |  |  |  | Done | 2016-01-11 |  | 2018-06-01 | 2018-09-01 | Entergy | Morehouse Parish | LA | DPP-2016-AUG | South | GIA | NRIS | Galion 115kV Substation | 98.1 | 98.1 | Solar | PV Photovoltaic | Not Started | 2021-09-15 | 98.1 | 98.1 | 98.1 | 98.1
|  |  |  | DPP-2017-AUG | West | Active | Not Started | J545 | [5 empty] | ERIS | N | 110 |  | Wind | Lincoln County | MN |  |  |  | 1 | 1 | 600000 | 0 | [7 empty] | 6390845 | 32469863 |  | 3501260 | 0 | 9892105 | 42361968 | 89.9282 | 385.1088 | 9892105 |  |  |  | Active | 2017-06-16 |  |  | 2020-08-31 | Northern States Power (Xcel Energy) | Lincoln County | MN | DPP-2017-AUG | West | PHASE 3 | ERIS | Buffalo 115kV Substation | 110 | 110 | Wind | WT Wind Turbine | Not Started |  | 110 | 0 | 110 | 0
|  |  |  | DPP-2016-FEB | West | Done | In Service | J460 | [5 empty] | NRIS |  | 200 |  | Wind | Lincoln County | MN | [27 empty] | Done | 2015-05-18 |  | 2018-10-02 | 2017-09-30 | Northern States Power (Xcel Energy) | Lincoln County | MN | DPP-2016-FEB | West | GIA | NRIS | on Brookings - H081 345 kV line approx. 10 miles west of proposed substation | 200 | 200 | Wind | WT Wind Turbine | In Service | 2019-09-13 | 200 | 200 | 200 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J546 | [5 empty] | NRIS |  | 260 |  | Wind | Huron County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-03-07 | 2017-05-03 |  | 2018-07-31 | ITC Transmission | Huron County | MI |  |  | Feasibility | NRIS | Rapson 120kV Substation | 260 | 260 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J547 | [5 empty] | ERIS |  | 100 |  | Solar | Sherburne County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-03-14 | 2017-07-21 |  | 2018-08-01 | Northern States Power (Xcel Energy) | Sherburne County | MN |  |  | Feasibility | ERIS | Unknown | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J548 | [5 empty] | ERIS |  | 150 |  | Solar | Yellow Medicine County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-03-14 | 2017-07-21 |  | 2018-08-31 | Northern States Power (Xcel Energy) | Yellow Medicine County | MN |  |  | Feasibility | ERIS | Unknown | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J549 | [5 empty] | NRIS |  | 49.8 |  | Solar | Acadia Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-03-14 | 2017-03-10 |  | 2018-04-15 | Entergy | Acadia Parish | LA |  |  | Feasibility | NRIS | Unknown | 49.8 | 49.8 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J550 | [5 empty] | NRIS |  | 49.8 |  | Solar | Acadia Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-03-14 | 2017-03-10 |  | 2018-04-15 | Entergy | Acadia Parish | LA |  |  | Feasibility | NRIS | Unknown | 49.8 | 49.8 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-AUG | East (ITC) | Done | Under Construction | J466 | [5 empty] | NRIS |  | 30 |  | Battery Storage | Huron County | MI | [27 empty] | Done | 2015-05-18 |  | 2017-07-20 | 2016-10-01 | ITC Transmission | Huron County | MI | DPP-2015-AUG | East (ITC) | DPP - SIS | NRIS | Stein 345 kV Substation | 30 | 30 | Battery Storage |  | Under Construction | 2015-10-22 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J551 | [5 empty] | NRIS |  | 49.8 |  | Solar | Concordia Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-03-14 | 2017-03-01 |  | 2018-04-15 | Entergy | Concordia Parish | LA |  |  | Feasibility | NRIS | Unknown | 49.8 | 49.8 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-FEB | Central | Done | In Service | J468 | [5 empty] | NRIS |  | 202 |  | Wind | Douglas County | IL | [27 empty] | Done | 2015-06-25 |  | 2017-06-12 | 2015-11-15 | Ameren Illinois | Douglas County | IL | DPP-2016-FEB | Central | GIA | NRIS | Along existing Sidney-Kansas West 345 kV line | 202 | 202 | Wind | WT Wind Turbine | In Service | 2019-05-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-AUG | East (ITC) | Done | In Service | J469 | [5 empty] | External NRIS |  | 2 |  | Wood | Crawford County | MI | [27 empty] | Done | 2015-06-30 |  | 2017-02-28 | 2016-02-01 | Michigan Electric Transmission Company, LLC | Crawford County | MI | DPP-2015-AUG | East (ITC) | DPP - SIS | External NRIS | Consumers Grayling Generation 46 kV Substation | 2 | 2 | Wood | OT Other | In Service | 2017-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | South | Done | Not Started | J552 | [5 empty] | NRIS |  | 100 |  | Solar | Lee County | AR | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-03-14 |  |  | 2018-10-15 | Entergy | Lee County | AR | DPP-2016-AUG | South | GIA | NRIS | Brinkley East - Moro 115kV Line | 100 | 100 | Solar | PV Photovoltaic | Not Started | 2021-06-01 | 100 | 100 | 100 | 100
|  |  |  | DPP-2016-AUG | South | Withdrawn | Not Started | J553 | [5 empty] | NRIS |  | 50 |  | Solar | East Feliciana Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-03-14 | 2017-05-16 |  | 2018-10-15 | Entergy | East Feliciana Parish | LA | DPP-2016-AUG | South | GIA | NRIS | Sandy Creek - Jackson 69kV Line (Entergy) | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | South | Done | In Service | J472 | [5 empty] | NRIS |  | 1044.8 |  | Gas | Montgomery County | TX | [27 empty] | Done | 2015-09-10 |  | 2018-07-27 | 2020-07-20 | Entergy | Montgomery County | TX | DPP-2016-AUG | South | GIA | NRIS | Entergyâ€™s 138 kV and 230kV Lewis Creek Substations | 923.8 | 1044.8 | Gas | Combined Cycle | In Service | 2020-07-01 | 1044.8 | 923.8 | 1044.8 | 923.8
|  |  |  | DPP-2016-FEB | South | Done | In Service | J473 | [5 empty] | ERIS |  | 52 |  | Solar | Lamar County | MS | [27 empty] | Done | 2015-09-11 |  | 2016-02-29 | 2017-03-23 | South Mississippi Electric Power Association | Lamar County | MS | DPP-2016-FEB | South | Int FaS | ERIS | Sumrall II substation | 52 | 52 | Solar | PV Photovoltaic | In Service | 2015-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | Central | Done | Under Construction | J474 | [5 empty] | NRIS |  | 144 |  | Wind | DeWitt County | IL | [27 empty] | Done | 2015-09-14 |  | 2018-10-25 | 2017-09-01 | Ameren Illinois | DeWitt County | IL | DPP-2016-AUG | Central | GIA | NRIS | New 138 kV Tabor substation | 144 | 144 | Wind | WT Wind Turbine | Under Construction | 2017-10-01 | 144 | 144 | 144 | 144
|  |  |  | DPP-2016-FEB | West | Done | In Service | J475 | [5 empty] | NRIS |  | 200 |  | Wind | Poweshiek County | IA | [27 empty] | Done | 2015-09-14 |  | 2019-02-08 | 2018-09-01 | MidAmerican Energy Company | Poweshiek County | IA | DPP-2016-FEB | West | GIA | NRIS | Existing 345 kV Montezuma Substation | 200 | 200 | Wind | WT Wind Turbine | In Service | 2018-07-01 | 200 | 200 | 200 | 200
|  |  |  | DPP-2016-AUG | West | Done | Under Construction | J476 | [5 empty] | NRIS |  | 246 |  | Wind | Atchison County | MO | [27 empty] | Done | 2015-09-14 |  | 2020-03-12 | 2020-07-01 | MidAmerican Energy Company | Atchison County | MO | DPP-2016-AUG | West | GIA | NRIS | Atchison County to Booneville 345 kV Line Tap | 246 | 246 | Wind | WT Wind Turbine | Under Construction | 2021-09-15 | 246 | 246 | 246 | 246
|  |  |  | DPP-2016-AUG | South | Done | In Service | J477 | [5 empty] | NRIS |  | 36.4 |  | Gas | Hinds County | MS | [27 empty] | Done | 2015-09-14 |  |  | 2018-11-01 | Entergy | Hinds County | MS | DPP-2016-AUG | South | GIA | NRIS | Close to Entergy Hinds Power Station | 31.9 | 36.4 | Gas | OT Other | In Service | 2018-11-01 | 36.4 | 31.9 | 36.4 | 31.9
|  |  |  | 0 | 0 | Done | In Service | J554 | [5 empty] | ERIS |  | 1 |  | Solar | Dodge County | MN | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-03-28 |  | 2017-03-06 | 2016-08-31 | Northern States Power (Xcel Energy) | Dodge County | MN |  |  | DPP - SIS | ERIS | Kasson - Dodge Center 69 kV | 1 | 1 | Solar | PV Photovoltaic | In Service | 2016-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Done | In Service | J555 | [5 empty] | NRIS | N | 140 |  | Wind | Poweshiek County | IA |  |  |  | 1 | 1 | 820523 | 3763917 | [9 empty] | 0 | 8435190 | 0 | 8435190 | 8435190 | 60.2514 | 60.2514 | 8435190 |  |  |  | Done | 2016-03-14 |  | 2020-08-17 | 2017-09-01 | MidAmerican Energy Company | Poweshiek County | IA | DPP-2016-AUG | West | GIA | NRIS | Montezuma, IA 50171 345kV substation | 140 | 140 | Wind | WT Wind Turbine | In Service | 2017-09-01 | 140 | 140 | 140 | 140
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J556 | [5 empty] | NRIS |  | 102 |  | Wind | Renville County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-04-04 | 2019-04-09 |  | 2019-12-31 | Great River Energy | Renville County | MN | DPP-2017-FEB | West | GIA | NRIS | Panther 230kV Substation | 102 | 102 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | South | Done | In Service | J481 | [5 empty] | NRIS |  | 134.82 |  | Gas | Orleans Parish | LA | [27 empty] | Done | 2015-09-14 |  |  | 2017-10-01 | Entergy | Orleans Parish | LA | DPP-2016-AUG | South | GIA | NRIS | Existing Michoud Power Station | 134.82 | 134.82 | Gas | OT Other | In Service | 2019-07-25 | 134.82 | 134.82 | 134.82 | 134.82
|  |  |  | DPP-2016-FEB | South | Done | In Service | J482 | [5 empty] | NRIS |  | 26.2 |  | Gas | St. Charles Parish | LA | [27 empty] | Done | 2015-09-14 |  | 2017-03-10 | 2018-07-01 | Entergy | St. Charles Parish | LA | DPP-2016-FEB | South | GIA | NRIS | Little Gypsy Power Station | 19.79 | 26.2 | Gas | Combined Cycle | In Service | 2018-05-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | South | Done | Under Construction | J483 | [5 empty] | NRIS |  | 99.96 |  | Solar | Liberty County | TX | [27 empty] | Done | 2015-09-14 |  | 2018-07-27 | 2017-09-01 | Entergy | Liberty County | TX | DPP-2016-AUG | South | GIA | NRIS | Line tap at 138 kV line approximately 6,000 ft SW of Gordon Sub | 99.96 | 99.96 | Solar | PV Photovoltaic | Under Construction | 2020-09-01 | 99.96 | 99.96 | 99.96 | 99.96
|  |  |  | DPP-2016-AUG | South | Done | Under Construction | J484 | [5 empty] | NRIS |  | 1056.19 |  | Gas | Calcasieu,Calcasieu Parish | LA | [27 empty] | Done | 2015-09-14 |  | 2018-07-27 | 2019-07-01 | Entergy | Calcasieu,Calcasieu Parish | LA | DPP-2016-AUG | South | GIA | NRIS | Existing Entergy Nelson Power Station | 933.8 | 1056.19 | Gas | Combined Cycle | Under Construction | 2019-07-01 | 1056.19 | 933.8 | 1056.19 | 933.8
|  |  |  | DPP-2016-FEB | West | Done | Not Started | J485 | [5 empty] | NRIS |  | 46.85 |  | Gas | Olmsted County | MN | [27 empty] | Done | 2015-10-12 |  | 2018-11-16 | 2018-01-01 | Rochester Public Utilities | Olmsted County | MN | DPP-2016-FEB | West | GIA | NRIS | West Side Substation - 5846 19th Street NW, Rochester, MN | 46.85 | 46.85 | Gas | OT Other | Not Started | 2017-09-15 | 46.85 | 46.85 | 46.85 | 46.85
|  |  |  | DPP-2016-FEB | South | Done | In Service | J486 | [5 empty] | NRIS Only |  | 51 |  | Combined Cycle | Grimes County | TX | [27 empty] | Done | 2015-10-22 |  | 2017-05-22 | 2015-10-22 | Entergy Texas, Inc. | Grimes County | TX | DPP-2016-FEB | South | GIA | NRIS Only | Grimes 345kV Substation | 51 | 51 | Combined Cycle | Combined Cycle | In Service | 2000-09-19 | 0 | 0 | 0 | 0
|  |  |  | MM-2016-AUG | East (ATC) | Done | In Service | J557 | [5 empty] | NRIS |  | 0.9 |  | Solar | Delta County | MI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-04-11 |  | 2017-04-17 | 2016-07-01 | American Transmission Co. LLC | Delta County | MI | MM-2016-AUG | East (ATC) | Out of Cycle | NRIS | Garden Corners Substation 138kV | 0.9 | 0.9 | Solar | PV Photovoltaic | In Service | 2016-08-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-FEB | West | Done | Under Construction | J488 | [5 empty] | ERIS |  | 151.8 |  | Wind | Grant County,Roberts County | SD | [27 empty] | Done | 2015-11-11 |  | 2019-02-06 | 2018-09-03 | Otter Tail Power Company | Grant County,Roberts County | SD | DPP-2016-FEB | West | GIA | ERIS | 345 kV at new Tap on proposed MVP Big Stone to Ellendale line | 151.8 | 151.8 | Wind | WT Wind Turbine | Under Construction | 2020-06-15 | 151.8 | 0 | 151.8 | 0
|  |  |  | MM-2016-AUG | WEST | Done | In Service | J558 | [5 empty] | ERIS |  | 9.2 |  | Wind | Pipestone County | MN | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-04-18 |  | 2017-04-17 |  | Northern States Power (Xcel Energy) | Pipestone County | MN | MM-2016-AUG | WEST | DPP - SIS | ERIS | Woodstock Tap 69 kV | 9.2 | 9.2 | Wind | WT Wind Turbine | In Service | 2017-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | South | Withdrawn | Not Started | J559 | [5 empty] | NRIS |  | 50 |  | Solar | Washington Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-04-26 | 2017-05-16 |  | 2018-11-01 | Entergy | Washington Parish | LA | DPP-2016-AUG | South | GIA | NRIS | EEL Holton - Franklinton 115kV | 50 | 50 | Solar | PV Photovoltaic | Not Started | 2017-10-10 | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Withdrawn | Not Started | J562 | [5 empty] | NRIS Only |  | 119.6 |  | Wind | Marshall County | IA |  |  |  |  | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-05 | 2017-01-24 |  |  | MidAmerican Energy Company | Marshall County | IA | DPP-2016-AUG | West | GIA | NRIS Only | Laurel 161kV switching station's 161kV bus | 119.6 | 119.6 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Withdrawn | Not Started | J563 | [5 empty] | NRIS Only |  | 150 |  | Wind | Marshall County,Tama County | IA |  |  |  |  | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-05 | 2017-01-24 |  |  | MidAmerican Energy Company | Marshall County,Tama County | IA | DPP-2016-AUG | West | GIA | NRIS Only | Abbott switching stationâ€™s 161 kV straight bus | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-FEB | West | Done | In Service | J493 | [5 empty] | NRIS |  | 150 |  | Wind | Yellow Medicine County | MN | [27 empty] | Done | 2015-11-12 |  | 2019-03-19 | 2019-12-31 | Otter Tail Power Company | Yellow Medicine County | MN | DPP-2016-FEB | West | GIA | NRIS | Big Stone - Brookings 345 kV Substation | 150 | 150 | Wind | WT Wind Turbine | In Service | 2020-04-30 | 150 | 150 | 150 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J564 | [5 empty] | NRIS |  | 176 |  | Wind | Fayette County, Shelby County | 0 | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-05 | 2017-07-21 |  | 2018-09-15 | Duke Energy Corporation | Fayette County, Shelby County |  |  |  | Feasibility | NRIS | Unknown | 176 | 176 | Wind |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-FEB | West | Done | In Service | J495 | [5 empty] | NRIS |  | 200 |  | Wind | Winnebago County | IA | [27 empty] | Done | 2015-11-12 |  | 2019-01-31 | 2019-09-15 | ITC Midwest | Winnebago County | IA | DPP-2016-FEB | West | GIA | NRIS | Ledyard-Colby 345kV line | 200 | 200 | Wind | WT Wind Turbine | In Service | 2019-09-28 | 200 | 200 | 200 | 50
|  |  |  | 0 | 0 | Withdrawn | Not Started | J565 | [5 empty] | NRIS |  | 101.8 |  | Solar | Concordia Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-06 | 2016-09-14 |  | 2019-04-15 | Entergy | Concordia Parish | LA |  |  | Feasibility | NRIS | Unknown | 101.8 | 101.8 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J566 | [5 empty] | NRIS |  | 101.9 |  | Solar | Acadia Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-06 | 2017-07-21 |  | 2019-04-15 | Entergy | Acadia Parish | LA |  |  | Feasibility | NRIS | Unknown | 101.9 | 101.9 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-FEB | West | Done | In Service | J498 | [5 empty] | NRIS |  | 340 |  | Wind | Boone County,Greene County | IA | [27 empty] | Done | 2015-11-13 |  | 2019-02-08 | 2017-07-01 | MidAmerican Energy Company | Boone County,Greene County | IA | DPP-2016-FEB | West | GIA | NRIS | MEC 345 kV Grimes-Lehigh line (18 miles south of Leigh substation) | 340 | 340 | Wind | WT Wind Turbine | In Service | 2017-01-31 | 340 | 340 | 340 | 340
|  |  |  | DPP-2016-FEB | West | Done | In Service | J499 | [5 empty] | NRIS |  | 340 |  | Wind | Adair County,Madison County | IA | [27 empty] | Done | 2015-11-13 |  | 2019-02-08 | 2017-07-01 | MidAmerican Energy Company | Adair County,Madison County | IA | DPP-2016-FEB | West | GIA | NRIS | MEC 345 kV Fallow-Grimes line (18 miles east of Fallow substation) | 340 | 340 | Wind | WT Wind Turbine | In Service | 2016-03-01 | 340 | 340 | 340 | 340
|  |  |  | DPP-2016-FEB | West | Done | In Service | J500 | [5 empty] | NRIS |  | 500 |  | Wind | Adair County | IA | [27 empty] | Done | 2015-11-13 |  | 2019-02-11 | 2017-07-01 | MidAmerican Energy Company | Adair County | IA | DPP-2016-FEB | West | GIA | NRIS | New substation at intersection of MEC 345 kV Boone-Atchison and MEC 345 kV Rolling Hills-Madison County substation | 500 | 500 | Wind | WT Wind Turbine | In Service | 2017-09-30 | 500 | 500 | 500 | 500
|  |  |  | DPP-2015-FEB | East (ITC) | Withdrawn | Withdrawn | J308 | [5 empty] | NRIS |  | 301 |  | Wind | Sanilac County | MI | [27 empty] | Withdrawn | 2013-11-18 | 2019-11-20 | 2016-07-06 | 2016-09-01 | ITC Transmission | Sanilac County | MI | DPP-2015-FEB | East (ITC) | Int FaS | NRIS | ITC Rapson-Banner 345kV Line | 301 | 301 | Wind | WT Wind Turbine | Withdrawn | 2016-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J567 | [5 empty] | NRIS |  | 201.5 |  | Solar | Iberville Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-06 | 2017-07-21 |  | 2019-04-15 | Entergy | Iberville Parish | LA |  |  | Feasibility | NRIS | Unknown | 201.5 | 201.5 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Done | In Service | J503 | [5 empty] | NRIS |  | 98.8 |  | Wind | Emmons County,Logan County | ND | [27 empty] | Done | 2015-11-13 |  | 2019-12-16 | 2019-09-20 | Montana-Dakota Utilities Company | Emmons County,Logan County | ND | DPP-2016-AUG | West | GIA | NRIS | 230 kV Heskett-Wishek, 20 miles NW of Wishek | 98.8 | 98.8 | Wind | WT Wind Turbine | In Service | 2019-11-15 | 100 | 100 | 100 | 100
|  |  |  | DPP-2016-FEB | West | Done | Under Construction | J504 | [5 empty] | NRIS |  | 50 |  | Solar | Linn County | IA | [27 empty] | Done | 2015-11-13 |  | 2019-02-07 |  | ITC Midwest | Linn County | IA | DPP-2016-FEB | West | GIA | NRIS | 161 kV Bertram-Duane Arnold line | 50 | 50 | Solar | PV Photovoltaic | Under Construction | 2020-10-15 | 50 | 50 | 50 | 50
|  |  |  | DPP-2016-FEB | East (ATC) | Done | Under Construction | J505 | [5 empty] | NRIS |  | 99 |  | Solar | Manitowoc County | WI | [27 empty] | Done | 2015-11-13 |  | 2018-02-05 | 2021-05-01 | American Transmission Co. LLC | Manitowoc County | WI | DPP-2016-FEB | East (ATC) | GIA | NRIS | Apollo 138kV Substation Mishicot-Kewaunee line | 99 | 99 | Solar | PV Photovoltaic | Under Construction | 2021-01-28 | 99 | 99 | 99 | 99
|  |  |  | DPP-2016-FEB | West | Done | In Service | J506 | [5 empty] | NRIS |  | 200 |  | Wind | Plymouth County | IA | [27 empty] | Done | 2015-11-13 |  | 2018-10-22 | 2019-09-15 | MidAmerican Energy Company | Plymouth County | IA | DPP-2016-FEB | West | GIA | NRIS | Raun-Lakefield Jct 345 kV line tap (T-19N, R-43W) | 200 | 200 | Wind | WT Wind Turbine | In Service | 2019-09-16 | 200 | 200 | 200 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J568 | [5 empty] | NRIS |  | 101.6 |  | Solar | Calcasieu Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-06 | 2016-09-14 |  | 2019-03-01 | Entergy | Calcasieu Parish | LA |  |  | Feasibility | NRIS | Unknown | 101.6 | 101.6 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1488 | [5 empty] | NRIS |  | 500 |  | High Voltage DC | Randolph County | MO | [27 empty] | Active | 2019-04-29 |  |  | 2024-03-31 | Ameren Missouri | Randolph County | MO | DPP-2019-Cycle | Central | PHASE 1 | NRIS | McCredie - Montgomery 345 kV Line Tap | 500 | 500 | High Voltage DC | HVDC | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Active | Not Started | J1490 | [5 empty] | NRIS |  | 1000 |  | High Voltage DC | Randolph County | MO | [27 empty] | Active | 2019-04-29 |  |  | 2024-03-31 | Ameren Missouri | Randolph County | MO | DPP-2019-Cycle | Central | PHASE 1 | NRIS | McCredie - Montgomery 345 kV Line Tap | 1000 | 1000 | High Voltage DC | HVDC | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-FEB | West | Done | Under Construction | J510 | [5 empty] | NRIS |  | 284.5 |  | Gas | Deuel County | SD | [27 empty] | Done | 2015-11-16 |  | 2018-12-19 | 2020-09-01 | Otter Tail Power Company | Deuel County | SD | DPP-2016-FEB | West | GIA | NRIS | Scandinavia Township 113N, Range 48W | 266 | 284.5 | Gas | CT Combustion Turbine (Simple Cycle) | Under Construction | 2018-09-30 | 284.5 | 266 | 284.5 | 0
|  |  |  | DPP-2019-Cycle | South | Withdrawn | Not Started | J1283 | [5 empty] | NRIS |  | 269.99 |  | Waste Heat Recovery | Jefferson County | AR | [27 empty] | Withdrawn | 2019-04-29 | 2019-09-05 |  | 2023-03-01 | Entergy Arkansas, LLC | Jefferson County | AR | DPP-2019-Cycle | South | PHASE 2 | NRIS | White Bluff - Arsenal C and White Bluff - Arsenal D 115kV Line | 269.99 | 269.99 | Waste Heat Recovery | OT - co-gen | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Done | In Service | J512 | [5 empty] | NRIS |  | 250 |  | Wind | Nobles County | MN | [27 empty] | Done | 2015-11-16 |  | 2019-09-12 | 2020-05-01 | Northern States Power (Xcel Energy) | Nobles County | MN | DPP-2016-AUG | West | GIA | NRIS | Nobles - Fenton 115kV line | 250 | 250 | Wind | WT Wind Turbine | In Service | 2020-06-30 | 250 | 250 | 250 | 250
|  |  |  | DPP-2016-AUG | Central | Done | In Service | J513 | [5 empty] | NRIS |  | 100.05 |  | Wind | White County | IN | [27 empty] | Done | 2015-11-16 |  | 2018-08-29 | 2017-10-15 | Northern Indiana Public Service Company | White County | IN | DPP-2016-AUG | Central | GIA | NRIS | 255173(17REYNOLDS) | 100.05 | 100.05 | Wind | WT Wind Turbine | In Service | 2020-08-15 | 100.05 | 100.05 | 100.05 | 100.05
|  |  |  | DPP-2016-FEB | West | Done | Under Construction | J514 | [5 empty] | NRIS |  | 65 |  | Combined Cycle | Marshall County | IA | [27 empty] | Done | 2015-11-16 |  | 2019-01-31 | 2017-03-01 | ITC Midwest | Marshall County | IA | DPP-2016-FEB | West | GIA | NRIS | Existing ITC Midwest Marshalltown substation | 30 | 65 | Combined Cycle | Combined Cycle | Under Construction | 2017-04-01 | 65 | 30 | 30 | 30
|  |  |  | DPP-2016-FEB | Central | Done | In Service | J515 | [5 empty] | ERIS |  | 400 |  | Wind | Benton County,Warren County | IN | [27 empty] | Done | 2015-11-16 |  | 2017-02-23 | 2017-06-01 | Duke Energy Corporation | Benton County,Warren County | IN | DPP-2016-FEB | Central | GIA | ERIS | 345 kV bus in Cayuga substation on north side of plant | 400 | 400 | Wind | WT Wind Turbine | In Service | 2019-04-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Done | Under Construction | J569 | [5 empty] | NRIS | N | 100 |  | Wind | Rock County | MN |  |  |  | 1 | 1 | 1027079 | 956851 | [10 empty] | 8073528 |  | 8073528 | 8073528 | 80.7353 | 80.7353 | 8073528 |  |  |  | Done | 2016-05-06 |  | 2020-02-13 | 2018-04-15 | Northern States Power (Xcel Energy) | Rock County | MN | DPP-2016-AUG | West | GIA | NRIS | NSP Rock County Substation | 100 | 100 | Wind | WT Wind Turbine | Under Construction | 2021-10-15 | 100 | 100 | 100 | 100
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J570 | [5 empty] | NRIS |  | 150 |  | Wind | Atchison County | MO | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-06 | 2019-08-05 |  | 2018-09-15 | MidAmerican Energy Company | Atchison County | MO | DPP-2017-FEB | West | GIA | NRIS | Cooper - Atchison 345kV Line | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 150 | 150 | 0 | 0
|  |  |  | DPP-2016-AUG | Central | Withdrawn | Not Started | J573 | [5 empty] | NRIS |  | 40 |  | Solar | Washington County | MO | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-06-29 |  | 2018-10-01 | Ameren Missouri | Washington County | MO | DPP-2016-AUG | Central | GIA | NRIS | Belgrade 161kV | 40 | 40 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J574 | [5 empty] | NRIS |  | 40 |  | Wind | Kandiyohi County, Meeker County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2016-11-21 |  | 2017-08-01 | Northern States Power (Xcel Energy) | Kandiyohi County, Meeker County | MN |  |  | Feasibility | NRIS | Unknown | 40 | 40 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Withdrawn | Not Started | J575 | [5 empty] | NRIS |  | 100 |  | Wind | Lincoln County | MN |  |  |  |  | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2018-10-12 |  | 2018-09-15 | Northern States Power (Xcel Energy) | Lincoln County | MN | DPP-2016-AUG | West | GIA | NRIS | Brookings County Substation 345 kV | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J576 | [5 empty] | NRIS |  | 100 |  | Wind | Allegan County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-07-21 |  | 2018-09-15 | Michigan Electric Transmission Company, LLC | Allegan County | MI |  |  | Feasibility | NRIS | Unknown | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Withdrawn | Not Started | J577 | [5 empty] | NRIS |  | 100 |  | Wind | Pipestone County | MN |  |  |  |  | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2018-10-12 |  | 2018-09-15 | Northern States Power (Xcel Energy) | Pipestone County | MN | DPP-2016-AUG | West | GIA | NRIS | 345kV Brookings County Sub | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-FEB | West | Done | Under Construction | J523 | [5 empty] | NRIS |  | 50 |  | Solar | Mower County | MN | [27 empty] | Done | 2015-11-16 |  | 2019-03-07 | 2019-09-15 | ITC Midwest | Mower County | MN | DPP-2016-FEB | West | GIA | NRIS | ITCM Adams 161 kV Substation | 50 | 50 | Solar | PV Photovoltaic | Under Construction | 2021-09-15 | 50 | 50 | 50 | 30
|  |  |  | DPP-2016-FEB | West | Done | Under Construction | J524 | [5 empty] | NRIS |  | 100 |  | Solar | Webster County | IA | [27 empty] | Done | 2015-11-16 |  | 2019-03-11 | 2019-09-15 | MidAmerican Energy Company | Webster County | IA | DPP-2016-FEB | West | GIA | NRIS | Webster substation 161 kV bus | 100 | 100 | Solar | PV Photovoltaic | Under Construction | 2021-12-15 | 100 | 100 | 100 | 60
|  |  |  | 0 | 0 | Withdrawn | Not Started | J578 | [5 empty] | NRIS |  | 400.2 |  | Wind | Audubon County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-07-21 |  | 2018-10-01 | MidAmerican Energy Company | Audubon County | IA |  |  | Feasibility | NRIS | Unknown | 400.2 | 400.2 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-FEB | West | Done | In Service | J526 | [5 empty] | NRIS |  | 300 |  | Wind | Deuel County | SD | [27 empty] | Done | 2015-11-16 |  | 2019-02-19 |  | Otter Tail Power Company | Deuel County | SD | DPP-2016-FEB | West | GIA | NRIS | Brooking County to Big Stone South 345 kV line | 300 | 300 | Wind | WT Wind Turbine | In Service | 2020-06-29 | 300 | 300 | 300 | 0
|  |  |  | DPP-2016-FEB | West | Done | Under Construction | J527 | [5 empty] | NRIS |  | 250 |  | Wind | Adair County | IA | [27 empty] | Done | 2015-11-16 |  | 2019-03-12 |  | MidAmerican Energy Company | Adair County | IA | DPP-2016-FEB | West | GIA | NRIS | Booneville Cooper 345kV line | 250 | 250 | Wind | WT Wind Turbine | Under Construction | 2020-10-01 | 250 | 250 | 250 | 250
|  |  |  | DPP-2017-AUG | East (ITC) | Withdrawn | Not Started | J579 | [5 empty] | NRIS |  | 200 |  | Wind | Allegan County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-09 |  | 2018-10-01 | Michigan Electric Transmission Company, LLC | Allegan County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Argenta 345kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-FEB | West | Done | In Service | J529 | [5 empty] | NRIS |  | 250 |  | Wind | Palo Alto County | IA | [27 empty] | Done | 2015-11-16 |  | 2019-03-12 | 2017-10-01 | MidAmerican Energy Company | Palo Alto County | IA | DPP-2016-FEB | West | GIA | NRIS | Obrien - Kossuth 345 kV line | 250 | 250 | Wind | WT Wind Turbine | In Service | 2018-07-01 | 250 | 250 | 250 | 250
|  |  |  | DPP-2016-FEB | West | Done | In Service | J530 | [5 empty] | NRIS |  | 250 |  | Wind | Iowa County | IA | [27 empty] | Done | 2015-11-16 |  | 2019-03-13 |  | MidAmerican Energy Company | Iowa County | IA | DPP-2016-FEB | West | GIA | NRIS | Montezuma - Hills 345kV Line | 250 | 250 | Wind | WT Wind Turbine | In Service | 2020-10-01 | 250 | 250 | 250 | 250
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J580 | [5 empty] | ERIS | E | 298 |  | Wind | Burleigh County | ND |  |  |  | 1 | 0 | 1223600 | 10282913 | [7 empty] | 19446106 | 0 |  | 226356861 | 0 | 245802967 | 245802967 | 824.8422 | 824.8422 | 245802967 |  |  |  | Withdrawn | 2017-06-16 | 2021-01-29 |  | 2021-09-15 | Montana-Dakota Utilities Company | Burleigh County | ND | DPP-2017-AUG | West | PHASE 3 | ERIS | Nepoleon Sub 230kV | 298 | 298 | Wind | WT Wind Turbine | Not Started |  | 298 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Withdrawn | Not Started | J1459 | [5 empty] | NRIS |  | 670 |  | Gas | Calhoun County | MI | [27 empty] | Withdrawn | 2019-04-29 | 2020-01-27 |  | 2024-03-01 | Michigan Electric Transmission Company, LLC | Calhoun County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Argenta - Tompkins 345 kV Line Tap | 670 | 670 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-FEB | East (ITC) | Done | In Service | J533 | [5 empty] | NRIS |  | 200 |  | Wind | Gratiot County | MI | [27 empty] | Done | 2015-11-16 |  | 2018-08-29 | 2017-10-01 | Michigan Electric Transmission Company, LLC | Gratiot County | MI | DPP-2016-FEB | East (ITC) | GIA | NRIS | Slate 345kV Substation | 200 | 200 | Wind | WT Wind Turbine | In Service | 2019-10-01 | 200 | 200 | 200 | 200
|  |  |  | DPP-2016-FEB | West | Done | In Service | J534 | [5 empty] | NRIS |  | 250 |  | Wind | Humboldt County,Kossuth County | IA | [27 empty] | Done | 2015-11-16 |  | 2019-02-11 | 2017-10-01 | MidAmerican Energy Company | Humboldt County,Kossuth County | IA | DPP-2016-FEB | West | GIA | NRIS | Kossuth â€“ Webster 345kV Line | 250 | 250 | Wind | WT Wind Turbine | In Service | 2020-04-01 | 250 | 250 | 250 | 250
|  |  |  | DPP-2016-FEB | West | Done | In Service | J535 | [5 empty] | NRIS |  | 210 |  | Wind | Sac County | IA | [27 empty] | Done | 2015-11-16 |  | 2018-12-20 | 2017-10-01 | MidAmerican Energy Company | Sac County | IA | DPP-2016-FEB | West | GIA | NRIS | J411 â€“ Lehigh 345kV Line | 210 | 210 | Wind | WT Wind Turbine | In Service | 2020-04-01 | 210 | 210 | 210 | 84
|  |  |  | DPP-2016-AUG | South | Done | Under Construction | J581 | [5 empty] | NRIS |  | 70 |  | Solar | Morehouse Parish | LA | [5 empty] | Bastrop - Sterlington 115kV Line | [15 empty] | 0 | 0 |  |  |  |  | Done | 2016-05-09 |  | 2018-05-02 | 2018-10-01 | Entergy | Morehouse Parish | LA | DPP-2016-AUG | South | GIA | NRIS | Bastrop - Sterlington 115kV Line | 70 | 70 | Solar | PV Photovoltaic | Under Construction | 2020-10-05 | 70 | 70 | 70 | 70
|  |  |  | 0 | 0 | Withdrawn | Not Started | J582 | [5 empty] | NRIS |  | 100 |  | Solar | Madison Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-07-21 |  | 2018-10-01 | Entergy | Madison Parish | LA |  |  | Feasibility | NRIS | Unknown | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-FEB | East (ITC) | Done | In Service | J538 | [5 empty] | NRIS |  | 150 |  | Wind | Hillsdale County | MI | [27 empty] | Done | 2015-11-16 |  | 2018-08-29 | 2017-10-01 | Michigan Electric Transmission Company, LLC | Hillsdale County | MI | DPP-2016-FEB | East (ITC) | GIA | NRIS | Moore Rd to Dowling 138kV line | 150 | 150 | Wind | WT Wind Turbine | In Service | 2020-10-01 | 150 | 150 | 150 | 150
|  |  |  | DPP-2016-AUG | West | Done | Under Construction | J583 | [5 empty] | NRIS | N | 200 |  | Wind | Audubon County | IA |  |  |  | 1 | 1 | 1045535 | 3970000 | [9 empty] | 0 | 14692471 | 0 | 14692471 | 14692471 | 73.4624 | 73.4624 | 14692471 |  |  |  | Done | 2016-05-09 |  | 2020-02-11 | 2021-09-10 | MidAmerican Energy Company | Audubon County | IA | DPP-2016-AUG | West | GIA | NRIS | Fallow Avenue 345kV Substation. Zip Code 50002 | 200 | 200 | Wind | WT Wind Turbine | Under Construction | 2021-12-31 | 200 | 200 | 200 | 200
|  |  |  | DPP-2016-FEB | East (ITC) | Done | In Service | J540 | [5 empty] | NRIS Only |  | 0 |  | Gas | Kalkaska County | MI | [27 empty] | Done | 2016-01-04 |  | 2018-10-01 |  | Wolverine Power Supply Cooperative, Inc. | Kalkaska County | MI | DPP-2016-FEB | East (ITC) | GIA | NRIS Only | Kalkaska County, MI - CP Node : CONS.KALK | 48.6 | 0 | Gas | CT Combustion Turbine (Simple Cycle) | In Service |  | 0 | 48.6 | 0 | 48.6
|  |  |  | DPP-2017-FEB | East (ATC) | Withdrawn | Withdrawn | J584 | [5 empty] | NRIS |  | 60 |  | Wind | Green County | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2020-09-29 | 2019-03-26 | 2018-09-15 | American Transmission Co. LLC | Green County | WI | DPP-2017-FEB | East (ATC) | GIA | NRIS | Blacksmith Tap - Spring Grove 69kV Line | 60 | 60 | Wind | WT Wind Turbine | Withdrawn | 2021-05-15 | 60 | 60 | 60 | 60
|  |  |  | 0 | 0 | Withdrawn | Not Started | J585 | [5 empty] | NRIS |  | 100 |  | Solar | Madison County | MS | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-07-21 |  | 2018-11-01 | Entergy | Madison County | MS |  |  | Feasibility | NRIS | Unknown | 100 | 100 | Solar | PV Photovoltaic | Not Started | 2016-01-31 | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | South | Done | Not Started | J586 | [5 empty] | NRIS |  | 175 |  | Solar | Mississippi County | AR | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-05-09 |  | 2018-06-11 | 2018-11-01 | Entergy | Mississippi County | AR | DPP-2016-AUG | South | GIA | NRIS | EAI Crooked Lake 161kV Substation | 175 | 175 | Solar | PV Photovoltaic | Not Started | 2021-03-01 | 175 | 175 | 175 | 175
|  |  | Bayou Galion Solar from 1803 2020 PPAs, document reads "project will be connected at existing Entergy Louisiana Galion Substation" at 138 kV | DPP-2016-AUG | West | Done | In Service | J587 | [5 empty] | NRIS | N | 200 |  | Wind | Lincoln County | MN |  |  |  | 1 | 1 | 1382159 | 9530643 | [9 empty] | 0 | 31681519 | 0 | 31681519 | 31681519 | 158.4076 | 158.4076 | 31681519 |  |  |  | Done | 2016-05-09 |  | 2019-09-23 | 2019-09-30 | Northern States Power (Xcel Energy) | Lincoln County | MN | DPP-2016-AUG | West | GIA | NRIS | J460 substation on the Brookings-H081 345kV line | 200 | 200 | Wind | WT Wind Turbine | In Service | 2020-09-14 | 200 | 200 | 200 | 200
|  |  |  | DPP-2016-AUG | South | Withdrawn | Not Started | J588 | [5 empty] | NRIS |  | 100 |  | Solar | Panola County,Quitman County,Tunica County | MS | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-05-16 |  | 2018-11-01 | Entergy | Panola County,Quitman County,Tunica County | MS | DPP-2016-AUG | South | GIA | NRIS | Tapping on Tunica to Crenshaw 115kV line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | East (ITC) | Done | In Service | J589 | [5 empty] | NRIS |  | 148.8 |  | Wind | Gratiot County | MI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-05-09 |  | 2018-11-28 | 2018-10-01 | Michigan Electric Transmission Company, LLC | Gratiot County | MI | DPP-2016-AUG | East (ITC) | GIA | NRIS | Regal-Summerton 138kV line | 148.8 | 148.8 | Wind | WT Wind Turbine | In Service | 2018-12-10 | 148.8 | 148.8 | 148.8 | 148.8
|  |  |  | DPP-2019-Cycle | Central | Withdrawn | Not Started | J1288 | [5 empty] | NRIS |  | 667.2 |  | Gas | Vermillion County | IN | [27 empty] | Withdrawn | 2019-04-29 | 2020-04-16 |  | 2023-08-01 | Duke Energy Indiana | Vermillion County | IN | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Cayuga - Sugar Creek 345kVLine | 606.7 | 667.2 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Done | In Service | J590 | [5 empty] | NRIS | N | 90 |  | Wind | Palo Alto County | IA |  |  |  | 1 | 1 | 819471 | 1512658 | [9 empty] | 0 | 7964204 | 0 | 7964204 | 7964204 | 88.4912 | 88.4912 | 7964204 |  |  |  | Done | 2016-05-09 |  |  | 2017-10-01 | MidAmerican Energy Company | Palo Alto County | IA | DPP-2016-AUG | West | GIA | NRIS | Obrien - Kossuth 345 kV line | 90 | 90 | Wind | WT Wind Turbine | In Service | 2019-10-01 | 90 | 90 | 90 | 90
|  |  |  | DPP-2019-Cycle | East (ATC) | Withdrawn | Not Started | J1264 | [5 empty] | NRIS |  | 20 |  | Gas | Schoolcraft County | MI | [27 empty] | Withdrawn | 2019-04-29 | 2020-05-11 |  | 2021-09-01 | American Transmission Co. LLC | Schoolcraft County | MI | DPP-2019-Cycle | East (ATC) | PHASE 2 | NRIS | Blaney Park - Engadine - Hiawatha - Alger - Munising 69kV Line | 20 | 20 | Gas | CT Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | East (ATC) | Withdrawn | Not Started | J592 | [5 empty] | NRIS |  | 48.3 |  | Wind | Delta County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-07-17 |  | 2018-07-15 | American Transmission Co. LLC | Delta County | MI | DPP-2016-AUG | East (ATC) | GIA | NRIS | Garden Corners 138kV Substation | 48.3 | 48.3 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Withdrawn | Not Started | J593 | [5 empty] | NRIS |  | 224 |  | Wind | Williams County | ND |  |  |  |  | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2018-10-12 |  | 2018-09-01 | Montana-Dakota Utilities Company | Williams County | ND | DPP-2016-AUG | West | GIA | NRIS | Tioga 4 230kV Substation (MDU) | 224 | 224 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Withdrawn | Not Started | J594 | [5 empty] | NRIS |  | 300 |  | Wind | Jackson County,Martin County | MN |  |  |  |  | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2018-10-12 |  | 2018-09-01 | ITC Midwest | Jackson County,Martin County | MN | DPP-2016-AUG | West | GIA | NRIS | Jackson North 161kV (ITCM) | 300 | 300 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | Central | Withdrawn | Not Started | J1489 | [5 empty] | NRIS |  | 500 |  | High Voltage DC | Ralls County | MO | [27 empty] | Withdrawn | 2019-04-29 | 2020-05-22 |  | 2024-03-31 | Ameren Missouri | Ralls County | MO | DPP-2019-Cycle | Central | PHASE 1 | NRIS | Maywood - Spencer Creek 345 kV Line Tap | 500 | 500 | High Voltage DC | HVDC | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2019-Cycle | East (ITC) | Withdrawn | Not Started | J1346 | [5 empty] | NRIS |  | 382 |  | Gas | Wayne County | MI | [27 empty] | Withdrawn | 2019-04-29 | 2020-05-29 |  | 2022-01-01 | ITC Transmission | Wayne County | MI | DPP-2019-Cycle | East (ITC) | PHASE 2 | NRIS | Brownstown 345kV Substation | 334 | 382 | Gas | CT Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | Central | Withdrawn | Not Started | J595 | [5 empty] | NRIS |  | 150 |  | Wind | Clinton County | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-06-29 |  | 2018-09-01 | Duke Energy Corporation | Clinton County | IN | DPP-2016-AUG | Central | GIA | NRIS | Frankfort to New London 230kV Line Tap | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | West | Withdrawn | Withdrawn | J391 | [5 empty] | NRIS |  | 50 |  | Gas | Lyon County | MN | [27 empty] | Withdrawn | 2014-09-15 | 2020-01-23 |  | 2016-09-01 | Missouri River Energy Services (MRES) | Lyon County | MN | DPP-2015-FEB | West | DPP - SIS | NRIS | MMU's N 7th Street substation | 50 | 50 | Gas | CT Combustion Turbine (Simple Cycle) | Withdrawn | 2016-02-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Withdrawn | Not Started | J596 | [5 empty] | NRIS |  | 100 |  | Wind | Big Stone County,Stevens County | MN |  |  |  |  | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2018-10-12 |  | 2018-09-01 | Great River Energy | Big Stone County,Stevens County | MN | DPP-2016-AUG | West | GIA | NRIS | Morris -Moro 115kV Tap | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Withdrawn | Not Started | J597 | [5 empty] | NRIS |  | 300 |  | Wind | Deuel County,Hamlin County | SD |  |  |  |  | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2018-10-12 |  | 2018-09-01 | Northern States Power (Xcel Energy) | Deuel County,Hamlin County | SD | DPP-2016-AUG | West | GIA | NRIS | Brookings County Substation 345 | 300 | 300 | Wind | WT Wind Turbine | Not Started | 2016-12-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Withdrawn | Withdrawn | J598 | [5 empty] | NRIS | N | 300 |  | Wind | Adair County,Schuyler County | MO |  |  |  | 1 | 0 | 1289238 | 8208476 | [9 empty] | 0 | 27522302 | 0 | 27522302 | 27522302 | 91.741 | 91.741 | 27522302 |  |  |  | Withdrawn | 2016-05-09 | 2020-01-16 |  | 2020-09-01 | Ameren Transmission Company of Illinois | Adair County,Schuyler County | MO | DPP-2016-AUG | West | GIA | NRIS | Zachary to Ottumwa 345kV tap | 300 | 300 | Wind | WT Wind Turbine | Withdrawn | 2021-10-01 | 300 | 300 | 300 | 300
|  |  |  | DPP-2016-AUG | West | Withdrawn | Not Started | J599 | [5 empty] | NRIS |  | 200 |  | Wind | Walworth County | SD |  |  |  |  | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2018-10-12 |  | 2018-09-01 | Montana-Dakota Utilities Company | Walworth County | SD | DPP-2016-AUG | West | GIA | NRIS | Glenham 230kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J600 | [5 empty] | NRIS |  | 150 |  | Wind | Rock County, Walworth County | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-06-08 |  | 2018-09-01 | American Transmission Co. LLC | Rock County, Walworth County | WI |  |  | Feasibility | NRIS | Unknown | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | East (ITC) | Withdrawn | Not Started | J601 | [5 empty] | NRIS |  | 100 |  | Wind | Lapeer County,Tuscola County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2018-01-16 |  | 2018-09-01 | ITC Transmission | Lapeer County,Tuscola County | MI | DPP-2016-AUG | East (ITC) | GIA | NRIS | Kilgore - Micah 120kV with the line distance 1 mile from Kilgore | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 100 | 100 | 0 | 0
|  |  |  | DPP-2016-FEB | West | Withdrawn | Withdrawn | J528 | [5 empty] | NRIS |  | 200 |  | Wind | Adair County | IA | [27 empty] | Withdrawn | 2015-11-16 | 2020-01-29 |  |  | MidAmerican Energy Company | Adair County | IA | DPP-2016-FEB | West | GIA | NRIS | Rolling Hills - Madison 345kV Line | 200 | 200 | Wind | WT Wind Turbine | Withdrawn | 2020-10-01 | 200 | 200 | 200 | 70
|  |  |  | DPP-2016-AUG | East (ITC) | Withdrawn | Withdrawn | J602 | [5 empty] | NRIS |  | 200 |  | Wind | Shiawassee County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2020-03-09 | 2018-11-08 | 2018-09-01 | Michigan Electric Transmission Company, LLC | Shiawassee County | MI | DPP-2016-AUG | East (ITC) | GIA | NRIS | Goss 138kV Substation | 200 | 200 | Wind | WT Wind Turbine | Withdrawn | 2021-09-01 | 200 | 200 | 200 | 200
|  |  |  | DPP-2016-AUG | South | Done | Not Started | J603 | [5 empty] | NRIS |  | 99.96 |  | Solar | 0 | AR | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-05-09 |  | 2018-06-11 | 2018-09-01 | Entergy |  | AR | DPP-2016-AUG | South | GIA | NRIS | Tap on Montrose â€“ Mist 115 kV line | 99.96 | 99.96 | Solar | PV Photovoltaic | Not Started | 2021-09-15 | 99.96 | 99.96 | 99.96 | 99.96
|  |  |  | DPP-2016-AUG | South | Done | Not Started | J604 | [5 empty] | NRIS |  | 99.96 |  | Solar | Sunflower County | MS | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-05-09 |  | 2018-06-12 | 2018-09-01 | Entergy | Sunflower County | MS | DPP-2016-AUG | South | GIA | NRIS | Ruleville 115kV Sub | 99.96 | 99.96 | Solar | PV Photovoltaic | Not Started | 2021-09-15 | 99.96 | 99.96 | 99.96 | 99.96
|  |  |  | 0 | 0 | Withdrawn | Not Started | J605 | [5 empty] | NRIS |  | 99.96 |  | Solar | Morehouse Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-06-08 |  | 2018-09-01 | Entergy | Morehouse Parish | LA |  |  | Feasibility | NRIS | Unknown | 99.96 | 99.96 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | East (ATC) | Withdrawn | Not Started | J606 | [5 empty] | NRIS |  | 150 |  | Wind | Monroe County | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-03-24 |  | 2018-09-18 | American Transmission Co. LLC | Monroe County | WI | DPP-2016-AUG | East (ATC) | GIA | NRIS | La Crosse to North Madison 345kV Line Tap (ATC) | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Withdrawn | Not Started | J607 | [5 empty] | NRIS |  | 150 |  | Wind | Logan County | ND |  |  |  |  | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2018-10-12 |  | 2018-09-01 | Montana-Dakota Utilities Company | Logan County | ND | DPP-2016-AUG | West | GIA | NRIS | Wishek - Heskett 230kV line | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | East (ITC) | Withdrawn | Not Started | J608 | [5 empty] | NRIS |  | 100 |  | Wind | Montcalm County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2018-01-16 |  | 2018-09-01 | Michigan Electric Transmission Company, LLC | Montcalm County | MI | DPP-2016-AUG | East (ITC) | GIA | NRIS | Deja 138kV Substation | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 100 | 100 | 0 | 0
|  |  |  | DPP-2016-AUG | East (ITC) | Withdrawn | Not Started | J609 | [5 empty] | NRIS |  | 136 |  | Wind | Muskegon County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-08-18 |  | 2018-09-01 | Michigan Electric Transmission Company, LLC | Muskegon County | MI | DPP-2016-AUG | East (ITC) | GIA | NRIS | White Road 115kV Substation | 136 | 136 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J610 | [5 empty] | NRIS |  | 300 |  | Wind | Benton County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-06-08 |  | 2018-09-01 | ITC Midwest | Benton County | IA |  |  | Feasibility | NRIS | Unknown | 300 | 300 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Done | In Service | J611 | [5 empty] | NRIS | N | 110 |  | Wind | Nodaway County | MO |  |  |  | 1 | 1 | 1106198 | 476247 | [9 empty] | 0 | 9371999 | 250000 | 9371999 | 9621999 | 85.2 | 87.4727 | 9621999 |  |  |  | Done | 2016-05-09 |  | 2019-12-18 | 2020-09-01 | MidAmerican Energy Company | Nodaway County | MO | DPP-2016-AUG | West | GIA | NRIS | Clarinda - Merryville 161kV tap | 110 | 110 | Wind | WT Wind Turbine | In Service | 2020-10-01 | 110 | 110 | 110 | 110
|  |  |  | 0 | 0 | Withdrawn | Not Started | J612 | [5 empty] | NRIS |  | 150 |  | Wind | Kittson County, Marshall County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-06-08 |  | 2018-09-01 | Otter Tail Power Company | Kittson County, Marshall County | MN |  |  | Feasibility | NRIS | Unknown | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Withdrawn | Not Started | J613 | [5 empty] | NRIS |  | 100 |  | Wind | Stutsman County | ND |  |  |  |  | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2018-10-12 |  | 2018-08-01 | Otter Tail Power Company | Stutsman County | ND | DPP-2016-AUG | West | GIA | NRIS | Jamestown Substation 115kV | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Done | In Service | J614 | [5 empty] | NRIS | N | 66 |  | Wind | Howard County | IA |  |  |  | 1 | 1 | 496212 | 1347250 | [9 empty] | 0 | 12168508 | 0 | 12168508 | 12168508 | 184.3713 | 184.3713 | 12168508 |  |  |  | Done | 2016-05-09 |  | 2020-02-14 | 2018-08-04 | Southern Minnesota Municipal Power Agency | Howard County | IA | DPP-2016-AUG | West | GIA | NRIS | Rice 161kV Substation | 66 | 66 | Wind | WT Wind Turbine | In Service | 2018-12-17 | 66 | 66 | 66 | 66
|  |  |  | DPP-2016-AUG | West | Withdrawn | Not Started | J615 | [5 empty] | NRIS |  | 70 |  | Wind | Black Hawk County | IA |  |  |  |  | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2018-10-12 |  | 2018-08-04 | MidAmerican Energy Company | Black Hawk County | IA | DPP-2016-AUG | West | GIA | NRIS | Electric Farms- Shaulis 161kV | 70 | 70 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J616 | [5 empty] | NRIS |  | 50 |  | Solar | Ouachita Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-07-21 |  | 2019-06-10 | Entergy | Ouachita Parish | LA |  |  | Feasibility | NRIS | Unknown | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J617 | [5 empty] | NRIS |  | 100 |  | Solar | Lincoln County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2016-12-27 |  | 2019-06-01 | Entergy | Lincoln County | AR |  |  | Feasibility | NRIS | Unknown | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA-2016-NOV | 0 | Withdrawn | Not Started | J618 | [5 empty] | NRIS |  | 58.7 |  | Solar | Franklin Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-05-03 |  | 2018-06-01 | Entergy | Franklin Parish | LA | SPA-2016-NOV |  | SPA - SIS | NRIS | Unknown | 58.7 | 58.7 | Solar | PV Photovoltaic | Not Started | 2018-07-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | South | Withdrawn | Withdrawn | J619 | [5 empty] | NRIS |  | 50 |  | Solar | St. Landry Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2019-01-18 | 2018-06-20 | 2018-01-30 | Entergy | St. Landry Parish | LA | DPP-2016-AUG | South | GIA | NRIS | Champagne 69kV Substation | 50 | 50 | Solar | PV Photovoltaic | Withdrawn |  | 50 | 50 | 50 | 50
|  |  |  | DPP-2016-AUG | South | Done | In Service | J620 | [5 empty] | NRIS |  | 100 |  | Solar | Chicot County | AR | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-05-09 |  | 2018-06-11 | 2018-01-30 | Entergy | Chicot County | AR | DPP-2016-AUG | South | GIA | NRIS | Tap 1396 - Tap 1398 115kV | 100 | 100 | Solar | PV Photovoltaic | In Service | 2019-12-19 | 100 | 100 | 100 | 100
|  |  |  | SPA-2016-NOV | 0 | Withdrawn | Not Started | J621 | [5 empty] | NRIS |  | 100 |  | Solar | Lincoln County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-07-21 |  | 2018-01-30 | Entergy | Lincoln County | AR | SPA-2016-NOV |  | SPA - SIS | NRIS | Unknown | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | South | Withdrawn | Not Started | J622 | [5 empty] | NRIS |  | 100 |  | Solar | Lonoke County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-05-16 |  | 2018-01-30 | Entergy | Lonoke County | AR | DPP-2016-AUG | South | GIA | NRIS | tap on Remington - Lonoke East 115 kV line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA-2016-NOV | 0 | Withdrawn | Not Started | J623 | [5 empty] | NRIS |  | 20 |  | Solar | Yellow Medicine County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-07-21 |  | 2018-09-01 | Northern States Power (Xcel Energy) | Yellow Medicine County | MN | SPA-2016-NOV |  | SPA - SIS | NRIS | Unknown | 20 | 20 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA-2016-NOV | 0 | Withdrawn | Not Started | J624 | [5 empty] | NRIS |  | 80 |  | Solar | Yellow Medicine County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-07-21 |  | 2018-09-01 | Northern States Power (Xcel Energy) | Yellow Medicine County | MN | SPA-2016-NOV |  | SPA - SIS | NRIS | Unknown | 80 | 80 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J625 | [5 empty] | NRIS |  | 400 |  | Wind | Meeker County,Renville County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-02-04 |  | 2019-09-15 | Northern States Power (Xcel Energy) | Meeker County,Renville County | MN | DPP-2017-AUG | West | PHASE 3 | NRIS | Blue Lake 345kV Substation | 400 | 400 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA-2016-NOV | 0 | Withdrawn | Not Started | J626 | [5 empty] | NRIS |  | 400 |  | Wind | Meeker County, Renville County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-07-21 |  | 2019-09-15 | Northern States Power (Xcel Energy) | Meeker County, Renville County | MN | SPA-2016-NOV |  | SPA - SIS | NRIS | Unknown | 400 | 400 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA-2016-NOV | 0 | Withdrawn | Not Started | J627 | [5 empty] | NRIS |  | 400 |  | Wind | Meeker County, Renville County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-07-21 |  | 2019-09-15 | Northern States Power (Xcel Energy) | Meeker County, Renville County | MN | SPA-2016-NOV |  | SPA - SIS | NRIS | Unknown | 400 | 400 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Active | Not Started | J628 | [5 empty] | ERIS | N | 400 |  | Wind | Grand Forks County,Nelson County | ND |  |  |  | 1 | 1 | 1600000 | 13627542 | [7 empty] | 14790414 | 148236421 |  | 33704318 | 0 | 48494732 | 196731153 | 121.2368 | 491.8279 | 48494732 |  |  |  | Active | 2017-06-16 |  |  | 2022-07-01 | Great River Energy | Grand Forks County,Nelson County | ND | DPP-2017-AUG | West | PHASE 3 | ERIS | Ramsey - Prairie 230kV Line Tap | 400 | 400 | Wind | WT Wind Turbine | Not Started |  | 400 | 400 | 400 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J629 | [5 empty] | NRIS |  | 200 |  | Wind | Deuel County | SD | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-07-21 |  | 2019-09-15 | Otter Tail Power Company | Deuel County | SD |  |  | SPA - SIS | NRIS | Unknown | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA-2016-NOV | 0 | Withdrawn | Not Started | J630 | [5 empty] | NRIS |  | 200 |  | Wind | Deuel County | SD | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-07-21 |  | 2019-09-15 | Otter Tail Power Company | Deuel County | SD | SPA-2016-NOV |  | SPA - SIS | NRIS | Unknown | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA-2016-NOV | 0 | Withdrawn | Not Started | J631 | [5 empty] | NRIS |  | 200 |  | Wind | Allegan County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-07-21 |  | 2019-09-15 | Michigan Electric Transmission Company, LLC | Allegan County | MI | SPA-2016-NOV |  | SPA - SIS | NRIS | Unknown | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ITC) | Withdrawn | Not Started | J632 | [5 empty] | NRIS |  | 200 |  | Wind | Berrien County,Van Buren County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-09 |  | 2018-09-15 | Michigan Electric Transmission Company, LLC | Berrien County,Van Buren County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Argenta - Plaisades 345kV Line | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA-2016-NOV | 0 | Withdrawn | Not Started | J633 | [5 empty] | NRIS |  | 50 |  | Solar | Jefferson Davis Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-07-21 |  | 2018-01-30 | Entergy | Jefferson Davis Parish | LA | SPA-2016-NOV |  | SPA - SIS | NRIS | Unknown | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | South | Withdrawn | Withdrawn | J634 | [5 empty] | NRIS |  | 72 |  | Solar | Calcasieu,Calcasieu Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2018-08-07 |  | 2018-01-30 | Entergy | Calcasieu,Calcasieu Parish | LA | DPP-2016-AUG | South | GIA | NRIS | Mossvile-Toomey 138kV Line | 72 | 72 | Solar | PV Photovoltaic | Withdrawn | 2020-07-31 | 72 | 72 | 72 | 72
|  |  |  | DPP-2017-FEB | South | Withdrawn | Not Started | J635 | [5 empty] | NRIS |  | 35 |  | Solar | Concordia Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-06-15 |  | 2018-02-28 | Entergy | Concordia Parish | LA | DPP-2017-FEB | South | GIA | NRIS | Tap - Entergy 115kV T-line Natchez/South Plantation (ID:668) 1mile from Plantation Sub | 35 | 35 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Withdrawn | Not Started | J637 | [5 empty] | NRIS | N | 98 |  | Wind | Deuel County | SD |  |  |  | 1 | 0 | 980000 | 6457111 | [9 empty] | 0 | 45156913 |  | 45156913 | 45156913 | 460.7848 | 460.7848 | 45156913 |  |  |  | Withdrawn | 2016-05-09 | 2019-01-14 |  | 2018-09-15 | Otter Tail Power Company | Deuel County | SD | DPP-2016-AUG | West | GIA | NRIS | Big Stone - Brookings 345 kV | 98 | 98 | Wind | WT Wind Turbine | Not Started |  | 98 | 98 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Withdrawn | Not Started | J638 | [5 empty] | NRIS |  | 204 |  | Wind | Deuel County | SD |  |  |  |  | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2018-10-12 |  | 2019-09-15 | Otter Tail Power Company | Deuel County | SD | DPP-2016-AUG | West | GIA | NRIS | Big Stone - Brookings 345 kV | 204 | 204 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | South | Done | Under Construction | J639 | [5 empty] | NRIS |  | 50 |  | Solar | West Baton Rouge Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-12-02 | 2019-04-01 | Entergy | West Baton Rouge Parish | LA | DPP-2017-AUG | South | GIA | NRIS | Addis - Big Cajun 230kV Line | 50 | 50 | Solar | PV Photovoltaic | Under Construction | 2020-11-25 | 50 | 50 | 50 | 50
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J640 | [5 empty] | NRIS |  | 50 |  | Solar | St. Helena Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-07 |  | 2019-04-01 | Entergy | St. Helena Parish | LA | DPP-2017-AUG | South | GIA | NRIS | Amite - Liberty 115kV Line | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | Central | Done | Under Construction | J641 | [5 empty] | NRIS |  | 111 |  | Solar | Morgan County,Scott County | IL | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-05-09 |  | 2018-10-31 | 2020-04-01 | Ameren Illinois | Morgan County,Scott County | IL | DPP-2016-AUG | Central | GIA | NRIS | Line tap of Meredoisa sub to Jacksonville Industrial Park 138kv | 140 | 111 | Solar | PV Photovoltaic | Under Construction | 2021-06-01 | 140 | 111 | 140 | 111
|  |  |  | DPP-2016-AUG | Central | Withdrawn | Not Started | J642 | [5 empty] | NRIS |  | 175 |  | Solar | Montgomery County | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-06-29 |  | 2020-04-10 | Duke Energy Corporation | Montgomery County | IN | DPP-2016-AUG | Central | GIA | NRIS | Whitesville Sub 230kV | 175 | 175 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | Central | Done | Under Construction | J643 | [5 empty] | NRIS |  | 175 |  | Solar | Jasper County | IN | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-05-09 |  | 2018-10-18 | 2019-04-01 | Northern Indiana Public Service Company | Jasper County | IN | DPP-2016-AUG | Central | GIA | NRIS | Schahfer Tap (17 SCHAFR_TAP)138kv | 175 | 175 | Solar | PV Photovoltaic | Under Construction | 2021-04-01 | 175 | 175 | 175 | 175
|  |  |  | DPP-2016-AUG | Central | Done | Under Construction | J644 | [5 empty] | NRIS |  | 110 |  | Solar | Greene County,Scott County | IL | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-05-09 |  | 2018-10-30 | 2020-05-01 | Ameren Illinois | Greene County,Scott County | IL | DPP-2016-AUG | Central | GIA | NRIS | Jerseyville 138kV | 110 | 110 | Solar | PV Photovoltaic | Under Construction | 2020-12-01 | 110 | 110 | 110 | 110
|  |  |  | SPA-2016-NOV | 0 | Withdrawn | Not Started | J645 | [5 empty] | NRIS |  | 45.9 |  | Solar | Lafayette Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-05-09 | 2017-05-03 |  | 2018-06-15 | Entergy | Lafayette Parish | LA | SPA-2016-NOV |  | SPA - SIS | NRIS | Unknown | 48.8 | 45.9 | Solar | PV Photovoltaic | Not Started | 2018-09-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | East (ITC) | Withdrawn | Not Started | J647 | [5 empty] | NRIS |  | 147.4 |  | Solar | Muskegon County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-06-20 | 2018-09-06 |  | 2021-09-01 | Michigan Electric Transmission Company, LLC | Muskegon County | MI | DPP-2017-FEB | East (ITC) | GIA | NRIS | BC Cobb - Four Mile 138kV Line | 147.4 | 147.4 | Solar | PV Photovoltaic | Not Started |  | 124.95 | 124.95 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Withdrawn | Not Started | J650 | [5 empty] | NRIS Only |  | 151.8 |  | Wind | Grant County,Roberts County | SD |  |  |  |  | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-06-27 | 2017-01-24 |  | 2019-09-05 | Otter Tail Power Company | Grant County,Roberts County | SD | DPP-2016-AUG | West | GIA | NRIS Only | 345kV interconnect at new Tap on proposed MVP Big Stone to Ellendale line | 151.8 | 151.8 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | West | Withdrawn | Not Started | J651 | [5 empty] | NRIS Only |  | 151.8 |  | Wind | Grant County,Roberts County | SD |  |  |  |  | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-06-27 | 2017-01-24 |  | 2018-09-03 | Otter Tail Power Company | Grant County,Roberts County | SD | DPP-2016-AUG | West | GIA | NRIS Only | 345 kV interconnect at new Tap on proposed MVP Big Stone to Ellendale line | 151.8 | 151.8 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2016-AUG | East (ATC) | Done | In Service | J652 | [5 empty] | NRIS Only |  | 98 |  | Wind | Lafayette County | WI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-07-05 |  | 2018-09-13 | 2018-09-01 | American Transmission Co. LLC | Lafayette County | WI | DPP-2016-AUG | East (ATC) | GIA | NRIS Only | Darlington - Hillman 138kV | 98 | 98 | Wind | WT Wind Turbine | In Service | 2017-09-15 | 0 | 98 | 0 | 98
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J653 | [5 empty] | NRIS |  | 50 |  | Solar | White County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-06 | 2017-06-12 |  | 2019-01-31 | Entergy | White County | AR | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J654 | [5 empty] | NRIS |  | 101.5 |  | Solar | Arkansas County, Clark County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-07 | 2016-12-27 |  | 2019-03-01 | Entergy | Arkansas County, Clark County | AR | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 101.5 | 101.5 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J655 | [5 empty] | NRIS |  | 101.5 |  | Solar | Jackson County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-06 | 2017-07-21 |  | 2019-03-01 | Entergy | Jackson County | AR | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 101.5 | 101.5 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J656 | [5 empty] | NRIS |  | 101.5 |  | Solar | Craighead County, Monroe County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-06 | 2017-07-21 |  | 2019-03-01 | Entergy | Craighead County, Monroe County | AR | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 101.5 | 101.5 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | East (ATC) | Withdrawn | Not Started | J657 | [5 empty] | NRIS |  | 100.8 |  | Wind | Manitowoc County | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-08 | 2018-04-10 |  | 2019-09-01 | American Transmission Co. LLC | Manitowoc County | WI | DPP-2017-FEB | East (ATC) | GIA | NRIS | Kewaunee - Shoto 138kV Line (at the existing Mishicot Tap) | 100.8 | 100.8 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | Central | Withdrawn | Not Started | J658 | [5 empty] | NRIS |  | 100.05 |  | Wind | Audrain County | MO | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-07 | 2017-06-21 |  | 2018-09-15 | Ameren Missouri | Audrain County | MO | DPP-2017-FEB | Central | GIA | NRIS | Spencer Creek 345 kV Substation | 100.05 | 100.05 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J659 | [5 empty] | NRIS |  | 50 |  | Solar | Franklin Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-07 |  | 2019-04-01 | Entergy | Franklin Parish | LA | DPP-2017-AUG | South | GIA | NRIS | Winnsboro to Gilbert 115 kV line | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | SPA-2016-NOV | 0 | Withdrawn | Not Started | J660 | [5 empty] | NRIS |  | 50 |  | Solar | Richland Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-07-21 |  | 2019-04-01 | Entergy | Richland Parish | LA | SPA-2016-NOV |  | SPA - SIS | NRIS | Unknown | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J661 | [5 empty] | ERIS |  | 90 |  | Solar | Bradley County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-07-21 |  | 2017-10-31 | Entergy | Bradley County | AR | FES-2016-JULY |  | Feasibility | ERIS | Unknown | 90 | 90 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | South | Withdrawn | Withdrawn | J662 | [5 empty] | NRIS |  | 100.05 |  | Wind | Crittenden County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2019-01-03 | 2018-10-09 | 2018-10-15 | Entergy | Crittenden County | AR | DPP-2017-FEB | South | GIA | NRIS | Marked Tree - Marion 161kV Line | 100.05 | 100.05 | Wind | WT Wind Turbine | Withdrawn | 2020-07-31 | 100.05 | 100.05 | 100.05 | 100.05
|  |  |  | DPP-2017-AUG | South | Done | Under Construction | J663 | [5 empty] | NRIS |  | 100 |  | Solar | Phillips County | AR | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-03-20 | 2018-10-01 | Entergy | Phillips County | AR | DPP-2017-AUG | South | GIA | NRIS | Robert E Ritchie 230kV Substation | 100 | 100 | Solar | PV Photovoltaic | Under Construction | 2022-05-01 | 100 | 100 | 100 | 100
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J664 | [5 empty] | NRIS |  | 50 |  | Solar | Avoyelles Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2016-10-27 |  | 2019-06-01 | CLECO Corporation | Avoyelles Parish | LA | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J665 | [5 empty] | NRIS |  | 47.5 |  | Solar | Morehouse Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-07-21 |  | 2019-04-01 | Entergy | Morehouse Parish | LA | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 44.5 | 47.5 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J666 | [5 empty] | NRIS |  | 100 |  | Solar | Crittenden County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-07-21 |  | 2019-05-01 | Entergy | Crittenden County | AR | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J667 | [5 empty] | NRIS |  | 80 |  | Solar | Massac County | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-07-21 |  | 2018-08-01 | Ameren Illinois | Massac County | IL | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 80 | 80 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J668 | [5 empty] | NRIS |  | 100 |  | Solar | Waushara County | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-07-21 |  | 2018-08-01 | American Transmission Co. LLC | Waushara County | WI | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J669 | [5 empty] | NRIS |  | 100 |  | Solar | Portage County | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-07-21 |  | 2018-08-01 | American Transmission Co. LLC | Portage County | WI | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J670 | [5 empty] | NRIS |  | 200 |  | Solar | Panola County | MS | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-06-21 |  | 2019-09-30 | Entergy | Panola County | MS | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J671 | [5 empty] | NRIS |  | 400 |  | Wind | Martin County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-06-21 |  | 2019-09-30 | ITC Midwest | Martin County | MN | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 400 | 400 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J672 | [5 empty] | NRIS |  | 150 |  | Wind | Jefferson Davis Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2016-11-02 |  | 2019-09-30 | Entergy | Jefferson Davis Parish | LA | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J673 | [5 empty] | NRIS |  | 50 |  | Solar | Ouachita Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-07-21 |  | 2018-02-28 | Entergy | Ouachita Parish | LA | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J674 | [5 empty] | NRIS |  | 47.5 |  | Solar | Morehouse Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-07-21 |  | 2019-04-01 | Entergy | Morehouse Parish | LA | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 44.5 | 47.5 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J675 | [5 empty] | NRIS |  | 100 |  | Solar | Acadia Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2016-11-02 |  | 2019-09-30 | Entergy | Acadia Parish | LA | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J676 | [5 empty] | NRIS |  | 50 |  | Solar | West Baton Rouge Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-07-21 |  | 2017-10-30 | Entergy | West Baton Rouge Parish | LA | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J677 | [5 empty] | NRIS |  | 100 |  | Solar | Cross County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-07-21 |  | 2016-07-18 | Entergy | Cross County | AR | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J678 | [5 empty] | NRIS |  | 100 |  | Solar | St. Francis County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-07-21 |  | 2018-04-15 | Entergy | St. Francis County | AR | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | South | Done | Under Construction | J679 | [5 empty] | NRIS |  | 100 |  | Solar | Carroll County | MS | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-07-11 |  | 2018-10-12 | 2018-05-15 | Entergy | Carroll County | MS | DPP-2017-FEB | South | GIA | NRIS | Greenwood - Winona 115kV | 100 | 100 | Solar | PV Photovoltaic | Under Construction | 2021-04-15 | 100 | 100 | 100 | 100
|  |  |  | DPP-2017-FEB | South | Done | Under Construction | J680 | [5 empty] | NRIS |  | 100 |  | Solar | Ashley County | AR | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-07-11 |  | 2018-10-09 | 2018-04-15 | Entergy | Ashley County | AR | DPP-2017-FEB | South | GIA | NRIS | Crosset West 115kV Substation | 100 | 100 | Solar | PV Photovoltaic | Under Construction | 2021-04-15 | 100 | 100 | 100 | 100
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J681 | [5 empty] | NRIS |  | 100 |  | Solar | Jackson County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-07-21 |  | 2018-04-08 | Entergy | Jackson County | AR | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J682 | [5 empty] | NRIS |  | 400 |  | Wind | Schuyler County | MO | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-06-21 |  | 2019-09-30 | Ameren Missouri | Schuyler County | MO | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 400 | 400 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | South | Done | In Service | J683 | [5 empty] | NRIS |  | 50 |  | Solar | West Baton Rouge Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-07-11 |  | 2018-09-11 | 2018-02-28 | Entergy | West Baton Rouge Parish | LA | DPP-2017-FEB | South | GIA | NRIS | Wilbert - Livonia 138kV Substation (~1.5 mi from Wilbert) | 50 | 50 | Solar | PV Photovoltaic | In Service | 2020-01-31 | 50 | 50 | 50 | 50
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J684 | [5 empty] | NRIS |  | 100 |  | Solar | Pulaski County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2016-10-27 |  | 2019-06-01 | Entergy | Pulaski County | AR | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J686 | [5 empty] | NRIS |  | 250 |  | Wind | Sunflower County | MS | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-06-21 |  | 2019-09-30 | Entergy | Sunflower County | MS | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 250 | 250 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | South | Withdrawn | Not Started | J687 | [5 empty] | NRIS |  | 20 |  | Solar | Orleans Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-02-17 |  | 2019-06-01 | Entergy | Orleans Parish | LA | DPP-2017-FEB | South | GIA | NRIS | Nasa 115kV Substation | 20 | 20 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J688 | [5 empty] | NRIS |  | 92 |  | Solar | Clark County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-07-21 |  | 2019-04-01 | Entergy | Clark County | AR | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 86 | 92 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J689 | [5 empty] | ERIS |  | 50 |  | Solar | Cross County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-07-21 |  | 2019-04-01 | Entergy | Cross County | AR | FES-2016-JULY |  | Feasibility | ERIS | Unknown | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J690 | [5 empty] | ERIS |  | 42 |  | Solar | Lonoke County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-07-21 |  | 2018-04-01 | Entergy | Lonoke County | AR | FES-2016-JULY |  | Feasibility | ERIS | Unknown | 42 | 42 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J691 | [5 empty] | ERIS |  | 160 |  | Wind | Boone County, Hamilton County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-05-23 |  | 2017-11-01 | ITC Midwest | Boone County, Hamilton County | IA | FES-2016-JULY |  | Feasibility | ERIS | Unknown | 160 | 160 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J692 | [5 empty] | NRIS |  | 5.49 |  | Solar | Allen Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2016-08-30 |  | 2018-04-01 | Entergy | Allen Parish | LA | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 5.49 | 5.49 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J693 | [5 empty] | NRIS |  | 16.49 |  | Solar | Jefferson Davis Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2016-08-30 |  | 2018-04-01 | Entergy | Jefferson Davis Parish | LA | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 16.49 | 16.49 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J694 | [5 empty] | NRIS |  | 14.66 |  | Solar | Iberia Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2016-08-30 |  | 2018-04-01 | Entergy | Iberia Parish | LA | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 14.66 | 14.66 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J695 | [5 empty] | NRIS |  | 99 |  | Solar | Prairie County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-01-03 |  | 2018-10-15 | Entergy | Prairie County | AR | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 99 | 99 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J696 | [5 empty] | NRIS |  | 150 |  | Solar | St. Francis County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-07-21 |  | 2020-05-01 | Entergy | St. Francis County | AR | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | South | Done | Under Construction | J697 | [5 empty] | NRIS |  | 150 |  | Solar | Morehouse Parish | LA | [5 empty] | Oak Ridge 115 kV Substation | [15 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-11-25 | 2022-10-15 | Entergy | Morehouse Parish | LA | DPP-2017-AUG | South | GIA | NRIS | Oak Ridge 115 kV Substation | 150 | 150 | Solar | PV Photovoltaic | Under Construction | 2022-10-15 | 150 | 150 | 150 | 150
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J698 | [5 empty] | NRIS |  | 150 |  | Solar | Chicot County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-07 |  | 2015-11-01 | Entergy | Chicot County | AR | DPP-2017-AUG | South | GIA | NRIS | Lake Village Bagby 115 kV Substation | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FES-2016-JULY | 0 | Withdrawn | Not Started | J699 | [5 empty] | NRIS |  | 48.3 |  | Wind | St. Mary Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-07-11 | 2017-06-13 |  |  | CLECO Corporation | St. Mary Parish | LA | FES-2016-JULY |  | Feasibility | NRIS | Unknown | 48.3 | 48.3 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FeS-2016-SEP | 0 | Withdrawn | Not Started | J700 | [5 empty] | ERIS |  | 49.98 |  | Solar | Acadia Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-08-03 | 2017-06-15 |  | 2018-12-31 | Entergy | Acadia Parish | LA | FeS-2016-SEP |  | Feasibility | ERIS | Unknown | 49.98 | 49.98 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ITC) | Done | In Service | J701 | [5 empty] | NRIS |  | 49 |  | Wind | Tuscola County | MI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-05-06 | 2017-09-15 | ITC Transmission | Tuscola County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Rapson - Grasssmere - Bauer 345kV Line Tap (Kirk 345 kV Sub) | 49 | 49 | Wind | WT Wind Turbine | In Service | 2018-10-01 | 49 | 49 | 49 | 49
|  |  |  | Fes-2016-SEP | 0 | Withdrawn | Not Started | J702 | [5 empty] | NRIS |  | 100 |  | Solar | Wadena County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-09-08 | 2017-07-21 |  | 2018-08-01 | Minnesota Power (Allete, Inc.) | Wadena County | MN | Fes-2016-SEP |  | Feasibility | NRIS | Unknown | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J705 | [5 empty] | NRIS | N | 100 |  | Wind | Morton County | ND |  |  |  | 1 | 0 | 400000 | 1788248 | [7 empty] | 4435188 | 70059305 |  | 83897334 | 1305000 | 88332522 | 159696827 | 883.3252 | 1596.9683 | 159696827 |  |  |  | Withdrawn | 2017-06-16 | 2021-01-29 |  | 2021-10-01 | Minnesota Power (Allete, Inc.) | Morton County | ND | DPP-2017-AUG | West | PHASE 3 | NRIS | Tri-county 230 kV substation | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 100 | 100 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J706 | [5 empty] | NRIS | N | 100 |  | Wind | Morton County | ND |  |  |  | 1 | 0 | 400000 | 1800000 | [7 empty] | 4435188 | 70059305 |  | 83897334 | 1305000 | 88332522 | 159696827 | 883.3252 | 1596.9683 | 159696827 |  |  |  | Withdrawn | 2017-06-16 | 2021-01-29 |  | 2021-10-01 | Minnesota Power (Allete, Inc.) | Morton County | ND | DPP-2017-AUG | West | PHASE 3 | NRIS | Tri-county 230kV sub | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 100 | 100 | 0 | 0
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J707 | [5 empty] | ERIS |  | 300 |  | Wind | Barnes County | ND | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-09-09 | 2019-04-09 |  | 2020-09-23 | Otter Tail Power Company | Barnes County | ND | DPP-2017-FEB | West | GIA | ERIS | Buffalo 345kV | 300 | 300 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | South | Withdrawn | Withdrawn | J709 | [5 empty] | NRIS |  | 100 |  | Solar | Greene County | MS | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-09-09 | 2019-01-11 | 2018-10-17 | 2020-04-01 | South Mississippi Electric Power Association | Greene County | MS | DPP-2017-FEB | South | GIA | NRIS | Green Substation 230kV | 100 | 100 | Solar | PV Photovoltaic | Withdrawn | 2020-04-01 | 60 | 60 | 60 | 60
|  |  |  | DPP-2017-FEB | South | Withdrawn | Not Started | J710 | [5 empty] | NRIS |  | 20 |  | Solar | Lafayette Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-09-09 | 2018-01-24 | 2018-01-24 | 2018-06-01 | Entergy | Lafayette Parish | LA | DPP-2017-FEB | South | GIA | NRIS | Duson - Scott line 69kV | 20 | 20 | Solar | PV Photovoltaic | Not Started | 2018-11-01 | 20 | 20 | 0 | 0
|  |  |  | DPP-2016-AUG/DPP-2017-FEB | East (UP) | Withdrawn | Withdrawn | J711 | [5 empty] | NRIS |  | 130 |  | Wind | Baraga County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-09-09 | 2018-12-10 |  | 2020-09-23 | American Transmission Co. LLC | Baraga County | MI | DPP-2016-AUG/DPP-2017-FEB | East (UP) | GIA | NRIS | Silver River 138kV | 130 | 130 | Wind | WT Wind Turbine | Withdrawn | 2020-09-23 | 130 | 130 | 130 | 130
|  |  |  | DPP-2017-FEB | East (ATC) | Withdrawn | Not Started | J712 | [5 empty] | NRIS |  | 200 |  | Wind | Iowa County | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-09-09 | 2018-04-10 |  | 2020-09-20 | American Transmission Co. LLC | Iowa County | WI | DPP-2017-FEB | East (ATC) | GIA | NRIS | Hill Valley 138kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J713 | [5 empty] | NRIS | N | 300 |  | Wind | Oliver County | ND |  |  |  | 1 | 0 | 1200000 | 4628612 | [7 empty] | 13305564 | 210177914 |  | 244972448 | 3915000 | 258278012 | 472370926 | 860.9267 | 1574.5698 | 472370926 |  |  |  | Withdrawn | 2017-06-16 | 2021-01-29 |  | 2020-09-15 | Minnesota Power (Allete, Inc.) | Oliver County | ND | DPP-2017-AUG | West | PHASE 3 | NRIS | Square Butte East 230kV Substation | 300 | 300 | Wind | WT Wind Turbine | Not Started |  | 300 | 300 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Withdrawn | Not Started | J714 | [5 empty] | NRIS |  | 200 |  | Wind | Montgomery County | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-04-17 |  | 2019-08-31 | Duke Energy Corporation | Montgomery County | IN | DPP-2017-AUG | Central | GIA | NRIS | Frankfurt - Cayuga 230kV line | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 192 | 192 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Done | Not Started | J715 | [5 empty] | NRIS |  | 100 |  | Wind | Marshall County | IL | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-12-09 | 2019-08-31 | Ameren Illinois | Marshall County | IL | DPP-2017-AUG | Central | GIA | NRIS | McLean County-Oglesby 138kV Line 1382 | 100 | 100 | Wind | WT Wind Turbine | Not Started | 2021-05-01 | 98 | 98 | 98 | 98
|  |  |  | FES-2016-SEP | 0 | Withdrawn | Not Started | J716 | [5 empty] | NRIS |  | 60 |  | Solar | Jefferson Davis Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-09-12 | 2017-07-21 |  | 2019-12-01 | Entergy | Jefferson Davis Parish | LA | FES-2016-SEP |  | Feasibility | NRIS | Unknown | 60 | 60 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | East (ITC) | Done | Under Construction | J717 | [5 empty] | NRIS |  | 200.1 |  | Wind | Isabella County | MI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-09-12 |  | 2019-10-08 | 2019-09-03 | Michigan Electric Transmission Company, LLC | Isabella County | MI | DPP-2017-FEB | East (ITC) | GIA | NRIS | Edenville Junction to Warren 138 kV Line | 200.1 | 200.1 | Wind | WT Wind Turbine | Under Construction | 2020-06-30 | 200.1 | 200.1 | 200.1 | 200.1
|  |  |  | DPP-2017-FEB | West | Done | Under Construction | J718 | [5 empty] | NRIS |  | 49.98 |  | Solar | Fillmore County | MN | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-09-13 |  | 2020-04-21 | 2020-12-31 | Dairyland Power Cooperative | Fillmore County | MN | DPP-2017-FEB | West | GIA | NRIS | Cherry Grove 69kV Substation | 49.98 | 49.98 | Solar | PV Photovoltaic | Under Construction | 2022-08-01 | 49.98 | 49.98 | 45 | 45
|  |  |  | FES-2016-NOV | 0 | Withdrawn | Not Started | J719 | [5 empty] | NRIS |  | 100 |  | Wind | Codington County, Grant County | SD | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-10-12 | 2017-05-23 |  | 2018-09-03 | Otter Tail Power Company | Codington County, Grant County | SD | FES-2016-NOV |  | Feasibility | NRIS | Unknown | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Under Construction | J720 | [5 empty] | NRIS | N | 200 |  | Wind | Jackson County | MN |  |  |  | 1 | 0 | 800000 | 362178 | [7 empty] | 0 | 48699911 |  | 82056001 | 0 | 82056001 | 130755912 | 410.28 | 653.7796 | 130755912 |  |  |  | Withdrawn | 2017-06-16 | 2021-01-29 |  | 2020-09-01 | ITC Midwest | Jackson County | MN | DPP-2017-AUG | West | PHASE 3 | NRIS | Lakefield - Raun 345 kV line | 200 | 200 | Wind | WT Wind Turbine | Under Construction | 2021-09-01 | 200 | 200 | 0 | 0
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J721 | [5 empty] | NRIS |  | 200 |  | Wind | Codington County,Deuel County | SD | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-10-24 | 2019-08-09 |  | 2019-09-15 | Otter Tail Power Company | Codington County,Deuel County | SD | DPP-2017-FEB | West | GIA | NRIS | Big Stone South substation, Big Stone City | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Active | Not Started | J722 | [5 empty] | ERIS | N | 200 |  | Wind | Codington County,Deuel County | SD |  |  |  | 1 | 1 | 800000 | 1864413 | [7 empty] | 23624496 | 92441809 |  | 34373478 |  | 57997974 | 150439783 | 289.9899 | 752.1989 | 57997974 |  |  |  | Active | 2017-06-16 |  |  | 2021-09-15 | Otter Tail Power Company | Codington County,Deuel County | SD | DPP-2017-AUG | West | PHASE 3 | ERIS | Big Stone South 230kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 200 | 200 | 200 | 0
|  |  |  | FeS-2016-NOV | 0 | Withdrawn | Not Started | J723 | [5 empty] | NRIS |  | 100 |  | Wind | Grant County | SD | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-10-24 | 2017-07-21 |  | 2020-07-01 | Northern States Power (Xcel Energy) | Grant County | SD | FeS-2016-NOV |  | Feasibility | NRIS | Unknown | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FeS-2016-NOV | 0 | Withdrawn | Not Started | J724 | [5 empty] | NRIS |  | 100 |  | Wind | Grant County | SD | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-10-24 | 2017-07-21 |  | 2020-07-02 | Northern States Power (Xcel Energy) | Grant County | SD | FeS-2016-NOV |  | Feasibility | NRIS | Unknown | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J725 | [5 empty] | NRIS |  | 200 |  | Wind | Murray County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-02-15 |  | 2020-09-15 | Great River Energy | Murray County | MN | DPP-2017-AUG | West | PHASE 3 | NRIS | Cedar Mountain 345 kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J726 | [5 empty] | NRIS |  | 200 |  | Wind | Cottonwood County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2018-11-19 |  | 2019-09-15 | Great River Energy | Cottonwood County | MN | DPP-2017-AUG | West | PHASE 3 | NRIS | Cedar Mountain 345kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FeS-2016-NOV | 0 | Withdrawn | Not Started | J727 | [5 empty] | NRIS |  | 100 |  | Wind | Barnes County, Stutsman County | ND | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-02 | 2017-07-21 |  | 2020-07-01 | Otter Tail Power Company | Barnes County, Stutsman County | ND | FeS-2016-NOV |  | Feasibility | NRIS | Unknown | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | East (ITC) | Done | Under Construction | J728 | [5 empty] | NRIS |  | 200.1 |  | Wind | Isabella County | MI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-11-02 |  | 2019-10-08 | 2019-09-03 | Michigan Electric Transmission Company, LLC | Isabella County | MI | DPP-2017-FEB | East (ITC) | GIA | NRIS | Edenville Junction to Warren 138 kV Line | 200.1 | 200.1 | Wind | WT Wind Turbine | Under Construction | 2020-06-30 | 200.1 | 200.1 | 186.3 | 186.3
|  |  |  | FeS-2016-NOV | 0 | Withdrawn | Not Started | J729 | [5 empty] | NRIS |  | 100 |  | Wind | Clark County | SD | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-04 | 2017-07-21 |  | 2019-08-01 | Otter Tail Power Company | Clark County | SD | FeS-2016-NOV |  | Feasibility | NRIS | Unknown | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FeS-2016-NOV | 0 | Withdrawn | Not Started | J730 | [5 empty] | NRIS |  | 100 |  | Wind | Clark County | SD | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-04 | 2017-07-21 |  | 2019-08-01 | Otter Tail Power Company | Clark County | SD | FeS-2016-NOV |  | Feasibility | NRIS | Unknown | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J731 | [5 empty] | ERIS |  | 200 |  | Wind | Palo Alto County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-08 | 2019-04-09 |  | 2020-09-23 | MidAmerican Energy Company | Palo Alto County | IA | DPP-2017-FEB | West | GIA | ERIS | Kossuth-O'Brien 345kV | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J733 | [5 empty] | ERIS |  | 200 |  | Wind | Franklin County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-08 | 2019-04-09 |  | 2020-09-23 | ITC Midwest | Franklin County | IA | DPP-2017-FEB | West | GIA | ERIS | J416 345 kV Interconnection Facilitities to be Owned by ITCM | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FeS-2016-NOV | 0 | Withdrawn | Not Started | J735 | [5 empty] | NRIS |  | 100 |  | Solar | Morrison County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-10 | 2017-07-21 |  | 2019-08-31 | Great River Energy | Morrison County | MN | FeS-2016-NOV |  | Feasibility | NRIS | Unknown | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FeS-2016-NOV | 0 | Withdrawn | Not Started | J736 | [5 empty] | NRIS |  | 100 |  | Solar | Cass County | ND | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-11 | 2017-07-21 |  | 2019-08-31 | Northern States Power (Xcel Energy) | Cass County | ND | FeS-2016-NOV |  | Feasibility | NRIS | Unknown | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FeS-2016-NOV | 0 | Withdrawn | Not Started | J737 | [5 empty] | NRIS |  | 100 |  | Solar | Cass County | ND | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-11 | 2017-07-21 |  | 2019-08-31 | Northern States Power (Xcel Energy) | Cass County | ND | FeS-2016-NOV |  | Feasibility | NRIS | Unknown | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FeS-2016-NOV | 0 | Withdrawn | Not Started | J738 | [5 empty] | NRIS |  | 150 |  | Wind | Green County | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-11 | 2017-07-21 |  | 2020-09-15 | American Transmission Co. LLC | Green County | WI | FeS-2016-NOV |  | Feasibility | NRIS | Unknown | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J739 | [5 empty] | NRIS |  | 200 |  | Wind | Lyon County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-11 | 2019-08-09 |  | 2020-09-15 | Northern States Power (Xcel Energy) | Lyon County | MN | DPP-2017-FEB | West | GIA | NRIS | Lyon County 345kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
|  |  |  | DPP-2017-FEB | Central | Withdrawn | Withdrawn | J740 | [5 empty] | NRIS |  | 200 |  | Wind | Jasper County,Pulaski County | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-11 | 2020-08-10 | 2019-03-15 | 2020-09-23 | Northern Indiana Public Service Company | Jasper County,Pulaski County | IN | DPP-2017-FEB | Central | GIA | NRIS | Reynold 345kV substation | 200 | 200 | Wind | WT Wind Turbine | Withdrawn | 2020-10-15 | 200 | 200 | 200 | 200
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J741 | [5 empty] | NRIS |  | 51 |  | Wind | Emmons County,Logan County | ND | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2019-08-09 |  | 2019-09-01 | Montana-Dakota Utilities Company | Emmons County,Logan County | ND | DPP-2017-FEB | West | GIA | NRIS | Wishek - Linton 115kV | 51 | 51 | Wind | WT Wind Turbine | Not Started |  | 50.4 | 50.4 | 0 | 0
|  |  |  | FeS-2016-NOV | 0 | Withdrawn | Not Started | J742 | [5 empty] | NRIS |  | 211 |  | Wind | Cottonwood County, Murray County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2017-07-21 |  | 2020-08-01 | Northern States Power (Xcel Energy) | Cottonwood County, Murray County | MN | FeS-2016-NOV |  | Feasibility | NRIS | Unknown | 211 | 211 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J743 | [5 empty] | NRIS |  | 200 |  | Wind | Cass County | ND | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-10-24 |  | 2020-07-31 | Northern States Power (Xcel Energy) | Cass County | ND | DPP-2017-AUG | West | PHASE 3 | NRIS | Bison 345kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FeS-2016-NOV | 0 | Withdrawn | Not Started | J744 | [5 empty] | NRIS |  | 400 |  | Wind | Lincoln County | SD | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2017-04-12 |  | 2020-06-01 | Northern States Power (Xcel Energy) | Lincoln County | SD | FeS-2016-NOV |  | Feasibility | NRIS | Unknown | 400 | 400 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J745 | [5 empty] | NRIS |  | 100 |  | Wind | Nobles County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2019-04-09 |  | 2021-06-01 | Northern States Power (Xcel Energy) | Nobles County | MN | DPP-2017-FEB | West | GIA | NRIS | Nobles-Fenton 115kV | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J746 | [5 empty] | NRIS |  | 200 |  | Wind | McHenry County,McLean County,Ward County | ND | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2019-08-09 |  | 2020-08-01 | Great River Energy | McHenry County,McLean County,Ward County | ND | DPP-2017-FEB | West | GIA | NRIS | Stanton-McHenry 230kV | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J747 | [5 empty] | NRIS |  | 200 |  | Wind | Deuel County | SD | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2019-04-09 |  | 2017-10-01 | Otter Tail Power Company | Deuel County | SD | DPP-2017-FEB | West | GIA | NRIS | Brooking County - Big Stone South (J510 Tap - J630 Tap) 345kV Line | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | West | Done | Under Construction | J748 | [5 empty] | NRIS |  | 200 |  | Wind | Plymouth County | IA | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-11-14 |  | 2020-03-20 | 2020-10-01 | MidAmerican Energy Company | Plymouth County | IA | DPP-2017-FEB | West | GIA | NRIS | Highland - Raun 345kV Line Tap | 200 | 200 | Wind | WT Wind Turbine | Under Construction | 2021-10-01 | 200 | 200 | 200 | 175
|  |  |  | DPP-2017-FEB | East (ITC) | Withdrawn | Not Started | J749 | [5 empty] | NRIS |  | 20 |  | Battery Storage | Gratiot County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2018-05-01 |  | 2018-09-01 | Michigan Electric Transmission Company, LLC | Gratiot County | MI | DPP-2017-FEB | East (ITC) | GIA | NRIS | Redstone 138 kV Substation | 20 | 20 | Battery Storage |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Done | Under Construction | J750 | [5 empty] | NRIS |  | 150 |  | Wind | Morgan County | IL | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-01-14 | 2019-08-15 | City of Springfield, IL - CWLP | Morgan County | IL | DPP-2017-AUG | Central | GIA | NRIS | Westchester 138kV Substation | 150 | 150 | Wind | WT Wind Turbine | Under Construction | 2022-05-15 | 150 | 150 | 150 | 150
|  |  |  | FeS-2016-NOV | 0 | Withdrawn | Not Started | J751 | [5 empty] | NRIS |  | 150 |  | Wind | Adams County | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2017-06-06 |  | 2019-08-15 | Ameren Illinois | Adams County | IL | FeS-2016-NOV |  | Feasibility | NRIS | Unknown | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | East (ITC) | Done | In Service | J752 | [5 empty] | NRIS |  | 100 |  | Wind | Tuscola County | MI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-11-14 |  | 2019-10-10 | 2020-01-02 | ITC Transmission | Tuscola County | MI | DPP-2017-FEB | East (ITC) | GIA | NRIS | Ringle 345kV Switchyard | 100 | 100 | Wind | WT Wind Turbine | In Service | 2019-10-04 | 100 | 100 | 0 | 0
|  |  |  | DPP-2017-FEB | Central | Done | Under Construction | J753 | [5 empty] | NRIS |  | 100 |  | Solar | Breckinridge County | KY | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-11-14 |  | 2019-03-08 | 2021-04-01 | Big Rivers Electric Corporation | Breckinridge County | KY | DPP-2017-FEB | Central | GIA | NRIS | Hardinsburg Sub 161kV | 100 | 100 | Solar | PV Photovoltaic | Under Construction | 2021-04-01 | 100 | 100 | 100 | 100
|  |  |  | DPP-2017-FEB | Central | Withdrawn | Withdrawn | J754 | [5 empty] | NRIS |  | 303.6 |  | Wind | Montgomery County | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2020-09-30 | 2019-04-11 | 2019-03-08 | Duke Energy Corporation | Montgomery County | IN | DPP-2017-FEB | Central | GIA | NRIS | Cayuga - Nucor 345kV | 303.6 | 303.6 | Wind | WT Wind Turbine | Withdrawn | 2020-04-30 | 303.6 | 303.6 | 303.6 | 303.6
|  |  |  | FeS-2016-NOV | 0 | Withdrawn | Not Started | J755 | [5 empty] | NRIS |  | 200.1 |  | Wind | Bowman County | ND | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2017-06-20 |  | 2019-03-08 | Montana-Dakota Utilities Company | Bowman County | ND | FeS-2016-NOV |  | Feasibility | NRIS | Unknown | 200.1 | 200.1 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | Central | Done | In Service | J756 | [5 empty] | NRIS |  | 202.4 |  | Wind | Logan County | IL | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-11-14 |  | 2019-03-26 | 2019-08-15 | Ameren Illinois | Logan County | IL | DPP-2017-FEB | Central | GIA | NRIS | Mason City to Fogarty 138kV | 202.4 | 202.4 | Wind | WT Wind Turbine | In Service | 2020-04-23 | 202.4 | 202.4 | 202.4 | 202.4
|  |  |  | DPP-2017-FEB | Central | Done | Under Construction | J757 | [5 empty] | NRIS |  | 303.6 |  | Wind | Morgan County,Sangamon County | IL | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-11-14 |  | 2019-05-31 | 2020-08-14 | Ameren Transmission Company of Illinois | Morgan County,Sangamon County | IL | DPP-2017-FEB | Central | GIA | NRIS | Austin-Meredosia 345kV line | 303.6 | 303.6 | Wind | WT Wind Turbine | Under Construction | 2021-10-31 | 303.6 | 303.6 | 303.6 | 303.6
|  |  |  | DPP-2017-FEB | East (ITC) | Done | Under Construction | J758 | [5 empty] | NRIS |  | 200 |  | Solar | Calhoun County | MI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-11-14 |  | 2019-10-25 | 2018-10-01 | Michigan Electric Transmission Company, LLC | Calhoun County | MI | DPP-2017-FEB | East (ITC) | GIA | NRIS | Verona-Foundry 138kV | 200 | 200 | Solar | PV Photovoltaic | Under Construction | 2022-04-08 | 200 | 200 | 200 | 200
|  |  |  | DPP-2017-FEB | Central | Done | Under Construction | J759 | [5 empty] | NRIS |  | 70 |  | Solar | Spencer County | IN | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-11-14 |  | 2019-02-15 | 2021-04-01 | Hoosier Energy REC, Inc. | Spencer County | IN | DPP-2017-FEB | Central | GIA | NRIS | Troy 161kV Sub | 70 | 70 | Solar | PV Photovoltaic | Under Construction | 2020-07-02 | 70 | 69.9 | 70 | 69.9
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J761 | [5 empty] | NRIS |  | 200 |  | Wind | Faribault County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2019-04-09 |  | 2020-09-15 | ITC Midwest | Faribault County | MN | DPP-2017-FEB | West | GIA | NRIS | Huntley 345 kV sub | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | Central | Done | Under Construction | J762 | [5 empty] | NRIS |  | 200 |  | Solar | Meade County | KY | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-11-14 |  | 2019-03-08 | 2021-04-01 | Big Rivers Electric Corporation | Meade County | KY | DPP-2017-FEB | Central | GIA | NRIS | Meade Sub 161kV | 200 | 200 | Solar | PV Photovoltaic | Under Construction | 2021-04-01 | 200 | 200 | 200 | 200
|  |  |  | FeS-2016-NOV | 0 | Withdrawn | Not Started | J763 | [5 empty] | NRIS |  | 5.28 |  | Wind | Hancock County, Winnebago County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2017-07-21 |  | 2018-01-01 | ITC Midwest | Hancock County, Winnebago County | IA | FeS-2016-NOV |  | Feasibility | NRIS | Unknown | 5.28 | 5.28 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FeS-2016-NOV | 0 | Withdrawn | Not Started | J764 | [5 empty] | NRIS |  | 12 |  | Wind | Story County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2017-07-21 |  | 2018-01-01 | ITC Midwest | Story County | IA | FeS-2016-NOV |  | Feasibility | NRIS | Unknown | 12 | 12 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FeS-2016-NOV | 0 | Withdrawn | Not Started | J765 | [5 empty] | NRIS |  | 4.32 |  | Wind | Dodge County | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2017-07-21 |  | 2018-01-01 | American Transmission Co. LLC | Dodge County | WI | FeS-2016-NOV |  | Feasibility | NRIS | Unknown | 4.32 | 4.32 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J766 | [5 empty] | NRIS |  | 3.84 |  | Wind | Oliver County | ND | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2019-04-09 |  | 2018-01-01 | Minnesota Power (Allete, Inc.) | Oliver County | ND | DPP-2017-FEB | West | GIA | NRIS | Square Butte 230kV Substation | 3.84 | 3.84 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J767 | [5 empty] | NRIS |  | 12 |  | Wind | Hancock County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2019-08-09 |  | 2019-01-01 | ITC Midwest | Hancock County | IA | DPP-2017-FEB | West | GIA | NRIS | Lime Creek 161 kV substation | 12 | 12 | Wind | WT Wind Turbine | Not Started |  | 12 | 12 | 0 | 0
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J768 | [5 empty] | NRIS |  | 12 |  | Wind | Story County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2019-08-09 |  | 2019-01-01 | ITC Midwest | Story County | IA | DPP-2017-FEB | West | GIA | NRIS | Story County Substation | 12 | 12 | Wind | WT Wind Turbine | Not Started |  | 12 | 12 | 0 | 0
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J769 | [5 empty] | NRIS |  | 33 |  | Solar | Renville County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2019-04-09 |  | 2019-07-31 | Northern States Power (Xcel Energy) | Renville County | MN | DPP-2017-FEB | West | GIA | NRIS | Kingman Run-Bird Island 69kV | 33 | 33 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J770 | [5 empty] | NRIS |  | 90 |  | Solar | Renville County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2019-04-09 |  | 2019-07-31 | Northern States Power (Xcel Energy) | Renville County | MN | DPP-2017-FEB | West | GIA | NRIS | Bird Island to Henryville Tap 69kV Line | 90 | 90 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J771 | [5 empty] | NRIS |  | 50 |  | Solar | Stearns County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2019-04-09 |  | 2019-07-31 | Great River Energy | Stearns County | MN | DPP-2017-FEB | West | GIA | NRIS | Lake Koronis-Paynesville 69kV | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FeS-2016-NOV | 0 | Withdrawn | Not Started | J772 | [5 empty] | NRIS |  | 7.4 |  | Wind | Cerro Gordo County, Hancock County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2017-07-21 |  | 2018-01-01 | ITC Midwest | Cerro Gordo County, Hancock County | IA | FeS-2016-NOV |  | Feasibility | NRIS | Unknown | 7.4 | 7.4 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FeS-2016-NOV | 0 | Withdrawn | Not Started | J773 | [5 empty] | NRIS |  | 400 |  | Wind | Codington County, Deuel County | SD | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2017-07-21 |  | 2019-09-15 | Northern States Power (Xcel Energy) | Codington County, Deuel County | SD | FeS-2016-NOV |  | Feasibility | NRIS | Unknown | 400 | 400 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FeS-2016-NOV | 0 | Withdrawn | Not Started | J774 | [5 empty] | NRIS |  | 200 |  | Wind | Codington County, Deuel County | SD | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2017-07-21 |  | 2019-09-15 | Northern States Power (Xcel Energy) | Codington County, Deuel County | SD | FeS-2016-NOV |  | Feasibility | NRIS | Unknown | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FeS-2016-NOV | 0 | Withdrawn | Not Started | J775 | [5 empty] | NRIS |  | 200 |  | Wind | Codington County, Deuel County | SD | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2017-07-21 |  | 2019-09-15 | Northern States Power (Xcel Energy) | Codington County, Deuel County | SD | FeS-2016-NOV |  | Feasibility | NRIS | Unknown | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J776 | [5 empty] | NRIS |  | 99 |  | Wind | Franklin County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2019-04-09 |  | 2019-11-01 | MidAmerican Energy Company | Franklin County | IA | DPP-2017-FEB | West | GIA | NRIS | Black Hawk-Killdeer 345kV | 99 | 99 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J777 | [5 empty] | NRIS |  | 99 |  | Wind | Franklin County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2019-08-09 |  | 2019-11-01 | ITC Midwest | Franklin County | IA | DPP-2017-FEB | West | GIA | NRIS | Whispering Willow 161kV substation | 99 | 99 | Wind | WT Wind Turbine | Not Started |  | 99 | 99 | 0 | 0
|  |  |  | FeS-2016-NOV | 0 | Withdrawn | Not Started | J778 | [5 empty] | NRIS |  | 12 |  | Wind | McLean County | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2017-07-21 |  | 2018-01-01 | Ameren Illinois | McLean County | IL | FeS-2016-NOV |  | Feasibility | NRIS | Unknown | 12 | 12 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J779 | [5 empty] | NRIS |  | 51 |  | Wind | Emmons County,Logan County | ND | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2019-08-09 |  | 2019-09-01 | Montana-Dakota Utilities Company | Emmons County,Logan County | ND | DPP-2017-FEB | West | GIA | NRIS | Bismarck-Linton 115kV | 51 | 51 | Wind | WT Wind Turbine | Not Started |  | 50.4 | 50.4 | 0 | 0
|  |  |  | DPP-2017-FEB | West | Withdrawn | Not Started | J780 | [5 empty] | NRIS |  | 200 |  | Wind | Sheridan County | ND | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2019-04-09 |  | 2020-12-15 | Otter Tail Power Company | Sheridan County | ND | DPP-2017-FEB | West | GIA | NRIS | Harvey - Underwood 230kV Line | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | FeS-2016-NOV | 0 | Withdrawn | Not Started | J781 | [5 empty] | NRIS |  | 170 |  | Wind | Kandiyohi County, Meeker County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2017-06-16 |  | 2018-08-01 | Northern States Power (Xcel Energy) | Kandiyohi County, Meeker County | MN | FeS-2016-NOV |  | Feasibility | NRIS | Willmar - Paynesville 230kV | 170 | 170 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | Central | Withdrawn | Not Started | J782 | [5 empty] | NRIS |  | 100 |  | Solar | Stoddard County | MO | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2018-05-31 |  | 2021-04-01 | Ameren Missouri | Stoddard County | MO | DPP-2017-FEB | Central | GIA | NRIS | Stoddart sub 161kV | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-FEB | Central | Done | Under Construction | J783 | [5 empty] | NRIS |  | 70 |  | Solar | Spencer County | IN | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-11-14 |  | 2019-07-24 | 2021-04-01 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Spencer County | IN | DPP-2017-FEB | Central | GIA | NRIS | Grandview Sub | 70 | 70 | Solar | PV Photovoltaic | Under Construction | 2021-04-01 | 70 | 69.9 | 70 | 69.9
|  |  |  | FeS-2016-NOV | 0 | Withdrawn | Not Started | J784 | [5 empty] | ERIS |  | 39.96 |  | Solar | Renville County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-11-14 | 2017-06-15 |  | 2018-11-01 | Northern States Power (Xcel Energy) | Renville County | MN | FeS-2016-NOV |  | Feasibility | ERIS | Unknown | 39.96 | 39.96 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J785 | [5 empty] | NRIS | N | 105 |  | Wind | Jackson County,Martin County | MN |  |  |  | 1 | 0 | 420000 | 624613 | [7 empty] | 0 | 26623038 |  | 29625115 |  | 29625115 | 56248153 | 282.144 | 535.6967 | 56248153 |  |  |  | Withdrawn | 2017-06-16 | 2021-01-29 |  | 2021-09-15 | ITC Midwest | Jackson County,Martin County | MN | DPP-2017-AUG | West | PHASE 3 | NRIS | Lakefield Junction - Huntley 345 kV line (Tap) | 105 | 105 | Wind | WT Wind Turbine | Not Started |  | 105 | 105 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | J786 | [5 empty] | NRIS |  | 10 |  | Battery Storage | Tuscola County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2016-12-20 | 2017-07-21 |  | 2019-09-01 | ITC Transmission | Tuscola County | MI |  |  |  | NRIS | Unknown | 10 | 10 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Under Construction | J788 | [5 empty] | ERIS |  | 0 |  | Wind | Lincoln County | MN | [21 empty] | #DIV/0! | #DIV/0! |  |  |  |  | Done | 2017-02-17 |  | 2017-02-23 | 2017-09-15 | Northern States Power (Xcel Energy) | Lincoln County | MN |  |  |  | ERIS | Brookings County - Lyon County | 0 | 0 | Wind | WT Wind Turbine | Under Construction |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | J789 | [5 empty] | NRIS |  | 0 |  | Wind | Nobles County | MN | [21 empty] | #DIV/0! | #DIV/0! |  |  |  |  | Done | 2017-02-27 |  | 2017-06-19 |  | Northern States Power (Xcel Energy) | Nobles County | MN |  |  | DPP - SIS | NRIS | Fenton Substation | 0 | 0 | Wind | WT Wind Turbine | In Service | 2017-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | J790 | [5 empty] | NRIS |  | 0 |  | Wind | Pipestone County | MN | [21 empty] | #DIV/0! | #DIV/0! |  |  |  |  | Done | 2017-03-24 |  |  | 2018-09-01 | Northern States Power (Xcel Energy) | Pipestone County | MN |  |  | Out of Cycle | NRIS | 4 miles north of Holland, MN56139 | 0 | 0 | Wind | WT Wind Turbine | In Service | 2019-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Under Construction | J791 | [5 empty] | ERIS |  | 52 |  | Solar | Lamar County | MS | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-04-24 |  | 2017-05-08 | 2017-10-31 | South Mississippi Electric Power Association | Lamar County | MS |  |  | Out of Cycle | ERIS | Sumrall II Substation | 52 | 52 | Solar | PV Photovoltaic | Under Construction | 2020-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ITC) | Done | In Service | J794 | [5 empty] | NRIS |  | 12.5 |  | Wind | Gratiot County | MI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-06-18 | 2018-09-10 | Michigan Electric Transmission Company, LLC | Gratiot County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | J589 138kV Substation (Regal - Summerton 138kV Line) | 12.5 | 12.5 | Wind | WT Wind Turbine | In Service | 2018-10-26 | 12.5 | 12.5 | 12.5 | 12.5
|  |  |  | DPP-2017-AUG | Central | Withdrawn | Not Started | J795 | [5 empty] | NRIS |  | 69 |  | Solar | Gallatin County | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-08 |  | 2019-09-01 | Southern Illinois Power Cooperative | Gallatin County | IL | DPP-2017-AUG | Central | GIA | NRIS | Gallatin Junction 161 kV Substation | 69 | 69 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ITC) | Done | Under Construction | J796 | [5 empty] | NRIS |  | 239 |  | Solar | Shiawassee County | MI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-06-12 | 2019-09-01 | Michigan Electric Transmission Company, LLC | Shiawassee County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Goss 138kV Substation | 239 | 239 | Solar | PV Photovoltaic | Under Construction | 2020-11-20 | 239 | 239 | 239 | 239
|  |  |  | DPP-2017-AUG | Central | Withdrawn | Not Started | J797 | [5 empty] | NRIS |  | 70 |  | Solar | Washington County | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2018-05-30 |  | 2019-09-01 | Ameren Illinois | Washington County | IL | DPP-2017-AUG | Central | GIA | NRIS | Ashley 138 kV Substation | 70 | 70 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ATC) | Withdrawn | Not Started | J798 | [5 empty] | NRIS |  | 124 |  | Solar | Walworth County | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-08 |  | 2019-09-01 | American Transmission Co. LLC | Walworth County | WI | DPP-2017-AUG | East (ATC) | GIA | NRIS | University - Mukwanago UNIG52 Line Tap | 124 | 124 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ITC) | Done | Under Construction | J799 | [5 empty] | NRIS |  | 189 |  | Solar | Washtenaw County | MI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-05-13 | 2019-09-01 | ITC Transmission | Washtenaw County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Milan - Pioneer 120kV Line Tap | 189 | 189 | Solar | PV Photovoltaic | Under Construction | 2021-11-11 | 189 | 189 | 189 | 189
|  |  |  | DPP-2017-AUG | Central | Done | Under Construction | J800 | [5 empty] | NRIS |  | 250 |  | Solar | White County | IL | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-04-22 | 2020-09-30 | Ameren Illinois | White County | IL | DPP-2017-AUG | Central | GIA | NRIS | Crossville West Substation 138kV Bus - Albion South - Norris City 138 kV Line | 250 | 250 | Solar | PV Photovoltaic | Under Construction | 2022-10-01 | 250 | 250 | 250 | 250
|  |  |  | DPP-2017-AUG | West | Active | Not Started | J801 | [5 empty] | ERIS | N | 74 |  | Solar | Pierce County | WI |  |  |  | 1 | 1 | 296000 | 44000 | [7 empty] | 10821 | 9504535 |  | 5338631 |  | 5349452 | 14853987 | 72.2899 | 200.7296 | 5349452 |  |  |  | Active | 2017-06-16 |  |  | 2020-09-01 | Dairyland Power Cooperative | Pierce County | WI | DPP-2017-AUG | West | PHASE 3 | ERIS | Crystal Cave-Rock Elm 161kV line tap | 74 | 74 | Solar | PV Photovoltaic | Not Started |  | 74 | 74 | 74 | 0
|  |  |  | DPP-2017-AUG | West | Active | Not Started | J803 | [5 empty] | ERIS | E | 32.5 |  | Solar | Lyon County | MN |  |  |  | 1 | 1 | 130000 | 0 | [7 empty] | 1710190 | 0 |  | 1217553 |  | 2927743 | 2927743 | 90.0844 | 90.0844 | 2927743 |  |  |  | Active | 2017-06-16 |  |  | 2019-10-01 | Northern States Power (Xcel Energy) | Lyon County | MN | DPP-2017-AUG | West | PHASE 3 | ERIS | Tracy to Walnut Grove 69 kV line | 32.5 | 32.5 | Solar | PV Photovoltaic | Not Started |  | 32.5 | 0 | 32.5 | 0
|  |  |  | DPP-2017-AUG | Central | Withdrawn | Not Started | J804 | [5 empty] | NRIS |  | 119 |  | Solar | Decatur County | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2018-04-16 |  | 2019-09-01 | Hoosier Energy REC, Inc. | Decatur County | IN | DPP-2017-AUG | Central | GIA | NRIS | Decatur 138kV Substation | 119 | 119 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Done | Under Construction | J805 | [5 empty] | NRIS |  | 199 |  | Solar | Shelby County | IN | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-05-08 | 2019-09-01 | Duke Energy Corporation | Shelby County | IN | DPP-2017-AUG | Central | GIA | NRIS | Gwynneville 345kV Substation | 199 | 199 | Solar | PV Photovoltaic | Under Construction | 2022-05-01 | 199 | 199 | 199 | 199
|  |  |  | DPP-2017-AUG | East (ITC) | Done | Under Construction | J806 | [5 empty] | NRIS |  | 149 |  | Solar | Calhoun County | MI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-05-11 | 2019-09-01 | Michigan Electric Transmission Company, LLC | Calhoun County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Rice Creek - Vrooman 138kV Line Tap | 149 | 149 | Solar | PV Photovoltaic | Under Construction | 2021-06-01 | 149 | 149 | 149 | 149
|  |  |  | DPP-2017-AUG | East (ATC) | Withdrawn | Withdrawn | J807 | [5 empty] | NRIS |  | 41.4 |  | Wind | Lafayette County | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2020-05-26 | 2019-10-17 | 2020-09-15 | American Transmission Co. LLC | Lafayette County | WI | DPP-2017-AUG | East (ATC) | GIA | NRIS | Darlington - Hillman 138kV Line (Falcon Substation J395) | 41.4 | 41.4 | Wind | WT Wind Turbine | Withdrawn | 2021-08-27 | 41.4 | 41.4 | 41.4 | 41.4
|  |  |  | DPP-2017-AUG | Central | Done | Under Construction | J808 | [5 empty] | NRIS |  | 99 |  | Solar | Randolph County | IL | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-05-06 | 2019-09-01 | Ameren Illinois | Randolph County | IL | DPP-2017-AUG | Central | GIA | NRIS | Aster Substation 138kV Bus | 99 | 99 | Solar | PV Photovoltaic | Under Construction | 2020-07-01 | 99 | 99 | 99 | 99
|  |  |  | DPP-2017-AUG | East (ITC) | Withdrawn | Not Started | J809 | [5 empty] | NRIS |  | 99 |  | Solar | Ottawa County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-09 |  | 2019-09-01 | Michigan Electric Transmission Company, LLC | Ottawa County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Bass Creek - Black River 138 kV Line Tap | 99 | 99 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Done | Under Construction | J811 | [5 empty] | NRIS |  | 99 |  | Solar | Fayette County | IL | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-03-25 | 2019-09-01 | Ameren Illinois | Fayette County | IL | DPP-2017-AUG | Central | GIA | NRIS | Ramsey East 138kV Substation | 99 | 99 | Solar | PV Photovoltaic | Under Construction | 2021-05-28 | 99 | 99 | 99 | 99
|  |  |  | DPP-2017-AUG | Central | Done | Under Construction | J813 | [5 empty] | NRIS |  | 275 |  | Solar | Clay County | IL | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-12-16 | 2020-09-30 | Ameren Illinois | Clay County | IL | DPP-2017-AUG | Central | GIA | NRIS | Louisville South Substation 138kV Line | 275 | 275 | Solar | PV Photovoltaic | Under Construction | 2021-10-29 | 250 | 250 | 250 | 250
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J814 | [5 empty] | NRIS |  | 99.9 |  | Wind | Clark County | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-02-04 |  | 2020-09-15 | Northern States Power (Xcel Energy) | Clark County | WI | DPP-2017-AUG | West | PHASE 3 | NRIS | Eau Claire - Arpin 345kV Line | 99.9 | 99.9 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Done | Under Construction | J815 | [5 empty] | NRIS |  | 250 |  | Solar | Christian County | IL | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-04-16 | 2020-09-30 | Ameren Illinois | Christian County | IL | DPP-2017-AUG | Central | GIA | NRIS | Taylorville South-Austin (formerly Pawnee)138kV Line | 250 | 250 | Solar | PV Photovoltaic | Under Construction | 2022-10-28 | 250 | 250 | 250 | 250
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J816 | [5 empty] | NRIS | N | 60 |  | Solar | Cass County | ND |  |  |  | 1 | 0 | 240000 | 546310 | [7 empty] | 1258861 | 41154412 |  | 6468410 |  | 7727271 | 48881683 | 128.7878 | 814.6947 | 48881683 |  |  |  | Withdrawn | 2017-06-16 | 2021-01-29 |  | 2022-09-15 | Otter Tail Power Company | Cass County | ND | DPP-2017-AUG | West | PHASE 3 | NRIS | Buffalo 115kV Substation | 60 | 60 | Solar | PV Photovoltaic | Not Started |  | 60 | 60 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Done | Under Construction | J817 | [5 empty] | NRIS |  | 139 |  | Solar | Warren County | MO | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-12-17 | 2019-09-01 | Ameren Missouri | Warren County | MO | DPP-2017-AUG | Central | GIA | NRIS | Warrenton 161kV Substation | 139 | 139 | Solar | PV Photovoltaic | Under Construction | 2021-10-29 | 139 | 139 | 139 | 139
|  |  |  | DPP-2017-AUG | East (ATC) | Done | Under Construction | J818 | [5 empty] | NRIS |  | 149 |  | Solar | Jefferson County | WI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-05-06 | 2019-09-01 | American Transmission Co. LLC | Jefferson County | WI | DPP-2017-AUG | East (ATC) | GIA | NRIS | Jefferson 138kV Substation | 149 | 149 | Solar | PV Photovoltaic | Under Construction | 2022-04-01 | 149 | 149 | 149 | 149
|  |  |  | DPP-2017-AUG | East (ATC) | Withdrawn | Withdrawn | J819 | [5 empty] | NRIS |  | 99.9 |  | Wind | Lafayette County | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2020-05-26 | 2020-05-20 | 2020-09-15 | American Transmission Co. LLC | Lafayette County | WI | DPP-2017-AUG | East (ATC) | GIA | NRIS | Darlington 138kV Substation | 99.9 | 99.9 | Wind | WT Wind Turbine | Withdrawn | 2021-09-01 | 99.9 | 99.9 | 99.9 | 99.9
|  |  |  | DPP-2017-AUG | East (ITC) | Withdrawn | Not Started | J820 | [5 empty] | NRIS |  | 100.05 |  | Wind | Eaton County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2017-08-03 |  | 2020-09-15 | Michigan Electric Transmission Company, LLC | Eaton County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Oneida 345kV Substation | 100.05 | 100.05 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ATC) | Withdrawn | Withdrawn | J821 | [5 empty] | NRIS |  | 99.9 |  | Wind | Marathon County | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2020-05-26 | 2019-10-17 | 2020-09-15 | American Transmission Co. LLC | Marathon County | WI | DPP-2017-AUG | East (ATC) | GIA | NRIS | Wein - Stratford 115 kV Line Tap | 99.9 | 99.9 | Wind | WT Wind Turbine | Withdrawn | 2021-08-27 | 99.9 | 99.9 | 99.9 | 99.9
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J822 | [5 empty] | NRIS |  | 100 |  | Solar | Lonoke County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-08 |  | 2019-01-30 | Entergy | Lonoke County | AR | DPP-2017-AUG | South | GIA | NRIS | Lynch SES Switchyard - Carlisle 115kV Line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J823 | [5 empty] | NRIS |  | 50 |  | Solar | Clark County | MO | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-02-06 |  | 2020-09-15 | ITC Midwest | Clark County | MO | DPP-2017-AUG | West | PHASE 3 | NRIS | Twin Rivers - Twin Rivers Tap - Palmyra 161kV Line | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Withdrawn | Not Started | J824 | [5 empty] | NRIS |  | 245 |  | Solar | Sullivan County,Vigo County | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-04-17 |  | 2020-09-30 | Duke Energy Corporation | Sullivan County,Vigo County | IN | DPP-2017-AUG | Central | GIA | NRIS | Vigo-Farmersburg Junction 138kV Line | 245 | 245 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ATC) | Withdrawn | Not Started | J825 | [5 empty] | NRIS |  | 99.9 |  | Wind | Green County | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-08 |  | 2020-09-15 | American Transmission Co. LLC | Green County | WI | DPP-2017-AUG | East (ATC) | GIA | NRIS | North Monroe - Albany 138kV Line | 99.9 | 99.9 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Done | Under Construction | J826 | [5 empty] | NRIS |  | 100 |  | Wind | McLean County | IL | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-12-17 | 2020-09-01 | Ameren Illinois | McLean County | IL | DPP-2017-AUG | Central | GIA | NRIS | Weedman Substation 138kV Bus | 100 | 100 | Wind | WT Wind Turbine | Under Construction | 2021-05-28 | 100 | 100 | 100 | 100
|  |  |  | DPP-2017-AUG | Central | Withdrawn | Not Started | J827 | [5 empty] | NRIS |  | 300 |  | Wind | Fountain County,Montgomery County,Tippecanoe County | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-08 |  | 2020-09-30 | Duke Energy Corporation | Fountain County,Montgomery County,Tippecanoe County | IN | DPP-2017-AUG | Central | GIA | NRIS | Lafayette - Veedsburg West - Attica 230kV Line | 300 | 300 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Withdrawn | Not Started | J828 | [5 empty] | NRIS |  | 151.8 |  | Wind | Montgomery County | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2018-02-07 |  | 2020-08-01 | Duke Energy Corporation | Montgomery County | IN | DPP-2017-AUG | Central | GIA | NRIS | Crawfordsville - Linden Tap 138kV Line | 151.8 | 151.8 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Done | Under Construction | J829 | [5 empty] | NRIS |  | 250 |  | Solar | Sullivan County | IN | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-05-26 | 2020-09-30 | Duke Energy Corporation | Sullivan County | IN | DPP-2017-AUG | Central | GIA | NRIS | Dresser - Merom 345kV Line | 250 | 250 | Solar | PV Photovoltaic | Under Construction | 2022-09-01 | 250 | 250 | 250 | 250
|  |  |  | DPP-2017-AUG | South | Done | Under Construction | J830 | [5 empty] | NRIS |  | 100 |  | Solar | Madison County | MS | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-03-05 | 2020-06-01 | Entergy | Madison County | MS | DPP-2017-AUG | South | GIA | NRIS | Canton South to Hoy Road 230 kV Line | 100 | 100 | Solar | PV Photovoltaic | Under Construction | 2021-11-15 | 100 | 100 | 100 | 100
|  |  |  | DPP-2017-AUG | East (ITC) | Done | Under Construction | J832 | [5 empty] | NRIS |  | 100 |  | Solar | Cheboygan County | MI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-06-12 | 2020-04-01 | Michigan Electric Transmission Company, LLC | Cheboygan County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Port Calcite - Riggsville 138kV Line | 100 | 100 | Solar | PV Photovoltaic | Under Construction | 2022-12-31 | 91 | 91 | 91 | 91
|  |  |  | DPP-2017-AUG | East (ITC) | Done | Under Construction | J833 | [5 empty] | NRIS |  | 100 |  | Solar | Washtenaw County | MI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-06-17 | 2020-04-01 | ITC Transmission | Washtenaw County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Milan-Pioneer 120kV line tap | 100 | 100 | Solar | PV Photovoltaic | Under Construction | 2022-04-29 | 50 | 50 | 50 | 50
|  |  |  | DPP-2017-AUG | South | Done | Under Construction | J834 | [5 empty] | NRIS |  | 100 |  | Solar | Phillips County | AR | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-03-06 | 2020-09-01 | Entergy | Phillips County | AR | DPP-2017-AUG | South | GIA | NRIS | Robert E Ritchie 230kV Substation | 100 | 100 | Solar | PV Photovoltaic | Under Construction | 2021-11-15 | 100 | 100 | 100 | 100
|  |  |  | DPP-2017-AUG | Central | Withdrawn | Not Started | J835 | [5 empty] | NRIS |  | 200 |  | Wind | Morgan County | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-04-17 |  | 2020-07-01 | Ameren Illinois | Morgan County | IL | DPP-2017-AUG | Central | GIA | NRIS | Meredosia - Austin 345kV Line | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Active | Not Started | J836 | [5 empty] | ERIS | E | 200 |  | Wind | Kossuth County | IA |  |  |  | 1 | 1 | 800000 | 0 | [7 empty] | 0 | 0 |  | 1416960 |  | 1416960 | 1416960 | 7.0848 | 7.0848 | 1416960 |  |  |  | Active | 2017-06-16 |  |  | 2021-11-01 | ITC Midwest | Kossuth County | IA | DPP-2017-AUG | West | PHASE 3 | ERIS | Ledyard 345kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 200 | 0 | 200 | 0
|  |  |  | DPP-2017-AUG | Central | Done | Under Construction | J837 | [5 empty] | NRIS |  | 200.1 |  | Wind | White County | IN | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-10-21 | 2020-08-01 | Northern Indiana Public Service Company | White County | IN | DPP-2017-AUG | Central | GIA | NRIS | Reynolds 345kV Substation | 200.1 | 200.1 | Wind | WT Wind Turbine | Under Construction | 2021-08-15 | 200.1 | 80 | 200.1 | 80
|  |  |  | DPP-2017-AUG | Central | Done | Under Construction | J838 | [5 empty] | NRIS |  | 200.1 |  | Wind | White County | IN | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-10-21 | 2020-08-01 | Northern Indiana Public Service Company | White County | IN | DPP-2017-AUG | Central | GIA | NRIS | Reynolds 345kV Substation | 200.1 | 200.1 | Wind | WT Wind Turbine | Under Construction | 2021-08-15 | 100 | 40 | 100 | 40
|  |  |  | DPP-2017-AUG | East (ITC) | Withdrawn | Withdrawn | J839 | [5 empty] | NRIS |  | 100 |  | Solar | Lapeer County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2020-05-27 |  | 2020-04-01 | ITC Transmission | Lapeer County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Otsego Tap - Otsego 120 kV Line Tap | 100 | 100 | Solar | PV Photovoltaic | Withdrawn | 2023-03-31 | 58 | 58 | 58 | 58
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J840 | [5 empty] | NRIS | N | 150 |  | Wind | Humboldt County | IA |  |  |  | 1 | 0 | 600000 | 856128 | [7 empty] | 0 | 34212765 |  | 15180241 |  | 15180241 | 49393006 | 101.2016 | 329.2867 | 49393006 |  |  |  | Withdrawn | 2017-06-16 | 2021-01-29 |  | 2021-07-01 | MidAmerican Energy Company | Humboldt County | IA | DPP-2017-AUG | West | PHASE 3 | NRIS | Kossuth - Webster 345 kV Line | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 150 | 150 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Withdrawn | Not Started | J842 | [5 empty] | NRIS |  | 200 |  | Wind | Gibson County | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2020-02-10 |  | 2020-07-01 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Gibson County | IN | DPP-2017-AUG | Central | GIA | NRIS | Gibson - Brown 345kV Line | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2022-09-14 | 200 | 200 | 200 | 200
|  |  |  | DPP-2017-AUG | Central | Withdrawn | Not Started | J843 | [5 empty] | NRIS |  | 200 |  | Wind | Gibson County | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2020-02-10 |  | 2020-07-01 | Duke Energy Corporation | Gibson County | IN | DPP-2017-AUG | Central | GIA | NRIS | Gibson - Francisco 345kV Line | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2021-09-01 | 200 | 200 | 200 | 200
|  |  |  | DPP-2020-Cycle | East (ITC) | Active | Not Started | J1798 | [5 empty] | ERIS |  | 25 |  | Gas | Wayne | MI | [27 empty] | Active | 2020-07-24 |  |  | 2021-06-01 | ITC Transmission | Wayne | MI | DPP-2020-Cycle | East (ITC) | PHASE 1 | ERIS | Waterman 120kV | 0 | 25 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Done | Under Construction | J844 | [5 empty] | ERIS |  | 300 |  | Wind | Knox County | IL | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-12-10 | 2020-09-01 | Ameren Transmission Company of Illinois | Knox County | IL | DPP-2017-AUG | Central | GIA | ERIS | Sandburg Substation 138kV Bus | 300 | 300 | Wind | WT Wind Turbine | Under Construction | 2021-05-28 | 147 | 0 | 147 | 0
|  |  |  | DPP-2017-AUG | Central | Done | Under Construction | J845 | [5 empty] | NRIS |  | 120 |  | Wind | Ford County | IL | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-12-06 | 2020-09-01 | Ameren Illinois | Ford County | IL | DPP-2017-AUG | Central | GIA | NRIS | Gibson City South - Paxton East 138kV Line | 120 | 120 | Wind | WT Wind Turbine | Under Construction | 2021-06-01 | 120 | 52 | 120 | 52
|  |  |  | DPP-2017-AUG | East (ITC) | Withdrawn | Not Started | J846 | [5 empty] | NRIS |  | 140 |  | Solar | Hillsdale County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-09 |  | 2020-04-01 | Michigan Electric Transmission Company, LLC | Hillsdale County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Moore Roadtyd - Coldwater Creek 138 kV Line Tap | 140 | 140 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Done | Under Construction | J847 | [5 empty] | NRIS |  | 90 |  | Solar | Jasper County | IN | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-09-17 | 2020-04-01 | Northern Indiana Public Service Company | Jasper County | IN | DPP-2017-AUG | Central | GIA | NRIS | Schahfer Tap 138kV Substation | 90 | 90 | Solar | PV Photovoltaic | Under Construction | 2021-04-01 | 90 | 90 | 90 | 90
|  |  |  | DPP-2017-AUG | Central | Done | Under Construction | J848 | [5 empty] | NRIS |  | 250 |  | Wind | Christian County | IL | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-04-17 | 2020-09-30 | Ameren Transmission Company of Illinois | Christian County | IL | DPP-2017-AUG | Central | GIA | NRIS | Pana Substation 138kV Bus | 250 | 250 | Wind | WT Wind Turbine | Under Construction | 2021-05-28 | 250 | 250 | 235 | 235
|  |  |  | DPP-2017-AUG | East (UP) | Done | Under Construction | J849 | [5 empty] | NRIS |  | 125 |  | Solar | Delta County | MI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-06-26 | 2020-04-01 | American Transmission Co. LLC | Delta County | MI | DPP-2017-AUG | East (UP) | GIA | NRIS | Chandler 138 kV Substation | 125 | 125 | Solar | PV Photovoltaic | Under Construction | 2022-04-01 | 125 | 125 | 125 | 125
|  |  |  | DPP-2017-AUG | East (ATC) | Done | Under Construction | J850 | [5 empty] | NRIS |  | 250 |  | Solar | Rock County | WI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-04-24 | 2021-09-30 | American Transmission Co. LLC | Rock County | WI | DPP-2017-AUG | East (ATC) | GIA | NRIS | RCEC Bradford - W. Darien 138kV Line | 250 | 250 | Solar | PV Photovoltaic | Under Construction | 2022-09-24 | 250 | 250 | 250 | 250
|  |  |  | DPP-2017-AUG | Central | Withdrawn | Not Started | J851 | [5 empty] | NRIS |  | 50 |  | Wind | Henry County | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-08 |  | 2019-10-01 | Duke Energy Corporation | Henry County | IN | DPP-2017-AUG | Central | GIA | NRIS | Fall Creek - New Castle 138kV Line | 50 | 50 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J852 | [5 empty] | NRIS |  | 100 |  | Solar | Ouachita Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-07 |  | 2019-07-01 | Entergy | Ouachita Parish | LA | DPP-2017-AUG | South | GIA | NRIS | Rilla - Riverton 115kV Line Tap | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1813 | [5 empty] | NRIS |  | 153 |  | Gas | DeSoto | MS | [27 empty] | Active | 2020-07-28 |  |  | 2020-03-20 | Entergy Mississippi LLC | DeSoto | MS | DPP-2020-Cycle | South | PHASE 1 | NRIS | Entergy Freeport 230 kV Substation | 107 | 153 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Done | Under Construction | J853 | [5 empty] | NRIS |  | 149 |  | Solar | White County | IL | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-12-20 | 2019-09-01 | Ameren Illinois | White County | IL | DPP-2017-AUG | Central | GIA | NRIS | Norris City North Substation 138kV Bus | 149 | 149 | Solar | PV Photovoltaic | Under Construction | 2021-05-28 | 149 | 149 | 149 | 149
|  |  |  | DPP-2017-AUG | Central | Withdrawn | Not Started | J854 | [5 empty] | ERIS |  | 30 |  | Solar | Randolph County | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2017-08-08 |  | 2019-04-01 | Ameren Illinois | Randolph County | IL | DPP-2017-AUG | Central | GIA | ERIS | Baldwin 138KV Substation | 30 | 30 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ATC) | Done | Under Construction | J855 | [5 empty] | NRIS |  | 100 |  | Wind | Grant County,Iowa County | WI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-11-14 | 2019-08-01 | American Transmission Co. LLC | Grant County,Iowa County | WI | DPP-2017-AUG | East (ATC) | GIA | NRIS | Lancaster - Eden 138 kV Line Tap | 100 | 100 | Wind | WT Wind Turbine | Under Construction | 2020-11-06 | 100 | 100 | 99.99 | 99.99
|  |  |  | DPP-2017-AUG | Central | Done | Under Construction | J856 | [5 empty] | NRIS |  | 80 |  | Solar | Vanderburgh County | IN | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-11-15 | 2021-04-01 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Vanderburgh County | IN | DPP-2017-AUG | Central | GIA | NRIS | Scott (TWP 138/69) 138 kV Substation | 80 | 80 | Solar | PV Photovoltaic | Under Construction | 2021-03-15 | 80 | 80 | 80 | 80
|  |  |  | DPP-2017-AUG | East (ITC) | Done | Under Construction | J857 | [5 empty] | NRIS |  | 124.95 |  | Solar | Calhoun County | MI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-06-10 | 2019-09-01 | Michigan Electric Transmission Company, LLC | Calhoun County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Verona - Foundry 138 kV Line Tap | 124.95 | 124.95 | Solar | PV Photovoltaic | Under Construction | 2022-02-07 | 124.95 | 124.95 | 124.95 | 124.95
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J858 | [5 empty] | NRIS |  | 140 |  | Solar | Bradley County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2017-09-01 |  | 2019-09-29 | Entergy | Bradley County | AR | DPP-2017-AUG | South | GIA | NRIS | Hilo 115 kV Switch | 140 | 140 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Done | Under Construction | J859 | [5 empty] | NRIS |  | 149.94 |  | Solar | Cass County | IL | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-01-23 | 2019-09-01 | Ameren Illinois | Cass County | IL | DPP-2017-AUG | Central | GIA | NRIS | Frederick North - Meredosia East 138kV Line | 149.94 | 149.94 | Solar | PV Photovoltaic | Under Construction | 2022-05-31 | 149.94 | 149.94 | 149.94 | 149.94
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1833 | [5 empty] | NRIS |  | 115.56 |  | Gas | Lafourche | LA | [27 empty] | Active | 2020-07-30 |  |  | 2022-10-01 | Entergy Louisiana LLC | Lafourche | LA | DPP-2020-Cycle | South | PHASE 1 | NRIS | Leeville 115kV | 115.56 | 115.56 | Gas | piston) Engine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | South | Active | Not Started | J1834 | [5 empty] | NRIS |  | 1292 |  | Gas | Orange | TX | [27 empty] | Active | 2020-07-30 |  |  | 2025-04-25 | Entergy Texas Inc | Orange | TX | DPP-2020-Cycle | South | PHASE 1 | NRIS | Sabine 138/230 kV Substation | 1230 | 1292 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J860 | [5 empty] | NRIS |  | 200 |  | Wind | Jefferson Davis Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-07 |  | 2020-03-30 | Entergy | Jefferson Davis Parish | LA | DPP-2017-AUG | South | GIA | NRIS | New Jefferson Davis 138 kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (UP) | Withdrawn | Not Started | J861 | [5 empty] | NRIS |  | 99.96 |  | Solar | Marquette County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2018-05-22 |  | 2020-09-01 | American Transmission Co. LLC | Marquette County | MI | DPP-2017-AUG | East (UP) | GIA | NRIS | Dead River - Arnold 345 kV Line | 99.96 | 99.96 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | Central | Active | Not Started | J1839 | [5 empty] | NRIS |  | 340.3 |  | Gas | Macon | IL | [27 empty] | Active | 2020-07-31 |  |  | 2023-11-01 | Ameren Illinois | Macon | IL | DPP-2020-Cycle | Central | PHASE 1 | NRIS | Decatur ADM North 138 kV | 325 | 340.3 | Gas | Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J862 | [5 empty] | NRIS |  | 20 |  | Solar | Orleans Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-03-25 |  | 2019-05-31 | Entergy | Orleans Parish | LA | DPP-2017-AUG | South | GIA | NRIS | NASA-Michoud 115 kV Line | 20 | 20 | Solar | PV Photovoltaic | Not Started |  | 20 | 20 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Active | Not Started | J1843 | [5 empty] | NRIS |  | 12 |  | Gas | Dane | WI | [27 empty] | Active | 2020-07-31 |  |  | 2023-03-15 | American Transmission Co. LLC | Dane | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Christiana 138 kV | 12 | 12 | Gas | Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | East (ATC) | Withdrawn | Not Started | J1838 | [5 empty] | NRIS |  | 320 |  | Gas | Dane | WI | [27 empty] | Withdrawn | 2020-07-31 | 2021-02-23 |  | 2025-02-12 | American Transmission Co. LLC | Dane | WI | DPP-2020-Cycle | East (ATC) | PHASE 1 | NRIS | Christiana 138 kV | 320 | 320 | Gas | Combined-Cycle - Steam Part | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ATC) | Done | Under Construction | J864 | [5 empty] | NRIS |  | 49.98 |  | Solar | Richland County | WI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-04-27 | 2021-09-01 | American Transmission Co. LLC | Richland County | WI | DPP-2017-AUG | East (ATC) | GIA | NRIS | Lone Rock 69kV Substation | 49.98 | 49.98 | Solar | PV Photovoltaic | Under Construction | 2022-09-01 | 49.98 | 49.98 | 49.98 | 49.98
|  |  |  | DPP-2017-AUG | East (ITC) | Withdrawn | Not Started | J865 | [5 empty] | NRIS |  | 79.97 |  | Solar | St. Clair County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-09 |  | 2020-09-01 | ITC Transmission | St. Clair County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Lee - Menlo 120kV Line | 79.97 | 79.97 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | South | Done | Under Construction | J866 | [5 empty] | NRIS |  | 200 |  | Wind | Tunica County | MS | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-04-06 | 2020-03-30 | Entergy | Tunica County | MS | DPP-2017-AUG | South | GIA | NRIS | Batesville - Robert E. Ritchie 230 kV line | 200 | 200 | Wind | WT Wind Turbine | Under Construction | 2021-07-01 | 200 | 200 | 200 | 200
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J867 | [5 empty] | NRIS |  | 200 |  | Solar | Polk County | TX | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-07 |  | 2019-09-29 | Entergy | Polk County | TX | DPP-2017-AUG | South | GIA | NRIS | Gulf Livingston - SHECO Menard | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J869 | [5 empty] | NRIS |  | 49.98 |  | Solar | Sherburne County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-10-24 |  | 2022-09-01 | Great River Energy | Sherburne County | MN | DPP-2017-AUG | West | PHASE 3 | NRIS | Cable - Cable Tap 69kV Substation | 49.98 | 49.98 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ATC) | Done | Under Construction | J870 | [5 empty] | NRIS |  | 200 |  | Solar | Grant County,Iowa County | WI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-02-21 | 2021-09-10 | American Transmission Co. LLC | Grant County,Iowa County | WI | DPP-2017-AUG | East (ATC) | GIA | NRIS | Eden - Wyoming Valley 138kV Line Tap | 200 | 200 | Solar | PV Photovoltaic | Under Construction | 2020-08-01 | 200 | 200 | 200 | 200
|  |  |  | DPP-2017-AUG | East (ATC) | Done | Under Construction | J871 | [5 empty] | NRIS |  | 100 |  | Solar | Grant County,Iowa County | WI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-02-21 | 2021-09-10 | American Transmission Co. LLC | Grant County,Iowa County | WI | DPP-2017-AUG | East (ATC) | GIA | NRIS | Eden - Wyoming Valley 138kV Line Tap | 100 | 100 | Solar | PV Photovoltaic | Under Construction | 2021-08-01 | 100 | 100 | 100 | 100
|  |  |  | DPP-2017-AUG | Central | Withdrawn | Not Started | J872 | [5 empty] | NRIS |  | 200 |  | Wind | Macon County | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-08 |  | 2020-09-01 | Ameren Illinois | Macon County | IL | DPP-2017-AUG | Central | GIA | NRIS | Blue Mount tap on the Pana-Route 51D-1462 138kV line | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J873 | [5 empty] | NRIS | N | 200 |  | Wind | Hardin County | IA |  |  |  | 1 | 0 | 800000 | 778552 | [7 empty] | 0 | 94244425 |  | 36601622 |  | 36601622 | 130846047 | 183.0081 | 654.2302 | 130846047 |  |  |  | Withdrawn | 2017-06-16 | 2021-01-29 |  | 2021-07-01 | ITC Midwest | Hardin County | IA | DPP-2017-AUG | West | PHASE 3 | NRIS | Killdeer- Blackhawk 345kV Line | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Active | Not Started | J874 | [5 empty] | NRIS | N | 150 |  | Solar | Murray County | MN |  |  |  | 1 | 1 | 600000 | 464501 | [7 empty] | 3569462 | 45564314 |  | 8941965 |  | 12511427 | 58075741 | 83.4095 | 387.1716 | 58075741 |  |  |  | Active | 2017-06-16 |  |  | 2021-09-30 | Northern States Power (Xcel Energy) | Murray County | MN | DPP-2017-AUG | West | PHASE 3 | NRIS | Fenton - Chanarambie 115kV Line | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
|  |  |  | DPP-2017-AUG | East (ITC) | Done | Under Construction | J875 | [5 empty] | NRIS |  | 150 |  | Solar | Lenawee County | MI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-08-06 | 2020-09-10 | Michigan Electric Transmission Company, LLC | Lenawee County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Par - Raisin Road 138kV Line | 150 | 150 | Solar | PV Photovoltaic | Under Construction | 2022-11-18 | 150 | 150 | 150 | 150
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J876 | [5 empty] | NRIS |  | 200 |  | Wind | Faribault County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-07-23 |  | 2020-09-15 | ITC Midwest | Faribault County | MN | DPP-2017-AUG | West | PHASE 3 | NRIS | Huntley 345kV sub | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Active | Not Started | J877 | [5 empty] | NRIS | N | 250 |  | Solar | Palo Alto County | IA |  |  |  | 1 | 1 | 1000000 | 0 | [7 empty] | 0 | 60459128 |  | 1862468 |  | 1862468 | 62321596 | 7.4499 | 249.2864 | 62321596 |  |  |  | Active | 2017-06-16 |  |  | 2021-09-30 | MidAmerican Energy Company | Palo Alto County | IA | DPP-2017-AUG | West | PHASE 3 | NRIS | Obrien - Kossuth 345kV Line (J529 & J590 New Substation) | 250 | 250 | Solar | PV Photovoltaic | Not Started |  | 250 | 250 | 250 | 250
|  |  |  | DPP-2017-AUG | East (ATC) | Done | Under Construction | J878 | [5 empty] | NRIS |  | 200 |  | Solar | Kenosha County | WI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-04-28 | 2021-09-10 | American Transmission Co. LLC | Kenosha County | WI | DPP-2017-AUG | East (ATC) | GIA | NRIS | Paris 138kV Substation | 200 | 200 | Solar | PV Photovoltaic | Under Construction | 2022-09-01 | 200 | 200 | 200 | 200
|  |  |  | DPP-2017-AUG | East (UP) | Withdrawn | Not Started | J879 | [5 empty] | NRIS |  | 70 |  | Wind | Baraga County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2018-05-11 |  | 2020-09-23 | American Transmission Co. LLC | Baraga County | MI | DPP-2017-AUG | East (UP) | GIA | NRIS | North Lake 138 kV Substation | 70 | 70 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J880 | [5 empty] | NRIS |  | 150 |  | Wind | Ward County | ND | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-10-24 |  | 2020-09-15 | Northern States Power (Xcel Energy) | Ward County | ND | DPP-2017-AUG | West | PHASE 3 | NRIS | Magic City 230kV sub | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Withdrawn | Not Started | J881 | [5 empty] | ERIS |  | 45 |  | Solar | Jasper County | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2017-07-17 |  | 2019-04-01 | Ameren Illinois | Jasper County | IL | DPP-2017-AUG | Central | GIA | ERIS | Newton 138kV Substation | 45 | 45 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Withdrawn | Not Started | J882 | [5 empty] | ERIS |  | 15 |  | Solar | Montgomery County | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2017-08-08 |  | 2019-04-01 | Ameren Illinois | Montgomery County | IL | DPP-2017-AUG | Central | GIA | ERIS | Coffeen North 138kV Substation | 15 | 15 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Withdrawn | Withdrawn | J883 | [5 empty] | NRIS |  | 80 |  | Wind | Pulaski County | IN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2020-12-04 | 2019-12-04 | 2020-10-01 | Northern Indiana Public Service Company | Pulaski County | IN | DPP-2017-AUG | Central | GIA | NRIS | Monticello-East Winamac | 80 | 80 | Wind | WT Wind Turbine | Withdrawn | 2022-05-01 | 80 | 80 | 80 | 80
|  |  |  | DPP-2017-AUG | Central | Withdrawn | Not Started | J884 | [5 empty] | NRIS |  | 100 |  | Solar | McLean County | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-12-18 |  | 2020-09-15 | Ameren Illinois | McLean County | IL | DPP-2017-AUG | Central | GIA | NRIS | Brokaw - Gibson City South 138 kV Line | 100 | 100 | Solar | PV Photovoltaic | Not Started | 2021-05-28 | 100 | 100 | 100 | 100
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J885 | [5 empty] | NRIS | N | 64 |  | Wind | Worth County | IA |  |  |  | 1 | 0 | 256000 | 0 | [7 empty] | 0 | 14624732 |  | 8748925 |  | 8748925 | 23373657 | 136.702 | 365.2134 | 23373657 |  |  |  | Withdrawn | 2017-06-16 | 2021-01-29 |  | 2020-09-30 | ITC Midwest | Worth County | IA | DPP-2017-AUG | West | PHASE 3 | NRIS | J407 Glenworth 161kV Substation | 64 | 64 | Wind | WT Wind Turbine | Not Started |  | 64 | 64 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ATC) | Done | In Service | J886 | [5 empty] | NRIS |  | 150 |  | Solar | Manitowoc County | WI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-11-25 | 2020-09-15 | American Transmission Co. LLC | Manitowoc County | WI | DPP-2017-AUG | East (ATC) | GIA | NRIS | Kewaunee 138 kV Substation | 150 | 150 | Solar | PV Photovoltaic | In Service | 2020-08-01 | 150 | 150 | 150 | 150
|  |  |  | DPP-2017-AUG | Central | Withdrawn | Not Started | J887 | [5 empty] | NRIS |  | 75 |  | Wind | Knox County | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-08 |  | 2020-09-30 | Ameren Illinois | Knox County | IL | DPP-2017-AUG | Central | GIA | NRIS | G545 138kV Substation | 75 | 75 | Wind | WT Wind Turbine | Not Started | 2019-09-15 | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J889 | [5 empty] | NRIS |  | 150 |  | Wind | Nelson County | ND | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-10-24 |  | 2020-09-15 | Great River Energy | Nelson County | ND | DPP-2017-AUG | West | PHASE 3 | NRIS | Ramsey - Prairie 230KV Line Tap | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ITC) | Withdrawn | Not Started | J890 | [5 empty] | NRIS |  | 100 |  | Wind | Presque Isle County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-09 |  | 2020-09-15 | Michigan Electric Transmission Company, LLC | Presque Isle County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Port Calcite - Riggsville 138kV Line | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J891 | [5 empty] | NRIS |  | 300 |  | Wind | Pipestone County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-07-23 |  | 2020-09-15 | Northern States Power (Xcel Energy) | Pipestone County | MN | DPP-2017-AUG | West | PHASE 3 | NRIS | Buffalo Ridge - Pipestone 115kV Line Tap | 300 | 300 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2020-Cycle | West | Active | Not Started | J1826 | [5 empty] | NRIS |  | 4 |  | Hydro | Dakota | MN | [27 empty] | Active | 2020-12-21 |  |  | 2022-03-01 | Northern States Power (Xcel Energy) | Dakota | MN | DPP-2020-Cycle | West | PHASE 1 | NRIS | Cannon Falls Transmission 69 kV | 4 | 4 | Hydro | Hydroelectric | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ATC) | Withdrawn | Not Started | J892 | [5 empty] | NRIS |  | 74.97 |  | Solar | Walworth County | WI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2018-03-12 |  | 2019-09-01 | American Transmission Co. LLC | Walworth County | WI | DPP-2017-AUG | East (ATC) | GIA | NRIS | Bluff Creek (Tap) to Sugar Creek 138 kV line tap | 74.97 | 74.97 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | South | Done | Under Construction | J893 | [5 empty] | NRIS |  | 100 |  | Solar | White County | AR | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-11-20 | 2021-08-01 | Entergy | White County | AR | DPP-2017-AUG | South | GIA | NRIS | Searcy Price Sub 161kV | 100 | 100 | Solar | PV Photovoltaic | Under Construction | 2021-08-01 | 100 | 100 | 100 | 100
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J894 | [5 empty] | ERIS |  | 45 |  | Solar | Woodruff County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-07 |  | 2020-04-01 | Entergy | Woodruff County | AR | DPP-2017-AUG | South | GIA | ERIS | McCrory - Moses 161kV Substation | 45 | 45 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J895 | [5 empty] | ERIS |  | 33 |  | Solar | Lonoke County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-07 |  | 2020-04-01 | Entergy | Lonoke County | AR | DPP-2017-AUG | South | GIA | ERIS | Carlisle - Lonoke East 115kV Line Tap | 33 | 33 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J896 | [5 empty] | NRIS |  | 150 |  | Wind | Crawford County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2018-06-18 |  | 2019-10-15 | MidAmerican Energy Company | Crawford County | IA | DPP-2017-AUG | West | PHASE 3 | NRIS | Victory 161 kV Substation | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Active | Not Started | J897 | [5 empty] | ERIS | N | 190 |  | Wind | Grand Forks County | ND |  |  |  | 1 | 1 | 760000 | 10701615 | [7 empty] | 7008189 | 73226568 |  | 21765774 |  | 28773963 | 102000531 | 151.4419 | 536.8449 | 28773963 |  |  |  | Active | 2017-06-16 |  |  | 2021-10-01 | Great River Energy | Grand Forks County | ND | DPP-2017-AUG | West | PHASE 3 | ERIS | Prairie - Ramsey 230 kV line | 190 | 190 | Wind | WT Wind Turbine | Not Started |  | 190 | 190 | 190 | 0
|  |  |  | DPP-2017-AUG | West | Active | Not Started | J898 | [5 empty] | ERIS | N | 100 |  | Wind | Howard County | IA |  |  |  | 1 | 1 | 400000 | 250000 | [7 empty] | 0 | 10917450 |  | 29392052 |  | 29392052 | 40309502 | 293.9205 | 403.095 | 29392052 |  |  |  | Active | 2017-06-16 |  |  | 2021-10-01 | Dairyland Power Cooperative | Howard County | IA | DPP-2017-AUG | West | PHASE 3 | ERIS | Rice - Beaver Creek 161kV line tap | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 100 | 100 | 100 | 0
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J899 | [5 empty] | NRIS |  | 180 |  | Wind | Carroll County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-03-25 |  | 2019-10-15 | Entergy | Carroll County | AR | DPP-2017-AUG | South | GIA | NRIS | Green Forest South - Harrison West 161kV | 180 | 180 | Wind | WT Wind Turbine | Not Started |  | 180 | 180 | 0 | 0
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J900 | [5 empty] | NRIS |  | 200 |  | Solar | Livingston Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-07 |  | 2020-09-15 | Entergy | Livingston Parish | LA | DPP-2017-AUG | South | GIA | NRIS | Coly - Vignes 230kV Line | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Active | Not Started | J901 | [5 empty] | ERIS | N | 200 |  | Wind | Redwood County | MN |  |  |  | 1 | 1 | 800000 | 951699 | [7 empty] | 445030 | 48894553 |  | 79171991 |  | 79617021 | 128511574 | 398.0851 | 642.5579 | 79617021 |  |  |  | Active | 2017-06-16 |  |  | 2021-10-01 | Northern States Power (Xcel Energy) | Redwood County | MN | DPP-2017-AUG | West | PHASE 3 | ERIS | Lyon County - Cedar Mountain Line | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 200 | 200 | 200 | 0
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J902 | [5 empty] | NRIS |  | 99.96 |  | Solar | Ashley County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-07 |  | 2019-09-01 | Entergy | Ashley County | AR | DPP-2017-AUG | South | GIA | NRIS | AECC Mist to Montrose 115 kV line | 99.96 | 99.96 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Done | Under Construction | J903 | [5 empty] | NRIS |  | 100 |  | Solar | Henry County | IN | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-12-06 | 2020-09-15 | Duke Energy Corporation | Henry County | IN | DPP-2017-AUG | Central | GIA | NRIS | Greensboro 138 kV Substation | 100 | 100 | Solar | PV Photovoltaic | Under Construction | 2023-05-01 | 100 | 100 | 100 | 100
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J904 | [5 empty] | NRIS |  | 100 |  | Solar | Ashley County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-07 |  | 2019-09-15 | Entergy | Ashley County | AR | DPP-2017-AUG | South | GIA | NRIS | Hamburg - Mist 115kV Line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J905 | [5 empty] | NRIS | N | 40 |  | Solar | Pipestone County | MN |  |  |  | 1 | 0 | 160000 | 90866 | [7 empty] | 2323944 | 11807223 |  | 1458865 |  | 3782809 | 15590032 | 94.5702 | 389.7508 | 15590032 |  |  |  | Withdrawn | 2017-06-16 | 2021-01-29 |  | 2020-09-15 | Northern States Power (Xcel Energy) | Pipestone County | MN | DPP-2017-AUG | West | PHASE 3 | NRIS | Buffalo Ridge 115kV Substation | 40 | 40 | Solar | PV Photovoltaic | Not Started |  | 40 | 40 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ITC) | Withdrawn | Withdrawn | J906 | [5 empty] | NRIS |  | 100 |  | Wind | Muskegon County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2020-02-07 |  | 2020-07-01 | Michigan Electric Transmission Company, LLC | Muskegon County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Kenowa - Ludington 345 kV Line Tap | 100 | 100 | Wind | WT Wind Turbine | Withdrawn |  | 100 | 100 | 100 | 100
|  |  |  | DPP-2017-AUG | South | Done | Under Construction | J907 | [5 empty] | NRIS |  | 200 |  | Solar | Monroe County | AR | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-03-24 | 2022-09-01 | Entergy | Monroe County | AR | DPP-2017-AUG | South | GIA | NRIS | Brinkley East - Aubrey 230 kV Line | 200 | 200 | Solar | PV Photovoltaic | Under Construction | 2022-06-01 | 100 | 100 | 100 | 100
|  |  |  | DPP-2017-AUG | South | Done | Under Construction | J908 | [5 empty] | NRIS |  | 100 |  | Solar | Tallahatchie County | MS | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-03-04 | 2021-09-01 | Entergy | Tallahatchie County | MS | DPP-2017-AUG | South | GIA | NRIS | Webb 115kV Substation | 100 | 100 | Solar | PV Photovoltaic | Under Construction | 2023-06-01 | 100 | 100 | 100 | 100
|  |  |  | DPP-2017-AUG | South | Done | Under Construction | J909 | [5 empty] | NRIS |  | 100 |  | Solar | Tangipahoa Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-11-22 | 2021-09-01 | Entergy | Tangipahoa Parish | LA | DPP-2017-AUG | South | GIA | NRIS | Amite 115 kV Substation | 100 | 100 | Solar | PV Photovoltaic | Under Construction | 2022-02-15 | 100 | 100 | 100 | 100
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J910 | [5 empty] | NRIS |  | 150 |  | Solar | Hinds County | MS | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-07 |  | 2020-09-15 | Entergy | Hinds County | MS | DPP-2017-AUG | South | GIA | NRIS | Clinton Industrial 230kV Substation | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J911 | [5 empty] | NRIS |  | 150 |  | Solar | Montgomery County | TX | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-07 |  | 2020-09-15 | Entergy | Montgomery County | TX | DPP-2017-AUG | South | GIA | NRIS | Porter 230kV Substation | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Done | Under Construction | J912 | [5 empty] | NRIS |  | 100 |  | Solar | Christian County | IL | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-04-16 | 2020-09-15 | Ameren Transmission Company of Illinois | Christian County | IL | DPP-2017-AUG | Central | GIA | NRIS | Pana Substation 138kV Bus | 100 | 100 | Solar | PV Photovoltaic | Under Construction | 2023-09-15 | 100 | 100 | 100 | 100
|  |  |  | DPP-2017-AUG | Central | Done | Under Construction | J913 | [5 empty] | NRIS |  | 200 |  | Solar | White County | IN | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-12-03 | 2020-08-01 | Northern Indiana Public Service Company | White County | IN | DPP-2017-AUG | Central | GIA | NRIS | Reynolds 345kV Substation | 200 | 200 | Solar | PV Photovoltaic | Under Construction | 2022-08-15 | 200 | 160 | 200 | 160
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J915 | [5 empty] | NRIS |  | 100 |  | Solar | Liberty County | TX | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-07 |  | 2020-09-15 | Entergy | Liberty County | TX | DPP-2017-AUG | South | GIA | NRIS | Parkway - East Gate 138kV line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J917 | [5 empty] | NRIS |  | 78 |  | Solar | Liberty County | TX | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-07 |  | 2019-11-01 | Entergy | Liberty County | TX | DPP-2017-AUG | South | GIA | NRIS | Tarkington - New Long John 138kV line tap | 78 | 78 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | South | Done | Under Construction | J919 | [5 empty] | NRIS |  | 180 |  | Solar | Jackson County | AR | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-11-21 | 2021-08-01 | Entergy | Jackson County | AR | DPP-2017-AUG | South | GIA | NRIS | Cash - Newport AB 161 kV Line Tap | 180 | 180 | Solar | PV Photovoltaic | Under Construction | 2022-02-02 | 180 | 180 | 180 | 180
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J919A - Error | [5 empty] | NRIS |  | 100 |  | Solar | Richland Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-03-25 |  | 2021-09-01 | Entergy | Richland Parish | LA | DPP-2017-AUG | South | GIA | NRIS | Oak Ridge - Dunn 115kV Line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 100 | 100 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Withdrawn | Not Started | J920 | [5 empty] | NRIS |  | 100 |  | Solar | Pulaski County | IL | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2017-08-29 |  | 2019-08-31 | Ameren Illinois | Pulaski County | IL | DPP-2017-AUG | Central | GIA | NRIS | Joppa 161 kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ITC) | Withdrawn | Not Started | J921 | [5 empty] | NRIS |  | 146.7 |  | Wind | Ionia County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-04-23 |  | 2019-07-01 | Michigan Electric Transmission Company, LLC | Ionia County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Thompson Road 138 kV Substation | 146.7 | 146.7 | Wind | WT Wind Turbine | Not Started |  | 146.7 | 146.7 | 0 | 0
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J922 | [5 empty] | NRIS |  | 100 |  | Solar | Chicot County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-07 |  | 2020-06-30 | Entergy | Chicot County | AR | DPP-2017-AUG | South | GIA | NRIS | Lake Village Bagby - Chicot 115kV Line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J923 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Montgomery County | TX | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-08 |  | 2020-09-15 | Entergy | Montgomery County | TX | DPP-2017-AUG | South | GIA | NRIS | Porter 230kV Substation | 50 | 50 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J924 | [5 empty] | NRIS |  | 50 |  | Battery Storage | Monroe County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-08 |  | 2020-09-15 | Entergy | Monroe County | AR | DPP-2017-AUG | South | GIA | NRIS | Brinkley East - Aubrey 230 kV line | 50 | 50 | Battery Storage | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ITC) | Withdrawn | Not Started | J925 | [5 empty] | NRIS |  | 50 |  | Solar | Shiawassee County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2018-04-24 |  | 2019-06-30 | Michigan Electric Transmission Company, LLC | Shiawassee County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | North Cournna - Bell Road 138 kV line | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Active | Not Started | J926 | [5 empty] | ERIS | N | 101.28 |  | Wind | Saint Croix County | WI |  |  |  | 1 | 1 | 405120 | 694880 | [7 empty] | 15627 | 13300115 |  | 8527000 |  | 8542627 | 21842742 | 84.3466 | 215.6669 | 8542627 |  |  |  | Active | 2017-06-16 |  |  | 2021-09-01 | Northern States Power (Xcel Energy) | Saint Croix County | WI | DPP-2017-AUG | West | PHASE 3 | ERIS | Pine Lake - Apple River 161 kV Line | 101.28 | 101.28 | Wind | WT Wind Turbine | Not Started |  | 101.28 | 101.28 | 101.28 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J927 | [5 empty] | NRIS | N | 100 |  | Wind | Faribault County,Freeborn County | MN |  |  |  | 1 | 0 | 400000 | 656027 | [7 empty] | 0 | 22543972 |  | 16296287 |  | 16296287 | 38840259 | 162.9629 | 388.4026 | 38840259 |  |  |  | Withdrawn | 2017-06-16 | 2021-01-29 |  | 2021-10-01 | ITC Midwest | Faribault County,Freeborn County | MN | DPP-2017-AUG | West | PHASE 3 | NRIS | Walters 69 kV Substation | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 100 | 100 | 0 | 0
|  |  |  | DPP-2017-AUG | East (UP) | Done | Under Construction | J928 | [5 empty] | NRIS |  | 79.99 |  | Wind | Delta County,Schoolcraft County | MI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-04-19 | 2019-08-15 | American Transmission Co. LLC | Delta County,Schoolcraft County | MI | DPP-2017-AUG | East (UP) | GIA | NRIS | Garden Corners 138 kV Substation | 79.99 | 79.99 | Wind | WT Wind Turbine | Under Construction | 2019-10-01 | 79.99 | 79.99 | 79.99 | 79.99
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J929 | [5 empty] | NRIS |  | 25 |  | Solar | McIntosh County | ND | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-10-24 |  | 2021-06-30 | Montana-Dakota Utilities Company | McIntosh County | ND | DPP-2017-AUG | West | PHASE 3 | NRIS | Wishek 41.6 kV Substation | 25 | 25 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J930 | [5 empty] | NRIS |  | 38 |  | Wind | Sioux County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2017-11-16 |  | 2019-09-15 | MidAmerican Energy Company | Sioux County | IA | DPP-2017-AUG | West | PHASE 3 | NRIS | Boyden - Sheldon 69kV line | 38 | 38 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | East (ITC) | Withdrawn | Not Started | J931 | [5 empty] | NRIS |  | 150 |  | Wind | Ottawa County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-04-23 |  | 2021-09-15 | Michigan Electric Transmission Company, LLC | Ottawa County | MI | DPP-2017-AUG | East (ITC) | GIA | NRIS | Kenowa 345kV Substation | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 150 | 150 | 0 | 0
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J932 | [5 empty] | NRIS |  | 100 |  | Solar | Liberty County | TX | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-07 |  | 2019-09-15 | Entergy | Liberty County | TX | DPP-2017-AUG | South | GIA | NRIS | Porter - China 230 kV Line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J933 | [5 empty] | NRIS | N | 200 |  | Wind | Day County | SD |  |  |  | 1 | 0 | 800000 | 6919581 | [7 empty] | 37992071 | 123672178 |  | 167771599 |  | 205763670 | 329435848 | 1028.8184 | 1647.1792 | 329435848 |  |  |  | Withdrawn | 2017-06-16 | 2021-01-29 |  | 2021-09-15 | Otter Tail Power Company | Day County | SD | DPP-2017-AUG | West | PHASE 3 | NRIS | Ellendale - Big Stone South 345kV Line | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
|  |  |  | DPP-2017-AUG | South | Done | Under Construction | J934 | [5 empty] | NRIS |  | 200 |  | Solar | Crittenden County | AR | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-02-28 | 2021-09-01 | Entergy | Crittenden County | AR | DPP-2017-AUG | South | GIA | NRIS | Kuhn 161kV Substation | 200 | 200 | Solar | PV Photovoltaic | Under Construction | 2022-06-01 | 180 | 180 | 180 | 180
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J935 | [5 empty] | NRIS |  | 200 |  | Solar | Hubbard County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-02-04 |  | 2020-09-15 | Minnesota Power (Allete, Inc.) | Hubbard County | MN | DPP-2017-AUG | West | PHASE 3 | NRIS | Hubbard - Badoura 230kV Line | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J938 | [5 empty] | NRIS |  | 50 |  | Wind | Palo Alto County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2017-10-09 |  | 2019-09-15 | MidAmerican Energy Company | Palo Alto County | IA | DPP-2017-AUG | West | PHASE 3 | NRIS | Emmestburg - Freedom 69kV Line | 50 | 50 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J939 | [5 empty] | NRIS |  | 38 |  | Wind | Wright County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2018-10-12 |  | 2019-09-15 | MidAmerican Energy Company | Wright County | IA | DPP-2017-AUG | West | PHASE 3 | NRIS | Clarion-Eagle Grove 69kV line | 38 | 38 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J940 | [5 empty] | NRIS |  | 100 |  | Wind | Burleigh County | ND | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-02-06 |  | 2019-09-15 | Otter Tail Power Company | Burleigh County | ND | DPP-2017-AUG | West | PHASE 3 | NRIS | Jamestown - Center 345kV Line | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J941 | [5 empty] | NRIS |  | 200 |  | Wind | Grant County | SD | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2018-11-01 |  | 2020-07-01 | Otter Tail Power Company | Grant County | SD | DPP-2017-AUG | West | PHASE 3 | NRIS | Big Stone-Brookings County 345KV Line | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J942 | [5 empty] | NRIS |  | 107 |  | Solar | Craighead County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-03-25 |  | 2021-08-01 | Entergy | Craighead County | AR | DPP-2017-AUG | South | GIA | NRIS | Cash - Newport AB 161kV Line Tap | 107 | 107 | Solar | PV Photovoltaic | Not Started |  | 107 | 107 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Withdrawn | Not Started | J943 | [5 empty] | NRIS |  | 200 |  | Wind | Lincoln County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-03-12 |  | 2020-09-30 | Northern States Power (Xcel Energy) | Lincoln County | MN | DPP-2017-AUG | West | PHASE 3 | NRIS | J460 substation on the Brookings - H081 345kV Line | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | South | Done | Not Started | J944 | [5 empty] | NRIS |  | 200 |  | Solar | New Madrid County | MO | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-12-17 | 2021-09-01 | Entergy | New Madrid County | MO | DPP-2017-AUG | South | GIA | NRIS | Portageville - New Madrid 161kV Line | 200 | 200 | Solar | PV Photovoltaic | Not Started | 2022-10-01 | 200 | 200 | 200 | 200
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J945 | [5 empty] | NRIS |  | 200 |  | Solar | Washington County | MS | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-07 |  | 2019-09-15 | Entergy | Washington County | MS | DPP-2017-AUG | South | GIA | NRIS | Gerald Andrus - Clinton Industrial 230 kV Line | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | West | Active | Not Started | J946 | [5 empty] | NRIS | N | 200 |  | Solar | Cass County | ND |  |  |  | 1 | 1 | 800000 | 1245693 | [7 empty] | 3759194 | 122846445 |  | 16953953 |  | 20713147 | 143559592 | 103.5657 | 717.798 | 143559592 |  |  |  | Active | 2017-06-16 |  |  | 2020-07-31 | Northern States Power (Xcel Energy) | Cass County | ND | DPP-2017-AUG | West | PHASE 3 | NRIS | Bison 345kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
|  |  |  | DPP-2017-AUG | East (ATC) | Done | Under Construction | J947 | [5 empty] | NRIS |  | 200 |  | Solar | Grant County | WI | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2020-04-17 | 2019-09-15 | American Transmission Co. LLC | Grant County | WI | DPP-2017-AUG | East (ATC) | GIA | NRIS | Potosis - Hillman 138kV Line | 200 | 200 | Solar | PV Photovoltaic | Under Construction | 2023-07-01 | 200 | 200 | 200 | 200
|  |  |  | DPP-2017-AUG | South | Withdrawn | Not Started | J948 | [5 empty] | ERIS |  | 100 |  | Solar | Poinsett County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2017-06-16 | 2019-01-07 |  | 2020-06-01 | Entergy | Poinsett County | AR | DPP-2017-AUG | South | GIA | ERIS | Harrisburg Tap - Harrisburg 161kV Line | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2017-AUG | Central | Done | Under Construction | J949 | [5 empty] | NRIS |  | 200 |  | Solar | Coles County | IL | [21 empty] | 0 | 0 |  |  |  |  | Done | 2017-06-16 |  | 2019-12-10 | 2020-08-31 | Ameren Transmission Company of Illinois | Coles County | IL | DPP-2017-AUG | Central | GIA | NRIS | Kansas Substation 138kV Bus #3 | 200 | 200 | Solar | PV Photovoltaic | Under Construction | 2020-10-31 | 200 | 170 | 200 | 170
|  |  |  | 0 | 0 | Done | Not Started | J950 | [5 empty] | NRIS |  | 0 |  | Wind | Murray County, Pipestone County | MN | [21 empty] | #DIV/0! | #DIV/0! |  |  |  |  | Done | 2017-08-04 |  |  | 2016-09-01 | Northern States Power (Xcel Energy) | Murray County, Pipestone County | MN |  |  |  | NRIS | Xcel Chanarambie Substation | 0 | 0 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J951 | [5 empty] | ERIS |  | 80 |  | Wind | Kittson County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-02-02 | 2020-03-25 |  | 2018-11-15 | Otter Tail Power Company | Kittson County | MN | DPP-2018-APR | West | PHASE 3 | ERIS | Donaldson - Warsaw 115 kV Line Tap | 80 | 80 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J952 | [5 empty] | ERIS | N | 54 |  | Wind | Corson County | SD |  |  |  | 1 | 0 | 216000 | 400435 | [7 empty] | 8700000 | 0 | 0 | 4672223 | 0 | 13372223 | 13372223 | 247.6338 | 247.6338 | 13372223 |  |  |  | Withdrawn | 2018-02-05 | 2021-03-09 |  | 2022-09-01 | Montana-Dakota Utilities Co. | Corson County | SD | DPP-2018-APR | West | PHASE 3 | ERIS | McLaughlin - McIntosh Junction 115 kV Line Tap | 54 | 54 | Wind | WT Wind Turbine | Not Started |  | 54 | 54 | 0 | 0
|  |  |  | DPP-2018-APR | West | Active | Not Started | J954 | [5 empty] | External NRIS | N | 1.4 |  | Solar | Johnson County | IA |  |  |  | 1 | 1 | 5600 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Active | 2018-03-08 |  |  | 2016-10-30 | ITC Midwest | Johnson County | IA | DPP-2018-APR | West | PHASE 3 | External NRIS | AMIL.IOW_AFRYT | 1.4 | 1.4 | Solar | PV Photovoltaic | Not Started |  | 1.4 | 1.4 | 1.4 | 1.4
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J956 | [5 empty] | NRIS | N | 200 |  | Solar | Ralls County | MO |  |  |  | 1 | 1 | 800000 | 9725 | [9 empty] | 0 | 1170000 | 8734641 | 1170000 | 9904641 | 5.85 | 49.5232 | 9904641 |  |  |  | Active | 2018-03-09 |  |  | 2021-09-15 | Ameren Missouri | Ralls County | MO | DPP-2018-APR | Central | PHASE 3 | NRIS | Spencer Creek 345kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J957 | [5 empty] | NRIS | N | 800 |  | Wind | Mercer County,Putnam County,Sullivan County | MO |  |  |  | 0 | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-09 | 2019-03-19 |  | 2010-09-01 | Ameren Transmission Company of Illinois | Mercer County,Putnam County,Sullivan County | MO | DPP-2018-APR | Central | PHASE 3 | NRIS | Maywood 345kV Substation | 800 | 800 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J958 | [5 empty] | NRIS |  | 100 |  | Wind | Lincoln County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2020-09-01 | Northern States Power (Xcel Energy) | Lincoln County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Buffalo Ridge 115kV Substation | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J959 | [5 empty] | NRIS | N | 150 |  | Wind | Fayette County | IA |  |  |  | 1 | 0 | 600000 | 0 | [7 empty] | 0 | 47918 | 37301 | 5448373 | 0 | 5448373 | 5533592 | 36.3225 | 36.8906 | 5533592 |  |  |  | Withdrawn | 2018-03-12 | 2021-03-09 |  | 2020-09-01 | SMMPA | Fayette County | IA | DPP-2018-APR | West | PHASE 3 | NRIS | Windsor 161kV Substation | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 150 | 150 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J960 | [5 empty] | NRIS |  | 400 |  | Wind | Presque Isle County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-03-21 |  | 2020-09-01 | Michigan Electric Transmission Company, LLC | Presque Isle County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Livingston 345kV Substation | 400 | 400 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J961 | [5 empty] | NRIS |  | 150 |  | Solar | West Baton Rouge Parish | LA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-29 |  | 2021-01-31 | Entergy Louisiana, LLC | West Baton Rouge Parish | LA | DPP-2018-APR | South | GIA | NRIS | Livonia - Wilbert 138 kV Line Tap | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Done | Under Construction | J962 | [5 empty] | ERIS |  | 100 |  | Solar | DeSoto County | MS | [21 empty] | 0 | 0 |  |  |  |  | Done | 2018-03-12 |  | 2020-08-12 | 2021-01-31 | Entergy Mississippi, LLC | DeSoto County | MS | DPP-2018-APR | South | GIA | ERIS | Twinkletown 230 kV Substation | 100 | 100 | Solar | PV Photovoltaic | Under Construction | 2022-06-30 | 100 | 0 | 100 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J964 | [5 empty] | NRIS |  | 70 |  | Solar | Hinds County | MS | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-29 |  | 2020-10-02 | Entergy Mississippi, LLC | Hinds County | MS | DPP-2018-APR | South | GIA | NRIS | Edwards - Bolton 115kV Line Tap | 70 | 70 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G001 | [5 empty] | ERIS |  | 255 |  | 0 | Brown County | WI | [27 empty] | Withdrawn | 1995-11-08 |  |  |  | American Transmission Co. LLC | Brown County | WI |  |  | SPA - SIS | ERIS | Unknown | 255 | 255 |  |  | Withdrawn | 2014-11-17 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J965 | [5 empty] | NRIS |  | 150 |  | Wind | Cottonwood County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2018-11-19 |  | 2020-09-01 | Xcel Energy | Cottonwood County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Lakefield Generation SW 345kV Substation | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J966 | [5 empty] | NRIS |  | 400 |  | Wind | Putnam County,Sullivan County | MO | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2020-12-01 | Ameren Transmission Company of Illinois | Putnam County,Sullivan County | MO | DPP-2018-APR | West | PHASE 3 | NRIS | Zachary 345kV Substation | 400 | 400 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Active | Not Started | J967 | [5 empty] | NRIS | N | 150 |  | Wind | Mower County | MN |  |  |  | 1 | 1 | 600000 | 111927 | [7 empty] | 0 | 71345 | 0 | 5874605 | 0 | 5874605 | 5945950 | 39.164 | 39.6397 | 5945950 |  |  |  | Active | 2018-03-12 |  |  | 2020-09-01 | Northern States Power (Xcel Energy) | Mower County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Adams 345kV Substation | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 150 | 150 | 150 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G013 | [5 empty] | ERIS |  | 99 |  | 0 | Manitowoc County | WI | [27 empty] | Withdrawn | 1999-10-21 |  |  |  | American Transmission Co. LLC | Manitowoc County | WI |  |  |  | ERIS | Unknown | 99 | 99 |  |  | Not Started | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G027 | [5 empty] | ERIS |  | 650 |  | 0 | Jefferson County | IN | [27 empty] | Withdrawn | 2000-01-25 |  |  |  | Duke Energy Corporation | Jefferson County | IN |  |  |  | ERIS | Unknown | 650 | 650 |  |  | Not Started | 2002-05-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J968 | [5 empty] | NRIS | N | 200 |  | Wind | Jasper County,White County | IN |  |  |  | 1 | 1 | 800000 | 0 | [9 empty] | 0 | 1102243 | 0 | 1102243 | 1102243 | 5.5112 | 5.5112 | 1102243 |  |  |  | Active | 2018-03-12 |  |  | 2022-09-01 | Northern Indiana Public Service Company | Jasper County,White County | IN | DPP-2018-APR | Central | PHASE 3 | NRIS | Reynolds 345kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 200 | 200 | 200 | 200
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J969 | [5 empty] | NRIS |  | 100 |  | Solar | Tuscola County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2018-11-01 |  | 2020-12-01 | ITC Transmission | Tuscola County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Kirk 345kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G028 | [5 empty] | ERIS |  | 650 |  | 0 | Jefferson County | IN | [27 empty] | Withdrawn | 2000-01-25 |  |  |  | Duke Energy Corporation | Jefferson County | IN |  |  |  | ERIS | Unknown | 650 | 650 |  |  | Not Started | 2000-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G036 | [5 empty] | ERIS |  | 600 |  | 0 | Wood County | WI | [27 empty] | Withdrawn | 2000-05-05 |  |  |  | American Transmission Co. LLC | Wood County | WI |  |  | Network Upgrade | ERIS | Unknown | 600 | 600 |  |  | Not Started | 2007-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G039 | [5 empty] | ERIS |  | 600 |  | Coal | Sullivan County | IN | [27 empty] | Withdrawn | 2000-05-23 |  |  |  | Hoosier Energy REC, Inc. | Sullivan County | IN |  |  |  | ERIS | Unknown | 600 | 600 | Coal |  | Not Started | 2003-04-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G047 | [5 empty] | ERIS |  | 340 |  | Gas | Washtenaw County | MI | [27 empty] | Withdrawn | 2000-08-03 |  |  |  | ITC Transmission | Washtenaw County | MI |  |  |  | ERIS | Unknown | 340 | 340 | Gas |  | Withdrawn | 2002-05-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J970 | [5 empty] | NRIS |  | 50 |  | Solar | Oscoda County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2018-10-17 |  | 2020-01-01 | Michigan Electric Transmission Company, LLC | Oscoda County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Mio Dam - Gaylord 138 kV Line Tap | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G050 | [5 empty] | ERIS |  | 320 |  | 0 | Portage County | WI | [27 empty] | Withdrawn | 2000-08-18 |  |  |  | American Transmission Co. LLC | Portage County | WI |  |  |  | ERIS | Unknown | 320 | 320 |  |  | Not Started | 2008-02-28 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G052 | [5 empty] | ERIS |  | 1000 |  | 0 | Sheboygan County | WI | [27 empty] | Withdrawn | 2000-08-22 |  |  |  | American Transmission Co. LLC | Sheboygan County | WI |  |  |  | ERIS | Unknown | 1000 | 1000 |  |  | Not Started | 2004-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G054 | [5 empty] | ERIS |  | 350 |  | 0 | Waukesha County | WI | [27 empty] | Withdrawn | 2000-08-24 |  |  |  | American Transmission Co. LLC | Waukesha County | WI |  |  | Network Upgrade | ERIS | Unknown | 350 | 350 |  |  | Not Started | 2008-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G055 | [5 empty] | ERIS |  | 220 |  | 0 | Dubuque County | IA | [27 empty] | Withdrawn | 2000-08-30 |  |  |  | ITC Midwest | Dubuque County | IA |  |  |  | ERIS | Unknown | 220 | 220 |  |  | Not Started | 2007-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G061 | [5 empty] | ERIS |  | 165 |  | 0 | Jackson County | IL | [27 empty] | Withdrawn | 2000-09-23 |  |  |  | Southern Illinois Power Cooperative | Jackson County | IL |  |  |  | ERIS | Unknown | 165 | 165 |  |  | Not Started | 2003-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G065 | [5 empty] | ERIS |  | 1050 |  | Gas | St. Clair County | MI | [27 empty] | Withdrawn | 2000-11-02 |  |  |  | ITC Transmission | St. Clair County | MI |  |  |  | ERIS | Unknown | 1050 | 1050 | Gas |  | Not Started | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G066 | [5 empty] | ERIS |  | 800 |  | 0 | Monroe County | MI | [27 empty] | Withdrawn | 2000-11-02 |  |  |  | ITC Transmission | Monroe County | MI |  |  |  | ERIS | Unknown | 800 | 800 |  |  | Not Started | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J971 | [5 empty] | NRIS |  | 250 |  | Wind | Nobles County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2020-09-30 | Northern States Power (Xcel Energy) | Nobles County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Nobles Co - Fenton 115 kV Line Tap | 250 | 250 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G068 | [5 empty] | ERIS |  | 800 |  | Combined Cycle | Racine County | WI | [27 empty] | Withdrawn | 2000-11-27 |  |  |  | American Transmission Co. LLC | Racine County | WI |  |  | SPA - SIS | ERIS | Unknown | 800 | 800 | Combined Cycle |  | Not Started | 2004-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J972 | [5 empty] | NRIS |  | 140 |  | Solar | St. Francis County | AR | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-29 |  | 2021-10-31 | Entergy Arkansas, LLC | St. Francis County | AR | DPP-2018-APR | South | GIA | NRIS | Hughes-Forest City South 161kv line | 140 | 140 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G070 | [5 empty] | ERIS |  | 900 |  | 0 | McCracken County | KY | [27 empty] | Withdrawn | 2000-12-21 |  |  |  | LG&E and KU Services Company as agent for Louisville Gas and Electric Company and Kentucky Utilities Company | McCracken County | KY |  |  |  | ERIS | Unknown | 900 | 900 |  |  | Not Started | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G076 | [5 empty] | ERIS |  | 52 |  | 0 | Grant County | WI | [27 empty] | Withdrawn | 2001-02-07 |  |  |  | American Transmission Co. LLC | Grant County | WI |  |  | Network Upgrade | ERIS | Unknown | 52 | 52 |  |  | Not Started | 2011-10-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G077 | [5 empty] | ERIS |  | 150 |  | 0 | Washtenaw County | MI | [27 empty] | Withdrawn | 2001-02-09 |  |  |  | ITC Transmission | Washtenaw County | MI |  |  |  | ERIS | Unknown | 150 | 150 |  |  | Not Started | 2001-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G078 | [5 empty] | ERIS |  | 85 |  | 0 | Wood County | WI | [27 empty] | Withdrawn | 2001-02-12 |  |  |  | American Transmission Co. LLC | Wood County | WI |  |  |  | ERIS | Unknown | 85 | 85 |  |  | Withdrawn | 2002-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G079 | [5 empty] | ERIS |  | 160 |  | 0 | Vermillion County | IN | [27 empty] | Withdrawn | 2001-02-14 |  |  |  | Duke Energy Corporation | Vermillion County | IN |  |  | SPA - SIS | ERIS | Unknown | 160 | 160 |  |  | Not Started | 2002-05-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J973 | [5 empty] | NRIS | N | 250 |  | Wind | Coles County,Edgar County | IL |  |  |  | 0 | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-03-19 |  | 2020-09-01 | Ameren Transmission Company of Illinois | Coles County,Edgar County | IL | DPP-2018-APR | Central | PHASE 3 | NRIS | Kansas West 345kV Substation | 250 | 250 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G080 | [5 empty] | ERIS |  | 320 |  | 0 | Vermillion County | IN | [27 empty] | Withdrawn | 2001-02-14 |  |  |  | Duke Energy Corporation | Vermillion County | IN |  |  |  | ERIS | Unknown | 320 | 320 |  |  | Not Started | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G083 | [5 empty] | ERIS |  | 800 |  | 0 | Hamilton County | OH | [27 empty] | Withdrawn | 2001-03-05 |  |  |  | DEO&K | Hamilton County | OH |  |  |  | ERIS | Unknown | 800 | 800 |  |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G086 | [5 empty] | ERIS |  | 600 |  | 0 | Brown County | WI | [27 empty] | Withdrawn | 2001-03-15 |  |  |  | American Transmission Co. LLC | Brown County | WI |  |  |  | ERIS | Unknown | 600 | 600 |  |  | Not Started | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G088 | [5 empty] | ERIS |  | 350 |  | 0 | Shelby County | IN | [27 empty] | Withdrawn | 2001-03-30 |  |  |  | Indianapolis Power & Light Company | Shelby County | IN |  |  |  | ERIS | Unknown | 350 | 350 |  |  | Not Started | 2007-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G092 | [5 empty] | ERIS |  | 46 |  | 0 | Lancaster County | NE | [27 empty] | Withdrawn | 2001-04-16 |  |  |  | Lincoln Electric System | Lancaster County | NE |  |  |  | ERIS | Unknown | 46 | 46 |  |  | Not Started | 2005-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G098 | [5 empty] | ERIS |  | 165 |  | 0 | Butler County | OH | [27 empty] | Withdrawn | 2001-06-18 |  |  |  | DEO&K | Butler County | OH |  |  |  | ERIS | Unknown | 165 | 165 |  |  | Withdrawn | 2002-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G099 | [5 empty] | ERIS |  | 250 |  | 0 | Jackson County | IL | [27 empty] | Withdrawn | 2001-06-19 |  |  |  | Southern Illinois Power Cooperative | Jackson County | IL |  |  |  | ERIS | Unknown | 250 | 250 |  |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G100 | [5 empty] | ERIS |  | 530 |  | 0 | Winnebago County | WI | [27 empty] | Withdrawn | 2001-06-20 |  |  |  | American Transmission Co. LLC | Winnebago County | WI |  |  |  | ERIS | Unknown | 530 | 530 |  |  | Not Started | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G101 | [5 empty] | ERIS |  | 530 |  | 0 | Outagamie County | WI | [27 empty] | Withdrawn | 2001-06-20 |  |  |  | American Transmission Co. LLC | Outagamie County | WI |  |  |  | ERIS | Unknown | 530 | 530 |  |  | Not Started | 2006-06-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J974 | [5 empty] | NRIS | N | 250 |  | Wind | Fulton County,Peoria County | IL |  |  |  | 1 | 1 | 1000000 | 0 | [9 empty] | 4777168 | 1596000 | 0 | 1596000 | 6373168 | 6.384 | 25.4927 | 6373168 |  |  |  | Active | 2018-03-12 |  |  | 2021-09-01 | Ameren Illinois | Fulton County,Peoria County | IL | DPP-2018-APR | Central | PHASE 3 | NRIS | Mapleridge 345kV Switching Station | 250 | 250 | Wind | WT Wind Turbine | Not Started |  | 250 | 250 | 225 | 225
|  |  |  | 0 | 0 | Withdrawn | Not Started | G102 | [5 empty] | ERIS |  | 530 |  | 0 | Calumet County | WI | [27 empty] | Withdrawn | 2001-06-20 |  |  |  | American Transmission Co. LLC | Calumet County | WI |  |  |  | ERIS | Unknown | 530 | 530 |  |  | Not Started | 2005-06-25 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Active | Not Started | J975 |  |  | Scoping Calls - Max Blackburn | Invenergy |  | ERIS | N | 150 |  | Wind | Cass County | ND |  |  |  | 1 | 1 | 600000 | 1558786 | [7 empty] | 215892 | 6707887 | 0 | 4829091 | 0 | 5044983 | 11752870 | 33.6332 | 78.3525 | 5044983 |  |  |  | Active | 2018-03-12 |  |  | 2023-10-31 | Otter Tail Power Company | Cass County | ND | DPP-2018-APR | West | PHASE 3 | ERIS | Buffalo 115kV Substation | 150 | 150 | Wind | WT Wind Turbine | Not Started |  | 150 | 150 | 150 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J976 | [5 empty] | NRIS | N | 300 |  | Solar | Warren County | MO |  |  |  | 1 | 1 | 1200000 | 0 | [9 empty] | 0 | 5906500 | 5265682 | 5906500 | 11172182 | 19.6883 | 37.2406 | 11172182 |  |  |  | Active | 2018-03-12 |  |  | 2021-10-31 | Ameren Missouri | Warren County | MO | DPP-2018-APR | Central | PHASE 3 | NRIS | Montgomery - Enon 345kV Line Tap | 300 | 300 | Solar | PV Photovoltaic | Not Started |  | 300 | 300 | 300 | 300
|  |  |  | 0 | 0 | Withdrawn | Not Started | G109 | [5 empty] | ERIS |  | 50 |  | 0 | Faribault County | MN | [27 empty] | Withdrawn | 2001-07-20 |  |  |  | Northern States Power (Xcel Energy) | Faribault County | MN |  |  |  | ERIS | Unknown | 50 | 50 |  |  | Not Started | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J977 | [5 empty] | NRIS |  | 300 |  | Wind | Jackson County,Martin County | MN | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2021-03-01 | ITC Midwest | Jackson County,Martin County | MN | DPP-2018-APR | West | PHASE 3 | NRIS | Jackson North 161kV Substation | 300 | 300 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J978 | [5 empty] | NRIS |  | 100 |  | Wind | Montcalm County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-11-21 |  | 2021-03-01 | Michigan Electric Transmission Company, LLC | Montcalm County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Eureka - Vestaburg 138kV Line Tap | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G110 | [5 empty] | ERIS |  | 500 |  | 0 | Bowman County | ND | [27 empty] | Withdrawn | 2001-07-30 |  |  |  | Montana-Dakota Utilities Company | Bowman County | ND |  |  | SPA - SIS | ERIS | Unknown | 500 | 500 |  |  | Not Started | 2006-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G112 | [5 empty] | ERIS |  | 85 |  | 0 | Marathon County | WI | [27 empty] | Withdrawn | 2001-08-03 |  |  |  | American Transmission Co. LLC | Marathon County | WI |  |  |  | ERIS | Unknown | 85 | 85 |  |  | Not Started | 1905-06-26 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J979 | [5 empty] | NRIS | N | 200 |  | Wind | Christian County | IL |  |  |  | 1 | 1 | 800000 | 0 | [9 empty] | 3275500 | 4042000 | 0 | 4042000 | 7317500 | 20.21 | 36.5875 | 7317500 |  |  |  | Active | 2018-03-12 |  |  | 2021-03-01 | Ameren Transmission Company of Illinois | Christian County | IL | DPP-2018-APR | Central | PHASE 3 | NRIS | Pana Substation 345kV Bus | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 170 | 170 | 170 | 170
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J980 | [5 empty] | NRIS | N | 200 |  | Wind | Christian County | IL |  |  |  | 0 | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-01-06 |  | 2021-03-01 | Ameren Transmission Company of Illinois | Christian County | IL | DPP-2018-APR | Central | PHASE 3 | NRIS | Pana Substation 345kV Bus | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J981 | [5 empty] | NRIS |  | 200 |  | Wind | Washington County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2021-03-09 |  | 2021-03-01 | MidAmerican Energy Company | Washington County | IA | DPP-2018-APR | West | PHASE 3 | NRIS | Sub T 345kV Substation | 200 | 200 | Wind | WT Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
|  |  |  | DPP-2018-APR | West | Active | Not Started | J982 |  |  | Scoping Calls - Max Blackburn | Invenergy |  | NRIS | N | 300 |  | Wind | Dickinson County,Emmet County | IA |  |  |  | 1 | 1 | 1200000 | 2354531 | [7 empty] | 0 | 255190 | 6410000 | 30203354 | 0 | 30203354 | 36868544 | 100.6778 | 122.8951 | 36868544 |  |  |  | Active | 2018-03-12 |  |  | 2021-03-01 | MidAmerican Energy Company | Dickinson County,Emmet County | IA | DPP-2018-APR | West | PHASE 3 | NRIS | Obrien County - Kossuth 345 kV Line Tap | 300 | 300 | Wind | WT Wind Turbine | Not Started |  | 300 | 300 | 300 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G114 | [5 empty] | ERIS |  | 60 |  | 0 | Juneau County | WI | [27 empty] | Withdrawn | 2001-08-08 |  |  |  | American Transmission Co. LLC | Juneau County | WI |  |  |  | ERIS | Unknown | 60 | 60 |  |  | Not Started | 2006-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G115 | [5 empty] | ERIS |  | 100 |  | 0 | Juneau County | WI | [27 empty] | Withdrawn | 2001-08-08 |  |  |  | American Transmission Co. LLC | Juneau County | WI |  |  |  | ERIS | Unknown | 100 | 100 |  |  | Not Started | 2005-06-25 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G116 | [5 empty] | ERIS |  | 300 |  | 0 | Knox County | IN | [27 empty] | Withdrawn | 2001-08-08 |  |  |  | Duke Energy Corporation | Knox County | IN |  |  |  | ERIS | Unknown | 300 | 300 |  |  | Not Started | 2005-06-24 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G119 | [5 empty] | ERIS |  | 750 |  | 0 | McLean County | ND | [27 empty] | Withdrawn | 2001-08-16 |  |  |  | Great River Energy | McLean County | ND |  |  |  | ERIS | Unknown | 750 | 750 |  |  | Not Started | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G120 | [5 empty] | ERIS |  | 225 |  | 0 | Itasca County | MN | [27 empty] | Withdrawn | 2001-08-16 |  |  |  | Minnesota Power (Allete, Inc.) | Itasca County | MN |  |  |  | ERIS | Unknown | 225 | 225 |  |  | Withdrawn |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J983 | [5 empty] | NRIS | N | 100 |  | Wind | Brown County,LaSalle County | IL |  |  |  | 0 | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2018-11-01 |  | 2021-03-01 | Ameren Illinois | Brown County,LaSalle County | IL | DPP-2018-APR | Central | PHASE 3 | NRIS | Oglesby - Minonk Tap 138kV Line Tap | 100 | 100 | Wind | WT Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Active | Not Started | J984 | [5 empty] | NRIS |  | 200 |  | Wind | Gratiot County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2018-03-12 |  |  | 2021-06-01 | Michigan Electric Transmission Company, LLC | Gratiot County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Nelson Road â€“ Murphy 345kV line | 200 | 200 | Wind | WT Wind Turbine | Not Started | 2022-10-31 | 200 | 200 | 200 | 200
|  |  |  | 0 | 0 | Withdrawn | Not Started | G122 | [5 empty] | ERIS |  | 300 |  | 0 | Knox County | IN | [27 empty] | Withdrawn | 2001-08-22 |  |  |  | Indianapolis Power & Light Company | Knox County | IN |  |  |  | ERIS | Unknown | 300 | 300 |  |  | Not Started | 2005-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G125 | [5 empty] | ERIS |  | 325 |  | 0 | Clinton County | IA | [27 empty] | Withdrawn | 2001-09-06 |  |  |  | ITC Midwest | Clinton County | IA |  |  |  | ERIS | Unknown | 325 | 325 |  |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G126 | [5 empty] | ERIS |  | 325 |  | 0 | Des Moines County | IA | [27 empty] | Withdrawn | 2001-09-06 |  |  |  | ITC Midwest | Des Moines County | IA |  |  |  | ERIS | Unknown | 325 | 325 |  |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J985 | [5 empty] | NRIS | N | 120 |  | Solar | Scott County | MO |  |  |  | 0 | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-01-06 |  | 2020-12-01 | Ameren Missouri | Scott County | MO | DPP-2018-APR | Central | PHASE 3 | NRIS | Miner - Kelso 161kV Line Tap | 120 | 120 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ATC) | Active | Not Started | J986 | [5 empty] | NRIS | N | 149.76 |  | Solar | Wood County | WI |  |  |  | 1 | 1 | 599040 | 776690 | [9 empty] | 659824 | 6740635 | 0 | 6740635 | 7400459 | 45.0096 | 49.4155 | 7400459 |  |  |  | Active | 2018-03-12 |  |  | 2020-09-01 | American Transmission Co. LLC | Wood County | WI | DPP-2018-APR | East (ATC) | PHASE 3 | NRIS | Port Edwards - Sand Lake 138kV | 149.76 | 149.76 | Solar | PV Photovoltaic | Not Started |  | 149.76 | 149.76 | 149.76 | 149.76
|  |  |  | 0 | 0 | Withdrawn | Not Started | G127 | [5 empty] | ERIS |  | 600 |  | 0 | Des Moines County | IA | [27 empty] | Withdrawn | 2001-09-06 |  |  |  | ITC Midwest | Des Moines County | IA |  |  |  | ERIS | Unknown | 600 | 600 |  |  | Not Started | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G128 | [5 empty] | ERIS |  | 600 |  | 0 | Marshall County | IA | [27 empty] | Withdrawn | 2001-09-06 |  |  |  | ITC Midwest | Marshall County | IA |  |  |  | ERIS | Unknown | 600 | 600 |  |  | Not Started | 2003-06-02 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G129 | [5 empty] | ERIS |  | 600 |  | 0 | Wapello County | IA | [27 empty] | Withdrawn | 2001-09-06 |  |  |  | ITC Midwest | Wapello County | IA |  |  |  | ERIS | Unknown | 600 | 600 |  |  | Not Started | 2007-06-03 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G130 | [5 empty] | ERIS |  | 22 |  | 0 | Murray County | MN | [27 empty] | Withdrawn | 2001-09-10 |  |  |  | ITC Midwest | Murray County | MN |  |  |  | ERIS | Unknown | 22 | 22 |  |  | Not Started | 2007-06-04 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G131 | [5 empty] | ERIS |  | 500 |  | 0 | Brown County | WI | [27 empty] | Withdrawn | 2001-09-11 |  |  |  | American Transmission Co. LLC | Brown County | WI |  |  |  | ERIS | Unknown | 500 | 500 |  |  | Not Started | 2007-06-05 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J987 | [5 empty] | NRIS | N | 100 |  | Solar | Montgomery County | MO |  |  |  | 1 | 1 | 400000 | 0 | [9 empty] | 0 | 831000 | 1801909 | 831000 | 2632909 | 8.31 | 26.3291 | 2632909 |  |  |  | Active | 2018-03-12 |  |  | 2021-09-01 | Ameren Missouri | Montgomery County | MO | DPP-2018-APR | Central | PHASE 3 | NRIS | Montgomery 161kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 100 | 100 | 100 | 100
|  |  |  | DPP-2018-APR | South | Withdrawn | Not Started | J988 | [5 empty] | NRIS |  | 200 |  | Solar | Wayne County | MS | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-08-29 |  | 2022-09-01 | Cooperative Energy | Wayne County | MS | DPP-2018-APR | South | GIA | NRIS | W Waynesboro 230kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Withdrawn | Not Started | J989 | [5 empty] | NRIS |  | 80 |  | Solar | Oakland County | MI | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-02-12 | 2020-06-30 |  | 2021-09-01 | Michigan Electric Transmission Company, LLC | Oakland County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Halsey 138kV Substation | 80 | 80 | Solar | PV Photovoltaic | Not Started |  | 80 | 80 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Withdrawn | G133 | [5 empty] | ERIS |  | 585 |  | 0 | Monroe County | MI | [27 empty] | Withdrawn | 2001-09-18 |  |  |  | ITC Transmission | Monroe County | MI |  |  |  | ERIS | Unknown | 585 | 585 |  |  | Withdrawn | 2002-08-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G136 | [5 empty] | ERIS |  | 91 |  | Coal | Logan County | IL | [27 empty] | Withdrawn | 2001-09-28 |  |  |  | Ameren Illinois | Logan County | IL |  |  |  | ERIS | Unknown | 91 | 91 | Coal |  | Not Started | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J990 | [5 empty] | NRIS |  | 150 |  | Solar | Dubuque County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2019-02-15 |  | 2020-09-01 | ITC Midwest | Dubuque County | IA | DPP-2018-APR | West | PHASE 3 | NRIS | Salem 345kV Substation | 150 | 150 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G138 | [5 empty] | ERIS |  | 352 |  | 0 | Walworth County | WI | [27 empty] | Withdrawn | 2001-10-08 |  |  |  | American Transmission Co. LLC | Walworth County | WI |  |  |  | ERIS | Unknown | 352 | 352 |  |  | Not Started | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G139 | [5 empty] | ERIS |  | 250 |  | 0 | Grant County | WI | [27 empty] | Withdrawn | 2001-10-10 |  |  |  | American Transmission Co. LLC | Grant County | WI |  |  |  | ERIS | Unknown | 250 | 250 |  |  | Not Started | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J991 | [5 empty] | NRIS | N | 200 |  | Solar | Clay County | IL |  |  |  | 1 | 1 | 800000 | 0 | [9 empty] | 298000 | 2391000 | 0 | 2391000 | 2689000 | 11.955 | 13.445 | 2689000 |  |  |  | Active | 2018-03-12 |  |  | 2021-09-01 | Ameren Illinois | Clay County | IL | DPP-2018-APR | Central | PHASE 3 | NRIS | Xenia 345kV Switching Station | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
|  |  |  | 0 | 0 | Withdrawn | Not Started | G143 | [5 empty] | ERIS |  | 250 |  | 0 | Monroe County | IA | [27 empty] | Withdrawn | 2001-10-23 |  |  |  | ITC Midwest | Monroe County | IA |  |  |  | ERIS | Unknown | 250 | 250 |  |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J992 | [5 empty] | NRIS | N | 200 |  | Solar | Cass County | IN |  |  |  | 1 | 1 | 800000 | 0 | [9 empty] | 0 | 4509448 | 0 | 4509448 | 4509448 | 22.5472 | 22.5472 | 4509448 |  |  |  | Active | 2018-03-12 |  |  | 2021-09-01 | Duke Energy Indiana | Cass County | IN | DPP-2018-APR | Central | PHASE 3 | NRIS | Walton 230kV Substation | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
|  |  |  | 0 | 0 | Withdrawn | Not Started | G145 | [5 empty] | ERIS |  | 85 |  | 0 | Wood County | WI | [27 empty] | Withdrawn | 2001-10-24 |  |  |  | American Transmission Co. LLC | Wood County | WI |  |  |  | ERIS | Unknown | 85 | 85 |  |  | Not Started | 2002-05-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J993 | [5 empty] | NRIS | N | 200 |  | Solar | Boone County | IN |  |  |  | 1 | 1 | 800000 | 242500 | [9 empty] | 0 | 491808 | 0 | 491808 | 491808 | 2.459 | 2.459 | 491808 |  |  |  | Active | 2018-03-12 |  |  | 2021-09-01 | Indianapolis Power & Light Company | Boone County | IN | DPP-2018-APR | Central | PHASE 3 | NRIS | Hortonville - Whitestown 345kV Line Tap | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
|  |  |  | DPP-2018-APR | Central | Active | Not Started | J994 | [5 empty] | NRIS | N | 100 |  | Solar | Callaway County | MO |  |  |  | 1 | 1 | [14 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | Active | 2018-03-12 |  |  | 2021-09-01 | Ameren Missouri | Callaway County | MO | DPP-2018-APR | Central | PHASE 3 | NRIS | Guthrie 161 kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 100 | 100 | 100 | 100
|  |  |  | 0 | 0 | Withdrawn | Not Started | G147 | [5 empty] | ERIS |  | 100 |  | 0 | Iowa County | WI | [27 empty] | Withdrawn | 2001-11-02 |  |  |  | American Transmission Co. LLC | Iowa County | WI |  |  |  | ERIS | Unknown | 100 | 100 |  |  | Not Started | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G151 | [5 empty] | ERIS |  | 12 |  | 0 | McIntosh County | ND | [27 empty] | Withdrawn | 2001-11-14 |  |  |  | Montana-Dakota Utilities Company | McIntosh County | ND |  |  |  | ERIS | Unknown | 12 | 12 |  |  | Not Started | 2002-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G152 | [5 empty] | ERIS |  | 530 |  | 0 | Calumet County | WI | [27 empty] | Withdrawn | 2001-11-16 |  |  |  | American Transmission Co. LLC | Calumet County | WI |  |  |  | ERIS | Unknown | 530 | 530 |  |  | Not Started | 2003-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | Central | Withdrawn | Not Started | J995 | [5 empty] | NRIS | N | 100 |  | Solar | Brown County,Jersey County | IL |  |  |  | 0 | 0 | [16 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-01-06 |  | 2021-09-01 | Ameren Illinois | Brown County,Jersey County | IL | DPP-2018-APR | Central | PHASE 3 | NRIS | NW Jerseyville Northwest Substation 138kV Bus | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | East (ITC) | Active | Not Started | J996 | [5 empty] | NRIS |  | 80 |  | Solar | Lenawee County | MI | [21 empty] | 0 | 0 |  |  |  |  | Active | 2018-03-12 |  |  | 2021-09-01 | Michigan Electric Transmission Company, LLC | Lenawee County | MI | DPP-2018-APR | East (ITC) | PHASE 3 | NRIS | Beecher - Moraco 138kV Line | 80 | 80 | Solar | PV Photovoltaic | Not Started | 2022-10-31 | 80 | 80 | 80 | 80
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J997 | [5 empty] | NRIS |  | 200 |  | Solar | LaMoure County | ND | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2020-09-01 | Montana-Dakota Utilities Co. | LaMoure County | ND | DPP-2018-APR | West | PHASE 3 | NRIS | Ellendale 345 kV Sub, 230 kV Bus - 661098 | 200 | 200 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J998 | [5 empty] | NRIS |  | 50 |  | Solar | Dallas County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2020-09-01 | MidAmerican Energy Company | Dallas County | IA | DPP-2018-APR | West | PHASE 3 | NRIS | Adel - Waukee 69kV Line Tap | 50 | 50 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G156 | [5 empty] | ERIS |  | 500 |  | 0 | Cerro Gordo County | IA | [27 empty] | Withdrawn | 2001-11-27 |  |  |  | ITC Midwest | Cerro Gordo County | IA |  |  |  | ERIS | Unknown | 500 | 500 |  |  | Not Started | 2005-06-26 | 0 | 0 | 0 | 0
|  |  |  | DPP-2018-APR | West | Withdrawn | Not Started | J999 | [5 empty] | NRIS |  | 100 |  | Solar | Linn County | IA | [21 empty] | 0 | 0 |  |  |  |  | Withdrawn | 2018-03-12 | 2020-03-25 |  | 2020-09-01 | ITC Midwest | Linn County | IA | DPP-2018-APR | West | PHASE 3 | NRIS | Fairfax 161kV Substation | 100 | 100 | Solar | PV Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G157 | [5 empty] | ERIS |  | 500 |  | 0 | Linn County | IA | [27 empty] | Withdrawn | 2001-11-27 |  |  |  | ITC Midwest | Linn County | IA |  |  |  | ERIS | Unknown | 500 | 500 |  |  | Not Started | 2003-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G158 | [5 empty] | ERIS |  | 500 |  | 0 | Linn County | IA | [27 empty] | Withdrawn | 2001-11-27 |  |  |  | ITC Midwest | Linn County | IA |  |  |  | ERIS | Unknown | 500 | 500 |  |  | Not Started | 2003-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G159 | [5 empty] | ERIS |  | 500 |  | 0 | Buchanan County | IA | [27 empty] | Withdrawn | 2001-11-27 |  |  |  | ITC Midwest | Buchanan County | IA |  |  |  | ERIS | Unknown | 500 | 500 |  |  | Not Started | 2003-06-02 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Not Started | L002 | [5 empty] | ERIS |  | -28 |  | 0 | Scott County | MN | [27 empty] | Done | 2004-05-11 |  |  |  | Northern States Power (Xcel Energy) | Scott County | MN |  |  |  | ERIS | Unknown | -28 | -28 |  |  | Not Started | 2015-10-30 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Not Started | L003 | [5 empty] | ERIS |  | -10 |  | 0 | Lenawee County | MI | [27 empty] | Done | 2004-05-24 |  |  |  | Michigan Electric Transmission Company, LLC | Lenawee County | MI |  |  |  | ERIS | Unknown | -10 | -10 |  |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Not Started | L004 | [5 empty] | ERIS |  | -22 |  | 0 | Williams County | OH | [27 empty] | Done | 2004-07-22 |  |  |  | FirstEnergy Solutions Corp. | Williams County | OH |  |  |  | ERIS | Unknown | -22 | -22 |  |  | Not Started | 2009-04-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Not Started | L006 | [5 empty] | ERIS |  | -5 |  | 0 | Otsego County | MI | [27 empty] | Done | 2004-09-27 |  |  |  | Michigan Electric Transmission Company, LLC | Otsego County | MI |  |  |  | ERIS | Unknown | -5 | -5 |  |  | Not Started | 2005-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Not Started | L008 | [5 empty] | ERIS |  | -4 |  | 0 | Delaware County | OH | [27 empty] | Done | 2004-11-15 |  |  |  | FirstEnergy Solutions Corp. | Delaware County | OH |  |  |  | ERIS | Unknown | -4 | -4 |  |  | Not Started | 2004-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Not Started | L009 | [5 empty] | ERIS |  | -11 |  | 0 | Jackson County | MN | [27 empty] | Done | 2005-01-14 |  |  |  | ITC Midwest | Jackson County | MN |  |  |  | ERIS | Unknown | -11 | -11 |  |  | Not Started | 2005-01-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Not Started | L010 | [5 empty] | ERIS |  | -8 |  | 0 | 0 | MI | [27 empty] | Done | 2005-04-01 |  |  |  | Michigan Electric Transmission Company, LLC |  | MI |  |  |  | ERIS | Unknown | -8 | -8 |  |  | Not Started | 2005-04-01 | 0 | 0 | 0 | 0
|  |  |  | N001 | N001 | Done | In Service | N001 | [5 empty] | 0 |  | 100 |  | Wind | Benton County | IN | [27 empty] | Done | 2003-01-30 |  | 2005-10-18 | 2009-07-01 | Northern Indiana Public Service Company | Benton County | IN | N001 | N001 | Network Upgrade |  | Goodland 138 / 69 kV Substation | 100 | 100 | Wind | WT Wind Turbine | In Service | 2008-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G161 | [5 empty] | ERIS |  | 110 |  | 0 | Iron County | WI | [27 empty] | Withdrawn | 2001-12-01 |  |  |  | Northern States Power (Xcel Energy) | Iron County | WI |  |  | SPA - SIS | ERIS | Unknown | 110 | 110 |  |  | Not Started | 2003-06-03 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G166 | [5 empty] | ERIS |  | 2400 |  | 0 | Sheboygan County | WI | [27 empty] | Withdrawn | 2000-08-22 |  |  |  | American Transmission Co. LLC | Sheboygan County | WI |  |  |  | ERIS | Unknown | 2400 | 2400 |  |  | Not Started | 2007-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Under Construction | R101 | [5 empty] | NRIS |  | 4.6 |  | Wind | Red Lake County | MN | [21 empty] | 0 | 0 |  |  |  |  | Done | 2016-03-17 |  | 2017-04-28 | 2016-11-15 | Otter Tail Power Company | Red Lake County | MN |  |  |  | NRIS | 1.5 miles SW of Red Lake Falls, MN | 4.6 | 4.6 | Wind | Combined Cycle | Under Construction | 2016-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | R15 | [5 empty] | NRIS |  | 80 |  | Wind | Pocahontas County | IA | [27 empty] | Done | 2003-04-11 |  | 2009-12-23 | 2011-12-31 | MidAmerican Energy Company | Pocahontas County | IA |  |  |  | NRIS | Pomeroy 161 kV substation | 80 | 80 | Wind | WT Wind Turbine | In Service | 2006-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | R23 | [5 empty] | NRIS |  | 100 |  | Wind | Crawford County | IA | [27 empty] | Done | 2005-09-17 |  | 2010-11-12 | 2012-05-05 | MidAmerican Energy Company | Crawford County | IA |  |  |  | NRIS | Monona - Carroll 161 kV | 100 | 100 | Wind | WT Wind Turbine | In Service |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Withdrawn | R25 | [5 empty] | NRIS |  | 50 |  | Wind | Crawford County | IA | [27 empty] | Done | 2005-12-22 |  | 2009-03-06 | 2014-09-01 | MidAmerican Energy Company | Crawford County | IA |  |  |  | NRIS | Monona - Carroll 161 kV | 50 | 50 | Wind | WT Wind Turbine | Withdrawn | 2011-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | R26 | [5 empty] | ERIS |  | 400 |  | Wind | Atchison County | MO | [27 empty] | Done | 2006-02-28 |  | 2015-06-16 |  | MidAmerican Energy Company | Atchison County | MO |  |  |  | ERIS | MEC Cooper - Booneville 345 kV | 400 | 400 | Wind | WT Wind Turbine | In Service |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Withdrawn | R29 | [5 empty] | NRIS |  | 100.8 |  | Wind | Crawford County | IA | [27 empty] | Done | 2006-12-22 |  | 2009-08-26 |  | MidAmerican Energy Company | Crawford County | IA |  |  |  | NRIS | Schleswig Substation | 100.8 | 100.8 | Wind | WT Wind Turbine | Withdrawn | 2014-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | R34 | [5 empty] | NRIS |  | 250 |  | Wind | Madison County | IA | [27 empty] | Done | 2007-02-21 |  | 2009-10-05 | 2011-12-01 | MidAmerican Energy Company | Madison County | IA |  |  |  | NRIS | Council Bluffs - Madison County 345 kV | 250 | 250 | Wind | WT Wind Turbine | In Service | 2008-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | R35 | [5 empty] | 0 |  | 80 |  | Wind | Calhoun County | IA | [27 empty] | Done | 1899-12-31 |  | 2015-05-04 |  | MidAmerican Energy Company | Calhoun County | IA |  |  | DPP - SIS |  | Pomeroy Wind Farm site | 80 | 80 | Wind | WT Wind Turbine | In Service | 2008-11-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | R38 | [5 empty] | NRIS |  | 200 |  | Wind | Adair County | IA | [27 empty] | Done | 2007-02-23 |  | 2009-08-31 | 2012-09-17 | MidAmerican Energy Company | Adair County | IA |  |  |  | NRIS | MEC Council Bluffs - Grimes 345 kV | 200 | 200 | Wind | WT Wind Turbine | In Service | 2008-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | R39 | [5 empty] | NRIS |  | 500 |  | Wind | O'Brien County | IA | [27 empty] | Done | 2007-03-08 |  | 2009-08-28 | 2015-05-25 | MidAmerican Energy Company | O'Brien County | IA |  |  | Optional | NRIS | Raun - Lakefield Junction | 500 | 500 | Wind | WT Wind Turbine | In Service |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | In Service | R41 | [5 empty] | NRIS |  | 100 |  | Wind | Adair County | IA | [27 empty] | Done | 2007-04-17 |  | 2009-08-31 | 2012-10-29 | MidAmerican Energy Company | Adair County | IA |  |  |  | NRIS | MEC Council Bluffs - Grimes 345 kV | 100 | 100 | Wind | WT Wind Turbine | In Service | 2009-10-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | West | Done | In Service | R42 | [5 empty] | NRIS |  | 250 |  | Wind | Webster County | IA | [27 empty] | Done | 2007-07-17 |  | 2015-05-04 | 2014-09-27 | MidAmerican Energy Company | Webster County | IA | DPP-2012-AUG | West | Network Upgrade | NRIS | Lehigh 345 kV Substation | 250 | 250 | Wind | WT Wind Turbine | In Service | 2008-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G184 | [5 empty] | ERIS |  | 14 |  | 0 | Pipestone County | MN | [27 empty] | Withdrawn | 2002-03-16 |  |  |  | Northern States Power (Xcel Energy) | Pipestone County | MN |  |  |  | ERIS | Unknown | 14 | 14 |  |  | Not Started | 2004-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G187 | [5 empty] | ERIS |  | 600 |  | 0 | Muscatine County | IA | [27 empty] | Withdrawn | 2002-04-01 |  |  |  | ITC Midwest | Muscatine County | IA |  |  |  | ERIS | Unknown | 600 | 600 |  |  | Not Started | 2003-11-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | WEST | Done | In Service | R49 | [5 empty] | NRIS |  | 12 |  | Wind | Calhoun County | IA | [27 empty] | Done | 2008-01-16 |  | 2015-03-16 | 2011-10-30 | MidAmerican Energy Company | Calhoun County | IA | DPP-2012-AUG | WEST | Network Upgrade | NRIS | Pomeroy Generating station | 12 | 12 | Wind | WT Wind Turbine | In Service | 2010-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G194 CONS 7 | [5 empty] | ERIS |  | 300 |  | 0 | Saginaw County | MI | [27 empty] | Withdrawn | 1998-11-10 |  |  |  | Michigan Electric Transmission Company, LLC | Saginaw County | MI |  |  |  | ERIS | Unknown | 300 | 300 |  |  | Not Started | 2005-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G207 CONS 37 | [5 empty] | ERIS |  | 560 |  | 0 | Saginaw County | MI | [27 empty] | Withdrawn | 2000-02-14 |  |  |  | Michigan Electric Transmission Company, LLC | Saginaw County | MI |  |  |  | ERIS | Unknown | 560 | 560 |  |  | Not Started | 2002-06-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G210 CONS 103 | [5 empty] | ERIS |  | 875 |  | 0 | Saginaw County | MI | [27 empty] | Withdrawn | 2001-06-18 |  |  |  | Michigan Electric Transmission Company, LLC | Saginaw County | MI |  |  |  | ERIS | Unknown | 875 | 875 |  |  | Not Started | 2000-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G212 CONS 105 | [5 empty] | ERIS |  | 200 |  | 0 | Cheboygan County | MI | [27 empty] | Withdrawn | 2001-06-29 |  |  |  | Michigan Electric Transmission Company, LLC | Cheboygan County | MI |  |  |  | ERIS | Unknown | 200 | 200 |  |  | Not Started | 2002-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G216 CONS 110 | [5 empty] | ERIS |  | 280 |  | 0 | Livingston County | MI | [27 empty] | Withdrawn | 2001-11-06 |  |  |  | Michigan Electric Transmission Company, LLC | Livingston County | MI |  |  |  | ERIS | Unknown | 280 | 280 |  |  | Not Started | 2004-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G216 CONS 90 | [5 empty] | ERIS |  | 80 |  | 0 | Ionia County | MI | [27 empty] | Withdrawn | 2001-01-30 |  |  |  | Michigan Electric Transmission Company, LLC | Ionia County | MI |  |  |  | ERIS | Unknown | 80 | 80 |  |  | Not Started | 2002-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G217 CONS 94 | [5 empty] | ERIS |  | 510 |  | 0 | Livingston County | MI | [27 empty] | Withdrawn | 2001-03-06 |  |  |  | Michigan Electric Transmission Company, LLC | Livingston County | MI |  |  |  | ERIS | Unknown | 510 | 510 |  |  | Not Started | 2002-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G235 | [5 empty] | ERIS |  | 79 |  | 0 | Washington County | MN | [27 empty] | Withdrawn | 2002-01-16 |  |  |  | Northern States Power (Xcel Energy) | Washington County | MN |  |  |  | ERIS | Unknown | 79 | 79 |  |  | Not Started | 2003-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G247 | [5 empty] | ERIS |  | 100 |  | 0 | Mower County | MN | [27 empty] | Withdrawn | 2002-08-19 |  |  |  | Northern States Power (Xcel Energy) | Mower County | MN |  |  |  | ERIS | Unknown | 100 | 100 |  |  | Not Started | 2003-10-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G259 | [5 empty] | ERIS |  | 1100 |  | Combined Cycle | Dakota County | MN | [27 empty] | Withdrawn | 2002-10-07 |  |  |  | Northern States Power (Xcel Energy) | Dakota County | MN |  |  |  | ERIS | Unknown | 1100 | 1100 | Combined Cycle |  | Not Started | 2005-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G265 | [5 empty] | ERIS |  | 1420 |  | 0 | Campbell County | WY | [27 empty] | Withdrawn | 2002-11-12 |  |  |  | -- No Company -- | Campbell County | WY |  |  |  | ERIS | Unknown | 1420 | 1420 |  |  | Not Started | 2004-09-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G273 | [5 empty] | ERIS |  | 100 |  | 0 | Franklin County | IA | [27 empty] | Withdrawn | 2002-12-12 |  |  |  | ITC Midwest | Franklin County | IA |  |  |  | ERIS | Unknown | 100 | 100 |  |  | Not Started | 2003-05-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G274 | [5 empty] | ERIS |  | 200 |  | 0 | Franklin County | IA | [27 empty] | Withdrawn | 2002-12-12 |  |  |  | ITC Midwest | Franklin County | IA |  |  |  | ERIS | Unknown | 200 | 200 |  |  | Not Started | 2006-01-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2012-AUG | WEST | Done | In Service | R65 | [5 empty] | NRIS |  | 92 |  | Wind | Cass County | IA | [27 empty] | Done | 2009-04-08 |  | 2015-05-04 | 2011-12-22 | MidAmerican Energy Company | Cass County | IA | DPP-2012-AUG | WEST | Network Upgrade | NRIS | R34 Expansion | 92 | 92 | Wind | WT Wind Turbine | In Service | 2009-12-31 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G290 | [5 empty] | ERIS |  | 86 |  | 0 | Lawrence County | IN | [27 empty] | Withdrawn | 2003-01-28 |  |  |  | Hoosier Energy REC, Inc. | Lawrence County | IN |  |  |  | ERIS | Unknown | 86 | 86 |  |  | Not Started | 2004-12-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Withdrawn | Not Started | G295 | [5 empty] | ERIS |  | 525 |  | Coal | Portage County | WI | [27 empty] | Withdrawn | 2003-02-07 |  |  |  | American Transmission Co. LLC | Portage County | WI |  |  |  | ERIS | Unknown | 525 | 525 | Coal |  | Not Started | 2004-05-01 | 0 | 0 | 0 | 0
|  |  |  | DPP-2015-FEB | East (ITC) | Withdrawn | Withdrawn | J321 | [5 empty] | NRIS |  | 151.2 |  | Wind | Sanilac County | MI | [27 empty] | Withdrawn | 2014-01-13 |  | 2016-07-13 | 2016-10-01 | ITC Transmission | Sanilac County | MI | DPP-2015-FEB | East (ITC) | Int FaS | NRIS | 345 kV Rapson to Banner | 151.2 | 151.2 | Wind | WT Wind Turbine | Withdrawn | 2015-07-01 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | Done | Not Started | Temp3257 | [5 empty] | 0 |  | 0 |  | 0 | 0 | 0 | [27 empty] | Done | 1969-12-31 |  |  |  | -- No Company -- | [6 empty] | Unknown | 0 | 0 |  |  | Not Started |  | 0 | 0 | 0 | 0
|  |  |  | 125 | sss | Withdrawn | Not Started | Test 1234 | [5 empty] | 0 |  | 0 |  | 0 | Jackson County | TX | [27 empty] | Withdrawn | 2000-01-01 |  | 2018-09-12 | 2010-01-01 | -- No Company -- | Jackson County | TX | 125 | sss | MTEP |  | test line 1 - test line 2 138 kV | 0 | 0 |  | BS Battery Storage | Not Started |  | 0 | 0 | 0 | 0
Note on AM2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: All except AFS and NRIS, includes TO NU substation

## Sheet1
DPP Study Cycle | DPP Study Group | ERIS MW | NRIS MW | Tech | State | stayed | M2 | M3 | Total Security | NEW ERIS ($ MM) | NEW NRIS ($ MM) | NEW ERIS ($/kW) | NEW NRIS ($/kW) | Total Network Upgrades
DPP-2018-APR | East (ATC) | 50 |  | Solar | WI | 1 | 200000 | 0 | 200000 | 6441458 | 6441458 | 128.8292 | 128.8292 | 6441458
DPP-2018-APR | West | 40 |  | Solar | MN | 0 | 160000 | 345292 | 505292 | 8265000 | 8298148 | 206.625 | 207.4537 | 8298148
DPP-2018-APR | East (ATC) | 99 |  | Solar | WI | 1 | 396000 | 0 | 396000 | 2618981 | 3506253 | 26.4544 | 35.4167 | 3506253
DPP-2018-APR | East (ATC) | 50 |  | Solar | WI | 1 | 200000 | 0 | 200000 | 366697 | 3575532 | 7.3339 | 71.5106 | 3575532
DPP-2018-APR | East (ATC) | 400 |  | Solar | WI | 0 | 1600000 | 0 | 1600000 | 10951322 | 17001322 | 27.3783 | 42.5033 | 17001322
DPP-2018-APR | East (ATC) | 400 |  | Solar | WI | 0 | 1600000 | 0 | 1600000 | 2753837 | 9273837 | 6.8846 | 23.1846 | 9273837
DPP-2018-APR | East (ATC) | 400 |  | Solar | WI | 0 | 1600000 | 0 | 1600000 | 2753837 | 28121837 | 6.8846 | 70.3046 | 28121837
DPP-2018-APR | Central | 150 |  | Wind | IL | 1 | 600000 | 0 | 600000 | 1970000 | 2121000 | 13.1333 | 14.14 | 1970000
DPP-2018-APR | West | 200 |  | Wind | MO | 0 | 800000 | 1510089 | 2310089 | 22633003 | 30021446 | 113.165 | 150.1072 | 30021446
DPP-2018-APR | Central | 300 |  | Wind | MO | 1 | 1200000 | 2948233 | 4148233 | 27457764 | 27457764 | 91.5259 | 91.5259 | 27457764
DPP-2018-APR | Central | 400 |  | Wind | MO | 1 | 1600000 | 1203627 | 2803627 | 14009254 | 34490098 | 35.0231 | 86.2252 | 34490098
DPP-2018-APR | Central | 150 |  | Solar | IN | 1 | 600000 | 507695 | 1107695 | 717200 | 10872353 | 4.7813 | 72.4824 | 10872353
DPP-2018-APR | Central | 150 |  | Solar | IN | 1 | 600000 | 1109879 | 1709879 | 9916400 | 21962219 | 66.1093 | 146.4148 | 21962219
DPP-2018-APR | Central | 225 |  | Solar | MO | 1 | 900000 | 0 | 900000 | 3054500 | 6521315 | 13.5756 | 28.9836 | 6521315
DPP-2018-APR | West | 250 |  | Wind | ND | 1 | 1000000 | 6723874 | 7723874 | 163996022 | 166487103 | 655.9841 | 665.9484 | 166487103
DPP-2018-APR | East (ATC) | 200 |  | Solar | WI | 1 | 800000 | 258992 | 1058992 | 750098 | 16525307 | 3.7505 | 82.6265 | 16525307
DPP-2018-APR | West | 225 |  | Wind | IA | 1 | 900000 | 0 | 900000 | 439861 | 2458206 | 1.9549 | 10.9254 | 2458206
DPP-2018-APR | East (ATC) | 300 |  | Solar | WI | 0 | 1200000 | 1969396 | 3169396 | 6009313 | 40154250 | 20.031 | 133.8475 | 40154250
DPP-2018-APR | Central | 144 |  | Wind | IL | 1 | 576000 | 0 | 576000 | 1156000 | 1305800 | 8.0278 | 9.0681 | 1305800
DPP-2018-APR | Central | 300 |  | Solar | IN | 1 | 1200000 | 300000 | 1500000 | 24582234 | 30862234 | 81.9408 | 102.8741 | 30862234
DPP-2018-APR | Central | 195 |  | Solar | IN | 1 | 1200000 | 4996500 | 6196500 | 24214951 | 48824151 | 124.1792 | 250.3803 | 48824151
DPP-2018-APR | Central | 240 |  | Solar | IN | 1 | 960000 | 540000 | 1500000 | 22837834 | 22837834 | 95.1576 | 95.1576 | 22837834
DPP-2018-APR | Central | 200 |  | Wind | IN | 1 | 800000 | 0 | 800000 | 1102243 | 1102243 | 5.5112 | 5.5112 | 1102243
DPP-2018-APR | West | 150 |  | Solar | MN | 1 | 600000 | 80963 | 680963 | 2764007 | 2835352 | 18.9023 | 18.9023 | 2835352
DPP-2018-APR | Central | 200 |  | Solar | IN | 1 | 800000 | 1805435 | 2605435 | 1216300 | 30545615 | 6.0815 | 152.7281 | 30545615
DPP-2018-APR | East (ATC) | 300 |  | Wind | WI | 0 | 1200000 | 547326 | 1747326 | 11492260 | 26953260 | 38.3075 | 89.8442 | 26953260
DPP-2018-APR | Central | 200 |  | Solar | MO | 1 | 800000 | 935301 | 1735301 | 8322000 | 10297532 | 41.61 | 51.4877 | 10297532
DPP-2018-APR | West | 100 |  | Solar | WI | 1 | 400000 | 0 | 400000 | 12415962 | 12470917 | 124.1596 | 124.7092 | 12470917
DPP-2018-APR | Central | 150 |  | Solar | IL | 1 | 600000 | 27877 | 627877 | 7653000 | 8880725 | 51.02 | 59.2048 | 8880725
DPP-2018-APR | Central | 150 |  | Solar | IL | 1 | 600000 | 200000 | 800000 | 6422000 | 6422000 | 42.8133 | 42.8133 | 6422000
DPP-2018-APR | West | 40 |  | Solar | MN | 0 | 160000 | 225567 | 385567 | 96800000 | 107050853 | 2420 | 2676.2713 | 107050853
DPP-2018-APR | Central | 70 |  | Solar | IL | 1 | 280000 | 0 | 280000 | 1031000 | 1031000 | 14.7286 | 14.7286 | 1031000
DPP-2018-APR | West | 200 |  | Solar | MN | 0 | 800000 | 738148 | 1538148 | 18109762 | 18230245 | 90.5488 | 91.1512 | 18230245
DPP-2018-APR | West | 414 |  | Wind | MN | 0 | 1656000 | 4314168 | 5970168 | 157774968 | 158082866 | 381.099 | 381.8427 | 158082866
DPP-2018-APR | Central | 200 |  | Solar | MO | 1 | 800000 | 704358 | 1504358 | 9813000 | 11618952 | 49.065 | 58.0948 | 11618952
DPP-2018-APR | West | 100 |  | Solar | MN | 1 | 400000 | 0 | 400000 | 5165437 | 9582222 | 51.6544 | 95.8222 | 9582222
DPP-2018-APR | Central | 150 |  | Solar | IL | 0 | 600000 | 824911 | 1424911 | 20227000 | 21255551 | 134.8467 | 141.7037 | 21255551
DPP-2018-APR | Central | 150 |  | Solar | IN | 0 | 800000 | 0 | 800000 | 4326378 | 4326378 | 28.8425 | 28.8425 | 4326378
DPP-2018-APR | Central | 200 |  | Wind | IL | 1 | 800000 | 280000 | 1080000 | 9847000 | 19528700 | 49.235 | 97.6435 | 19528700
DPP-2018-APR | East (ATC) | 200 |  | Solar | WI | 0 | 800000 | 521010 | 1321010 | 11492261 | 29441261 | 57.4613 | 147.2063 | 29441261
DPP-2018-APR | West | 200 |  | Wind | IA | 0 | 800000 | 1350268 | 2150268 | 14036304 | 14181163 | 70.1815 | 70.9058 | 14181163
DPP-2018-APR | West | 100 |  | Solar | MN | 1 | 400000 | 0 | 400000 | 4051078 | 4102795 | 40.5108 | 41.0279 | 4102795
DPP-2018-APR | West | 150 |  | Solar | MN | 0 | 600000 | 1338204 | 1938204 | 18950622 | 26828801 | 126.3375 | 178.8587 | 26828801
DPP-2018-APR | West | 50 |  | Solar | IA | 1 | 200000 | 330511 | 530511 | 230544 | 5966897 | 4.6109 | 119.3379 | 5966897
DPP-2018-APR | Central | 150 |  | Solar | IL | 1 | 600000 | 0 | 600000 | 290000 | 42151500 | 1.9333 | 281.01 | 42151500
DPP-2018-APR | West | 80 |  | Solar | MN | 0 | 400000 | 969933 | 1369933 | 46446170 | 46495990 | 580.5771 | 581.1999 | 46495990
DPP-2018-APR | Central | 250 |  | Solar | MO | 1 | 1000000 | 388122 | 1388122 | 9855000 | 15392284 | 39.42 | 61.5691 | 15392284
DPP-2018-APR | East (ATC) | 150 |  | Solar | WI | 1 | 600000 | 0 | 600000 | 4106408 | 16685408 | 27.3761 | 111.2361 | 16685408
DPP-2018-APR | East (ATC) | 75 |  | Solar | WI | 1 | 800000 | 0 | 800000 | 0 | 5994932 | 0 | 79.9324 | 5994932
DPP-2018-APR | Central | 200 |  | Solar | IN | 1 | 800000 | 242500 | 1042500 | 0 | 6090818 | 0 | 30.4541 | 6090818
DPP-2018-APR | West | 80 |  | Solar | MN | 1 | 800000 | 3874879 | 4674879 | 6923598 | 7679731 | 86.545 | 95.9966 | 7679731
DPP-2018-APR | West | 50 |  | Solar | SD | 1 | 200000 | 293034 | 493034 | 5496551 | 7462269 | 109.931 | 149.2454 | 7462269
DPP-2018-APR | East (ATC) | 100 |  | Solar | WI | 1 | 400000 | 0 | 400000 | 1521698 | 7288957 | 15.217 | 72.8896 | 7288957
DPP-2018-APR | West | 165 |  | Solar | IA | 1 | 1200000 | 996501 | 2196501 | 12469083 | 21000103 | 75.5702 | 127.2734 | 21000103
DPP-2018-APR | West | 165 |  | Wind | IA | 1 | 1200000 | 1390809 | 2590809 | 19144001 | 27684980 | 116.0242 | 167.7878 | 27684980
DPP-2018-APR | West | 200 |  | Wind | IA | 1 | 800000 | 629023 | 1429023 | 17731384 | 22760508 | 88.6569 | 113.8025 | 22760508
DPP-2018-APR | Central | 75 |  | Solar | IL | 1 | 300000 | 880000 | 1180000 | 15006000 | 15006000 | 200.08 | 200.08 | 15006000
DPP-2018-APR | East (ATC) | 1.35 |  | Solar | MI | 1 | 5400 |  | 5400 | 0 | 0 | 0 | 0 | 0
DPP-2018-APR | West | 151.8 |  | Wind | ND | 0 | 607200 | 1627631 | 2234831 | 4838259 | 48812651 | 31.8726 | 321.559 | 48812651
DPP-2018-APR | East (ATC) | 50 |  | Solar | WI | 1 | 200000 | 135899 | 335899 | 1362993 | 6826341 | 27.2599 | 136.5268 | 6826341
DPP-2018-APR | Central | 250 |  | Solar | MO | 1 | 0 | 390083 | 390083 | 1367000 | 3465000 | 5.468 | 13.86 | 3465000
DPP-2019-Cycle | South | 125 |  | Solar | LA | 1 | 500000 | 3475319 | 3975319 | 10094000 | 43810350 | 80.752 | 350.4828 | 43810350
DPP-2019-Cycle | South | 200 |  | Solar | AR | 1 | 800000 | 4252878 | 5052878 | 13149000 | 14368794 | 65.745 | 71.844 | 14368794
DPP-2019-Cycle | South | 200 |  | Solar | LA | 1 | 800000 | 6670422 | 7470422 | 8978660 | 68830374 | 44.8933 | 344.1519 | 68830374
DPP-2019-Cycle | South | 100 |  | Solar | LA | 1 | 400000 | 350977 | 750977 | 5946000 | 5946000 | 59.46 | 59.46 | 5946000
DPP-2019-Cycle | South | 150 |  | Solar | MS | 1 | 600000 | 151444 | 751444 | 13688000 | 13688000 | 91.2533 | 91.2533 | 13688000
DPP-2019-Cycle | South | 100 |  | Solar | LA | 1 | 400000 | 4016325 | 4416325 | 3802000 | 6384309 | 38.02 | 63.8431 | 6384309
DPP-2019-Cycle | South | 100 |  | Solar | TX | 1 | 400000 | 3212224 | 3612224 | 15446000 | 56881794 | 154.46 | 568.8179 | 56881794
DPP-2019-Cycle | South | 75 |  | Solar | AR | 1 | 300000 | 1828655 | 2128655 | 11779000 | 14110278 | 157.0533 | 188.137 | 14110278
DPP-2019-Cycle | South | 200 |  | Solar | LA | 1 | 800000 | 8857952 | 9657952 | 11249146 | 101688380 | 56.2457 | 508.4419 | 101688380
DPP-2019-Cycle | South | 150 |  | Solar | LA | 1 | 600000 | 5978388 | 6578388 | 2426089 | 70953722 | 16.1739 | 473.0248 | 70953722
DPP-2019-Cycle | South | 99 |  | Solar | MS | 1 | 396000 | 1831523 | 2227523 | 12015000 | 17106107 | 121.3636 | 172.789 | 17106107
DPP-2019-Cycle | South | 175 |  | Solar | MS | 1 | 800000 | 1822322 | 2622322 | 12910000 | 27110000 | 73.7714 | 154.9143 | 12910000
DPP-2019-Cycle | South | 50 |  | Solar | LA | 1 | 200000 | 200480 | 400480 | 1364000 | 1364000 | 27.28 | 27.28 | 1364000
DPP-2019-Cycle | South | 95 |  | Solar | LA | 1 | 380000 | 923623 | 1303623 | 3650000 | 10964765 | 38.4211 | 115.4186 | 10964765
DPP-2019-Cycle | South | 200 |  | Solar | LA | 1 | 800000 | 5418271 | 6218271 | 7500000 | 50200207 | 37.5 | 251.001 | 50200207
DPP-2019-Cycle | South | 100 |  | Solar | LA | 1 | 400000 | 3084135 | 3484135 | 7500000 | 28850104 | 75 | 288.501 | 28850104
DPP-2019-Cycle | South | 95 |  | Solar | AR | 1 | 380000 | 2117528 | 2497528 | 10453000 | 10453000 | 110.0316 | 110.0316 | 10453000
DPP-2019-Cycle | South | 250 |  | Solar | AR | 1 | 1000000 | 0 | 1000000 | 1959500 | 1959500 | 7.838 | 7.838 | 1959500
DPP-2019-Cycle | South | 300 |  | Solar | LA | 1 | 1200000 | 1553225 | 2753225 | 34600000 | 34600000 | 115.3333 | 115.3333 | 34600000
DPP-2019-Cycle | South | 200 |  | Solar | LA | 1 | 800000 | 8439655 | 9239655 | 11478660 | 102097089 | 57.3933 | 510.4854 | 102097089
DPP-2019-Cycle | South | 200 |  | Solar | LA | 1 | 800000 | 3382034 | 4182034 | 608000 | 9286439 | 3.04 | 46.4322 | 9286439
DPP-2019-Cycle | South | 100 |  | Solar | AR | 1 | 400000 | 1921525 | 2321525 | 0 | 1003598 | 0 | 10.036 | 1003598
DPP-2019-Cycle | South | 50 |  | Solar | LA | 1 | 200000 | 157619 | 357619 | 0 | 0 | 0 | 0 | 0
DPP-2019-Cycle | South | 180 |  | Wind | AR | 1 | 720000 | 0 | 720000 | 2500000 | 3000000 | 13.8889 | 16.6667 | 3000000
DPP-2019-Cycle | South | 160 |  | Solar | MS | 1 | 650000 | 2419980 | 3069980 | 12064000 | 13389113 | 75.4 | 83.682 | 13389113
DPP-2019-Cycle | South | 200 |  | Solar | LA | 1 | 800000 | 3675142 | 4475142 | 3255000 | 22876561 | 16.275 | 114.3828 | 22876561
DPP-2019-Cycle | South | 165 |  | Solar | TX | 1 | 660000 | 5668331 | 6328331 | 13578000 | 57862120 | 82.2909 | 350.6795 | 57862120
DPP-2019-Cycle | South | 200 |  | Solar | LA | 1 | 800000 | 2311132 | 3111132 | 10250000 | 15511535 | 51.25 | 77.5577 | 15511535
DPP-2019-Cycle | South | 150 |  | Solar | LA | 1 | 600000 | 1957465 | 2557465 | 10814000 | 22847496 | 72.0933 | 152.3166 | 22847496
DPP-2019-Cycle | South | 200 |  | Solar | MS | 1 | 800000 | 3839272 | 4639272 | 4380000 | 18810412 | 21.9 | 94.0521 | 18810412
DPP-2019-Cycle | South | 150 |  | Solar | LA | 1 | 600000 | 2934367 | 3534367 | 0 | 22427269 | 0 | 149.5151 | 22427269
DPP-2019-Cycle | South | 150 |  | Solar | LA | 1 | 600000 | 3130304 | 3730304 | 15000000 | 47493325 | 100 | 316.6222 | 47493325
DPP-2016-AUG | West | 400 |  | Wind | MO | 1 | 1513856 | 11213124 | 12726980 | 34555897 | 37935897 | 86.3897 | 94.8397 | 37935897
DPP-2017-AUG | West | 110 |  | Wind | MN | 1 | 600000 | 0 | 600000 | 9892105 | 42361968 | 89.9282 | 385.1088 | 9892105
DPP-2016-AUG | West | 140 |  | Wind | IA | 1 | 820523 | 3763917 | 4584440 | 8435190 | 8435190 | 60.2514 | 60.2514 | 8435190
DPP-2016-AUG | West | 100 |  | Wind | MN | 1 | 1027079 | 956851 | 1983930 | 8073528 | 8073528 | 80.7353 | 80.7353 | 8073528
DPP-2017-AUG | West | 298 |  | Wind | ND | 0 | 1223600 | 10282913 | 11506513 | 245802967 | 245802967 | 824.8422 | 824.8422 | 245802967
DPP-2016-AUG | West | 200 |  | Wind | IA | 1 | 1045535 | 3970000 | 5015535 | 14692471 | 14692471 | 73.4624 | 73.4624 | 14692471
DPP-2016-AUG | West | 200 |  | Wind | MN | 1 | 1382159 | 9530643 | 10912802 | 31681519 | 31681519 | 158.4076 | 158.4076 | 31681519
DPP-2016-AUG | West | 90 |  | Wind | IA | 1 | 819471 | 1512658 | 2332129 | 7964204 | 7964204 | 88.4912 | 88.4912 | 7964204
DPP-2016-AUG | West | 300 |  | Wind | MO | 0 | 1289238 | 8208476 | 9497714 | 27522302 | 27522302 | 91.741 | 91.741 | 27522302
DPP-2016-AUG | West | 110 |  | Wind | MO | 1 | 1106198 | 476247 | 1582445 | 9371999 | 9621999 | 85.2 | 87.4727 | 9621999
DPP-2016-AUG | West | 66 |  | Wind | IA | 1 | 496212 | 1347250 | 1843462 | 12168508 | 12168508 | 184.3713 | 184.3713 | 12168508
DPP-2017-AUG | West | 400 |  | Wind | ND | 1 | 1600000 | 13627542 | 15227542 | 48494732 | 196731153 | 121.2368 | 491.8279 | 48494732
DPP-2016-AUG | West | 98 |  | Wind | SD | 0 | 980000 | 6457111 | 7437111 | 45156913 | 45156913 | 460.7848 | 460.7848 | 45156913
DPP-2017-AUG | West | 100 |  | Wind | ND | 0 | 400000 | 1788248 | 2188248 | 88332522 | 159696827 | 883.3252 | 1596.9683 | 159696827
DPP-2017-AUG | West | 100 |  | Wind | ND | 0 | 400000 | 1800000 | 2200000 | 88332522 | 159696827 | 883.3252 | 1596.9683 | 159696827
DPP-2017-AUG | West | 300 |  | Wind | ND | 0 | 1200000 | 4628612 | 5828612 | 258278012 | 472370926 | 860.9267 | 1574.5698 | 472370926
DPP-2017-AUG | West | 200 |  | Wind | MN | 0 | 800000 | 362178 | 1162178 | 82056001 | 130755912 | 410.28 | 653.7796 | 130755912
DPP-2017-AUG | West | 200 |  | Wind | SD | 1 | 800000 | 1864413 | 2664413 | 57997974 | 150439783 | 289.9899 | 752.1989 | 57997974
DPP-2017-AUG | West | 105 |  | Wind | MN | 0 | 420000 | 624613 | 1044613 | 29625115 | 56248153 | 282.144 | 535.6967 | 56248153
DPP-2017-AUG | West | 74 |  | Solar | WI | 1 | 296000 | 44000 | 340000 | 5349452 | 14853987 | 72.2899 | 200.7296 | 5349452
DPP-2017-AUG | West | 32.5 |  | Solar | MN | 1 | 130000 | 0 | 130000 | 2927743 | 2927743 | 90.0844 | 90.0844 | 2927743
DPP-2017-AUG | West | 60 |  | Solar | ND | 0 | 240000 | 546310 | 786310 | 7727271 | 48881683 | 128.7878 | 814.6947 | 48881683
DPP-2017-AUG | West | 200 |  | Wind | IA | 1 | 800000 | 0 | 800000 | 1416960 | 1416960 | 7.0848 | 7.0848 | 1416960
DPP-2017-AUG | West | 150 |  | Wind | IA | 0 | 600000 | 856128 | 1456128 | 15180241 | 49393006 | 101.2016 | 329.2867 | 49393006
DPP-2017-AUG | West | 200 |  | Wind | IA | 0 | 800000 | 778552 | 1578552 | 36601622 | 130846047 | 183.0081 | 654.2302 | 130846047
DPP-2017-AUG | West | 150 |  | Solar | MN | 1 | 600000 | 464501 | 1064501 | 12511427 | 58075741 | 83.4095 | 387.1716 | 58075741
DPP-2017-AUG | West | 250 |  | Solar | IA | 1 | 1000000 | 0 | 1000000 | 1862468 | 62321596 | 7.4499 | 249.2864 | 62321596
DPP-2017-AUG | West | 64 |  | Wind | IA | 0 | 256000 | 0 | 256000 | 8748925 | 23373657 | 136.702 | 365.2134 | 23373657
DPP-2017-AUG | West | 190 |  | Wind | ND | 1 | 760000 | 10701615 | 11461615 | 28773963 | 102000531 | 151.4419 | 536.8449 | 28773963
DPP-2017-AUG | West | 100 |  | Wind | IA | 1 | 400000 | 250000 | 650000 | 29392052 | 40309502 | 293.9205 | 403.095 | 29392052
DPP-2017-AUG | West | 200 |  | Wind | MN | 1 | 800000 | 951699 | 1751699 | 79617021 | 128511574 | 398.0851 | 642.5579 | 79617021
DPP-2017-AUG | West | 40 |  | Solar | MN | 0 | 160000 | 90866 | 250866 | 3782809 | 15590032 | 94.5702 | 389.7508 | 15590032
DPP-2017-AUG | West | 101.28 |  | Wind | WI | 1 | 405120 | 694880 | 1100000 | 8542627 | 21842742 | 84.3466 | 215.6669 | 8542627
DPP-2017-AUG | West | 100 |  | Wind | MN | 0 | 400000 | 656027 | 1056027 | 16296287 | 38840259 | 162.9629 | 388.4026 | 38840259
DPP-2017-AUG | West | 200 |  | Wind | SD | 0 | 800000 | 6919581 | 7719581 | 205763670 | 329435848 | 1028.8184 | 1647.1792 | 329435848
DPP-2017-AUG | West | 200 |  | Solar | ND | 1 | 800000 | 1245693 | 2045693 | 20713147 | 143559592 | 103.5657 | 717.798 | 143559592
DPP-2018-APR | West | 54 |  | Wind | SD | 0 | 216000 | 400435 | 616435 | 13372223 | 13372223 | 247.6338 | 247.6338 | 13372223
DPP-2018-APR | West | 1.4 |  | Solar | IA | 1 | 5600 | 0 | 5600 | 0 | 0 | 0 | 0 | 0
DPP-2018-APR | Central | 200 |  | Solar | MO | 1 | 800000 | 9725 | 809725 | 1170000 | 9904641 | 5.85 | 49.5232 | 9904641
DPP-2018-APR | West | 150 |  | Wind | IA | 0 | 600000 | 0 | 600000 | 5448373 | 5533592 | 36.3225 | 36.8906 | 5533592
DPP-2018-APR | West | 150 |  | Wind | MN | 1 | 600000 | 111927 | 711927 | 5874605 | 5945950 | 39.164 | 39.6397 | 5945950
DPP-2018-APR | Central | 200 |  | Wind | IN | 1 | 800000 | 0 | 800000 | 1102243 | 1102243 | 5.5112 | 5.5112 | 1102243
DPP-2018-APR | Central | 250 |  | Wind | IL | 1 | 1000000 | 0 | 1000000 | 1596000 | 6373168 | 6.384 | 25.4927 | 6373168
DPP-2018-APR | West | 150 |  | Wind | ND | 1 | 600000 | 1558786 | 2158786 | 5044983 | 11752870 | 33.6332 | 78.3525 | 5044983
DPP-2018-APR | Central | 300 |  | Solar | MO | 1 | 1200000 | 0 | 1200000 | 5906500 | 11172182 | 19.6883 | 37.2406 | 11172182
DPP-2018-APR | Central | 200 |  | Wind | IL | 1 | 800000 | 0 | 800000 | 4042000 | 7317500 | 20.21 | 36.5875 | 7317500
DPP-2018-APR | West | 300 |  | Wind | IA | 1 | 1200000 | 2354531 | 3554531 | 30203354 | 36868544 | 100.6778 | 122.8951 | 36868544
DPP-2018-APR | East (ATC) | 149.76 |  | Solar | WI | 1 | 599040 | 776690 | 1375730 | 6740635 | 7400459 | 45.0096 | 49.4155 | 7400459
DPP-2018-APR | Central | 100 |  | Solar | MO | 1 | 400000 | 0 | 400000 | 831000 | 2632909 | 8.31 | 26.3291 | 2632909
DPP-2018-APR | Central | 200 |  | Solar | IL | 1 | 800000 | 0 | 800000 | 2391000 | 2689000 | 11.955 | 13.445 | 2689000
DPP-2018-APR | Central | 200 |  | Solar | IN | 1 | 800000 | 0 | 800000 | 4509448 | 4509448 | 22.5472 | 22.5472 | 4509448
DPP-2018-APR | Central | 200 |  | Solar | IN | 1 | 800000 | 242500 | 1042500 | 491808 | 491808 | 2.459 | 2.459 | 491808
DPP-2018-APR | Central | 100 |  | Solar | MO | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0